## Projects
Project ID | Project Name | Program | Theme | Portfolio Category | Business Unit | Sponsor | Delivery Lead | PM | Priority | Investment Type | Delivery Method | Funding Type | Governance Channel | Financial Year | Start Date | End Date | Go Live Date | Progress % | Approved Funding | CAPEX | OPEX | Total Funding | Actual Spend | Forecast At Completion | Remaining Budget | Forecast Variance | Contingency | Benefits Forecast | Benefits Realised | Benefits Remaining | Benefit Realisation % | Budget | Actual Cost | Forecast | Status | RAG
PRJ001 | Customer Portal | Digital Transformation | Digital & Applications | Business Strategic | Wholesale | CTO | Alex Brown | John Smith | P2 - High | Transform | Hybrid | CAPEX | Channel B (>$200K) | FY25-26 | 2025-02-14 | 2026-03-13 | 2026-02-14 | 74 | 2593765 | 1319588 | 1274177 |  | 937070 | 2407335 |  |  | 259376 | 6550938 | 2659810 |  |  | 2593765 | 937070 | 2407335 | Completed | Green
PRJ002 | Cloud Migration | Digital Transformation | Cyber Security | CAPEX | Retail | COO | Carlos Diaz | Mike Johnson | P3 - Medium | Run | Agile | CAPEX | Channel B (>$200K) | FY25 | 2025-03-21 | 2025-10-07 | 2025-08-20 | 40 | 1851915 | 1106272 | 745643 |  | 1714568 | 2065964 |  |  | 185192 | 2754514 | 698458 |  |  | 1851915 | 1714568 | 2065964 | Pipeline | Green
PRJ003 | Data Platform | Cyber Security | Data & Analytics | Business Strategic | Retail | CFO | Carlos Diaz | John Smith | P4 - Low | Grow | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-04-09 | 2026-07-03 | 2026-06-29 | 78 | 3895151 | 2463632 | 1431519 |  | 2432283 | 4441608 |  |  | 389515 | 9010791 | 4658796 |  |  | 3895151 | 2432283 | 4441608 | Active | Green
PRJ004 | AI Assistant | Data & AI | Data & Analytics | IT Strategic | HR | CTO | Jane Doe | Priya Patel | P3 - Medium | Run | Waterfall | OPEX | Channel B (>$200K) | FY25-27 | 2025-10-01 | 2027-01-07 | 2026-12-23 | 26 | 1543706 | 885049 | 658657 |  | 545899 | 1818222 |  |  | 154371 | 3653124 | 1335139 |  |  | 1543706 | 545899 | 1818222 | Active | Green
PRJ005 | Network Refresh | Cyber Security | Data & Analytics | Unfunded | Wholesale | CFO | Priya Patel | Alex Brown | P3 - Medium | Transform | Hybrid | Unfunded | Channel B (>$200K) | FY25-27 | 2025-07-22 | 2027-01-15 | 2026-11-18 | 68 | 1664543 | 870832 | 793711 |  | 1610411 | 1745295 |  |  | 166454 | 4148450 | 529242 |  |  | 1664543 | 1610411 | 1745295 | Completed | Amber
PRJ006 | Cyber Security Program | Customer Experience | Infrastructure | Unfunded | Technology | CMO | Alex Brown | Sarah Lee | P3 - Medium | Transform | Waterfall | Unfunded | Channel B (>$200K) | FY25-26 | 2025-03-20 | 2026-05-05 | 2026-04-25 | 19 | 1657662 | 956077 | 701585 |  | 1736667 | 1704631 |  |  | 165766 | 2260449 | 63902 |  |  | 1657662 | 1736667 | 1704631 | Active | Red
PRJ007 | CRM Upgrade | Digital Transformation | Data & Analytics | IT Strategic | Marketing | CTO | Alex Brown | Jane Doe | P2 - High | Grow | Waterfall | Mixed | Channel B (>$200K) | FY25-26 | 2025-05-15 | 2026-12-23 | 2026-11-21 | 5 | 3550675 | 2708481 | 842194 |  | 2947660 | 3440822 |  |  | 355068 | 6136632 | 582334 |  |  | 3550675 | 2947660 | 3440822 | Pipeline | Amber
PRJ008 | Mobile App | Data & AI | Infrastructure | Business Strategic | Marketing | CTO | Carlos Diaz | Jane Doe | P2 - High | Transform | Agile | CAPEX | Channel B (>$200K) | FY25 | 2025-05-03 | 2025-08-30 | 2025-08-15 | 44 | 3682125 | 2612949 | 1069176 |  | 2077364 | 3273975 |  |  | 368212 | 6824323 | 4034491 |  |  | 3682125 | 2077364 | 3273975 | Pipeline | Green
PRJ009 | ERP Modernisation | Customer Experience | Cyber Security | CAPEX | Retail | CFO | Jane Doe | John Smith | P3 - Medium | Run | Hybrid | OPEX | Channel B (>$200K) | FY26 | 2026-01-01 | 2026-09-07 | 2026-08-13 | 30 | 1133721 | 913044 | 220677 |  | 569106 | 1047705 |  |  | 113372 | 2461006 | 1077819 |  |  | 1133721 | 569106 | 1047705 | Pipeline | Green
PRJ010 | Workforce Enablement | Data & AI | Digital & Applications | CAPEX | Finance | CFO | Priya Patel | Alex Brown | P4 - Low | Run | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-02-06 | 2026-01-25 | 2026-01-10 | 47 | 2394916 | 1203486 | 1191430 |  | 1849950 | 2085028 |  |  | 239492 | 3164452 | 59643 |  |  | 2394916 | 1849950 | 2085028 | Completed | Green
PRJ011 | IoT Initiative | Cloud Migration | Infrastructure | Unfunded | Wholesale | CFO | Jane Doe | Alex Brown | P4 - Low | Run | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-11-27 | 2026-04-16 | 2026-04-13 | 88 | 467871 | 341847 | 126024 |  | 204264 | 465010 |  |  | 46787 | 1288941 | 41894 |  |  | 467871 | 204264 | 465010 | Active | Green
PRJ012 | Analytics Platform | Cyber Security | Cyber Security | Business Strategic | Technology | CMO | Jane Doe | Carlos Diaz | P4 - Low | Run | Waterfall | CAPEX | Channel B (>$200K) | FY25-27 | 2025-10-04 | 2027-03-06 | 2027-03-06 | 88 | 1904249 | 1534958 | 369291 |  | 326799 | 2157148 |  |  | 190425 | 5219052 | 306594 |  |  | 1904249 | 326799 | 2157148 | Completed | Green
PRJ013 | API Gateway | Cloud Migration | Digital & Applications | IT Strategic | Retail | CTO | Priya Patel | Alex Brown | P1 - Critical | Transform | Agile | CAPEX | Channel B (>$200K) | FY25-27 | 2025-12-05 | 2027-03-07 | 2027-02-04 | 76 | 3942704 | 2337318 | 1605386 |  | 3331061 | 3979186 |  |  | 394270 | 7733273 | 4441919 |  |  | 3942704 | 3331061 | 3979186 | Active | Green
PRJ014 | Identity Mgmt | Digital Transformation | Business Transformation | IT Strategic | Wholesale | CTO | Alex Brown | John Smith | P1 - Critical | Grow | Hybrid | OPEX | Channel B (>$200K) | FY25-26 | 2025-02-05 | 2026-03-06 | 2026-03-02 | 28 | 2378293 | 1607720 | 770573 |  | 2164446 | 2152596 |  |  | 237829 | 6966976 | 334881 |  |  | 2378293 | 2164446 | 2152596 | Pipeline | Amber
PRJ015 | Service Desk | Data & AI | Business Transformation | Business Strategic | Finance | CIO | John Smith | Alex Brown | P2 - High | Transform | Agile | CAPEX | Channel B (>$200K) | FY25-26 | 2025-06-03 | 2026-04-23 | 2026-04-03 | 87 | 1333842 | 788658 | 545184 |  | 982027 | 1280441 |  |  | 133384 | 2238328 | 175769 |  |  | 1333842 | 982027 | 1280441 | Active | Green
PRJ016 | Infrastructure Upg | Digital Transformation | Digital & Applications | CAPEX | Operations | CIO | John Smith | Priya Patel | P2 - High | Grow | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-12-01 | 2026-11-26 | 2026-11-26 | 83 | 3535370 | 2855676 | 679694 |  | 1594631 | 3200257 |  |  | 353537 | 9548118 | 4030489 |  |  | 3535370 | 1594631 | 3200257 | Pipeline | Green
PRJ017 | App Modernisation | Digital Transformation | Data & Analytics | CAPEX | Marketing | CFO | Priya Patel | Mike Johnson | P2 - High | Transform | Agile | CAPEX | Channel B (>$200K) | FY25-26 | 2025-02-17 | 2026-04-07 | 2026-03-11 | 11 | 2898688 | 1655902 | 1242786 |  | 2036404 | 2731707 |  |  | 289869 | 6027408 | 3274099 |  |  | 2898688 | 2036404 | 2731707 | Pipeline | Red
PRJ018 | RPA Program | Cyber Security | Infrastructure | Unfunded | Operations | COO | Carlos Diaz | Carlos Diaz | P1 - Critical | Grow | Waterfall | Unfunded | Channel B (>$200K) | FY25-26 | 2025-10-26 | 2026-11-02 | 2026-10-24 | 52 | 1767979 | 889973 | 878006 |  | 303176 | 2049242 |  |  | 176798 | 4998203 | 1636183 |  |  | 1767979 | 303176 | 2049242 | Active | Red
PRJ019 | Vendor Mgmt | Digital Transformation | Digital & Applications | IT Strategic | HR | COO | Carlos Diaz | Sarah Lee | P2 - High | Grow | Waterfall | OPEX | Channel B (>$200K) | FY25-26 | 2025-03-25 | 2026-11-04 | 2026-09-14 | 35 | 500895 | 387212 | 113683 |  | 470805 | 497004 |  |  | 50090 | 1160669 | 107631 |  |  | 500895 | 470805 | 497004 | Active | Amber
PRJ020 | Process Automation | Cloud Migration | Data & Analytics | IT Strategic | Marketing | CIO | Carlos Diaz | Mike Johnson | P3 - Medium | Transform | Hybrid | OPEX | Channel B (>$200K) | FY25 | 2025-04-25 | 2025-08-05 | 2025-06-24 | 34 | 3501450 | 2802937 | 698513 |  | 1090044 | 3976966 |  |  | 350145 | 7102852 | 1300635 |  |  | 3501450 | 1090044 | 3976966 | Completed | Red
PRJ021 | Data Warehouse | Cloud Migration | Data & Analytics | Unfunded | Technology | CTO | Alex Brown | John Smith | P4 - Low | Transform | Waterfall | Unfunded | Channel B (>$200K) | FY25 | 2025-01-20 | 2025-06-14 | 2025-05-07 | 38 | 3926484 | 2700147 | 1226337 |  | 3896153 | 3496022 |  |  | 392648 | 11570253 | 1239645 |  |  | 3926484 | 3896153 | 3496022 | Active | Green
PRJ022 | DevOps Tools | Cloud Migration | Business Transformation | Business Strategic | Operations | CIO | Priya Patel | Mike Johnson | P3 - Medium | Transform | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-04-11 | 2026-01-12 | 2025-12-16 | 90 | 2864263 | 1433827 | 1430436 |  | 2804962 | 2974417 |  |  | 286426 | 7146262 | 3181302 |  |  | 2864263 | 2804962 | 2974417 | Active | Amber
PRJ023 | Workforce Portal | Customer Experience | Infrastructure | Unfunded | Operations | COO | Jane Doe | Sarah Lee | P3 - Medium | Grow | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-11-12 | 2026-11-28 | 2026-11-09 | 27 | 2819113 | 1956589 | 862524 |  | 795689 | 3052325 |  |  | 281911 | 5306872 | 2382153 |  |  | 2819113 | 795689 | 3052325 | Completed | Red
PRJ024 | Process Mining | Cyber Security | Data & Analytics | CAPEX | Wholesale | CFO | Jane Doe | John Smith | P1 - Critical | Run | Agile | CAPEX | Channel B (>$200K) | FY25-27 | 2025-12-06 | 2027-01-24 | 2026-12-16 | 70 | 933435 | 621308 | 312127 |  | 892478 | 1053483 |  |  | 93344 | 1405235 | 71495 |  |  | 933435 | 892478 | 1053483 | Pipeline | Green
PRJ025 | Customer Insights | Cyber Security | Digital & Applications | Business Strategic | Marketing | CTO | Sarah Lee | John Smith | P2 - High | Run | Agile | OPEX | Channel B (>$200K) | FY25-27 | 2025-12-02 | 2027-02-17 | 2027-02-17 | 23 | 1876123 | 1519937 | 356186 |  | 1213640 | 2066401 |  |  | 187612 | 3548051 | 850793 |  |  | 1876123 | 1213640 | 2066401 | Active | Amber
PRJ026 | ERP Modernisation 2 | Cyber Security | Cyber Security | Unfunded | Technology | COO | Carlos Diaz | Jane Doe | P3 - Medium | Transform | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-09-16 | 2026-07-21 | 2026-05-29 | 97 | 2703553 | 2286563 | 416990 |  | 1799700 | 3196989 |  |  | 270355 | 7582295 | 2787186 |  |  | 2703553 | 1799700 | 3196989 | Active | Green
PRJ027 | Cyber Program | Cyber Security | Infrastructure | IT Strategic | Technology | CMO | Mike Johnson | Alex Brown | P4 - Low | Grow | Waterfall | Mixed | Channel B (>$200K) | FY25-26 | 2025-04-29 | 2026-02-09 | 2025-12-27 | 24 | 1815503 | 1361156 | 454347 |  | 585988 | 1756584 |  |  | 181550 | 5096931 | 246419 |  |  | 1815503 | 585988 | 1756584 | Active | Amber
PRJ028 | Mobile App 2 | Data & AI | Business Transformation | CAPEX | HR | CTO | Carlos Diaz | Alex Brown | P2 - High | Grow | Waterfall | OPEX | Channel B (>$200K) | FY25-26 | 2025-01-04 | 2026-07-30 | 2026-07-08 | 66 | 1618960 | 1245674 | 373286 |  | 1616951 | 1387184 |  |  | 161896 | 4509098 | 1557507 |  |  | 1618960 | 1616951 | 1387184 | Active | Amber
PRJ029 | Analytics Platform 2 | Customer Experience | Business Transformation | Unfunded | HR | CIO | John Smith | Priya Patel | P4 - Low | Run | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-11-15 | 2026-11-13 | 2026-11-12 | 21 | 1994004 | 1268386 | 725618 |  | 1466450 | 2251928 |  |  | 199400 | 4992042 | 2517504 |  |  | 1994004 | 1466450 | 2251928 | Active | Green
PRJ030 | Service Desk 2 | Digital Transformation | Business Transformation | Unfunded | Retail | COO | Jane Doe | Priya Patel | P1 - Critical | Transform | Waterfall | Unfunded | Channel B (>$200K) | FY25-26 | 2025-05-10 | 2026-10-09 | 2026-10-04 | 58 | 1114610 | 685010 | 429600 |  | 592933 | 1079082 |  |  | 111461 | 3102352 | 517950 |  |  | 1114610 | 592933 | 1079082 | Active | Green
PRJ031 | Quality Mgmt | Customer Experience | Business Transformation | CAPEX | HR | CIO | Carlos Diaz | Carlos Diaz | P2 - High | Grow | Waterfall | CAPEX | Channel B (>$200K) | FY25-26 | 2025-08-27 | 2026-11-18 | 2026-11-02 | 32 | 877507 | 445013 | 432494 |  | 214781 | 784647 |  |  | 87751 | 2110427 | 714130 |  |  | 877507 | 214781 | 784647 | Pipeline | Green
PRJ032 | Compliance Hub | Cloud Migration | Business Transformation | IT Strategic | Marketing | CIO | Carlos Diaz | Alex Brown | P1 - Critical | Grow | Hybrid | CAPEX | Channel B (>$200K) | FY25-27 | 2025-12-20 | 2027-05-19 | 2027-04-09 | 80 | 3722660 | 2611553 | 1111107 |  | 3583525 | 3653260 |  |  | 372266 | 10775787 | 1282296 |  |  | 3722660 | 3583525 | 3653260 | Completed | Red
PRJ033 | Risk Platform | Cyber Security | Cyber Security | Unfunded | Wholesale | CTO | Priya Patel | Mike Johnson | P4 - Low | Grow | Agile | Unfunded | Channel B (>$200K) | FY25-27 | 2025-11-22 | 2027-05-22 | 2027-03-30 | 51 | 1545226 | 1046251 | 498975 |  | 655438 | 1772917 |  |  | 154523 | 4141508 | 262254 |  |  | 1545226 | 655438 | 1772917 | Pipeline | Green
PRJ034 | Treasury Sys | Data & AI | Data & Analytics | CAPEX | Wholesale | CMO | Jane Doe | Mike Johnson | P3 - Medium | Grow | Agile | CAPEX | Channel B (>$200K) | FY25-27 | 2025-11-09 | 2027-01-15 | 2026-12-22 | 77 | 1356988 | 795091 | 561897 |  | 1340556 | 1285916 |  |  | 135699 | 2729505 | 1229057 |  |  | 1356988 | 1340556 | 1285916 | Pipeline | Red
PRJ035 | Payroll Cloud | Data & AI | Infrastructure | Unfunded | Retail | COO | Jane Doe | Sarah Lee | P2 - High | Grow | Hybrid | Unfunded | Channel B (>$200K) | FY25-26 | 2025-05-04 | 2026-07-21 | 2026-06-21 | 76 | 3532419 | 2453360 | 1079059 |  | 2086939 | 3238768 |  |  | 353242 | 5773530 | 1407915 |  |  | 3532419 | 2086939 | 3238768 | Active | Amber
PRJ036 | HR Self-Service | Digital Transformation | Business Transformation | IT Strategic | Marketing | CFO | Jane Doe | Jane Doe | P4 - Low | Grow | Hybrid | OPEX | Channel B (>$200K) | FY25 | 2025-05-09 | 2025-12-03 | 2025-11-26 | 44 | 2258545 | 1401010 | 857535 |  | 2364245 | 2354840 |  |  | 225854 | 4140498 | 1127239 |  |  | 2258545 | 2364245 | 2354840 | Pipeline | Amber
PRJ037 | SAP S/4HANA | Cloud Migration | Digital & Applications | Business Strategic | HR | CMO | John Smith | Carlos Diaz | P1 - Critical | Transform | Agile | Mixed | Channel B (>$200K) | FY25 | 2025-03-06 | 2025-10-22 | 2025-10-20 | 73 | 1203695 | 644198 | 559497 |  | 342345 | 1118978 |  |  | 120370 | 1833221 | 15562 |  |  | 1203695 | 342345 | 1118978 | Completed | Amber
PRJ038 | Salesforce CRM | Cyber Security | Business Transformation | Business Strategic | Operations | CIO | Jane Doe | John Smith | P4 - Low | Transform | Hybrid | CAPEX | Channel B (>$200K) | FY25-26 | 2025-09-09 | 2026-01-14 | 2025-12-09 | 56 | 1817828 | 1026214 | 791614 |  | 270507 | 2143896 |  |  | 181783 | 3744567 | 1847080 |  |  | 1817828 | 270507 | 2143896 | Pipeline | Green
PRJ039 | M365 Rollout | Cyber Security | Data & Analytics | Business Strategic | HR | CIO | Jane Doe | Jane Doe | P2 - High | Transform | Waterfall | CAPEX | Channel B (>$200K) | FY25-26 | 2025-11-14 | 2026-03-14 | 2026-02-03 | 77 | 3125205 | 1978668 | 1146537 |  | 3009820 | 2981676 |  |  | 312520 | 7060917 | 1816759 |  |  | 3125205 | 3009820 | 2981676 | Active | Green
PRJ040 | Zero-Trust Net | Customer Experience | Digital & Applications | CAPEX | Technology | CIO | Alex Brown | Jane Doe | P2 - High | Grow | Waterfall | Mixed | Channel B (>$200K) | FY25-26 | 2025-02-06 | 2026-04-23 | 2026-04-09 | 63 | 1693219 | 1255149 | 438070 |  | 925203 | 1458579 |  |  | 169322 | 2909947 | 493617 |  |  | 1693219 | 925203 | 1458579 | Active | Green

## Roadmap
Project ID | Month | Year | Phase | Status
PRJ001 | Mar | 2025 | Design | Completed
PRJ001 | Apr | 2025 | Build | Completed
PRJ001 | May | 2025 | Deploy | Completed
PRJ001 | Jun | 2025 | Deploy | Completed
PRJ001 | Jul | 2025 | Build | Completed
PRJ001 | Aug | 2025 | Test | Completed
PRJ001 | Sep | 2025 | Discovery | Completed
PRJ001 | Oct | 2025 | Test | Completed
PRJ001 | Nov | 2025 | Build | Completed
PRJ001 | Dec | 2025 | Test | Completed
PRJ001 | Jan | 2026 | Build | Completed
PRJ001 | Feb | 2026 | Deploy | Completed
PRJ001 | Mar | 2026 | Deploy | Completed
PRJ002 | Apr | 2025 | Test | Pipeline
PRJ002 | May | 2025 | Test | Pipeline
PRJ002 | Jun | 2025 | Discovery | Pipeline
PRJ002 | Jul | 2025 | Deploy | Pipeline
PRJ002 | Aug | 2025 | Discovery | Pipeline
PRJ002 | Sep | 2025 | Test | Pipeline
PRJ002 | Oct | 2025 | Build | Pipeline
PRJ003 | May | 2025 | Deploy | Active
PRJ003 | Jun | 2025 | Build | Active
PRJ003 | Jul | 2025 | Discovery | Active
PRJ003 | Aug | 2025 | Discovery | Active
PRJ003 | Sep | 2025 | Design | Active
PRJ003 | Oct | 2025 | Deploy | Active
PRJ003 | Nov | 2025 | Deploy | Active
PRJ003 | Dec | 2025 | Discovery | Active
PRJ003 | Jan | 2026 | Build | Active
PRJ003 | Feb | 2026 | Deploy | Active
PRJ003 | Mar | 2026 | Discovery | Active
PRJ003 | Apr | 2026 | Design | Active
PRJ003 | May | 2026 | Test | Active
PRJ003 | Jun | 2026 | Deploy | Active
PRJ003 | Jul | 2026 | Test | Active
PRJ004 | Oct | 2025 | Build | Active
PRJ004 | Nov | 2025 | Design | Active
PRJ004 | Dec | 2025 | Deploy | Active
PRJ004 | Jan | 2026 | Test | Active
PRJ004 | Feb | 2026 | Test | Active
PRJ004 | Mar | 2026 | Discovery | Active
PRJ004 | Apr | 2026 | Test | Active
PRJ004 | May | 2026 | Build | Active
PRJ004 | Jun | 2026 | Test | Active
PRJ004 | Jul | 2026 | Build | Active
PRJ004 | Aug | 2026 | Build | Active
PRJ004 | Sep | 2026 | Discovery | Active
PRJ004 | Oct | 2026 | Design | Active
PRJ004 | Nov | 2026 | Build | Active
PRJ004 | Dec | 2026 | Test | Active
PRJ004 | Jan | 2027 | Test | Active
PRJ005 | Aug | 2025 | Build | Completed
PRJ005 | Sep | 2025 | Test | Completed
PRJ005 | Oct | 2025 | Deploy | Completed
PRJ005 | Nov | 2025 | Discovery | Completed
PRJ005 | Dec | 2025 | Test | Completed
PRJ005 | Jan | 2026 | Discovery | Completed
PRJ005 | Feb | 2026 | Build | Completed
PRJ005 | Mar | 2026 | Build | Completed
PRJ005 | Apr | 2026 | Build | Completed
PRJ005 | May | 2026 | Discovery | Completed
PRJ005 | Jun | 2026 | Test | Completed
PRJ005 | Jul | 2026 | Deploy | Completed
PRJ005 | Aug | 2026 | Discovery | Completed
PRJ005 | Sep | 2026 | Deploy | Completed
PRJ005 | Oct | 2026 | Test | Completed
PRJ005 | Nov | 2026 | Test | Completed
PRJ005 | Dec | 2026 | Discovery | Completed
PRJ005 | Jan | 2027 | Design | Completed
PRJ006 | Apr | 2025 | Deploy | Active
PRJ006 | May | 2025 | Build | Active
PRJ006 | Jun | 2025 | Deploy | Active
PRJ006 | Jul | 2025 | Test | Active
PRJ006 | Aug | 2025 | Test | Active
PRJ006 | Sep | 2025 | Discovery | Active
PRJ006 | Oct | 2025 | Design | Active
PRJ006 | Nov | 2025 | Build | Active
PRJ006 | Dec | 2025 | Deploy | Active
PRJ006 | Jan | 2026 | Design | Active
PRJ006 | Feb | 2026 | Build | Active
PRJ006 | Mar | 2026 | Test | Active
PRJ006 | Apr | 2026 | Test | Active
PRJ006 | May | 2026 | Discovery | Active
PRJ007 | Jun | 2025 | Discovery | Pipeline
PRJ007 | Jul | 2025 | Deploy | Pipeline
PRJ007 | Aug | 2025 | Design | Pipeline
PRJ007 | Sep | 2025 | Design | Pipeline
PRJ007 | Oct | 2025 | Build | Pipeline
PRJ007 | Nov | 2025 | Deploy | Pipeline
PRJ007 | Dec | 2025 | Discovery | Pipeline
PRJ007 | Jan | 2026 | Deploy | Pipeline
PRJ007 | Feb | 2026 | Test | Pipeline
PRJ007 | Mar | 2026 | Discovery | Pipeline
PRJ007 | Apr | 2026 | Design | Pipeline
PRJ007 | May | 2026 | Discovery | Pipeline
PRJ007 | Jun | 2026 | Test | Pipeline
PRJ007 | Jul | 2026 | Discovery | Pipeline
PRJ007 | Aug | 2026 | Design | Pipeline
PRJ007 | Sep | 2026 | Test | Pipeline
PRJ007 | Oct | 2026 | Build | Pipeline
PRJ007 | Nov | 2026 | Deploy | Pipeline
PRJ007 | Dec | 2026 | Build | Pipeline
PRJ008 | Jun | 2025 | Test | Pipeline
PRJ008 | Jul | 2025 | Test | Pipeline
PRJ008 | Aug | 2025 | Test | Pipeline
PRJ009 | Jan | 2026 | Design | Pipeline
PRJ009 | Feb | 2026 | Test | Pipeline
PRJ009 | Mar | 2026 | Deploy | Pipeline
PRJ009 | Apr | 2026 | Design | Pipeline
PRJ009 | May | 2026 | Test | Pipeline
PRJ009 | Jun | 2026 | Design | Pipeline
PRJ009 | Jul | 2026 | Deploy | Pipeline
PRJ009 | Aug | 2026 | Deploy | Pipeline
PRJ009 | Sep | 2026 | Design | Pipeline
PRJ010 | Mar | 2025 | Discovery | Completed
PRJ010 | Apr | 2025 | Build | Completed
PRJ010 | May | 2025 | Test | Completed
PRJ010 | Jun | 2025 | Build | Completed
PRJ010 | Jul | 2025 | Deploy | Completed
PRJ010 | Aug | 2025 | Build | Completed
PRJ010 | Sep | 2025 | Discovery | Completed
PRJ010 | Oct | 2025 | Build | Completed
PRJ010 | Nov | 2025 | Build | Completed
PRJ010 | Dec | 2025 | Deploy | Completed
PRJ010 | Jan | 2026 | Deploy | Completed
PRJ011 | Dec | 2025 | Test | Active
PRJ011 | Jan | 2026 | Design | Active
PRJ011 | Feb | 2026 | Test | Active
PRJ011 | Mar | 2026 | Deploy | Active
PRJ011 | Apr | 2026 | Test | Active
PRJ012 | Nov | 2025 | Build | Completed
PRJ012 | Dec | 2025 | Build | Completed
PRJ012 | Jan | 2026 | Deploy | Completed
PRJ012 | Feb | 2026 | Deploy | Completed
PRJ012 | Mar | 2026 | Test | Completed
PRJ012 | Apr | 2026 | Test | Completed
PRJ012 | May | 2026 | Build | Completed
PRJ012 | Jun | 2026 | Design | Completed
PRJ012 | Jul | 2026 | Design | Completed
PRJ012 | Aug | 2026 | Deploy | Completed
PRJ012 | Sep | 2026 | Test | Completed
PRJ012 | Oct | 2026 | Design | Completed
PRJ012 | Nov | 2026 | Test | Completed
PRJ012 | Dec | 2026 | Discovery | Completed
PRJ012 | Jan | 2027 | Build | Completed
PRJ012 | Feb | 2027 | Test | Completed
PRJ012 | Mar | 2027 | Test | Completed
PRJ013 | Jan | 2026 | Test | Active
PRJ013 | Feb | 2026 | Design | Active
PRJ013 | Mar | 2026 | Test | Active
PRJ013 | Apr | 2026 | Discovery | Active
PRJ013 | May | 2026 | Design | Active
PRJ013 | Jun | 2026 | Deploy | Active
PRJ013 | Jul | 2026 | Deploy | Active
PRJ013 | Aug | 2026 | Build | Active
PRJ013 | Sep | 2026 | Discovery | Active
PRJ013 | Oct | 2026 | Test | Active
PRJ013 | Nov | 2026 | Discovery | Active
PRJ013 | Dec | 2026 | Deploy | Active
PRJ013 | Jan | 2027 | Test | Active
PRJ013 | Feb | 2027 | Discovery | Active
PRJ013 | Mar | 2027 | Design | Active
PRJ014 | Mar | 2025 | Test | Pipeline
PRJ014 | Apr | 2025 | Design | Pipeline
PRJ014 | May | 2025 | Discovery | Pipeline
PRJ014 | Jun | 2025 | Test | Pipeline
PRJ014 | Jul | 2025 | Build | Pipeline
PRJ014 | Aug | 2025 | Build | Pipeline
PRJ014 | Sep | 2025 | Deploy | Pipeline
PRJ014 | Oct | 2025 | Test | Pipeline
PRJ014 | Nov | 2025 | Discovery | Pipeline
PRJ014 | Dec | 2025 | Build | Pipeline
PRJ014 | Jan | 2026 | Deploy | Pipeline
PRJ014 | Feb | 2026 | Test | Pipeline
PRJ014 | Mar | 2026 | Build | Pipeline
PRJ015 | Jul | 2025 | Test | Active
PRJ015 | Aug | 2025 | Deploy | Active
PRJ015 | Sep | 2025 | Discovery | Active
PRJ015 | Oct | 2025 | Deploy | Active
PRJ015 | Nov | 2025 | Discovery | Active
PRJ015 | Dec | 2025 | Design | Active
PRJ015 | Jan | 2026 | Build | Active
PRJ015 | Feb | 2026 | Design | Active
PRJ015 | Mar | 2026 | Discovery | Active
PRJ015 | Apr | 2026 | Test | Active
PRJ016 | Dec | 2025 | Discovery | Pipeline
PRJ016 | Jan | 2026 | Discovery | Pipeline
PRJ016 | Feb | 2026 | Test | Pipeline
PRJ016 | Mar | 2026 | Design | Pipeline
PRJ016 | Apr | 2026 | Build | Pipeline
PRJ016 | May | 2026 | Discovery | Pipeline
PRJ016 | Jun | 2026 | Discovery | Pipeline
PRJ016 | Jul | 2026 | Build | Pipeline
PRJ016 | Aug | 2026 | Discovery | Pipeline
PRJ016 | Sep | 2026 | Build | Pipeline
PRJ016 | Oct | 2026 | Build | Pipeline
PRJ016 | Nov | 2026 | Build | Pipeline
PRJ017 | Mar | 2025 | Test | Pipeline
PRJ017 | Apr | 2025 | Design | Pipeline
PRJ017 | May | 2025 | Design | Pipeline
PRJ017 | Jun | 2025 | Deploy | Pipeline
PRJ017 | Jul | 2025 | Test | Pipeline
PRJ017 | Aug | 2025 | Deploy | Pipeline
PRJ017 | Sep | 2025 | Design | Pipeline
PRJ017 | Oct | 2025 | Design | Pipeline
PRJ017 | Nov | 2025 | Design | Pipeline
PRJ017 | Dec | 2025 | Discovery | Pipeline
PRJ017 | Jan | 2026 | Deploy | Pipeline
PRJ017 | Feb | 2026 | Test | Pipeline
PRJ017 | Mar | 2026 | Deploy | Pipeline
PRJ017 | Apr | 2026 | Design | Pipeline
PRJ018 | Nov | 2025 | Test | Active
PRJ018 | Dec | 2025 | Deploy | Active
PRJ018 | Jan | 2026 | Design | Active
PRJ018 | Feb | 2026 | Design | Active
PRJ018 | Mar | 2026 | Test | Active
PRJ018 | Apr | 2026 | Build | Active
PRJ018 | May | 2026 | Test | Active
PRJ018 | Jun | 2026 | Build | Active
PRJ018 | Jul | 2026 | Discovery | Active
PRJ018 | Aug | 2026 | Test | Active
PRJ018 | Sep | 2026 | Build | Active
PRJ018 | Oct | 2026 | Deploy | Active
PRJ018 | Nov | 2026 | Design | Active
PRJ019 | Apr | 2025 | Discovery | Active
PRJ019 | May | 2025 | Test | Active
PRJ019 | Jun | 2025 | Build | Active
PRJ019 | Jul | 2025 | Deploy | Active
PRJ019 | Aug | 2025 | Build | Active
PRJ019 | Sep | 2025 | Test | Active
PRJ019 | Oct | 2025 | Build | Active
PRJ019 | Nov | 2025 | Test | Active
PRJ019 | Dec | 2025 | Build | Active
PRJ019 | Jan | 2026 | Design | Active
PRJ019 | Feb | 2026 | Test | Active
PRJ019 | Mar | 2026 | Test | Active
PRJ019 | Apr | 2026 | Discovery | Active
PRJ019 | May | 2026 | Design | Active
PRJ019 | Jun | 2026 | Test | Active
PRJ019 | Jul | 2026 | Deploy | Active
PRJ019 | Aug | 2026 | Build | Active
PRJ019 | Sep | 2026 | Deploy | Active
PRJ019 | Oct | 2026 | Build | Active
PRJ019 | Nov | 2026 | Build | Active
PRJ020 | May | 2025 | Discovery | Completed
PRJ020 | Jun | 2025 | Test | Completed
PRJ020 | Jul | 2025 | Build | Completed
PRJ020 | Aug | 2025 | Discovery | Completed
PRJ021 | Feb | 2025 | Deploy | Active
PRJ021 | Mar | 2025 | Discovery | Active
PRJ021 | Apr | 2025 | Deploy | Active
PRJ021 | May | 2025 | Test | Active
PRJ021 | Jun | 2025 | Build | Active
PRJ022 | May | 2025 | Design | Active
PRJ022 | Jun | 2025 | Deploy | Active
PRJ022 | Jul | 2025 | Build | Active
PRJ022 | Aug | 2025 | Design | Active
PRJ022 | Sep | 2025 | Design | Active
PRJ022 | Oct | 2025 | Deploy | Active
PRJ022 | Nov | 2025 | Build | Active
PRJ022 | Dec | 2025 | Design | Active
PRJ022 | Jan | 2026 | Discovery | Active
PRJ023 | Dec | 2025 | Discovery | Completed
PRJ023 | Jan | 2026 | Build | Completed
PRJ023 | Feb | 2026 | Test | Completed
PRJ023 | Mar | 2026 | Discovery | Completed
PRJ023 | Apr | 2026 | Deploy | Completed
PRJ023 | May | 2026 | Build | Completed
PRJ023 | Jun | 2026 | Design | Completed
PRJ023 | Jul | 2026 | Discovery | Completed
PRJ023 | Aug | 2026 | Build | Completed
PRJ023 | Sep | 2026 | Build | Completed
PRJ023 | Oct | 2026 | Test | Completed
PRJ023 | Nov | 2026 | Design | Completed
PRJ024 | Jan | 2026 | Design | Pipeline
PRJ024 | Feb | 2026 | Design | Pipeline
PRJ024 | Mar | 2026 | Deploy | Pipeline
PRJ024 | Apr | 2026 | Build | Pipeline
PRJ024 | May | 2026 | Deploy | Pipeline
PRJ024 | Jun | 2026 | Deploy | Pipeline
PRJ024 | Jul | 2026 | Build | Pipeline
PRJ024 | Aug | 2026 | Design | Pipeline
PRJ024 | Sep | 2026 | Build | Pipeline
PRJ024 | Oct | 2026 | Test | Pipeline
PRJ024 | Nov | 2026 | Build | Pipeline
PRJ024 | Dec | 2026 | Build | Pipeline
PRJ024 | Jan | 2027 | Discovery | Pipeline
PRJ025 | Jan | 2026 | Test | Active
PRJ025 | Feb | 2026 | Discovery | Active
PRJ025 | Mar | 2026 | Design | Active
PRJ025 | Apr | 2026 | Design | Active
PRJ025 | May | 2026 | Test | Active
PRJ025 | Jun | 2026 | Deploy | Active
PRJ025 | Jul | 2026 | Build | Active
PRJ025 | Aug | 2026 | Discovery | Active
PRJ025 | Sep | 2026 | Test | Active
PRJ025 | Oct | 2026 | Discovery | Active
PRJ025 | Nov | 2026 | Build | Active
PRJ025 | Dec | 2026 | Deploy | Active
PRJ025 | Jan | 2027 | Discovery | Active
PRJ025 | Feb | 2027 | Test | Active
PRJ026 | Oct | 2025 | Build | Active
PRJ026 | Nov | 2025 | Build | Active
PRJ026 | Dec | 2025 | Deploy | Active
PRJ026 | Jan | 2026 | Test | Active
PRJ026 | Feb | 2026 | Build | Active
PRJ026 | Mar | 2026 | Discovery | Active
PRJ026 | Apr | 2026 | Design | Active
PRJ026 | May | 2026 | Test | Active
PRJ026 | Jun | 2026 | Discovery | Active
PRJ026 | Jul | 2026 | Deploy | Active
PRJ027 | May | 2025 | Deploy | Active
PRJ027 | Jun | 2025 | Build | Active
PRJ027 | Jul | 2025 | Deploy | Active
PRJ027 | Aug | 2025 | Design | Active
PRJ027 | Sep | 2025 | Discovery | Active
PRJ027 | Oct | 2025 | Test | Active
PRJ027 | Nov | 2025 | Build | Active
PRJ027 | Dec | 2025 | Test | Active
PRJ027 | Jan | 2026 | Discovery | Active
PRJ027 | Feb | 2026 | Design | Active
PRJ028 | Feb | 2025 | Discovery | Active
PRJ028 | Mar | 2025 | Discovery | Active
PRJ028 | Apr | 2025 | Build | Active
PRJ028 | May | 2025 | Test | Active
PRJ028 | Jun | 2025 | Discovery | Active
PRJ028 | Jul | 2025 | Discovery | Active
PRJ028 | Aug | 2025 | Design | Active
PRJ028 | Sep | 2025 | Deploy | Active
PRJ028 | Oct | 2025 | Design | Active
PRJ028 | Nov | 2025 | Test | Active
PRJ028 | Dec | 2025 | Test | Active
PRJ028 | Jan | 2026 | Build | Active
PRJ028 | Feb | 2026 | Deploy | Active
PRJ028 | Mar | 2026 | Test | Active
PRJ028 | Apr | 2026 | Deploy | Active
PRJ028 | May | 2026 | Design | Active
PRJ028 | Jun | 2026 | Test | Active
PRJ028 | Jul | 2026 | Discovery | Active
PRJ029 | Dec | 2025 | Test | Active
PRJ029 | Jan | 2026 | Deploy | Active
PRJ029 | Feb | 2026 | Test | Active
PRJ029 | Mar | 2026 | Build | Active
PRJ029 | Apr | 2026 | Discovery | Active
PRJ029 | May | 2026 | Build | Active
PRJ029 | Jun | 2026 | Design | Active
PRJ029 | Jul | 2026 | Test | Active
PRJ029 | Aug | 2026 | Test | Active
PRJ029 | Sep | 2026 | Design | Active
PRJ029 | Oct | 2026 | Build | Active
PRJ029 | Nov | 2026 | Discovery | Active
PRJ030 | Jun | 2025 | Build | Active
PRJ030 | Jul | 2025 | Deploy | Active
PRJ030 | Aug | 2025 | Build | Active
PRJ030 | Sep | 2025 | Discovery | Active
PRJ030 | Oct | 2025 | Test | Active
PRJ030 | Nov | 2025 | Build | Active
PRJ030 | Dec | 2025 | Design | Active
PRJ030 | Jan | 2026 | Discovery | Active
PRJ030 | Feb | 2026 | Test | Active
PRJ030 | Mar | 2026 | Discovery | Active
PRJ030 | Apr | 2026 | Design | Active
PRJ030 | May | 2026 | Deploy | Active
PRJ030 | Jun | 2026 | Discovery | Active
PRJ030 | Jul | 2026 | Discovery | Active
PRJ030 | Aug | 2026 | Build | Active
PRJ030 | Sep | 2026 | Design | Active
PRJ030 | Oct | 2026 | Design | Active
PRJ031 | Sep | 2025 | Deploy | Pipeline
PRJ031 | Oct | 2025 | Design | Pipeline
PRJ031 | Nov | 2025 | Discovery | Pipeline
PRJ031 | Dec | 2025 | Deploy | Pipeline
PRJ031 | Jan | 2026 | Design | Pipeline
PRJ031 | Feb | 2026 | Deploy | Pipeline
PRJ031 | Mar | 2026 | Design | Pipeline
PRJ031 | Apr | 2026 | Design | Pipeline
PRJ031 | May | 2026 | Build | Pipeline
PRJ031 | Jun | 2026 | Design | Pipeline
PRJ031 | Jul | 2026 | Deploy | Pipeline
PRJ031 | Aug | 2026 | Discovery | Pipeline
PRJ031 | Sep | 2026 | Build | Pipeline
PRJ031 | Oct | 2026 | Design | Pipeline
PRJ031 | Nov | 2026 | Design | Pipeline
PRJ032 | Jan | 2026 | Deploy | Completed
PRJ032 | Feb | 2026 | Build | Completed
PRJ032 | Mar | 2026 | Design | Completed
PRJ032 | Apr | 2026 | Discovery | Completed
PRJ032 | May | 2026 | Discovery | Completed
PRJ032 | Jun | 2026 | Design | Completed
PRJ032 | Jul | 2026 | Discovery | Completed
PRJ032 | Aug | 2026 | Build | Completed
PRJ032 | Sep | 2026 | Design | Completed
PRJ032 | Oct | 2026 | Deploy | Completed
PRJ032 | Nov | 2026 | Build | Completed
PRJ032 | Dec | 2026 | Discovery | Completed
PRJ032 | Jan | 2027 | Design | Completed
PRJ032 | Feb | 2027 | Build | Completed
PRJ032 | Mar | 2027 | Discovery | Completed
PRJ032 | Apr | 2027 | Design | Completed
PRJ032 | May | 2027 | Test | Completed
PRJ033 | Dec | 2025 | Deploy | Pipeline
PRJ033 | Jan | 2026 | Discovery | Pipeline
PRJ033 | Feb | 2026 | Discovery | Pipeline
PRJ033 | Mar | 2026 | Test | Pipeline
PRJ033 | Apr | 2026 | Test | Pipeline
PRJ033 | May | 2026 | Build | Pipeline
PRJ033 | Jun | 2026 | Deploy | Pipeline
PRJ033 | Jul | 2026 | Deploy | Pipeline
PRJ033 | Aug | 2026 | Discovery | Pipeline
PRJ033 | Sep | 2026 | Test | Pipeline
PRJ033 | Oct | 2026 | Deploy | Pipeline
PRJ033 | Nov | 2026 | Design | Pipeline
PRJ033 | Dec | 2026 | Deploy | Pipeline
PRJ033 | Jan | 2027 | Discovery | Pipeline
PRJ033 | Feb | 2027 | Deploy | Pipeline
PRJ033 | Mar | 2027 | Build | Pipeline
PRJ033 | Apr | 2027 | Test | Pipeline
PRJ033 | May | 2027 | Discovery | Pipeline
PRJ034 | Dec | 2025 | Discovery | Pipeline
PRJ034 | Jan | 2026 | Test | Pipeline
PRJ034 | Feb | 2026 | Test | Pipeline
PRJ034 | Mar | 2026 | Test | Pipeline
PRJ034 | Apr | 2026 | Discovery | Pipeline
PRJ034 | May | 2026 | Test | Pipeline
PRJ034 | Jun | 2026 | Test | Pipeline
PRJ034 | Jul | 2026 | Discovery | Pipeline
PRJ034 | Aug | 2026 | Discovery | Pipeline
PRJ034 | Sep | 2026 | Build | Pipeline
PRJ034 | Oct | 2026 | Deploy | Pipeline
PRJ034 | Nov | 2026 | Design | Pipeline
PRJ034 | Dec | 2026 | Discovery | Pipeline
PRJ034 | Jan | 2027 | Design | Pipeline
PRJ035 | Jun | 2025 | Build | Active
PRJ035 | Jul | 2025 | Deploy | Active
PRJ035 | Aug | 2025 | Deploy | Active
PRJ035 | Sep | 2025 | Deploy | Active
PRJ035 | Oct | 2025 | Build | Active
PRJ035 | Nov | 2025 | Test | Active
PRJ035 | Dec | 2025 | Deploy | Active
PRJ035 | Jan | 2026 | Deploy | Active
PRJ035 | Feb | 2026 | Build | Active
PRJ035 | Mar | 2026 | Test | Active
PRJ035 | Apr | 2026 | Deploy | Active
PRJ035 | May | 2026 | Deploy | Active
PRJ035 | Jun | 2026 | Test | Active
PRJ035 | Jul | 2026 | Discovery | Active
PRJ036 | Jun | 2025 | Discovery | Pipeline
PRJ036 | Jul | 2025 | Deploy | Pipeline
PRJ036 | Aug | 2025 | Design | Pipeline
PRJ036 | Sep | 2025 | Test | Pipeline
PRJ036 | Oct | 2025 | Test | Pipeline
PRJ036 | Nov | 2025 | Design | Pipeline
PRJ036 | Dec | 2025 | Test | Pipeline
PRJ037 | Apr | 2025 | Build | Completed
PRJ037 | May | 2025 | Test | Completed
PRJ037 | Jun | 2025 | Test | Completed
PRJ037 | Jul | 2025 | Test | Completed
PRJ037 | Aug | 2025 | Discovery | Completed
PRJ037 | Sep | 2025 | Build | Completed
PRJ037 | Oct | 2025 | Test | Completed
PRJ038 | Oct | 2025 | Build | Pipeline
PRJ038 | Nov | 2025 | Build | Pipeline
PRJ038 | Dec | 2025 | Build | Pipeline
PRJ038 | Jan | 2026 | Design | Pipeline
PRJ039 | Dec | 2025 | Test | Active
PRJ039 | Jan | 2026 | Discovery | Active
PRJ039 | Feb | 2026 | Discovery | Active
PRJ039 | Mar | 2026 | Discovery | Active
PRJ040 | Mar | 2025 | Discovery | Active
PRJ040 | Apr | 2025 | Test | Active
PRJ040 | May | 2025 | Discovery | Active
PRJ040 | Jun | 2025 | Build | Active
PRJ040 | Jul | 2025 | Design | Active
PRJ040 | Aug | 2025 | Deploy | Active
PRJ040 | Sep | 2025 | Discovery | Active
PRJ040 | Oct | 2025 | Deploy | Active
PRJ040 | Nov | 2025 | Deploy | Active
PRJ040 | Dec | 2025 | Deploy | Active
PRJ040 | Jan | 2026 | Build | Active
PRJ040 | Feb | 2026 | Discovery | Active
PRJ040 | Mar | 2026 | Test | Active
PRJ040 | Apr | 2026 | Build | Active

## Risks
Risk ID | Project ID | Description | Probability | Impact | Velocity | Owner | Mitigation Plan | Status
R001 | PRJ028 | Vendor delay impacting milestone | Medium | High | Medium | John Smith | Increase staffing | Open
R002 | PRJ010 | Stakeholder alignment risk | Low | Low | Medium | Carlos Diaz | Increase staffing | Mitigated
R003 | PRJ008 | Scope creep | High | Medium | Medium | Carlos Diaz | Increase staffing | Open
R004 | PRJ039 | Scope creep | Low | Medium | Medium | Priya Patel | Rebaseline budget | Mitigated
R005 | PRJ023 | Vendor delay impacting milestone | Low | Medium | Fast | Priya Patel | Patch & monitoring | Open
R006 | PRJ010 | Vendor delay impacting milestone | Low | Medium | Medium | Sarah Lee | Patch & monitoring | Mitigated
R007 | PRJ011 | Integration risk | Medium | High | Fast | Alex Brown | Add buffer | Open
R008 | PRJ010 | Resource shortage | High | Low | Fast | John Smith | Rebaseline budget | Closed
R009 | PRJ028 | Stakeholder alignment risk | High | Critical | Medium | Mike Johnson | Engage vendor | Open
R010 | PRJ023 | Regulatory change | Low | High | Fast | Priya Patel | Increase staffing | Closed
R011 | PRJ034 | Scope creep | Low | Medium | Medium | Alex Brown | Add buffer | Open
R012 | PRJ014 | Scope creep | Low | Medium | Medium | Mike Johnson | Rebaseline budget | Open
R013 | PRJ001 | Stakeholder alignment risk | High | Critical | Slow | Jane Doe | Patch & monitoring | Open
R014 | PRJ033 | Technology obsolescence | High | High | Slow | Sarah Lee | Stakeholder workshop | Open
R015 | PRJ028 | Vendor delay impacting milestone | Medium | Low | Medium | Alex Brown | Patch & monitoring | Closed
R016 | PRJ027 | Scope creep | Low | Critical | Slow | Mike Johnson | Engage vendor | Closed
R017 | PRJ024 | Budget overrun forecast | Medium | Low | Slow | Sarah Lee | Increase staffing | Closed
R018 | PRJ034 | Budget overrun forecast | Medium | High | Fast | Mike Johnson | Engage vendor | Mitigated
R019 | PRJ011 | Budget overrun forecast | High | Low | Fast | Alex Brown | Engage vendor | Mitigated
R020 | PRJ023 | Resource shortage | Low | Low | Slow | Mike Johnson | Engage vendor | Open
R021 | PRJ039 | Resource shortage | High | Low | Slow | Carlos Diaz | Stakeholder workshop | Closed
R022 | PRJ030 | Stakeholder alignment risk | High | High | Fast | Mike Johnson | Engage vendor | Closed
R023 | PRJ005 | Stakeholder alignment risk | Medium | High | Medium | Alex Brown | Add buffer | Mitigated
R024 | PRJ033 | Budget overrun forecast | Medium | Critical | Medium | John Smith | Add buffer | Mitigated
R025 | PRJ019 | Budget overrun forecast | High | Low | Fast | Alex Brown | Increase staffing | Closed
R026 | PRJ030 | Technology obsolescence | High | Low | Medium | Carlos Diaz | Increase staffing | Open
R027 | PRJ021 | Stakeholder alignment risk | High | Medium | Slow | Sarah Lee | Add buffer | Mitigated
R028 | PRJ006 | Technology obsolescence | High | Medium | Slow | Jane Doe | Stakeholder workshop | Closed
R029 | PRJ029 | Technology obsolescence | High | Medium | Medium | Mike Johnson | Rebaseline budget | Closed
R030 | PRJ027 | Integration risk | High | Low | Fast | Priya Patel | Rebaseline budget | Open
R031 | PRJ022 | Budget overrun forecast | High | Critical | Medium | Mike Johnson | Stakeholder workshop | Open
R032 | PRJ022 | Budget overrun forecast | High | Medium | Medium | Mike Johnson | Stakeholder workshop | Closed
R033 | PRJ009 | Budget overrun forecast | Medium | Critical | Fast | Carlos Diaz | Rebaseline budget | Open
R034 | PRJ034 | Budget overrun forecast | High | Critical | Fast | Mike Johnson | Add buffer | Mitigated
R035 | PRJ020 | Resource shortage | Low | High | Medium | Jane Doe | Engage vendor | Open
R036 | PRJ010 | Budget overrun forecast | Medium | Low | Fast | Carlos Diaz | Increase staffing | Open
R037 | PRJ022 | Resource shortage | High | Critical | Slow | Jane Doe | Engage vendor | Open
R038 | PRJ029 | Vendor delay impacting milestone | Medium | High | Fast | Priya Patel | Engage vendor | Closed
R039 | PRJ040 | Scope creep | High | Critical | Slow | Alex Brown | Engage vendor | Mitigated
R040 | PRJ031 | Cyber security vulnerability detected | Medium | Critical | Medium | Carlos Diaz | Rebaseline budget | Closed
R041 | PRJ033 | Technology obsolescence | Medium | Medium | Slow | Carlos Diaz | Increase staffing | Open
R042 | PRJ017 | Vendor delay impacting milestone | High | Critical | Medium | Alex Brown | Add buffer | Open
R043 | PRJ019 | Budget overrun forecast | Low | High | Medium | Alex Brown | Engage vendor | Closed
R044 | PRJ006 | Cyber security vulnerability detected | Medium | High | Slow | Sarah Lee | Add buffer | Closed
R045 | PRJ033 | Integration risk | Low | Critical | Slow | Mike Johnson | Engage vendor | Open
R046 | PRJ021 | Budget overrun forecast | High | High | Slow | Jane Doe | Add buffer | Mitigated
R047 | PRJ031 | Resource shortage | High | Critical | Medium | Alex Brown | Add buffer | Open
R048 | PRJ002 | Scope creep | Low | Medium | Fast | Priya Patel | Increase staffing | Closed
R049 | PRJ008 | Scope creep | Low | High | Slow | John Smith | Engage vendor | Closed
R050 | PRJ040 | Stakeholder alignment risk | Low | Low | Medium | Alex Brown | Increase staffing | Open
R051 | PRJ033 | Cyber security vulnerability detected | High | Medium | Medium | Sarah Lee | Add buffer | Mitigated
R052 | PRJ016 | Regulatory change | Low | Low | Fast | Mike Johnson | Add buffer | Open
R053 | PRJ025 | Stakeholder alignment risk | Low | Critical | Medium | Mike Johnson | Stakeholder workshop | Open
R054 | PRJ023 | Budget overrun forecast | Medium | Medium | Fast | Priya Patel | Stakeholder workshop | Open
R055 | PRJ038 | Integration risk | Low | Low | Medium | Alex Brown | Rebaseline budget | Open
R056 | PRJ030 | Stakeholder alignment risk | High | Medium | Slow | John Smith | Stakeholder workshop | Closed
R057 | PRJ003 | Scope creep | Low | Low | Slow | John Smith | Rebaseline budget | Mitigated
R058 | PRJ033 | Regulatory change | High | Critical | Medium | John Smith | Stakeholder workshop | Open
R059 | PRJ019 | Integration risk | Low | High | Medium | John Smith | Rebaseline budget | Closed
R060 | PRJ026 | Stakeholder alignment risk | Medium | High | Slow | Sarah Lee | Stakeholder workshop | Closed

## RAID
RAID ID | Project ID | Type | Description | Probability | Impact | RAG | Owner | Target Resolution Date | Mitigation | Status
RAID001 | PRJ024 | Assumption | Regulatory deadline | Low | Critical | Green | Sarah Lee | 2026-08-02 | Contingency plan | Closed
RAID002 | PRJ019 | Assumption | Cloud provider outage risk | Low | High | Red | Mike Johnson | 2026-05-18 | Re-baseline | Closed
RAID003 | PRJ028 | Issue | Staff turnover | Medium | High | Amber | John Smith | 2026-09-03 | Vendor escalation | Closed
RAID004 | PRJ028 | Assumption | Staff turnover | Low | Low | Red | Priya Patel | 2026-06-12 | Vendor escalation | Closed
RAID005 | PRJ011 | Risk | Test data not available | High | Critical | Green | Jane Doe | 2026-03-18 | Contingency plan | Closed
RAID006 | PRJ024 | Assumption | Depends on procurement signoff | High | Low | Red | Jane Doe | 2026-08-21 | Re-baseline | In Progress
RAID007 | PRJ024 | Dependency | Regulatory deadline | Low | Medium | Red | Mike Johnson | 2026-06-10 | Vendor escalation | Closed
RAID008 | PRJ018 | Issue | Cloud provider outage risk | Low | Medium | Amber | Alex Brown | 2026-06-08 | Add buffer | Open
RAID009 | PRJ017 | Assumption | Staff turnover | Medium | Medium | Red | Mike Johnson | 2026-08-25 | Re-baseline | Open
RAID010 | PRJ008 | Issue | Regulatory deadline | Low | Critical | Green | Priya Patel | 2026-06-22 | Active monitoring | Closed
RAID011 | PRJ021 | Assumption | Staff turnover | Low | High | Amber | Carlos Diaz | 2026-04-10 | Contingency plan | In Progress
RAID012 | PRJ033 | Issue | Cloud provider outage risk | Low | Medium | Green | Carlos Diaz | 2026-07-05 | Active monitoring | In Progress
RAID013 | PRJ036 | Assumption | Depends on procurement signoff | High | Medium | Red | John Smith | 2026-03-17 | Vendor escalation | In Progress
RAID014 | PRJ031 | Dependency | Regulatory deadline | Medium | Low | Green | Mike Johnson | 2026-08-12 | Active monitoring | In Progress
RAID015 | PRJ030 | Assumption | Test data not available | High | Medium | Green | Sarah Lee | 2026-07-07 | Active monitoring | Open
RAID016 | PRJ034 | Issue | Assumes API contract stable | Low | Medium | Amber | Priya Patel | 2026-04-27 | Vendor escalation | Closed
RAID017 | PRJ019 | Risk | Assumes API contract stable | Low | High | Green | Priya Patel | 2026-05-17 | Add buffer | Closed
RAID018 | PRJ006 | Issue | Vendor licence cost rise | High | Medium | Green | Priya Patel | 2026-08-07 | Add buffer | In Progress
RAID019 | PRJ037 | Risk | Regulatory deadline | Low | Low | Green | Priya Patel | 2026-09-14 | Add buffer | In Progress
RAID020 | PRJ014 | Dependency | Vendor licence cost rise | High | Low | Amber | Priya Patel | 2026-07-18 | Vendor escalation | Closed
RAID021 | PRJ020 | Dependency | Test data not available | High | Critical | Amber | Sarah Lee | 2026-03-19 | Active monitoring | Open
RAID022 | PRJ029 | Dependency | Depends on procurement signoff | Medium | Medium | Amber | Alex Brown | 2026-04-06 | Vendor escalation | Closed
RAID023 | PRJ021 | Assumption | Depends on procurement signoff | Low | High | Red | Alex Brown | 2026-03-28 | Vendor escalation | Open
RAID024 | PRJ030 | Risk | Assumes API contract stable | Medium | Medium | Green | John Smith | 2026-03-13 | Vendor escalation | In Progress
RAID025 | PRJ040 | Dependency | Test data not available | Low | High | Red | Priya Patel | 2026-05-20 | Contingency plan | Open
RAID026 | PRJ032 | Dependency | Depends on procurement signoff | Medium | Critical | Green | John Smith | 2026-06-09 | Add buffer | In Progress
RAID027 | PRJ016 | Issue | Vendor licence cost rise | Medium | Low | Green | Mike Johnson | 2026-07-05 | Add buffer | Closed
RAID028 | PRJ031 | Assumption | Vendor licence cost rise | Low | Low | Amber | Jane Doe | 2026-10-12 | Vendor escalation | Closed
RAID029 | PRJ024 | Dependency | Assumes API contract stable | Low | Critical | Green | Alex Brown | 2026-07-22 | Contingency plan | In Progress
RAID030 | PRJ036 | Assumption | Cloud provider outage risk | Medium | Critical | Red | Mike Johnson | 2026-09-28 | Add buffer | Closed
RAID031 | PRJ040 | Risk | Test data not available | Low | Critical | Amber | Carlos Diaz | 2026-05-26 | Add buffer | In Progress
RAID032 | PRJ010 | Issue | Vendor licence cost rise | High | Critical | Red | John Smith | 2026-03-12 | Active monitoring | Open
RAID033 | PRJ022 | Dependency | Vendor licence cost rise | Medium | Medium | Red | Alex Brown | 2026-04-05 | Vendor escalation | Closed
RAID034 | PRJ021 | Issue | Depends on procurement signoff | High | High | Red | Mike Johnson | 2026-07-08 | Add buffer | Closed
RAID035 | PRJ032 | Assumption | Depends on procurement signoff | Low | High | Amber | Priya Patel | 2026-03-29 | Re-baseline | Closed
RAID036 | PRJ020 | Risk | Vendor licence cost rise | Medium | High | Red | Carlos Diaz | 2026-09-15 | Add buffer | Closed
RAID037 | PRJ015 | Risk | Vendor licence cost rise | Medium | Medium | Red | Priya Patel | 2026-09-01 | Add buffer | In Progress
RAID038 | PRJ010 | Issue | Cloud provider outage risk | High | Low | Green | John Smith | 2026-06-21 | Vendor escalation | In Progress
RAID039 | PRJ010 | Dependency | Staff turnover | Low | Critical | Red | Carlos Diaz | 2026-08-04 | Re-baseline | Closed
RAID040 | PRJ004 | Issue | Vendor licence cost rise | Low | High | Red | Sarah Lee | 2026-07-13 | Re-baseline | In Progress
RAID041 | PRJ012 | Dependency | Vendor licence cost rise | Medium | High | Red | Carlos Diaz | 2026-10-09 | Vendor escalation | Closed
RAID042 | PRJ031 | Issue | Test data not available | Medium | High | Green | Mike Johnson | 2026-09-14 | Vendor escalation | Closed
RAID043 | PRJ014 | Dependency | Assumes API contract stable | Medium | High | Red | Carlos Diaz | 2026-09-01 | Vendor escalation | In Progress
RAID044 | PRJ008 | Dependency | Depends on procurement signoff | Medium | Medium | Amber | John Smith | 2026-05-13 | Active monitoring | In Progress
RAID045 | PRJ029 | Assumption | Staff turnover | Medium | Medium | Green | Carlos Diaz | 2026-07-16 | Vendor escalation | Closed
RAID046 | PRJ018 | Issue | Cloud provider outage risk | High | Medium | Green | John Smith | 2026-08-19 | Add buffer | Open
RAID047 | PRJ015 | Risk | Cloud provider outage risk | Medium | High | Red | Sarah Lee | 2026-03-26 | Contingency plan | Open
RAID048 | PRJ036 | Issue | Depends on procurement signoff | High | Critical | Amber | Priya Patel | 2026-04-21 | Vendor escalation | In Progress
RAID049 | PRJ019 | Risk | Regulatory deadline | Low | Medium | Red | Priya Patel | 2026-09-02 | Active monitoring | Open
RAID050 | PRJ027 | Issue | Cloud provider outage risk | Medium | Critical | Green | Priya Patel | 2026-10-10 | Vendor escalation | Open
RAID051 | PRJ001 | Assumption | Vendor licence cost rise | High | Low | Amber | Mike Johnson | 2026-06-25 | Add buffer | Closed
RAID052 | PRJ032 | Issue | Regulatory deadline | High | Critical | Amber | Jane Doe | 2026-09-24 | Active monitoring | In Progress
RAID053 | PRJ011 | Dependency | Staff turnover | Medium | Medium | Green | Priya Patel | 2026-05-26 | Vendor escalation | Closed
RAID054 | PRJ013 | Issue | Vendor licence cost rise | High | Critical | Amber | Alex Brown | 2026-05-23 | Active monitoring | In Progress
RAID055 | PRJ007 | Issue | Test data not available | Medium | High | Green | John Smith | 2026-05-06 | Re-baseline | Open
RAID056 | PRJ029 | Assumption | Assumes API contract stable | Medium | Low | Amber | Priya Patel | 2026-06-01 | Contingency plan | Open
RAID057 | PRJ008 | Dependency | Assumes API contract stable | Low | Critical | Red | Alex Brown | 2026-10-23 | Vendor escalation | Closed
RAID058 | PRJ008 | Assumption | Assumes API contract stable | High | Medium | Green | Jane Doe | 2026-07-01 | Contingency plan | In Progress
RAID059 | PRJ039 | Assumption | Depends on procurement signoff | High | Critical | Red | Carlos Diaz | 2026-08-18 | Contingency plan | Open
RAID060 | PRJ039 | Risk | Vendor licence cost rise | Medium | High | Green | Alex Brown | 2026-03-29 | Active monitoring | Closed
RAID061 | PRJ033 | Issue | Vendor licence cost rise | High | Medium | Green | Mike Johnson | 2026-10-05 | Add buffer | In Progress
RAID062 | PRJ008 | Issue | Staff turnover | High | Critical | Green | Alex Brown | 2026-06-23 | Active monitoring | In Progress
RAID063 | PRJ009 | Dependency | Depends on procurement signoff | High | Low | Red | Sarah Lee | 2026-08-20 | Vendor escalation | Closed
RAID064 | PRJ002 | Dependency | Assumes API contract stable | Low | Medium | Red | John Smith | 2026-03-12 | Re-baseline | In Progress
RAID065 | PRJ005 | Risk | Cloud provider outage risk | Medium | Low | Amber | Sarah Lee | 2026-04-16 | Contingency plan | Closed
RAID066 | PRJ027 | Assumption | Depends on procurement signoff | Medium | Critical | Amber | John Smith | 2026-08-22 | Add buffer | Open
RAID067 | PRJ023 | Risk | Test data not available | High | Critical | Red | Jane Doe | 2026-09-03 | Contingency plan | Open
RAID068 | PRJ002 | Assumption | Depends on procurement signoff | High | Critical | Red | Sarah Lee | 2026-09-27 | Contingency plan | Open
RAID069 | PRJ030 | Assumption | Test data not available | Medium | Medium | Red | Carlos Diaz | 2026-03-29 | Active monitoring | Closed
RAID070 | PRJ027 | Risk | Test data not available | Low | Low | Green | Alex Brown | 2026-03-09 | Re-baseline | Closed
RAID071 | PRJ004 | Issue | Staff turnover | Low | Critical | Amber | Jane Doe | 2026-07-17 | Contingency plan | Open
RAID072 | PRJ009 | Assumption | Test data not available | High | High | Red | Alex Brown | 2026-09-14 | Vendor escalation | Open
RAID073 | PRJ020 | Issue | Staff turnover | High | Medium | Amber | Mike Johnson | 2026-05-10 | Active monitoring | Closed
RAID074 | PRJ038 | Issue | Staff turnover | High | Critical | Red | Sarah Lee | 2026-03-13 | Vendor escalation | Closed
RAID075 | PRJ025 | Assumption | Staff turnover | Medium | Critical | Green | Mike Johnson | 2026-06-05 | Contingency plan | Closed
RAID076 | PRJ031 | Issue | Regulatory deadline | Low | High | Red | Jane Doe | 2026-09-23 | Re-baseline | Open
RAID077 | PRJ036 | Dependency | Depends on procurement signoff | High | Medium | Amber | Jane Doe | 2026-05-05 | Contingency plan | In Progress
RAID078 | PRJ006 | Dependency | Regulatory deadline | Medium | Low | Red | Priya Patel | 2026-09-29 | Contingency plan | Open
RAID079 | PRJ018 | Dependency | Staff turnover | High | Low | Green | Jane Doe | 2026-09-22 | Add buffer | Closed
RAID080 | PRJ036 | Issue | Depends on procurement signoff | Low | High | Amber | John Smith | 2026-04-24 | Contingency plan | Closed

## StageGates
Project ID | Project Name | Governance Channel | Stage | Next Gate | Gate Status | Status | Gate Owner | Planned Gate Date | Actual Gate Date | Gate Outcome | Gate Comments | Checklist Complete % | Days Late | _Key
PRJ001 |  |  | Discovery |  | Approved | Complete | CTO | 2025-02-14 | 2025-03-01 | Conditional | Approved with conditions | 100 | 15
PRJ001 |  |  | Business Case / Seed Funding |  | Pending Approval | In Progress | CTO | 2025-04-15 |  |  | Awaiting sponsor sign-off | 89 | 0
PRJ001 |  |  | Design |  | Not Started | Not Started | CTO | 2025-06-14 |  |  | On track | 0 | 0
PRJ001 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CTO | 2025-08-13 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ001 |  |  | Build |  | Not Started | Not Started | CTO | 2025-10-12 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ001 |  |  | Testing |  | Not Started | Not Started | CTO | 2025-12-11 |  |  | On track | 0 | 0
PRJ001 |  |  | Deployment |  | Not Started | Not Started | CTO | 2026-02-09 |  |  |  | 0 | 0
PRJ001 |  |  | Handover |  | Not Started | Not Started | CTO | 2026-04-10 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ002 |  |  | Discovery |  | Approved | Complete | COO | 2025-03-21 | 2025-03-29 | Rework | On track | 100 | 8
PRJ002 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2025-05-20 | 2025-05-07 | Conditional | Approved with conditions | 100 | 0
PRJ002 |  |  | Design |  | Approved | Complete | COO | 2025-07-19 | 2025-07-05 | Rework | On track | 100 | 0
PRJ002 |  |  | Business Case / Full Funding |  | Pending Approval | In Progress | COO | 2025-09-17 |  |  | Approved with conditions | 61 | 0
PRJ002 |  |  | Build |  | Not Started | Not Started | COO | 2025-11-16 |  |  | On track | 0 | 0
PRJ002 |  |  | Testing |  | Not Started | Not Started | COO | 2026-01-15 |  |  | Approved with conditions | 0 | 0
PRJ002 |  |  | Deployment |  | Not Started | Not Started | COO | 2026-03-16 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ002 |  |  | Handover |  | Not Started | Not Started | COO | 2026-05-15 |  |  | On track | 0 | 0
PRJ003 |  |  | Discovery |  | Approved | Complete | CFO | 2025-04-09 | 2025-04-23 | Conditional | Awaiting sponsor sign-off | 100 | 14
PRJ003 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2025-06-08 | 2025-06-03 | Conditional | On track | 100 | 0
PRJ003 |  |  | Design |  | Approved | Complete | CFO | 2025-08-07 | 2025-08-03 | Proceed |  | 100 | 0
PRJ003 |  |  | Business Case / Full Funding |  | Approved | Complete | CFO | 2025-10-06 | 2025-09-25 | Proceed |  | 100 | 0
PRJ003 |  |  | Build |  | Approved | Complete | CFO | 2025-12-05 | 2025-12-16 | Conditional | Approved with conditions | 100 | 11
PRJ003 |  |  | Testing |  | Approved | Complete | CFO | 2026-02-03 | 2026-01-23 | Conditional |  | 100 | 0
PRJ003 |  |  | Deployment |  | Approved | Complete | CFO | 2026-04-04 | 2026-04-02 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ003 |  |  | Handover |  | In Progress | In Progress | CFO | 2026-06-03 |  |  | On track | 41 | 0
PRJ004 |  |  | Discovery |  | In Progress | In Progress | CTO | 2025-10-01 |  |  |  | 41 | 0
PRJ004 |  |  | Business Case / Seed Funding |  | Not Started | Not Started | CTO | 2025-11-30 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ004 |  |  | Design |  | Not Started | Not Started | CTO | 2026-01-29 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ004 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CTO | 2026-03-30 |  |  | On track | 0 | 0
PRJ004 |  |  | Build |  | Not Started | Not Started | CTO | 2026-05-29 |  |  |  | 0 | 0
PRJ004 |  |  | Testing |  | Not Started | Not Started | CTO | 2026-07-28 |  |  | Approved with conditions | 0 | 0
PRJ004 |  |  | Deployment |  | Not Started | Not Started | CTO | 2026-09-26 |  |  | Approved with conditions | 0 | 0
PRJ004 |  |  | Handover |  | Not Started | Not Started | CTO | 2026-11-25 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ005 |  |  | Discovery |  | Approved | Complete | CFO | 2025-07-22 | 2025-07-24 | Held |  | 100 | 2
PRJ005 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2025-09-20 | 2025-09-28 | Held | On track | 100 | 8
PRJ005 |  |  | Design |  | Approved | Complete | CFO | 2025-11-19 | 2025-12-10 | Conditional | Approved with conditions | 100 | 21
PRJ005 |  |  | Business Case / Full Funding |  | Approved | Complete | CFO | 2026-01-18 | 2026-01-22 | Proceed |  | 100 | 4
PRJ005 |  |  | Build |  | Approved | Complete | CFO | 2026-03-19 | 2026-03-09 | Held | On track | 100 | 0
PRJ005 |  |  | Testing |  | In Progress | In Progress | CFO | 2026-05-18 |  |  |  | 80 | 0
PRJ005 |  |  | Deployment |  | Not Started | Not Started | CFO | 2026-07-17 |  |  | Approved with conditions | 0 | 0
PRJ005 |  |  | Handover |  | Not Started | Not Started | CFO | 2026-09-15 |  |  | On track | 0 | 0
PRJ006 |  |  | Discovery |  | Approved | Complete | CMO | 2025-03-20 | 2025-04-15 | Rework |  | 100 | 26
PRJ006 |  |  | Business Case / Seed Funding |  | Approved | Complete | CMO | 2025-05-19 | 2025-06-06 | Proceed | Approved with conditions | 100 | 18
PRJ006 |  |  | Design |  | Approved | Complete | CMO | 2025-07-18 | 2025-07-16 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ006 |  |  | Business Case / Full Funding |  | Approved | Complete | CMO | 2025-09-16 | 2025-09-03 | Proceed | Awaiting sponsor sign-off | 100 | 0
PRJ006 |  |  | Build |  | Approved | Complete | CMO | 2025-11-15 | 2025-12-04 | Proceed | Approved with conditions | 100 | 19
PRJ006 |  |  | Testing |  | Approved | Complete | CMO | 2026-01-14 | 2026-01-19 | Proceed | Approved with conditions | 100 | 5
PRJ006 |  |  | Deployment |  | Pending Approval | In Progress | CMO | 2026-03-15 |  |  | On track | 44 | 0
PRJ006 |  |  | Handover |  | Not Started | Not Started | CMO | 2026-05-14 |  |  | Approved with conditions | 0 | 0
PRJ007 |  |  | Discovery |  | Approved | Complete | CTO | 2025-05-15 | 2025-06-05 | Held | Awaiting sponsor sign-off | 100 | 21
PRJ007 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2025-07-14 | 2025-07-23 | Conditional |  | 100 | 9
PRJ007 |  |  | Design |  | Approved | Complete | CTO | 2025-09-12 | 2025-09-29 | Rework |  | 100 | 17
PRJ007 |  |  | Business Case / Full Funding |  | In Progress | In Progress | CTO | 2025-11-11 |  |  | Approved with conditions | 93 | 0
PRJ007 |  |  | Build |  | Not Started | Not Started | CTO | 2026-01-10 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ007 |  |  | Testing |  | Not Started | Not Started | CTO | 2026-03-11 |  |  | On track | 0 | 0
PRJ007 |  |  | Deployment |  | Not Started | Not Started | CTO | 2026-05-10 |  |  |  | 0 | 0
PRJ007 |  |  | Handover |  | Not Started | Not Started | CTO | 2026-07-09 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ008 |  |  | Discovery |  | Approved | Complete | CTO | 2025-05-03 | 2025-05-19 | Conditional | Awaiting sponsor sign-off | 100 | 16
PRJ008 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2025-07-02 | 2025-07-22 | Held | On track | 100 | 20
PRJ008 |  |  | Design |  | Approved | Complete | CTO | 2025-08-31 | 2025-08-27 | Held |  | 100 | 0
PRJ008 |  |  | Business Case / Full Funding |  | Approved | Complete | CTO | 2025-10-30 | 2025-11-23 | Rework | Approved with conditions | 100 | 24
PRJ008 |  |  | Build |  | Approved | Complete | CTO | 2025-12-29 | 2026-01-28 | Proceed |  | 100 | 30
PRJ008 |  |  | Testing |  | Approved | Complete | CTO | 2026-02-27 | 2026-03-01 | Conditional | On track | 100 | 2
PRJ008 |  |  | Deployment |  | Approved | Complete | CTO | 2026-04-28 | 2026-05-28 | Conditional | On track | 100 | 30
PRJ008 |  |  | Handover |  | In Progress | In Progress | CTO | 2026-06-27 |  |  |  | 45 | 0
PRJ009 |  |  | Discovery |  | In Progress | In Progress | CFO | 2026-01-01 |  |  | Awaiting sponsor sign-off | 88 | 0
PRJ009 |  |  | Business Case / Seed Funding |  | Not Started | Not Started | CFO | 2026-03-02 |  |  |  | 0 | 0
PRJ009 |  |  | Design |  | Not Started | Not Started | CFO | 2026-05-01 |  |  |  | 0 | 0
PRJ009 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CFO | 2026-06-30 |  |  | On track | 0 | 0
PRJ009 |  |  | Build |  | Not Started | Not Started | CFO | 2026-08-29 |  |  | On track | 0 | 0
PRJ009 |  |  | Testing |  | Not Started | Not Started | CFO | 2026-10-28 |  |  |  | 0 | 0
PRJ009 |  |  | Deployment |  | Not Started | Not Started | CFO | 2026-12-27 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ009 |  |  | Handover |  | Not Started | Not Started | CFO | 2027-02-25 |  |  |  | 0 | 0
PRJ010 |  |  | Discovery |  | Approved | Complete | CFO | 2025-02-06 | 2025-02-15 | Proceed | Awaiting sponsor sign-off | 100 | 9
PRJ010 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2025-04-07 | 2025-04-18 | Held |  | 100 | 11
PRJ010 |  |  | Design |  | Approved | Complete | CFO | 2025-06-06 | 2025-06-26 | Conditional | Approved with conditions | 100 | 20
PRJ010 |  |  | Business Case / Full Funding |  | Approved | Complete | CFO | 2025-08-05 | 2025-09-02 | Held | Approved with conditions | 100 | 28
PRJ010 |  |  | Build |  | Approved | Complete | CFO | 2025-10-04 | 2025-09-27 | Rework | Awaiting sponsor sign-off | 100 | 0
PRJ010 |  |  | Testing |  | In Progress | In Progress | CFO | 2025-12-03 |  |  | Approved with conditions | 44 | 0
PRJ010 |  |  | Deployment |  | Not Started | Not Started | CFO | 2026-02-01 |  |  | On track | 0 | 0
PRJ010 |  |  | Handover |  | Not Started | Not Started | CFO | 2026-04-02 |  |  | On track | 0 | 0
PRJ011 |  |  | Discovery |  | Approved | Complete | CFO | 2025-11-27 | 2025-12-12 | Proceed | Awaiting sponsor sign-off | 100 | 15
PRJ011 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2026-01-26 | 2026-01-27 | Conditional | On track | 100 | 1
PRJ011 |  |  | Design |  | Approved | Complete | CFO | 2026-03-27 | 2026-04-19 | Conditional | On track | 100 | 23
PRJ011 |  |  | Business Case / Full Funding |  | Approved | Complete | CFO | 2026-05-26 | 2026-05-17 | Conditional | Awaiting sponsor sign-off | 100 | 0
PRJ011 |  |  | Build |  | In Progress | In Progress | CFO | 2026-07-25 |  |  | Awaiting sponsor sign-off | 93 | 0
PRJ011 |  |  | Testing |  | Not Started | Not Started | CFO | 2026-09-23 |  |  | On track | 0 | 0
PRJ011 |  |  | Deployment |  | Not Started | Not Started | CFO | 2026-11-22 |  |  | On track | 0 | 0
PRJ011 |  |  | Handover |  | Not Started | Not Started | CFO | 2027-01-21 |  |  | On track | 0 | 0
PRJ012 |  |  | Discovery |  | Approved | Complete | CMO | 2025-10-04 | 2025-10-08 | Rework | Approved with conditions | 100 | 4
PRJ012 |  |  | Business Case / Seed Funding |  | Approved | Complete | CMO | 2025-12-03 | 2025-12-18 | Rework | Approved with conditions | 100 | 15
PRJ012 |  |  | Design |  | In Progress | In Progress | CMO | 2026-02-01 |  |  | Awaiting sponsor sign-off | 87 | 0
PRJ012 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CMO | 2026-04-02 |  |  | On track | 0 | 0
PRJ012 |  |  | Build |  | Not Started | Not Started | CMO | 2026-06-01 |  |  | Approved with conditions | 0 | 0
PRJ012 |  |  | Testing |  | Not Started | Not Started | CMO | 2026-07-31 |  |  | On track | 0 | 0
PRJ012 |  |  | Deployment |  | Not Started | Not Started | CMO | 2026-09-29 |  |  | On track | 0 | 0
PRJ012 |  |  | Handover |  | Not Started | Not Started | CMO | 2026-11-28 |  |  |  | 0 | 0
PRJ013 |  |  | Discovery |  | Approved | Complete | CTO | 2025-12-05 | 2025-12-27 | Conditional |  | 100 | 22
PRJ013 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2026-02-03 | 2026-02-17 | Conditional | On track | 100 | 14
PRJ013 |  |  | Design |  | Approved | Complete | CTO | 2026-04-04 | 2026-04-07 | Proceed | On track | 100 | 3
PRJ013 |  |  | Business Case / Full Funding |  | In Progress | In Progress | CTO | 2026-06-03 |  |  | Approved with conditions | 80 | 0
PRJ013 |  |  | Build |  | Not Started | Not Started | CTO | 2026-08-02 |  |  | Approved with conditions | 0 | 0
PRJ013 |  |  | Testing |  | Not Started | Not Started | CTO | 2026-10-01 |  |  | Approved with conditions | 0 | 0
PRJ013 |  |  | Deployment |  | Not Started | Not Started | CTO | 2026-11-30 |  |  | On track | 0 | 0
PRJ013 |  |  | Handover |  | Not Started | Not Started | CTO | 2027-01-29 |  |  |  | 0 | 0
PRJ014 |  |  | Discovery |  | Approved | Complete | CTO | 2025-02-05 | 2025-02-28 | Held | On track | 100 | 23
PRJ014 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2025-04-06 | 2025-04-25 | Held |  | 100 | 19
PRJ014 |  |  | Design |  | Approved | Complete | CTO | 2025-06-05 | 2025-06-13 | Proceed |  | 100 | 8
PRJ014 |  |  | Business Case / Full Funding |  | Approved | Complete | CTO | 2025-08-04 | 2025-08-04 | Rework | Approved with conditions | 100 | 0
PRJ014 |  |  | Build |  | Approved | Complete | CTO | 2025-10-03 | 2025-10-29 | Proceed | On track | 100 | 26
PRJ014 |  |  | Testing |  | Approved | Complete | CTO | 2025-12-02 | 2025-12-08 | Held |  | 100 | 6
PRJ014 |  |  | Deployment |  | Approved | Complete | CTO | 2026-01-31 | 2026-01-16 | Proceed | Awaiting sponsor sign-off | 100 | 0
PRJ014 |  |  | Handover |  | Pending Approval | In Progress | CTO | 2026-04-01 |  |  | On track | 63 | 0
PRJ015 |  |  | Discovery |  | Approved | Complete | CIO | 2025-06-03 | 2025-06-17 | Conditional | Awaiting sponsor sign-off | 100 | 14
PRJ015 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2025-08-02 | 2025-07-19 | Held |  | 100 | 0
PRJ015 |  |  | Design |  | Approved | Complete | CIO | 2025-10-01 | 2025-10-04 | Held |  | 100 | 3
PRJ015 |  |  | Business Case / Full Funding |  | Approved | Complete | CIO | 2025-11-30 | 2025-11-22 | Conditional | Awaiting sponsor sign-off | 100 | 0
PRJ015 |  |  | Build |  | Approved | Complete | CIO | 2026-01-29 | 2026-02-02 | Rework | On track | 100 | 4
PRJ015 |  |  | Testing |  | Approved | Complete | CIO | 2026-03-30 | 2026-03-28 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ015 |  |  | Deployment |  | Pending Approval | In Progress | CIO | 2026-05-29 |  |  | On track | 86 | 0
PRJ015 |  |  | Handover |  | Not Started | Not Started | CIO | 2026-07-28 |  |  | On track | 0 | 0
PRJ016 |  |  | Discovery |  | Approved | Complete | CIO | 2025-12-01 | 2025-11-20 | Rework |  | 100 | 0
PRJ016 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2026-01-30 | 2026-03-01 | Proceed |  | 100 | 30
PRJ016 |  |  | Design |  | Approved | Complete | CIO | 2026-03-31 | 2026-04-06 | Proceed | Approved with conditions | 100 | 6
PRJ016 |  |  | Business Case / Full Funding |  | Approved | Complete | CIO | 2026-05-30 | 2026-05-30 | Conditional | Approved with conditions | 100 | 0
PRJ016 |  |  | Build |  | Approved | Complete | CIO | 2026-07-29 | 2026-08-04 | Held | On track | 100 | 6
PRJ016 |  |  | Testing |  | In Progress | In Progress | CIO | 2026-09-27 |  |  | Approved with conditions | 51 | 0
PRJ016 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-11-26 |  |  | On track | 0 | 0
PRJ016 |  |  | Handover |  | Not Started | Not Started | CIO | 2027-01-25 |  |  |  | 0 | 0
PRJ017 |  |  | Discovery |  | Approved | Complete | CFO | 2025-02-17 | 2025-03-02 | Held | On track | 100 | 13
PRJ017 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2025-04-18 | 2025-04-03 | Conditional | Approved with conditions | 100 | 0
PRJ017 |  |  | Design |  | Approved | Complete | CFO | 2025-06-17 | 2025-06-19 | Proceed |  | 100 | 2
PRJ017 |  |  | Business Case / Full Funding |  | Pending Approval | In Progress | CFO | 2025-08-16 |  |  | Awaiting sponsor sign-off | 60 | 0
PRJ017 |  |  | Build |  | Not Started | Not Started | CFO | 2025-10-15 |  |  | On track | 0 | 0
PRJ017 |  |  | Testing |  | Not Started | Not Started | CFO | 2025-12-14 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ017 |  |  | Deployment |  | Not Started | Not Started | CFO | 2026-02-12 |  |  | On track | 0 | 0
PRJ017 |  |  | Handover |  | Not Started | Not Started | CFO | 2026-04-13 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ018 |  |  | Discovery |  | Approved | Complete | COO | 2025-10-26 | 2025-11-19 | Held |  | 100 | 24
PRJ018 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2025-12-25 | 2026-01-01 | Rework | On track | 100 | 7
PRJ018 |  |  | Design |  | Approved | Complete | COO | 2026-02-23 | 2026-03-19 | Conditional | Awaiting sponsor sign-off | 100 | 24
PRJ018 |  |  | Business Case / Full Funding |  | Approved | Complete | COO | 2026-04-24 | 2026-05-18 | Proceed | Approved with conditions | 100 | 24
PRJ018 |  |  | Build |  | Approved | Complete | COO | 2026-06-23 | 2026-06-28 | Proceed | Approved with conditions | 100 | 5
PRJ018 |  |  | Testing |  | Approved | Complete | COO | 2026-08-22 | 2026-08-26 | Proceed | Approved with conditions | 100 | 4
PRJ018 |  |  | Deployment |  | Pending Approval | In Progress | COO | 2026-10-21 |  |  | On track | 66 | 0
PRJ018 |  |  | Handover |  | Not Started | Not Started | COO | 2026-12-20 |  |  | Approved with conditions | 0 | 0
PRJ019 |  |  | Discovery |  | Approved | Complete | COO | 2025-03-25 | 2025-04-06 | Conditional | On track | 100 | 12
PRJ019 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2025-05-24 | 2025-06-18 | Conditional | Approved with conditions | 100 | 25
PRJ019 |  |  | Design |  | Approved | Complete | COO | 2025-07-23 | 2025-08-08 | Rework | Approved with conditions | 100 | 16
PRJ019 |  |  | Business Case / Full Funding |  | Approved | Complete | COO | 2025-09-21 | 2025-09-17 | Rework | On track | 100 | 0
PRJ019 |  |  | Build |  | Approved | Complete | COO | 2025-11-20 | 2025-12-14 | Proceed | Awaiting sponsor sign-off | 100 | 24
PRJ019 |  |  | Testing |  | Approved | Complete | COO | 2026-01-19 | 2026-01-04 | Held | Approved with conditions | 100 | 0
PRJ019 |  |  | Deployment |  | In Progress | In Progress | COO | 2026-03-20 |  |  | On track | 66 | 0
PRJ019 |  |  | Handover |  | Not Started | Not Started | COO | 2026-05-19 |  |  | On track | 0 | 0
PRJ020 |  |  | Discovery |  | Approved | Complete | CIO | 2025-04-25 | 2025-05-25 | Held | On track | 100 | 30
PRJ020 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2025-06-24 | 2025-06-19 | Proceed |  | 100 | 0
PRJ020 |  |  | Design |  | Approved | Complete | CIO | 2025-08-23 | 2025-08-22 | Rework |  | 100 | 0
PRJ020 |  |  | Business Case / Full Funding |  | Approved | Complete | CIO | 2025-10-22 | 2025-10-24 | Conditional | Awaiting sponsor sign-off | 100 | 2
PRJ020 |  |  | Build |  | Approved | Complete | CIO | 2025-12-21 | 2025-12-16 | Held | On track | 100 | 0
PRJ020 |  |  | Testing |  | Approved | Complete | CIO | 2026-02-19 | 2026-03-11 | Proceed |  | 100 | 20
PRJ020 |  |  | Deployment |  | In Progress | In Progress | CIO | 2026-04-20 |  |  |  | 88 | 0
PRJ020 |  |  | Handover |  | Not Started | Not Started | CIO | 2026-06-19 |  |  | Approved with conditions | 0 | 0
PRJ021 |  |  | Discovery |  | Approved | Complete | CTO | 2025-01-20 | 2025-01-11 | Conditional | Awaiting sponsor sign-off | 100 | 0
PRJ021 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2025-03-21 | 2025-03-08 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ021 |  |  | Design |  | Approved | Complete | CTO | 2025-05-20 | 2025-05-27 | Proceed | On track | 100 | 7
PRJ021 |  |  | Business Case / Full Funding |  | Approved | Complete | CTO | 2025-07-19 | 2025-07-11 | Conditional | Approved with conditions | 100 | 0
PRJ021 |  |  | Build |  | Approved | Complete | CTO | 2025-09-17 | 2025-10-09 | Rework | On track | 100 | 22
PRJ021 |  |  | Testing |  | Approved | Complete | CTO | 2025-11-16 | 2025-11-11 | Conditional | Approved with conditions | 100 | 0
PRJ021 |  |  | Deployment |  | Pending Approval | In Progress | CTO | 2026-01-15 |  |  | Awaiting sponsor sign-off | 74 | 0
PRJ021 |  |  | Handover |  | Not Started | Not Started | CTO | 2026-03-16 |  |  | Approved with conditions | 0 | 0
PRJ022 |  |  | Discovery |  | Approved | Complete | CIO | 2025-04-11 | 2025-05-11 | Rework | Awaiting sponsor sign-off | 100 | 30
PRJ022 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2025-06-10 | 2025-07-01 | Rework |  | 100 | 21
PRJ022 |  |  | Design |  | Approved | Complete | CIO | 2025-08-09 | 2025-08-02 | Held |  | 100 | 0
PRJ022 |  |  | Business Case / Full Funding |  | Approved | Complete | CIO | 2025-10-08 | 2025-10-10 | Conditional | Approved with conditions | 100 | 2
PRJ022 |  |  | Build |  | Approved | Complete | CIO | 2025-12-07 | 2025-12-07 | Conditional | Awaiting sponsor sign-off | 100 | 0
PRJ022 |  |  | Testing |  | In Progress | In Progress | CIO | 2026-02-05 |  |  | On track | 49 | 0
PRJ022 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-04-06 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ022 |  |  | Handover |  | Not Started | Not Started | CIO | 2026-06-05 |  |  | On track | 0 | 0
PRJ023 |  |  | Discovery |  | Approved | Complete | COO | 2025-11-12 | 2025-11-25 | Proceed |  | 100 | 13
PRJ023 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2026-01-11 | 2026-01-21 | Rework | Awaiting sponsor sign-off | 100 | 10
PRJ023 |  |  | Design |  | Approved | Complete | COO | 2026-03-12 | 2026-03-26 | Held | Awaiting sponsor sign-off | 100 | 14
PRJ023 |  |  | Business Case / Full Funding |  | Approved | Complete | COO | 2026-05-11 | 2026-06-02 | Proceed |  | 100 | 22
PRJ023 |  |  | Build |  | Approved | Complete | COO | 2026-07-10 | 2026-07-24 | Rework |  | 100 | 14
PRJ023 |  |  | Testing |  | Approved | Complete | COO | 2026-09-08 | 2026-09-27 | Held | Approved with conditions | 100 | 19
PRJ023 |  |  | Deployment |  | Pending Approval | In Progress | COO | 2026-11-07 |  |  | On track | 57 | 0
PRJ023 |  |  | Handover |  | Not Started | Not Started | COO | 2027-01-06 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ024 |  |  | Discovery |  | Approved | Complete | CFO | 2025-12-06 | 2025-12-26 | Conditional | On track | 100 | 20
PRJ024 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2026-02-04 | 2026-02-10 | Proceed |  | 100 | 6
PRJ024 |  |  | Design |  | Approved | Complete | CFO | 2026-04-05 | 2026-03-27 | Held |  | 100 | 0
PRJ024 |  |  | Business Case / Full Funding |  | Approved | Complete | CFO | 2026-06-04 | 2026-05-27 | Conditional | On track | 100 | 0
PRJ024 |  |  | Build |  | Approved | Complete | CFO | 2026-08-03 | 2026-08-17 | Proceed | On track | 100 | 14
PRJ024 |  |  | Testing |  | Pending Approval | In Progress | CFO | 2026-10-02 |  |  | Awaiting sponsor sign-off | 50 | 0
PRJ024 |  |  | Deployment |  | Not Started | Not Started | CFO | 2026-12-01 |  |  |  | 0 | 0
PRJ024 |  |  | Handover |  | Not Started | Not Started | CFO | 2027-01-30 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ025 |  |  | Discovery |  | Approved | Complete | CTO | 2025-12-02 | 2025-11-22 | Rework | Approved with conditions | 100 | 0
PRJ025 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2026-01-31 | 2026-01-19 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ025 |  |  | Design |  | Approved | Complete | CTO | 2026-04-01 | 2026-04-30 | Conditional | On track | 100 | 29
PRJ025 |  |  | Business Case / Full Funding |  | Approved | Complete | CTO | 2026-05-31 | 2026-06-26 | Proceed |  | 100 | 26
PRJ025 |  |  | Build |  | Pending Approval | In Progress | CTO | 2026-07-30 |  |  | On track | 44 | 0
PRJ025 |  |  | Testing |  | Not Started | Not Started | CTO | 2026-09-28 |  |  | Approved with conditions | 0 | 0
PRJ025 |  |  | Deployment |  | Not Started | Not Started | CTO | 2026-11-27 |  |  | On track | 0 | 0
PRJ025 |  |  | Handover |  | Not Started | Not Started | CTO | 2027-01-26 |  |  |  | 0 | 0
PRJ026 |  |  | Discovery |  | Approved | Complete | COO | 2025-09-16 | 2025-09-08 | Held | Approved with conditions | 100 | 0
PRJ026 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2025-11-15 | 2025-11-30 | Proceed | Approved with conditions | 100 | 15
PRJ026 |  |  | Design |  | Approved | Complete | COO | 2026-01-14 | 2026-01-23 | Proceed |  | 100 | 9
PRJ026 |  |  | Business Case / Full Funding |  | Approved | Complete | COO | 2026-03-15 | 2026-03-06 | Rework | Awaiting sponsor sign-off | 100 | 0
PRJ026 |  |  | Build |  | Approved | Complete | COO | 2026-05-14 | 2026-05-18 | Conditional | On track | 100 | 4
PRJ026 |  |  | Testing |  | Pending Approval | In Progress | COO | 2026-07-13 |  |  |  | 73 | 0
PRJ026 |  |  | Deployment |  | Not Started | Not Started | COO | 2026-09-11 |  |  |  | 0 | 0
PRJ026 |  |  | Handover |  | Not Started | Not Started | COO | 2026-11-10 |  |  | Approved with conditions | 0 | 0
PRJ027 |  |  | Discovery |  | Approved | Complete | CMO | 2025-04-29 | 2025-05-06 | Conditional | Approved with conditions | 100 | 7
PRJ027 |  |  | Business Case / Seed Funding |  | Approved | Complete | CMO | 2025-06-28 | 2025-07-09 | Held | Approved with conditions | 100 | 11
PRJ027 |  |  | Design |  | Approved | Complete | CMO | 2025-08-27 | 2025-08-17 | Proceed | Approved with conditions | 100 | 0
PRJ027 |  |  | Business Case / Full Funding |  | Approved | Complete | CMO | 2025-10-26 | 2025-10-18 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ027 |  |  | Build |  | Approved | Complete | CMO | 2025-12-25 | 2026-01-06 | Rework | Approved with conditions | 100 | 12
PRJ027 |  |  | Testing |  | Approved | Complete | CMO | 2026-02-23 | 2026-02-23 | Rework |  | 100 | 0
PRJ027 |  |  | Deployment |  | Approved | Complete | CMO | 2026-04-24 | 2026-04-24 | Rework |  | 100 | 0
PRJ027 |  |  | Handover |  | In Progress | In Progress | CMO | 2026-06-23 |  |  | Approved with conditions | 73 | 0
PRJ028 |  |  | Discovery |  | Approved | Complete | CTO | 2025-01-04 | 2025-01-14 | Rework |  | 100 | 10
PRJ028 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2025-03-05 | 2025-03-05 | Held | On track | 100 | 0
PRJ028 |  |  | Design |  | Approved | Complete | CTO | 2025-05-04 | 2025-04-26 | Conditional | On track | 100 | 0
PRJ028 |  |  | Business Case / Full Funding |  | Pending Approval | In Progress | CTO | 2025-07-03 |  |  |  | 63 | 0
PRJ028 |  |  | Build |  | Not Started | Not Started | CTO | 2025-09-01 |  |  | Approved with conditions | 0 | 0
PRJ028 |  |  | Testing |  | Not Started | Not Started | CTO | 2025-10-31 |  |  | On track | 0 | 0
PRJ028 |  |  | Deployment |  | Not Started | Not Started | CTO | 2025-12-30 |  |  | Approved with conditions | 0 | 0
PRJ028 |  |  | Handover |  | Not Started | Not Started | CTO | 2026-02-28 |  |  |  | 0 | 0
PRJ029 |  |  | Discovery |  | Pending Approval | In Progress | CIO | 2025-11-15 |  |  |  | 56 | 0
PRJ029 |  |  | Business Case / Seed Funding |  | Not Started | Not Started | CIO | 2026-01-14 |  |  |  | 0 | 0
PRJ029 |  |  | Design |  | Not Started | Not Started | CIO | 2026-03-15 |  |  | On track | 0 | 0
PRJ029 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CIO | 2026-05-14 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ029 |  |  | Build |  | Not Started | Not Started | CIO | 2026-07-13 |  |  | On track | 0 | 0
PRJ029 |  |  | Testing |  | Not Started | Not Started | CIO | 2026-09-11 |  |  | On track | 0 | 0
PRJ029 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-11-10 |  |  | Approved with conditions | 0 | 0
PRJ029 |  |  | Handover |  | Not Started | Not Started | CIO | 2027-01-09 |  |  |  | 0 | 0
PRJ030 |  |  | Discovery |  | Approved | Complete | COO | 2025-05-10 | 2025-04-30 | Conditional | Approved with conditions | 100 | 0
PRJ030 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2025-07-09 | 2025-07-28 | Rework | On track | 100 | 19
PRJ030 |  |  | Design |  | Approved | Complete | COO | 2025-09-07 | 2025-09-29 | Proceed | Awaiting sponsor sign-off | 100 | 22
PRJ030 |  |  | Business Case / Full Funding |  | Approved | Complete | COO | 2025-11-06 | 2025-12-05 | Held | Approved with conditions | 100 | 29
PRJ030 |  |  | Build |  | Pending Approval | In Progress | COO | 2026-01-05 |  |  |  | 67 | 0
PRJ030 |  |  | Testing |  | Not Started | Not Started | COO | 2026-03-06 |  |  | On track | 0 | 0
PRJ030 |  |  | Deployment |  | Not Started | Not Started | COO | 2026-05-05 |  |  |  | 0 | 0
PRJ030 |  |  | Handover |  | Not Started | Not Started | COO | 2026-07-04 |  |  | Approved with conditions | 0 | 0
PRJ031 |  |  | Discovery |  | Approved | Complete | CIO | 2025-08-27 | 2025-08-12 | Conditional |  | 100 | 0
PRJ031 |  |  | Business Case / Seed Funding |  | In Progress | In Progress | CIO | 2025-10-26 |  |  | Awaiting sponsor sign-off | 73 | 0
PRJ031 |  |  | Design |  | Not Started | Not Started | CIO | 2025-12-25 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ031 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CIO | 2026-02-23 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ031 |  |  | Build |  | Not Started | Not Started | CIO | 2026-04-24 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ031 |  |  | Testing |  | Not Started | Not Started | CIO | 2026-06-23 |  |  |  | 0 | 0
PRJ031 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-08-22 |  |  | On track | 0 | 0
PRJ031 |  |  | Handover |  | Not Started | Not Started | CIO | 2026-10-21 |  |  |  | 0 | 0
PRJ032 |  |  | Discovery |  | Approved | Complete | CIO | 2025-12-20 | 2026-01-19 | Proceed | On track | 100 | 30
PRJ032 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2026-02-18 | 2026-03-04 | Rework |  | 100 | 14
PRJ032 |  |  | Design |  | Approved | Complete | CIO | 2026-04-19 | 2026-05-05 | Conditional | Awaiting sponsor sign-off | 100 | 16
PRJ032 |  |  | Business Case / Full Funding |  | Approved | Complete | CIO | 2026-06-18 | 2026-06-13 | Rework |  | 100 | 0
PRJ032 |  |  | Build |  | Pending Approval | In Progress | CIO | 2026-08-17 |  |  | Approved with conditions | 87 | 0
PRJ032 |  |  | Testing |  | Not Started | Not Started | CIO | 2026-10-16 |  |  |  | 0 | 0
PRJ032 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-12-15 |  |  |  | 0 | 0
PRJ032 |  |  | Handover |  | Not Started | Not Started | CIO | 2027-02-13 |  |  |  | 0 | 0
PRJ033 |  |  | Discovery |  | Approved | Complete | CTO | 2025-11-22 | 2025-11-30 | Held | Approved with conditions | 100 | 8
PRJ033 |  |  | Business Case / Seed Funding |  | Approved | Complete | CTO | 2026-01-21 | 2026-01-17 | Proceed | On track | 100 | 0
PRJ033 |  |  | Design |  | Approved | Complete | CTO | 2026-03-22 | 2026-03-21 | Rework | Approved with conditions | 100 | 0
PRJ033 |  |  | Business Case / Full Funding |  | Approved | Complete | CTO | 2026-05-21 | 2026-06-01 | Rework | Awaiting sponsor sign-off | 100 | 11
PRJ033 |  |  | Build |  | Approved | Complete | CTO | 2026-07-20 | 2026-07-09 | Rework |  | 100 | 0
PRJ033 |  |  | Testing |  | Approved | Complete | CTO | 2026-09-18 | 2026-10-05 | Proceed | Approved with conditions | 100 | 17
PRJ033 |  |  | Deployment |  | Approved | Complete | CTO | 2026-11-17 | 2026-11-16 | Proceed | On track | 100 | 0
PRJ033 |  |  | Handover |  | In Progress | In Progress | CTO | 2027-01-16 |  |  | Awaiting sponsor sign-off | 89 | 0
PRJ034 |  |  | Discovery |  | Approved | Complete | CMO | 2025-11-09 | 2025-11-14 | Proceed | On track | 100 | 5
PRJ034 |  |  | Business Case / Seed Funding |  | Approved | Complete | CMO | 2026-01-08 | 2025-12-24 | Rework | Approved with conditions | 100 | 0
PRJ034 |  |  | Design |  | Approved | Complete | CMO | 2026-03-09 | 2026-03-12 | Rework | Approved with conditions | 100 | 3
PRJ034 |  |  | Business Case / Full Funding |  | Approved | Complete | CMO | 2026-05-08 | 2026-05-22 | Rework | On track | 100 | 14
PRJ034 |  |  | Build |  | Pending Approval | In Progress | CMO | 2026-07-07 |  |  | Approved with conditions | 40 | 0
PRJ034 |  |  | Testing |  | Not Started | Not Started | CMO | 2026-09-05 |  |  |  | 0 | 0
PRJ034 |  |  | Deployment |  | Not Started | Not Started | CMO | 2026-11-04 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ034 |  |  | Handover |  | Not Started | Not Started | CMO | 2027-01-03 |  |  |  | 0 | 0
PRJ035 |  |  | Discovery |  | Approved | Complete | COO | 2025-05-04 | 2025-04-19 | Held | Awaiting sponsor sign-off | 100 | 0
PRJ035 |  |  | Business Case / Seed Funding |  | Approved | Complete | COO | 2025-07-03 | 2025-06-24 | Conditional | Approved with conditions | 100 | 0
PRJ035 |  |  | Design |  | Approved | Complete | COO | 2025-09-01 | 2025-09-12 | Held |  | 100 | 11
PRJ035 |  |  | Business Case / Full Funding |  | Approved | Complete | COO | 2025-10-31 | 2025-10-25 | Rework |  | 100 | 0
PRJ035 |  |  | Build |  | Approved | Complete | COO | 2025-12-30 | 2025-12-17 | Conditional | On track | 100 | 0
PRJ035 |  |  | Testing |  | In Progress | In Progress | COO | 2026-02-28 |  |  | On track | 87 | 0
PRJ035 |  |  | Deployment |  | Not Started | Not Started | COO | 2026-04-29 |  |  |  | 0 | 0
PRJ035 |  |  | Handover |  | Not Started | Not Started | COO | 2026-06-28 |  |  | Approved with conditions | 0 | 0
PRJ036 |  |  | Discovery |  | Approved | Complete | CFO | 2025-05-09 | 2025-04-28 | Proceed | On track | 100 | 0
PRJ036 |  |  | Business Case / Seed Funding |  | Approved | Complete | CFO | 2025-07-08 | 2025-08-04 | Conditional | Approved with conditions | 100 | 27
PRJ036 |  |  | Design |  | Approved | Complete | CFO | 2025-09-06 | 2025-09-09 | Rework | Awaiting sponsor sign-off | 100 | 3
PRJ036 |  |  | Business Case / Full Funding |  | Approved | Complete | CFO | 2025-11-05 | 2025-11-15 | Rework | Awaiting sponsor sign-off | 100 | 10
PRJ036 |  |  | Build |  | Approved | Complete | CFO | 2026-01-04 | 2026-01-17 | Rework | Approved with conditions | 100 | 13
PRJ036 |  |  | Testing |  | Approved | Complete | CFO | 2026-03-05 | 2026-02-22 | Conditional | Approved with conditions | 100 | 0
PRJ036 |  |  | Deployment |  | Pending Approval | In Progress | CFO | 2026-05-04 |  |  | Approved with conditions | 46 | 0
PRJ036 |  |  | Handover |  | Not Started | Not Started | CFO | 2026-07-03 |  |  | On track | 0 | 0
PRJ037 |  |  | Discovery |  | Approved | Complete | CMO | 2025-03-06 | 2025-03-11 | Held |  | 100 | 5
PRJ037 |  |  | Business Case / Seed Funding |  | Approved | Complete | CMO | 2025-05-05 | 2025-05-24 | Rework | Approved with conditions | 100 | 19
PRJ037 |  |  | Design |  | Approved | Complete | CMO | 2025-07-04 | 2025-07-17 | Rework | On track | 100 | 13
PRJ037 |  |  | Business Case / Full Funding |  | Approved | Complete | CMO | 2025-09-02 | 2025-09-03 | Proceed |  | 100 | 1
PRJ037 |  |  | Build |  | Approved | Complete | CMO | 2025-11-01 | 2025-10-27 | Rework |  | 100 | 0
PRJ037 |  |  | Testing |  | Approved | Complete | CMO | 2025-12-31 | 2025-12-29 | Rework | Approved with conditions | 100 | 0
PRJ037 |  |  | Deployment |  | Approved | Complete | CMO | 2026-03-01 | 2026-02-19 | Conditional | Awaiting sponsor sign-off | 100 | 0
PRJ037 |  |  | Handover |  | Pending Approval | In Progress | CMO | 2026-04-30 |  |  | Awaiting sponsor sign-off | 56 | 0
PRJ038 |  |  | Discovery |  | Approved | Complete | CIO | 2025-09-09 | 2025-08-26 | Held | On track | 100 | 0
PRJ038 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2025-11-08 | 2025-11-28 | Conditional |  | 100 | 20
PRJ038 |  |  | Design |  | Pending Approval | In Progress | CIO | 2026-01-07 |  |  | Approved with conditions | 47 | 0
PRJ038 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CIO | 2026-03-08 |  |  |  | 0 | 0
PRJ038 |  |  | Build |  | Not Started | Not Started | CIO | 2026-05-07 |  |  | Approved with conditions | 0 | 0
PRJ038 |  |  | Testing |  | Not Started | Not Started | CIO | 2026-07-06 |  |  | On track | 0 | 0
PRJ038 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-09-04 |  |  |  | 0 | 0
PRJ038 |  |  | Handover |  | Not Started | Not Started | CIO | 2026-11-03 |  |  | Awaiting sponsor sign-off | 0 | 0
PRJ039 |  |  | Discovery |  | Approved | Complete | CIO | 2025-11-14 | 2025-10-31 | Proceed | Approved with conditions | 100 | 0
PRJ039 |  |  | Business Case / Seed Funding |  | In Progress | In Progress | CIO | 2026-01-13 |  |  | Approved with conditions | 45 | 0
PRJ039 |  |  | Design |  | Not Started | Not Started | CIO | 2026-03-14 |  |  |  | 0 | 0
PRJ039 |  |  | Business Case / Full Funding |  | Not Started | Not Started | CIO | 2026-05-13 |  |  | On track | 0 | 0
PRJ039 |  |  | Build |  | Not Started | Not Started | CIO | 2026-07-12 |  |  | Approved with conditions | 0 | 0
PRJ039 |  |  | Testing |  | Not Started | Not Started | CIO | 2026-09-10 |  |  | On track | 0 | 0
PRJ039 |  |  | Deployment |  | Not Started | Not Started | CIO | 2026-11-09 |  |  | On track | 0 | 0
PRJ039 |  |  | Handover |  | Not Started | Not Started | CIO | 2027-01-08 |  |  | On track | 0 | 0
PRJ040 |  |  | Discovery |  | Approved | Complete | CIO | 2025-02-06 | 2025-02-02 | Rework | Approved with conditions | 100 | 0
PRJ040 |  |  | Business Case / Seed Funding |  | Approved | Complete | CIO | 2025-04-07 | 2025-04-03 | Rework | Awaiting sponsor sign-off | 100 | 0
PRJ040 |  |  | Design |  | Approved | Complete | CIO | 2025-06-06 | 2025-06-19 | Conditional |  | 100 | 13
PRJ040 |  |  | Business Case / Full Funding |  | Approved | Complete | CIO | 2025-08-05 | 2025-08-29 | Conditional | Awaiting sponsor sign-off | 100 | 24
PRJ040 |  |  | Build |  | Approved | Complete | CIO | 2025-10-04 | 2025-10-20 | Held | On track | 100 | 16
PRJ040 |  |  | Testing |  | Approved | Complete | CIO | 2025-12-03 | 2025-11-21 | Proceed | Awaiting sponsor sign-off | 100 | 0
PRJ040 |  |  | Deployment |  | Pending Approval | In Progress | CIO | 2026-02-01 |  |  | On track | 52 | 0
PRJ040 |  |  | Handover |  | Not Started | Not Started | CIO | 2026-04-02 |  |  | Approved with conditions | 0 | 0

## Financials
Project ID | Month | CAPEX | OPEX | Actual | Forecast | Variance | Planned Value | Earned Value
PRJ001 | Jan |  |  | 261933 | 301306 |  | 251156 | 195289
PRJ001 | Feb |  |  | 231778 | 225033 |  | 192576 | 147431
PRJ001 | Mar |  |  | 174362 | 182142 |  | 135066 | 165831
PRJ001 | Apr |  |  | 272440 | 283263 |  | 203135 | 213717
PRJ001 | May |  |  | 237193 | 204783 |  | 223895 | 154098
PRJ001 | Jun |  |  | 222203 | 317214 |  | 276980 | 191631
PRJ001 | Jul |  |  | 245586 | 292094 |  | 208528 | 227833
PRJ001 | Aug |  |  | 239886 | 257711 |  | 271464 | 259232
PRJ001 | Sep |  |  | 164832 | 179916 |  | 165087 | 134079
PRJ001 | Oct |  |  | 175825 | 157796 |  | 137163 | 147237
PRJ001 | Nov |  |  | 227590 | 270516 |  | 274054 | 288863
PRJ001 | Dec |  |  | 291696 | 322783 |  | 247640 | 276531
PRJ002 | Jan |  |  | 90038 | 112009 |  | 99705 | 117449
PRJ002 | Feb |  |  | 194030 | 198009 |  | 208543 | 184132
PRJ002 | Mar |  |  | 150645 | 221694 |  | 176779 | 152997
PRJ002 | Apr |  |  | 143262 | 168928 |  | 147024 | 112397
PRJ002 | May |  |  | 140984 | 240376 |  | 225186 | 225828
PRJ002 | Jun |  |  | 141736 | 124067 |  | 125912 | 92231
PRJ002 | Jul |  |  | 185760 | 164296 |  | 167790 | 152441
PRJ002 | Aug |  |  | 136745 | 179635 |  | 151856 | 131156
PRJ002 | Sep |  |  | 69148 | 94453 |  | 86663 | 83175
PRJ002 | Oct |  |  | 127592 | 135243 |  | 130937 | 138204
PRJ002 | Nov |  |  | 122553 | 165200 |  | 174324 | 129142
PRJ002 | Dec |  |  | 105554 | 156157 |  | 144984 | 147917
PRJ003 | Jan |  |  | 246820 | 400266 |  | 352250 | 302762
PRJ003 | Feb |  |  | 191842 | 315504 |  | 233702 | 180038
PRJ003 | Mar |  |  | 215485 | 245450 |  | 214893 | 160400
PRJ003 | Apr |  |  | 155226 | 259102 |  | 240477 | 164323
PRJ003 | May |  |  | 214757 | 306212 |  | 264408 | 195386
PRJ003 | Jun |  |  | 140201 | 173015 |  | 182088 | 135960
PRJ003 | Jul |  |  | 281245 | 278907 |  | 274688 | 203699
PRJ003 | Aug |  |  | 319411 | 374893 |  | 346630 | 268023
PRJ003 | Sep |  |  | 219420 | 239819 |  | 183684 | 165785
PRJ003 | Oct |  |  | 348332 | 404205 |  | 376863 | 360982
PRJ003 | Nov |  |  | 322568 | 317967 |  | 304740 | 246739
PRJ003 | Dec |  |  | 273940 | 293508 |  | 280505 | 263358
PRJ004 | Jan |  |  | 97924 | 161584 |  | 123799 | 147410
PRJ004 | Feb |  |  | 119620 | 181451 |  | 179974 | 139656
PRJ004 | Mar |  |  | 175239 | 166179 |  | 169227 | 166386
PRJ004 | Apr |  |  | 72332 | 88892 |  | 77455 | 70936
PRJ004 | May |  |  | 156706 | 177183 |  | 151959 | 131649
PRJ004 | Jun |  |  | 105284 | 122028 |  | 105908 | 88714
PRJ004 | Jul |  |  | 75910 | 86245 |  | 77166 | 65885
PRJ004 | Aug |  |  | 82638 | 129400 |  | 110691 | 112653
PRJ004 | Sep |  |  | 122877 | 115596 |  | 99676 | 105649
PRJ004 | Oct |  |  | 110719 | 200408 |  | 156177 | 129233
PRJ004 | Nov |  |  | 90091 | 155062 |  | 114764 | 137361
PRJ004 | Dec |  |  | 104571 | 142927 |  | 132240 | 96098
PRJ005 | Jan |  |  | 135086 | 151706 |  | 135499 | 129231
PRJ005 | Feb |  |  | 88599 | 120394 |  | 96992 | 110288
PRJ005 | Mar |  |  | 94069 | 149703 |  | 130679 | 94531
PRJ005 | Apr |  |  | 155419 | 158059 |  | 157440 | 130895
PRJ005 | May |  |  | 76086 | 122810 |  | 113621 | 82981
PRJ005 | Jun |  |  | 132771 | 161214 |  | 167728 | 154138
PRJ005 | Jul |  |  | 109632 | 130009 |  | 126378 | 136262
PRJ005 | Aug |  |  | 163712 | 168669 |  | 153782 | 106024
PRJ005 | Sep |  |  | 106838 | 199355 |  | 164286 | 148552
PRJ005 | Oct |  |  | 86884 | 84616 |  | 86092 | 74279
PRJ005 | Nov |  |  | 96804 | 120387 |  | 111678 | 108870
PRJ005 | Dec |  |  | 101218 | 159778 |  | 144947 | 145700
PRJ006 | Jan |  |  | 123678 | 133263 |  | 112343 | 85531
PRJ006 | Feb |  |  | 190963 | 178836 |  | 174562 | 177291
PRJ006 | Mar |  |  | 99885 | 114337 |  | 97685 | 93605
PRJ006 | Apr |  |  | 146223 | 167983 |  | 144777 | 155337
PRJ006 | May |  |  | 90698 | 103797 |  | 107542 | 94659
PRJ006 | Jun |  |  | 90092 | 130943 |  | 121229 | 121943
PRJ006 | Jul |  |  | 155717 | 169032 |  | 148498 | 102387
PRJ006 | Aug |  |  | 61501 | 92935 |  | 80328 | 56771
PRJ006 | Sep |  |  | 92086 | 141250 |  | 135539 | 103255
PRJ006 | Oct |  |  | 110439 | 147223 |  | 146729 | 119201
PRJ006 | Nov |  |  | 184643 | 158061 |  | 168408 | 137806
PRJ006 | Dec |  |  | 120243 | 146619 |  | 155821 | 105119
PRJ007 | Jan |  |  | 196291 | 249973 |  | 197802 | 161202
PRJ007 | Feb |  |  | 307262 | 385177 |  | 304194 | 310907
PRJ007 | Mar |  |  | 164941 | 158475 |  | 160282 | 133863
PRJ007 | Apr |  |  | 296183 | 345522 |  | 287512 | 321938
PRJ007 | May |  |  | 165907 | 235515 |  | 190355 | 172825
PRJ007 | Jun |  |  | 327855 | 369186 |  | 296896 | 306555
PRJ007 | Jul |  |  | 185842 | 245786 |  | 195612 | 218176
PRJ007 | Aug |  |  | 227159 | 247232 |  | 204453 | 225103
PRJ007 | Sep |  |  | 416792 | 392642 |  | 332295 | 388445
PRJ007 | Oct |  |  | 273901 | 414869 |  | 316865 | 342709
PRJ007 | Nov |  |  | 229429 | 311248 |  | 236510 | 278438
PRJ007 | Dec |  |  | 151833 | 279366 |  | 226766 | 209506
PRJ008 | Jan |  |  | 177179 | 218094 |  | 199331 | 173096
PRJ008 | Feb |  |  | 227604 | 242557 |  | 231876 | 215128
PRJ008 | Mar |  |  | 177956 | 294826 |  | 218520 | 236227
PRJ008 | Apr |  |  | 123583 | 179691 |  | 158932 | 133435
PRJ008 | May |  |  | 271529 | 277840 |  | 230492 | 227827
PRJ008 | Jun |  |  | 215651 | 253800 |  | 263280 | 271290
PRJ008 | Jul |  |  | 266388 | 364302 |  | 356334 | 351233
PRJ008 | Aug |  |  | 141882 | 227456 |  | 170360 | 155788
PRJ008 | Sep |  |  | 118194 | 185503 |  | 183153 | 138289
PRJ008 | Oct |  |  | 315956 | 294132 |  | 313148 | 279246
PRJ008 | Nov |  |  | 182118 | 234738 |  | 216999 | 141712
PRJ008 | Dec |  |  | 277871 | 395974 |  | 296610 | 261866
PRJ009 | Jan |  |  | 117100 | 139244 |  | 104203 | 111279
PRJ009 | Feb |  |  | 46922 | 69310 |  | 63383 | 63573
PRJ009 | Mar |  |  | 80716 | 101130 |  | 82339 | 89290
PRJ009 | Apr |  |  | 85788 | 145716 |  | 106065 | 98577
PRJ009 | May |  |  | 42056 | 59776 |  | 51969 | 50382
PRJ009 | Jun |  |  | 110533 | 108352 |  | 88071 | 82141
PRJ009 | Jul |  |  | 95222 | 98423 |  | 88910 | 89050
PRJ009 | Aug |  |  | 80842 | 105464 |  | 74565 | 78836
PRJ009 | Sep |  |  | 76729 | 83566 |  | 60951 | 59581
PRJ009 | Oct |  |  | 52145 | 79711 |  | 77458 | 63499
PRJ009 | Nov |  |  | 73608 | 74447 |  | 71452 | 57292
PRJ009 | Dec |  |  | 60621 | 60554 |  | 57728 | 53829
PRJ010 | Jan |  |  | 98176 | 114790 |  | 93694 | 87427
PRJ010 | Feb |  |  | 201274 | 185485 |  | 151793 | 129013
PRJ010 | Mar |  |  | 182868 | 204656 |  | 187200 | 178143
PRJ010 | Apr |  |  | 132659 | 183878 |  | 180265 | 183959
PRJ010 | May |  |  | 172042 | 164878 |  | 150657 | 118701
PRJ010 | Jun |  |  | 159007 | 256149 |  | 203785 | 236531
PRJ010 | Jul |  |  | 182855 | 199187 |  | 151634 | 141342
PRJ010 | Aug |  |  | 246738 | 301534 |  | 245550 | 238180
PRJ010 | Sep |  |  | 177572 | 215865 |  | 169272 | 203642
PRJ010 | Oct |  |  | 198049 | 262071 |  | 193707 | 192775
PRJ010 | Nov |  |  | 147467 | 195111 |  | 181437 | 148942
PRJ010 | Dec |  |  | 249271 | 256961 |  | 201386 | 232185
PRJ011 | Jan |  |  | 34599 | 52062 |  | 48783 | 46675
PRJ011 | Feb |  |  | 36451 | 38135 |  | 34921 | 30178
PRJ011 | Mar |  |  | 23679 | 31337 |  | 29690 | 31535
PRJ011 | Apr |  |  | 40960 | 51615 |  | 41562 | 31066
PRJ011 | May |  |  | 30609 | 36883 |  | 30546 | 31087
PRJ011 | Jun |  |  | 47565 | 51209 |  | 42031 | 28349
PRJ011 | Jul |  |  | 21470 | 33359 |  | 25527 | 21921
PRJ011 | Aug |  |  | 33508 | 34518 |  | 33700 | 21726
PRJ011 | Sep |  |  | 45249 | 47474 |  | 42577 | 39251
PRJ011 | Oct |  |  | 37681 | 41766 |  | 32568 | 32882
PRJ011 | Nov |  |  | 53872 | 57150 |  | 43090 | 41008
PRJ011 | Dec |  |  | 20485 | 24647 |  | 21919 | 20974
PRJ012 | Jan |  |  | 201041 | 236940 |  | 197887 | 183096
PRJ012 | Feb |  |  | 155617 | 196708 |  | 195078 | 140558
PRJ012 | Mar |  |  | 92571 | 118224 |  | 106977 | 76539
PRJ012 | Apr |  |  | 123892 | 174425 |  | 134525 | 107088
PRJ012 | May |  |  | 130264 | 128763 |  | 113915 | 97280
PRJ012 | Jun |  |  | 162311 | 160257 |  | 138092 | 110204
PRJ012 | Jul |  |  | 83713 | 107159 |  | 84792 | 71333
PRJ012 | Aug |  |  | 91188 | 111544 |  | 111068 | 94904
PRJ012 | Sep |  |  | 253202 | 209468 |  | 216802 | 180694
PRJ012 | Oct |  |  | 194795 | 243818 |  | 200345 | 155819
PRJ012 | Nov |  |  | 178874 | 233493 |  | 193228 | 217584
PRJ012 | Dec |  |  | 196317 | 198274 |  | 158552 | 188065
PRJ013 | Jan |  |  | 290574 | 254795 |  | 268160 | 220530
PRJ013 | Feb |  |  | 163155 | 190760 |  | 169754 | 134284
PRJ013 | Mar |  |  | 243993 | 293409 |  | 244934 | 220206
PRJ013 | Apr |  |  | 302728 | 453864 |  | 387465 | 284002
PRJ013 | May |  |  | 247100 | 293397 |  | 237679 | 197743
PRJ013 | Jun |  |  | 264690 | 293123 |  | 302990 | 263854
PRJ013 | Jul |  |  | 363747 | 389196 |  | 349686 | 233962
PRJ013 | Aug |  |  | 356886 | 350380 |  | 293607 | 325511
PRJ013 | Sep |  |  | 281329 | 307980 |  | 274172 | 197928
PRJ013 | Oct |  |  | 302991 | 395733 |  | 287702 | 302316
PRJ013 | Nov |  |  | 432841 | 445683 |  | 444162 | 368564
PRJ013 | Dec |  |  | 174055 | 303083 |  | 262139 | 282754
PRJ014 | Jan |  |  | 197701 | 185330 |  | 165888 | 161347
PRJ014 | Feb |  |  | 126522 | 197458 |  | 149403 | 119781
PRJ014 | Mar |  |  | 267663 | 295690 |  | 260661 | 204723
PRJ014 | Apr |  |  | 121288 | 176961 |  | 180897 | 152141
PRJ014 | May |  |  | 140696 | 140283 |  | 140115 | 145596
PRJ014 | Jun |  |  | 154942 | 166586 |  | 156420 | 140961
PRJ014 | Jul |  |  | 136975 | 151621 |  | 142877 | 115853
PRJ014 | Aug |  |  | 230756 | 211193 |  | 214138 | 215169
PRJ014 | Sep |  |  | 138611 | 191125 |  | 153788 | 155168
PRJ014 | Oct |  |  | 178902 | 276271 |  | 227672 | 254878
PRJ014 | Nov |  |  | 69573 | 117241 |  | 92058 | 95086
PRJ014 | Dec |  |  | 201429 | 198512 |  | 173800 | 191166
PRJ015 | Jan |  |  | 95376 | 116442 |  | 116271 | 108823
PRJ015 | Feb |  |  | 81941 | 95737 |  | 86274 | 82886
PRJ015 | Mar |  |  | 134193 | 139289 |  | 133573 | 115177
PRJ015 | Apr |  |  | 102688 | 126129 |  | 104618 | 87633
PRJ015 | May |  |  | 75183 | 81588 |  | 77862 | 54984
PRJ015 | Jun |  |  | 86186 | 112329 |  | 98364 | 68294
PRJ015 | Jul |  |  | 128260 | 138835 |  | 130155 | 125846
PRJ015 | Aug |  |  | 67053 | 103804 |  | 85222 | 84077
PRJ015 | Sep |  |  | 105581 | 150945 |  | 121001 | 99284
PRJ015 | Oct |  |  | 113310 | 141602 |  | 121301 | 88323
PRJ015 | Nov |  |  | 64488 | 66666 |  | 58586 | 52115
PRJ015 | Dec |  |  | 77307 | 119206 |  | 102047 | 85677
PRJ016 | Jan |  |  | 185937 | 302783 |  | 219775 | 168626
PRJ016 | Feb |  |  | 267944 | 266487 |  | 267851 | 182296
PRJ016 | Mar |  |  | 236287 | 229876 |  | 199852 | 133009
PRJ016 | Apr |  |  | 264071 | 328052 |  | 316803 | 354993
PRJ016 | May |  |  | 368879 | 381607 |  | 348437 | 337267
PRJ016 | Jun |  |  | 166922 | 246429 |  | 197986 | 178121
PRJ016 | Jul |  |  | 238509 | 278949 |  | 252872 | 283972
PRJ016 | Aug |  |  | 196434 | 269006 |  | 260592 | 246248
PRJ016 | Sep |  |  | 171181 | 186801 |  | 180182 | 131076
PRJ016 | Oct |  |  | 354167 | 369446 |  | 314092 | 273210
PRJ016 | Nov |  |  | 205768 | 227765 |  | 228500 | 217881
PRJ016 | Dec |  |  | 263442 | 295925 |  | 254933 | 173445
PRJ017 | Jan |  |  | 135135 | 210321 |  | 161624 | 179369
PRJ017 | Feb |  |  | 187808 | 215899 |  | 180139 | 127320
PRJ017 | Mar |  |  | 178923 | 185575 |  | 165382 | 125472
PRJ017 | Apr |  |  | 243472 | 238354 |  | 206895 | 168293
PRJ017 | May |  |  | 236246 | 320988 |  | 262570 | 219104
PRJ017 | Jun |  |  | 168469 | 220523 |  | 210462 | 199999
PRJ017 | Jul |  |  | 299029 | 310618 |  | 288576 | 204096
PRJ017 | Aug |  |  | 147579 | 199078 |  | 180232 | 169354
PRJ017 | Sep |  |  | 146355 | 224100 |  | 201343 | 235653
PRJ017 | Oct |  |  | 133286 | 172495 |  | 151410 | 141319
PRJ017 | Nov |  |  | 275542 | 345155 |  | 294431 | 313257
PRJ017 | Dec |  |  | 246072 | 285390 |  | 279670 | 276724
PRJ018 | Jan |  |  | 87580 | 100155 |  | 82380 | 65001
PRJ018 | Feb |  |  | 56321 | 88155 |  | 93786 | 85575
PRJ018 | Mar |  |  | 114994 | 132557 |  | 121992 | 80794
PRJ018 | Apr |  |  | 102674 | 114194 |  | 87978 | 99682
PRJ018 | May |  |  | 96597 | 156884 |  | 126760 | 97592
PRJ018 | Jun |  |  | 71031 | 108698 |  | 110467 | 102849
PRJ018 | Jul |  |  | 210094 | 217848 |  | 195956 | 205888
PRJ018 | Aug |  |  | 168117 | 195870 |  | 153178 | 134716
PRJ018 | Sep |  |  | 78442 | 109283 |  | 110456 | 118912
PRJ018 | Oct |  |  | 106626 | 160229 |  | 127087 | 84962
PRJ018 | Nov |  |  | 99270 | 164054 |  | 148053 | 96798
PRJ018 | Dec |  |  | 137963 | 199560 |  | 151647 | 173854
PRJ019 | Jan |  |  | 43777 | 48952 |  | 48806 | 48910
PRJ019 | Feb |  |  | 21357 | 31074 |  | 24490 | 18936
PRJ019 | Mar |  |  | 53075 | 60010 |  | 54279 | 46517
PRJ019 | Apr |  |  | 24401 | 27423 |  | 26726 | 25700
PRJ019 | May |  |  | 58490 | 60461 |  | 45844 | 36889
PRJ019 | Jun |  |  | 39976 | 40774 |  | 36318 | 32032
PRJ019 | Jul |  |  | 27549 | 45853 |  | 37658 | 31421
PRJ019 | Aug |  |  | 30488 | 45178 |  | 37391 | 36527
PRJ019 | Sep |  |  | 24753 | 35062 |  | 31782 | 25711
PRJ019 | Oct |  |  | 37025 | 38689 |  | 37824 | 27733
PRJ019 | Nov |  |  | 24789 | 26721 |  | 22891 | 19765
PRJ019 | Dec |  |  | 25748 | 30504 |  | 32308 | 21493
PRJ020 | Jan |  |  | 292638 | 395633 |  | 333988 | 277831
PRJ020 | Feb |  |  | 269942 | 374503 |  | 328806 | 273305
PRJ020 | Mar |  |  | 312831 | 316629 |  | 287685 | 242315
PRJ020 | Apr |  |  | 215707 | 277658 |  | 208690 | 148988
PRJ020 | May |  |  | 243027 | 213407 |  | 205642 | 193165
PRJ020 | Jun |  |  | 180457 | 247934 |  | 208294 | 207624
PRJ020 | Jul |  |  | 279374 | 397649 |  | 311589 | 250720
PRJ020 | Aug |  |  | 324317 | 369396 |  | 343494 | 222627
PRJ020 | Sep |  |  | 149426 | 191667 |  | 168154 | 169013
PRJ020 | Oct |  |  | 242533 | 232984 |  | 215722 | 231906
PRJ020 | Nov |  |  | 154904 | 274053 |  | 236175 | 247262
PRJ020 | Dec |  |  | 214756 | 290891 |  | 255386 | 298974
PRJ021 | Jan |  |  | 231329 | 316137 |  | 236585 | 204234
PRJ021 | Feb |  |  | 276808 | 259448 |  | 225505 | 189453
PRJ021 | Mar |  |  | 324109 | 288458 |  | 296588 | 300225
PRJ021 | Apr |  |  | 310411 | 295470 |  | 243902 | 222053
PRJ021 | May |  |  | 311937 | 475435 |  | 419625 | 387064
PRJ021 | Jun |  |  | 316401 | 336233 |  | 299087 | 280660
PRJ021 | Jul |  |  | 305193 | 376165 |  | 335531 | 233911
PRJ021 | Aug |  |  | 334815 | 441233 |  | 347705 | 420213
PRJ021 | Sep |  |  | 257203 | 428671 |  | 365271 | 294607
PRJ021 | Oct |  |  | 163923 | 211577 |  | 178789 | 135332
PRJ021 | Nov |  |  | 291438 | 356642 |  | 326620 | 256963
PRJ021 | Dec |  |  | 430250 | 459128 |  | 367306 | 384552
PRJ022 | Jan |  |  | 272297 | 250778 |  | 227524 | 226686
PRJ022 | Feb |  |  | 205601 | 213626 |  | 181350 | 139835
PRJ022 | Mar |  |  | 133763 | 198712 |  | 193729 | 183006
PRJ022 | Apr |  |  | 139824 | 162725 |  | 142388 | 151878
PRJ022 | May |  |  | 292599 | 288735 |  | 284664 | 288175
PRJ022 | Jun |  |  | 138899 | 222333 |  | 183200 | 204651
PRJ022 | Jul |  |  | 208687 | 344782 |  | 268300 | 286832
PRJ022 | Aug |  |  | 160478 | 264155 |  | 248281 | 210359
PRJ022 | Sep |  |  | 275683 | 286616 |  | 253379 | 249585
PRJ022 | Oct |  |  | 203179 | 227469 |  | 219057 | 160446
PRJ022 | Nov |  |  | 232759 | 304777 |  | 304235 | 239625
PRJ022 | Dec |  |  | 113657 | 189011 |  | 138110 | 106245
PRJ023 | Jan |  |  | 250903 | 277371 |  | 228495 | 185244
PRJ023 | Feb |  |  | 188401 | 203223 |  | 163574 | 110327
PRJ023 | Mar |  |  | 271805 | 254260 |  | 231079 | 270969
PRJ023 | Apr |  |  | 301257 | 303335 |  | 251936 | 263084
PRJ023 | May |  |  | 194699 | 189503 |  | 164672 | 133201
PRJ023 | Jun |  |  | 169692 | 241553 |  | 231656 | 173808
PRJ023 | Jul |  |  | 279621 | 292357 |  | 264877 | 228943
PRJ023 | Aug |  |  | 112140 | 197903 |  | 163591 | 125935
PRJ023 | Sep |  |  | 179918 | 174763 |  | 171941 | 157212
PRJ023 | Oct |  |  | 201019 | 238878 |  | 212272 | 197097
PRJ023 | Nov |  |  | 141615 | 222786 |  | 175785 | 201881
PRJ023 | Dec |  |  | 141194 | 205706 |  | 165104 | 166847
PRJ024 | Jan |  |  | 85692 | 106787 |  | 84528 | 74136
PRJ024 | Feb |  |  | 76805 | 68662 |  | 64775 | 68930
PRJ024 | Mar |  |  | 40259 | 66391 |  | 63079 | 48947
PRJ024 | Apr |  |  | 77333 | 73865 |  | 61765 | 48009
PRJ024 | May |  |  | 85557 | 73201 |  | 74845 | 64361
PRJ024 | Jun |  |  | 45193 | 65903 |  | 52143 | 56130
PRJ024 | Jul |  |  | 58040 | 62471 |  | 56299 | 54680
PRJ024 | Aug |  |  | 61387 | 88976 |  | 77157 | 58992
PRJ024 | Sep |  |  | 79254 | 99944 |  | 101936 | 74526
PRJ024 | Oct |  |  | 63606 | 84372 |  | 71906 | 64383
PRJ024 | Nov |  |  | 74294 | 67337 |  | 69350 | 54441
PRJ024 | Dec |  |  | 85511 | 82178 |  | 70786 | 78138
PRJ025 | Jan |  |  | 89094 | 139595 |  | 100798 | 116392
PRJ025 | Feb |  |  | 152327 | 180513 |  | 171150 | 114985
PRJ025 | Mar |  |  | 62576 | 92738 |  | 85694 | 64820
PRJ025 | Apr |  |  | 146887 | 207407 |  | 173873 | 163328
PRJ025 | May |  |  | 186095 | 197036 |  | 168162 | 176947
PRJ025 | Jun |  |  | 156858 | 169642 |  | 132535 | 101123
PRJ025 | Jul |  |  | 187737 | 186911 |  | 181222 | 176447
PRJ025 | Aug |  |  | 113783 | 113999 |  | 120643 | 95076
PRJ025 | Sep |  |  | 102654 | 110611 |  | 106255 | 81220
PRJ025 | Oct |  |  | 84651 | 107498 |  | 97680 | 85230
PRJ025 | Nov |  |  | 91595 | 107209 |  | 93819 | 95205
PRJ025 | Dec |  |  | 61855 | 98718 |  | 91912 | 62781
PRJ026 | Jan |  |  | 133158 | 167733 |  | 132415 | 133547
PRJ026 | Feb |  |  | 166194 | 286005 |  | 226014 | 253452
PRJ026 | Mar |  |  | 124251 | 151084 |  | 132268 | 128197
PRJ026 | Apr |  |  | 139849 | 134764 |  | 127601 | 99327
PRJ026 | May |  |  | 143283 | 134882 |  | 124210 | 128233
PRJ026 | Jun |  |  | 175036 | 317339 |  | 274955 | 264394
PRJ026 | Jul |  |  | 255093 | 249954 |  | 239768 | 164091
PRJ026 | Aug |  |  | 120144 | 176445 |  | 145791 | 135774
PRJ026 | Sep |  |  | 243652 | 232159 |  | 235240 | 222103
PRJ026 | Oct |  |  | 94125 | 139194 |  | 117160 | 78805
PRJ026 | Nov |  |  | 188810 | 230053 |  | 230668 | 205382
PRJ026 | Dec |  |  | 287368 | 295332 |  | 235251 | 209132
PRJ027 | Jan |  |  | 144115 | 212388 |  | 172375 | 128299
PRJ027 | Feb |  |  | 159237 | 135602 |  | 127231 | 121582
PRJ027 | Mar |  |  | 87105 | 126670 |  | 111738 | 109133
PRJ027 | Apr |  |  | 118643 | 153839 |  | 129038 | 132708
PRJ027 | May |  |  | 127555 | 215534 |  | 177625 | 137090
PRJ027 | Jun |  |  | 130251 | 201385 |  | 200691 | 170927
PRJ027 | Jul |  |  | 111779 | 145616 |  | 154295 | 149606
PRJ027 | Aug |  |  | 93919 | 124799 |  | 121278 | 122850
PRJ027 | Sep |  |  | 176404 | 190920 |  | 153160 | 184868
PRJ027 | Oct |  |  | 204583 | 216623 |  | 165640 | 157859
PRJ027 | Nov |  |  | 142448 | 210238 |  | 177481 | 170114
PRJ027 | Dec |  |  | 154000 | 193211 |  | 188624 | 183061
PRJ028 | Jan |  |  | 171045 | 160180 |  | 144668 | 156427
PRJ028 | Feb |  |  | 123062 | 133398 |  | 117897 | 121868
PRJ028 | Mar |  |  | 105758 | 129384 |  | 116183 | 111625
PRJ028 | Apr |  |  | 112298 | 124070 |  | 111359 | 81382
PRJ028 | May |  |  | 108246 | 147768 |  | 139699 | 146595
PRJ028 | Jun |  |  | 157593 | 169870 |  | 144238 | 117945
PRJ028 | Jul |  |  | 83491 | 115556 |  | 93298 | 103197
PRJ028 | Aug |  |  | 105679 | 126664 |  | 107196 | 94518
PRJ028 | Sep |  |  | 157308 | 185206 |  | 176521 | 112810
PRJ028 | Oct |  |  | 149163 | 202632 |  | 170427 | 150779
PRJ028 | Nov |  |  | 100248 | 134389 |  | 115754 | 125184
PRJ028 | Dec |  |  | 116484 | 117392 |  | 116076 | 84404
PRJ029 | Jan |  |  | 190453 | 183909 |  | 189348 | 193189
PRJ029 | Feb |  |  | 132993 | 166941 |  | 137773 | 137830
PRJ029 | Mar |  |  | 141160 | 164224 |  | 160099 | 164283
PRJ029 | Apr |  |  | 139442 | 195653 |  | 187507 | 157016
PRJ029 | May |  |  | 160953 | 166188 |  | 160050 | 121494
PRJ029 | Jun |  |  | 179296 | 176792 |  | 158208 | 112053
PRJ029 | Jul |  |  | 177565 | 186642 |  | 160084 | 168544
PRJ029 | Aug |  |  | 110762 | 156850 |  | 141328 | 142749
PRJ029 | Sep |  |  | 141381 | 142505 |  | 110214 | 131115
PRJ029 | Oct |  |  | 120513 | 144200 |  | 117352 | 120827
PRJ029 | Nov |  |  | 129245 | 147641 |  | 137082 | 88007
PRJ029 | Dec |  |  | 85493 | 153943 |  | 129049 | 129299
PRJ030 | Jan |  |  | 60221 | 96837 |  | 80580 | 83780
PRJ030 | Feb |  |  | 95207 | 116354 |  | 88630 | 82970
PRJ030 | Mar |  |  | 72958 | 109998 |  | 98589 | 84807
PRJ030 | Apr |  |  | 57418 | 63845 |  | 54248 | 57589
PRJ030 | May |  |  | 69827 | 86964 |  | 74692 | 52125
PRJ030 | Jun |  |  | 120968 | 112929 |  | 103727 | 107690
PRJ030 | Jul |  |  | 102221 | 110664 |  | 102296 | 112799
PRJ030 | Aug |  |  | 62826 | 73419 |  | 66037 | 56815
PRJ030 | Sep |  |  | 74940 | 89901 |  | 62848 | 47871
PRJ030 | Oct |  |  | 88444 | 94995 |  | 86351 | 66125
PRJ030 | Nov |  |  | 78607 | 77245 |  | 71890 | 60974
PRJ030 | Dec |  |  | 87526 | 100617 |  | 82180 | 89679
PRJ031 | Jan |  |  | 68399 | 68345 |  | 62910 | 55157
PRJ031 | Feb |  |  | 77590 | 80614 |  | 68134 | 58122
PRJ031 | Mar |  |  | 79877 | 90481 |  | 88000 | 70413
PRJ031 | Apr |  |  | 70619 | 101853 |  | 81304 | 76712
PRJ031 | May |  |  | 68977 | 77411 |  | 60074 | 68154
PRJ031 | Jun |  |  | 52502 | 50810 |  | 46571 | 39835
PRJ031 | Jul |  |  | 74801 | 78829 |  | 68190 | 52592
PRJ031 | Aug |  |  | 44677 | 50515 |  | 46880 | 51614
PRJ031 | Sep |  |  | 36397 | 60813 |  | 53009 | 53551
PRJ031 | Oct |  |  | 45363 | 55267 |  | 45186 | 52271
PRJ031 | Nov |  |  | 81587 | 77296 |  | 80479 | 76721
PRJ031 | Dec |  |  | 63796 | 103506 |  | 85386 | 84773
PRJ032 | Jan |  |  | 286980 | 288485 |  | 247328 | 170877
PRJ032 | Feb |  |  | 224526 | 277887 |  | 225102 | 216888
PRJ032 | Mar |  |  | 232426 | 289795 |  | 261429 | 222407
PRJ032 | Apr |  |  | 176764 | 253727 |  | 210403 | 222488
PRJ032 | May |  |  | 221783 | 280282 |  | 236991 | 252278
PRJ032 | Jun |  |  | 152185 | 252192 |  | 207762 | 186145
PRJ032 | Jul |  |  | 212874 | 210317 |  | 184047 | 174928
PRJ032 | Aug |  |  | 223430 | 276439 |  | 234272 | 211004
PRJ032 | Sep |  |  | 285783 | 319030 |  | 270917 | 295651
PRJ032 | Oct |  |  | 241523 | 400139 |  | 356877 | 285560
PRJ032 | Nov |  |  | 303377 | 322829 |  | 268828 | 219016
PRJ032 | Dec |  |  | 422187 | 398843 |  | 375626 | 346113
PRJ033 | Jan |  |  | 140403 | 154148 |  | 152025 | 125785
PRJ033 | Feb |  |  | 109911 | 117410 |  | 92207 | 71620
PRJ033 | Mar |  |  | 128780 | 179322 |  | 161788 | 137247
PRJ033 | Apr |  |  | 106086 | 120832 |  | 115914 | 87802
PRJ033 | May |  |  | 114563 | 140226 |  | 113487 | 117051
PRJ033 | Jun |  |  | 113321 | 111882 |  | 119997 | 100955
PRJ033 | Jul |  |  | 109283 | 136532 |  | 126757 | 88124
PRJ033 | Aug |  |  | 98562 | 166212 |  | 143732 | 113201
PRJ033 | Sep |  |  | 87066 | 148999 |  | 131889 | 129709
PRJ033 | Oct |  |  | 80706 | 112341 |  | 108619 | 90610
PRJ033 | Nov |  |  | 115628 | 120346 |  | 112346 | 118642
PRJ033 | Dec |  |  | 106390 | 149121 |  | 113093 | 82747
PRJ034 | Jan |  |  | 82831 | 96234 |  | 88690 | 77212
PRJ034 | Feb |  |  | 90787 | 105432 |  | 83172 | 90102
PRJ034 | Mar |  |  | 118807 | 124735 |  | 107879 | 94075
PRJ034 | Apr |  |  | 99966 | 109356 |  | 89919 | 80922
PRJ034 | May |  |  | 106395 | 180595 |  | 146758 | 102715
PRJ034 | Jun |  |  | 59591 | 63376 |  | 55043 | 61788
PRJ034 | Jul |  |  | 74510 | 93515 |  | 88330 | 77631
PRJ034 | Aug |  |  | 79630 | 96707 |  | 82919 | 69141
PRJ034 | Sep |  |  | 86372 | 108013 |  | 82329 | 77795
PRJ034 | Oct |  |  | 85663 | 125141 |  | 99893 | 96429
PRJ034 | Nov |  |  | 81846 | 81004 |  | 81934 | 86018
PRJ034 | Dec |  |  | 131686 | 145462 |  | 154704 | 100509
PRJ035 | Jan |  |  | 335369 | 285482 |  | 287722 | 285394
PRJ035 | Feb |  |  | 166563 | 236242 |  | 192893 | 173748
PRJ035 | Mar |  |  | 250530 | 352422 |  | 296629 | 221220
PRJ035 | Apr |  |  | 231389 | 256797 |  | 216677 | 148267
PRJ035 | May |  |  | 162162 | 297368 |  | 249220 | 220185
PRJ035 | Jun |  |  | 181852 | 237309 |  | 182443 | 139250
PRJ035 | Jul |  |  | 171062 | 261449 |  | 235255 | 235758
PRJ035 | Aug |  |  | 219104 | 210678 |  | 205187 | 173282
PRJ035 | Sep |  |  | 299410 | 357503 |  | 321762 | 377870
PRJ035 | Oct |  |  | 244909 | 243971 |  | 189263 | 173294
PRJ035 | Nov |  |  | 286763 | 292423 |  | 275281 | 267495
PRJ035 | Dec |  |  | 148659 | 181384 |  | 176528 | 167554
PRJ036 | Jan |  |  | 174763 | 186840 |  | 152061 | 173903
PRJ036 | Feb |  |  | 133349 | 173013 |  | 160514 | 141233
PRJ036 | Mar |  |  | 151105 | 187345 |  | 145784 | 159083
PRJ036 | Apr |  |  | 160101 | 201794 |  | 203169 | 165103
PRJ036 | May |  |  | 230089 | 249128 |  | 199597 | 174850
PRJ036 | Jun |  |  | 163886 | 200345 |  | 181241 | 113430
PRJ036 | Jul |  |  | 92945 | 107839 |  | 96749 | 76485
PRJ036 | Aug |  |  | 110607 | 110079 |  | 100039 | 101394
PRJ036 | Sep |  |  | 144671 | 244216 |  | 181058 | 189075
PRJ036 | Oct |  |  | 259650 | 269335 |  | 225036 | 168055
PRJ036 | Nov |  |  | 198151 | 243687 |  | 184333 | 166124
PRJ036 | Dec |  |  | 193925 | 239443 |  | 207443 | 231895
PRJ037 | Jan |  |  | 54317 | 98188 |  | 73534 | 66921
PRJ037 | Feb |  |  | 108479 | 113208 |  | 107671 | 78805
PRJ037 | Mar |  |  | 93644 | 114624 |  | 95820 | 65160
PRJ037 | Apr |  |  | 58537 | 81633 |  | 79037 | 53230
PRJ037 | May |  |  | 119358 | 123750 |  | 120345 | 123140
PRJ037 | Jun |  |  | 112380 | 107413 |  | 93186 | 98480
PRJ037 | Jul |  |  | 111974 | 115933 |  | 127516 | 119326
PRJ037 | Aug |  |  | 109400 | 101427 |  | 95959 | 77910
PRJ037 | Sep |  |  | 83120 | 133136 |  | 127794 | 81426
PRJ037 | Oct |  |  | 102152 | 104392 |  | 89323 | 83331
PRJ037 | Nov |  |  | 97331 | 98206 |  | 80954 | 58864
PRJ037 | Dec |  |  | 79331 | 112284 |  | 111772 | 99129
PRJ038 | Jan |  |  | 105944 | 118928 |  | 110389 | 113665
PRJ038 | Feb |  |  | 111247 | 164394 |  | 172226 | 110996
PRJ038 | Mar |  |  | 129865 | 141123 |  | 130138 | 132097
PRJ038 | Apr |  |  | 134606 | 115197 |  | 104947 | 109155
PRJ038 | May |  |  | 110005 | 189903 |  | 145891 | 118128
PRJ038 | Jun |  |  | 99973 | 101698 |  | 83655 | 83883
PRJ038 | Jul |  |  | 129571 | 167931 |  | 128890 | 140750
PRJ038 | Aug |  |  | 180823 | 177260 |  | 143328 | 164125
PRJ038 | Sep |  |  | 136499 | 147232 |  | 127736 | 112237
PRJ038 | Oct |  |  | 75377 | 112825 |  | 105572 | 92320
PRJ038 | Nov |  |  | 108140 | 161246 |  | 169000 | 147297
PRJ038 | Dec |  |  | 120853 | 129178 |  | 119764 | 91076
PRJ039 | Jan |  |  | 260554 | 355264 |  | 307758 | 282748
PRJ039 | Feb |  |  | 194142 | 226020 |  | 222552 | 190237
PRJ039 | Mar |  |  | 130567 | 174752 |  | 142164 | 140258
PRJ039 | Apr |  |  | 134958 | 174733 |  | 170345 | 120002
PRJ039 | May |  |  | 228436 | 250747 |  | 250549 | 226826
PRJ039 | Jun |  |  | 193976 | 208161 |  | 193084 | 153455
PRJ039 | Jul |  |  | 138806 | 236990 |  | 191387 | 172820
PRJ039 | Aug |  |  | 256813 | 238880 |  | 248651 | 254384
PRJ039 | Sep |  |  | 197378 | 217639 |  | 229352 | 208161
PRJ039 | Oct |  |  | 181203 | 277025 |  | 224150 | 236186
PRJ039 | Nov |  |  | 187343 | 216077 |  | 169212 | 133084
PRJ039 | Dec |  |  | 265660 | 237955 |  | 250495 | 198753
PRJ040 | Jan |  |  | 111391 | 122774 |  | 115476 | 79012
PRJ040 | Feb |  |  | 68731 | 101938 |  | 105889 | 85494
PRJ040 | Mar |  |  | 105364 | 106142 |  | 96749 | 86375
PRJ040 | Apr |  |  | 152689 | 156725 |  | 115008 | 132667
PRJ040 | May |  |  | 141596 | 175336 |  | 135280 | 140998
PRJ040 | Jun |  |  | 119554 | 163580 |  | 153169 | 130992
PRJ040 | Jul |  |  | 64517 | 122606 |  | 86518 | 84403
PRJ040 | Aug |  |  | 131713 | 155187 |  | 146024 | 141293
PRJ040 | Sep |  |  | 111360 | 114382 |  | 119860 | 124118
PRJ040 | Oct |  |  | 87975 | 87867 |  | 85322 | 68750
PRJ040 | Nov |  |  | 170809 | 158960 |  | 156305 | 159422
PRJ040 | Dec |  |  | 175890 | 175479 |  | 157845 | 150862

## Resources
Resource | Skill | Role | Project ID | Project | Month | Allocation % | Capacity %
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-04-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-05-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-06-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-07-01 | 40 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-08-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-09-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-10-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-11-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-12-01 | 40 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2026-01-01 | 0 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-02-01 | 90 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-03-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-04-01 | 85 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-05-01 | 90 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-06-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-07-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-08-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-09-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-10-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-11-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-12-01 | 85 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-01-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-02-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-03-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-04-01 | 65 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-05-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-06-01 | 40 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-07-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-08-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-09-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-10-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-11-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-12-01 | 0 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-02-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-03-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-04-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-05-01 | 60 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-06-01 | 65 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-07-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-08-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-09-01 | 25 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-10-01 | 25 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-11-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-12-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2026-01-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2026-02-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2026-03-01 | 60 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2025-11-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2025-12-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-01-01 | 35 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-02-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-03-01 | 35 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-04-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-05-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-06-01 | 35 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-07-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-08-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-09-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-10-01 | 0 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-11-01 | 15 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-12-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2027-01-01 | 0 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-03-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-04-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-05-01 | 75 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-06-01 | 75 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-07-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-08-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-09-01 | 75 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-10-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-11-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-12-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-01-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-02-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-03-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-04-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-05-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-05-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-06-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-07-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-08-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-09-01 | 65 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-10-01 | 65 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-11-01 | 25 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-12-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-01-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-02-01 | 25 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-03-01 | 25 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-04-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-05-01 | 60 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-06-01 | 65 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-07-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-04-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-05-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-06-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-07-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-08-01 | 85 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-09-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-10-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-11-01 | 85 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-12-01 | 85 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2026-01-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2026-02-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-04-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-05-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-06-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-07-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-08-01 | 50 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-02-01 | 75 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-03-01 | 75 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-04-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-05-01 | 85 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-06-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-07-01 | 90 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-08-01 | 85 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-09-01 | 75 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-10-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-11-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-12-01 | 90 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2026-01-01 | 90 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-05-01 | 25 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-06-01 | 35 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-07-01 | 15 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-08-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-02-01 | 40 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-03-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-04-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-05-01 | 15 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-06-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-07-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-08-01 | 35 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-09-01 | 15 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-10-01 | 35 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-11-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-12-01 | 0 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2026-01-01 | 0 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2026-02-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2026-03-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-02-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-03-01 | 35 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-04-01 | 35 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-05-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-06-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-07-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-08-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-09-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-10-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-11-01 | 35 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-12-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2026-01-01 | 15 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-03-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-04-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-05-01 | 75 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-06-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-07-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-08-01 | 75 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-09-01 | 90 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-10-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-03-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-04-01 | 90 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-05-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-06-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-07-01 | 75 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-08-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-09-01 | 75 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-10-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2025-12-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-01-01 | 40 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-02-01 | 25 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-03-01 | 25 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-04-01 | 60 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-05-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-06-01 | 65 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-07-01 | 65 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-08-01 | 25 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-09-01 | 60 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-10-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-11-01 | 40 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-12-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2027-01-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2027-02-01 | 60 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2027-03-01 | 60 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2025-12-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-02-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-03-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-04-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-05-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-06-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-07-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-08-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-09-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-11-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-12-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2027-01-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-02-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-03-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-04-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-05-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-06-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-07-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-08-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-09-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-10-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-11-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-12-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-01-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-02-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-03-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-02-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-03-01 | 85 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-04-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-05-01 | 50 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-06-01 | 85 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-07-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-08-01 | 50 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-09-01 | 50 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-10-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-11-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-12-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-01-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-02-01 | 65 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-03-01 | 85 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2025-12-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-01-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-02-01 | 60 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-03-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-04-01 | 25 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-05-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-06-01 | 60 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-07-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-08-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-09-01 | 60 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-10-01 | 65 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-11-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-12-01 | 40 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2027-01-01 | 25 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2027-02-01 | 25 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2027-03-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-08-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-09-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-10-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-11-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-12-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-01-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-02-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-03-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-04-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-05-01 | 0 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-06-01 | 0 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-07-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-08-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-09-01 | 0 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-10-01 | 35 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-11-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2025-12-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-02-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-03-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-04-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-05-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-06-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-07-01 | 75 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-08-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-09-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-11-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-12-01 | 75 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2027-01-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2025-11-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2025-12-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-01-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-02-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-03-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-04-01 | 25 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2025-12-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-02-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-03-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-04-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-05-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-06-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-07-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-08-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-09-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-11-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-12-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2027-01-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2025-11-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2025-12-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-01-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-02-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-03-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-04-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-09-01 | 65 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-10-01 | 50 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-11-01 | 65 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-12-01 | 85 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2026-01-01 | 75 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2025-12-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-02-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-03-01 | 75 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-04-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-05-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-06-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-07-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-08-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-09-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-11-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-12-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2027-01-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-05-01 | 25 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-06-01 | 25 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-07-01 | 0 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-08-01 | 0 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-09-01 | 15 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-10-01 | 0 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-11-01 | 25 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-12-01 | 25 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2025-11-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2025-12-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-01-01 | 75 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-02-01 | 50 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-03-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-04-01 | 50 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-05-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-06-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-07-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-08-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-09-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-10-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-11-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-03-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-04-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-05-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-06-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-07-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-08-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-09-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-10-01 | 90 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-11-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-12-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-01-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-02-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-03-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-04-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-05-01 | 100 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-07-01 | 90 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-08-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-09-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-10-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-11-01 | 85 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-12-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-01-01 | 85 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-02-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-03-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-04-01 | 90 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-05-01 | 75 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-06-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-07-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-08-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-09-01 | 90 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-10-01 | 75 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-11-01 | 85 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-12-01 | 75 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2027-01-01 | 75 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-02-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-03-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-04-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-05-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-06-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-07-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-08-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-09-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-10-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-11-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-12-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-01-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-02-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-03-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-04-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-05-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-06-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-07-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-08-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-09-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-10-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-11-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-12-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-01-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-02-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-03-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-04-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-05-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-06-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-07-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-08-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-09-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-10-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-11-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-12-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-05-01 | 75 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-06-01 | 100 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-07-01 | 90 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-08-01 | 100 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-04-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-05-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-06-01 | 0 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-07-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-08-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-09-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-10-01 | 35 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-11-01 | 40 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-12-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-01-01 | 40 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-02-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-03-01 | 15 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-04-01 | 35 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-05-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-06-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-07-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2025-12-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-01-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-02-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-03-01 | 15 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-04-01 | 0 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-05-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-06-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-07-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-08-01 | 0 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-09-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-10-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-11-01 | 35 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-12-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2027-01-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2027-02-01 | 0 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2027-03-01 | 0 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-02-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-03-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-04-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-05-01 | 75 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-06-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-07-01 | 90 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-08-01 | 75 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-09-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-10-01 | 90 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-11-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-12-01 | 90 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2026-01-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-01-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-02-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-03-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-04-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-05-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-06-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-07-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-08-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-09-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-10-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-11-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-12-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-01-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-02-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-03-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-04-01 | 90 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-05-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-06-01 | 75 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-07-01 | 75 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-06-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-07-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-08-01 | 65 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-09-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-10-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-11-01 | 50 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-12-01 | 65 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-01-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-02-01 | 40 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-03-01 | 50 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-04-01 | 60 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-01-01 | 50 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-02-01 | 60 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-03-01 | 60 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-04-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-05-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-06-01 | 65 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2025-12-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-01-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-02-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-03-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-04-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-05-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-06-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-07-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-08-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-09-01 | 50 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-10-01 | 50 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-11-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-12-01 | 50 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2027-01-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2027-02-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2027-03-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2025-12-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-01-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-02-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-03-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-04-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-05-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-06-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-07-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-08-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-09-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-10-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-11-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-12-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2027-01-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2027-02-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2025-12-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-01-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-02-01 | 90 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-03-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-04-01 | 75 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-05-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-06-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-07-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-08-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-09-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-10-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-11-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-12-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-01-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-02-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-03-01 | 75 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-04-01 | 75 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-05-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-04-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-05-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-06-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-07-01 | 60 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-08-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-09-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-10-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-11-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-12-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-01-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-02-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-03-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-04-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-05-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-06-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-07-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2025-12-01 | 40 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-01-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-02-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-03-01 | 60 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-04-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-05-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-06-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-07-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-08-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-09-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-10-01 | 40 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-11-01 | 25 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-05-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-06-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-07-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-08-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-09-01 | 75 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-10-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-11-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-12-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-01-01 | 75 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-02-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-03-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-04-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-05-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-06-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-07-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-08-01 | 75 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-09-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-10-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2025-11-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2025-12-01 | 85 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-01-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-02-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-03-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-04-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-05-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-06-01 | 90 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-07-01 | 50 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-08-01 | 85 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-09-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-10-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-11-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-12-01 | 50 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-01-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-02-01 | 85 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-03-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-04-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-05-01 | 85 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-03-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-04-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-05-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-06-01 | 0 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-07-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-08-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-09-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-10-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-11-01 | 15 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-12-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-01-01 | 0 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-02-01 | 40 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-03-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-04-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-05-01 | 25 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2025-12-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-01-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-02-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-03-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-04-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-05-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-06-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-07-01 | 90 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-08-01 | 75 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-09-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-10-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-11-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-12-01 | 90 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2027-01-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2027-02-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2027-03-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-05-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-06-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-07-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-08-01 | 75 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-09-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-10-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-11-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-12-01 | 50 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-01-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-02-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-03-01 | 75 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-04-01 | 75 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-05-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-06-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-07-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-08-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-09-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-10-01 | 75 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-07-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-08-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-09-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-10-01 | 65 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-11-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-12-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-01-01 | 65 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-02-01 | 60 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-03-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-04-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-05-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-06-01 | 25 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-07-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-08-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-09-01 | 25 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-10-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-11-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-12-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2027-01-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-05-01 | 100 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-06-01 | 100 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-07-01 | 75 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-08-01 | 90 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-09-01 | 90 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-10-01 | 100 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-11-01 | 90 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-12-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-05-01 | 65 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-06-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-07-01 | 65 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-08-01 | 50 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-09-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-10-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-11-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-12-01 | 50 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2025-11-01 | 50 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2025-12-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2026-01-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2026-02-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2026-03-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-03-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-04-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-05-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-06-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-07-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-08-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-09-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-10-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-11-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-12-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-01-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-02-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-03-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-04-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-05-01 | 75 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-01-01 | 85 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-02-01 | 90 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-03-01 | 75 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-04-01 | 90 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-05-01 | 90 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-06-01 | 65 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-05-01 | 40 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-06-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-07-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-08-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-09-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-10-01 | 60 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-11-01 | 25 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-12-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-01-01 | 60 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-02-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-03-01 | 65 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-04-01 | 25 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-05-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-06-01 | 60 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-07-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-08-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-09-01 | 65 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-10-01 | 40 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-11-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-12-01 | 40 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2025-12-01 | 50 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-01-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-02-01 | 85 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-03-01 | 50 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-04-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-05-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-06-01 | 50 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-07-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-08-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-09-01 | 65 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-10-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-11-01 | 85 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-12-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2027-01-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2025-12-01 | 35 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-01-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-02-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-03-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-04-01 | 0 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-05-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-06-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-07-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-08-01 | 0 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-09-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-10-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-11-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-12-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2027-01-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-01-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-02-01 | 100 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-03-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-04-01 | 100 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-05-01 | 100 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-06-01 | 100 | 100

## Dependencies
From Project | To Project | Dependency Type | Status | Impact
PRJ027 | PRJ022 | Shared Resource | Healthy | Low
PRJ017 | PRJ033 | Finish-Start | At Risk | Medium
PRJ039 | PRJ036 | Blocks | At Risk | High
PRJ002 | PRJ004 | Start-Start | Blocked | Medium
PRJ009 | PRJ001 | Shared Resource | Healthy | High
PRJ020 | PRJ021 | Finish-Start | Healthy | Low
PRJ016 | PRJ034 | Start-Start | Blocked | High
PRJ027 | PRJ021 | Shared Resource | At Risk | High
PRJ009 | PRJ017 | Start-Start | Blocked | High
PRJ021 | PRJ019 | Start-Start | Healthy | Medium
PRJ024 | PRJ012 | Shared Resource | At Risk | High
PRJ015 | PRJ002 | Finish-Start | Blocked | High
PRJ040 | PRJ015 | Finish-Start | At Risk | Low
PRJ017 | PRJ011 | Finish-Start | At Risk | High
PRJ028 | PRJ039 | Blocks | Healthy | Low
PRJ024 | PRJ011 | Finish-Start | Healthy | High
PRJ034 | PRJ028 | Shared Resource | Blocked | Medium
PRJ008 | PRJ015 | Start-Start | Healthy | Medium
PRJ019 | PRJ032 | Shared Resource | Healthy | Medium
PRJ014 | PRJ039 | Start-Start | At Risk | High
PRJ013 | PRJ027 | Start-Start | At Risk | Low
PRJ002 | PRJ019 | Blocks | Healthy | High
PRJ029 | PRJ016 | Blocks | Blocked | High
PRJ030 | PRJ006 | Finish-Start | At Risk | Low
PRJ021 | PRJ026 | Start-Start | Blocked | Medium
PRJ028 | PRJ039 | Blocks | Healthy | Low
PRJ036 | PRJ004 | Finish-Start | At Risk | Low
PRJ031 | PRJ023 | Finish-Start | Healthy | Medium
PRJ033 | PRJ040 | Shared Resource | At Risk | Medium
PRJ024 | PRJ009 | Finish-Start | Blocked | Low
PRJ017 | PRJ011 | Shared Resource | At Risk | Medium
PRJ009 | PRJ006 | Blocks | Blocked | High
PRJ028 | PRJ010 | Blocks | Healthy | Medium
PRJ003 | PRJ009 | Shared Resource | At Risk | High
PRJ024 | PRJ028 | Blocks | At Risk | High
PRJ017 | PRJ034 | Blocks | At Risk | Low
PRJ021 | PRJ032 | Start-Start | Blocked | High
PRJ029 | PRJ004 | Start-Start | Healthy | Low
PRJ015 | PRJ012 | Finish-Start | At Risk | Medium
PRJ011 | PRJ030 | Shared Resource | Healthy | Medium

## Pipeline
Idea ID | Name | Submitter | Strategic Fit (1-5) | Value (1-5) | Risk (1-5) | Effort (1-5) | Priority Score | Decision | Est. Budget ($K)
IDEA008 | Quantum Pilot | Priya Patel | 4 | 4 | 3 | 5 |  | New | 724
IDEA004 | Edge Analytics | Alex Brown | 5 | 2 | 5 | 1 |  | Parked | 419
IDEA009 | SaaS Rationalisation | Priya Patel | 1 | 5 | 4 | 3 |  | Parked | 314
IDEA007 | Citizen Dev Studio | John Smith | 1 | 3 | 2 | 1 |  | Rejected | 1751
IDEA005 | Green IT | Priya Patel | 4 | 1 | 2 | 4 |  | New | 1867
IDEA001 | Process Automation v2 | Sarah Lee | 1 | 4 | 3 | 5 |  | Rejected | 1059
IDEA006 | ESG Data Hub | Sarah Lee | 3 | 1 | 3 | 1 |  | Approved | 1259
IDEA003 | ML Ops Platform | Carlos Diaz | 3 | 2 | 2 | 5 |  | Approved | 1203
IDEA002 | Customer 360 | John Smith | 1 | 2 | 1 | 3 |  | Under Review | 1828
IDEA010 | Zero Trust v2 | Carlos Diaz | 2 | 1 | 3 | 3 |  | New | 1573

## CostBenefit
Project ID | Project Name | Program | Year Offset | Year | CAPEX | OPEX | Total Cost | Benefit Recurring | Benefit One-Off | Total Benefit | Net Benefit | Benefit Type | Benefit Category | Confidence %
PRJ001 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Compliance | 70
PRJ001 |  |  | 1 |  |  |  |  | 738473 | 0 |  |  | Recurring | Compliance | 70
PRJ001 |  |  | 2 |  |  |  |  | 807665 | 0 |  |  | Recurring | Compliance | 70
PRJ001 |  |  | 3 |  |  |  |  | 859774 | 0 |  |  | Recurring | Compliance | 80
PRJ001 |  |  | 4 |  |  |  |  | 833860 | 0 |  |  | Recurring | Compliance | 60
PRJ002 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Compliance | 90
PRJ002 |  |  | 1 |  |  |  |  | 653868 | 0 |  |  | Recurring | Compliance | 70
PRJ002 |  |  | 2 |  |  |  |  | 563363 | 0 |  |  | Recurring | Compliance | 80
PRJ002 |  |  | 3 |  |  |  |  | 731003 | 0 |  |  | Recurring | Compliance | 70
PRJ002 |  |  | 4 |  |  |  |  | 730897 | 0 |  |  | Recurring | Compliance | 60
PRJ003 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Risk Avoidance | 70
PRJ003 |  |  | 1 |  |  |  |  | 2114749 | 0 |  |  | Recurring | Risk Avoidance | 90
PRJ003 |  |  | 2 |  |  |  |  | 1952878 | 0 |  |  | Recurring | Risk Avoidance | 60
PRJ003 |  |  | 3 |  |  |  |  | 2269327 | 0 |  |  | Recurring | Risk Avoidance | 90
PRJ003 |  |  | 4 |  |  |  |  | 2119194 | 0 |  |  | Recurring | Risk Avoidance | 80
PRJ004 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ004 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 90
PRJ004 |  |  | 2 |  |  |  |  | 0 | 509515 |  |  | One-Off | Cost Savings | 90
PRJ004 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ004 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ005 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Revenue Uplift | 60
PRJ005 |  |  | 1 |  |  |  |  | 1022279 | 0 |  |  | Recurring | Revenue Uplift | 60
PRJ005 |  |  | 2 |  |  |  |  | 1149000 | 0 |  |  | Recurring | Revenue Uplift | 90
PRJ005 |  |  | 3 |  |  |  |  | 1116960 | 0 |  |  | Recurring | Revenue Uplift | 90
PRJ005 |  |  | 4 |  |  |  |  | 911375 | 0 |  |  | Recurring | Revenue Uplift | 70
PRJ006 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 70
PRJ006 |  |  | 1 |  |  |  |  | 425057 | 0 |  |  | Recurring | Cost Savings | 70
PRJ006 |  |  | 2 |  |  |  |  | 347705 | 0 |  |  | Recurring | Cost Savings | 90
PRJ006 |  |  | 3 |  |  |  |  | 348394 | 0 |  |  | Recurring | Cost Savings | 90
PRJ006 |  |  | 4 |  |  |  |  | 462890 | 0 |  |  | Recurring | Cost Savings | 70
PRJ007 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Productivity | 60
PRJ007 |  |  | 1 |  |  |  |  | 2399019 | 0 |  |  | Recurring | Productivity | 90
PRJ007 |  |  | 2 |  |  |  |  | 2056671 | 0 |  |  | Recurring | Productivity | 80
PRJ007 |  |  | 3 |  |  |  |  | 2023700 | 0 |  |  | Recurring | Productivity | 90
PRJ007 |  |  | 4 |  |  |  |  | 1625671 | 0 |  |  | Recurring | Productivity | 80
PRJ008 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ008 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ008 |  |  | 2 |  |  |  |  | 0 | 3219136 |  |  | One-Off | Cost Savings | 70
PRJ008 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ008 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 90
PRJ009 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Productivity | 80
PRJ009 |  |  | 1 |  |  |  |  | 445276 | 0 |  |  | Recurring | Productivity | 70
PRJ009 |  |  | 2 |  |  |  |  | 417495 | 0 |  |  | Recurring | Productivity | 70
PRJ009 |  |  | 3 |  |  |  |  | 390121 | 0 |  |  | Recurring | Productivity | 90
PRJ009 |  |  | 4 |  |  |  |  | 349818 | 0 |  |  | Recurring | Productivity | 60
PRJ010 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Productivity | 60
PRJ010 |  |  | 1 |  |  |  |  | 665293 | 0 |  |  | Recurring | Productivity | 70
PRJ010 |  |  | 2 |  |  |  |  | 710566 | 0 |  |  | Recurring | Productivity | 80
PRJ010 |  |  | 3 |  |  |  |  | 871784 | 0 |  |  | Recurring | Productivity | 80
PRJ010 |  |  | 4 |  |  |  |  | 904389 | 0 |  |  | Recurring | Productivity | 60
PRJ011 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 60
PRJ011 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 60
PRJ011 |  |  | 2 |  |  |  |  | 0 | 277100 |  |  | One-Off | Cost Savings | 60
PRJ011 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ011 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 90
PRJ012 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ012 |  |  | 1 |  |  |  |  | 0 | 1433938 |  |  | One-Off | Cost Savings | 70
PRJ012 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ012 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ012 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ013 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Compliance | 90
PRJ013 |  |  | 1 |  |  |  |  | 1047962 | 0 |  |  | Recurring | Compliance | 80
PRJ013 |  |  | 2 |  |  |  |  | 1153749 | 0 |  |  | Recurring | Compliance | 60
PRJ013 |  |  | 3 |  |  |  |  | 1241960 | 0 |  |  | Recurring | Compliance | 70
PRJ013 |  |  | 4 |  |  |  |  | 848436 | 0 |  |  | Recurring | Compliance | 70
PRJ014 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ014 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ014 |  |  | 2 |  |  |  |  | 0 | 3086630 |  |  | One-Off | Cost Savings | 70
PRJ014 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ014 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 90
PRJ015 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 80
PRJ015 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 90
PRJ015 |  |  | 2 |  |  |  |  | 0 | 1172866 |  |  | One-Off | Productivity | 80
PRJ015 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 80
PRJ015 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 70
PRJ016 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 80
PRJ016 |  |  | 1 |  |  |  |  | 1253380 | 0 |  |  | Recurring | Cost Savings | 60
PRJ016 |  |  | 2 |  |  |  |  | 1489190 | 0 |  |  | Recurring | Cost Savings | 60
PRJ016 |  |  | 3 |  |  |  |  | 1261877 | 0 |  |  | Recurring | Cost Savings | 80
PRJ016 |  |  | 4 |  |  |  |  | 1389107 | 0 |  |  | Recurring | Cost Savings | 70
PRJ017 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 80
PRJ017 |  |  | 1 |  |  |  |  | 0 | 3587974 |  |  | One-Off | Compliance | 70
PRJ017 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ017 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ017 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 60
PRJ018 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Risk Avoidance | 70
PRJ018 |  |  | 1 |  |  |  |  | 319985 | 0 |  |  | Recurring | Risk Avoidance | 90
PRJ018 |  |  | 2 |  |  |  |  | 323427 | 0 |  |  | Recurring | Risk Avoidance | 80
PRJ018 |  |  | 3 |  |  |  |  | 404693 | 0 |  |  | Recurring | Risk Avoidance | 90
PRJ018 |  |  | 4 |  |  |  |  | 292102 | 0 |  |  | Recurring | Risk Avoidance | 70
PRJ019 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Risk Avoidance | 90
PRJ019 |  |  | 1 |  |  |  |  | 296269 | 0 |  |  | Recurring | Risk Avoidance | 80
PRJ019 |  |  | 2 |  |  |  |  | 287036 | 0 |  |  | Recurring | Risk Avoidance | 60
PRJ019 |  |  | 3 |  |  |  |  | 205318 | 0 |  |  | Recurring | Risk Avoidance | 70
PRJ019 |  |  | 4 |  |  |  |  | 238948 | 0 |  |  | Recurring | Risk Avoidance | 80
PRJ020 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 80
PRJ020 |  |  | 1 |  |  |  |  | 872874 | 0 |  |  | Recurring | Cost Savings | 90
PRJ020 |  |  | 2 |  |  |  |  | 640172 | 0 |  |  | Recurring | Cost Savings | 60
PRJ020 |  |  | 3 |  |  |  |  | 794427 | 0 |  |  | Recurring | Cost Savings | 80
PRJ020 |  |  | 4 |  |  |  |  | 842193 | 0 |  |  | Recurring | Cost Savings | 70
PRJ021 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Compliance | 80
PRJ021 |  |  | 1 |  |  |  |  | 2187373 | 0 |  |  | Recurring | Compliance | 90
PRJ021 |  |  | 2 |  |  |  |  | 2118510 | 0 |  |  | Recurring | Compliance | 90
PRJ021 |  |  | 3 |  |  |  |  | 2389439 | 0 |  |  | Recurring | Compliance | 60
PRJ021 |  |  | 4 |  |  |  |  | 2257247 | 0 |  |  | Recurring | Compliance | 60
PRJ022 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ022 |  |  | 1 |  |  |  |  | 0 | 2729899 |  |  | One-Off | Compliance | 70
PRJ022 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ022 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 90
PRJ022 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 80
PRJ023 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Compliance | 70
PRJ023 |  |  | 1 |  |  |  |  | 1518227 | 0 |  |  | Recurring | Compliance | 80
PRJ023 |  |  | 2 |  |  |  |  | 1665240 | 0 |  |  | Recurring | Compliance | 80
PRJ023 |  |  | 3 |  |  |  |  | 1369014 | 0 |  |  | Recurring | Compliance | 80
PRJ023 |  |  | 4 |  |  |  |  | 1348892 | 0 |  |  | Recurring | Compliance | 80
PRJ024 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 90
PRJ024 |  |  | 1 |  |  |  |  | 328407 | 0 |  |  | Recurring | Cost Savings | 60
PRJ024 |  |  | 2 |  |  |  |  | 289938 | 0 |  |  | Recurring | Cost Savings | 70
PRJ024 |  |  | 3 |  |  |  |  | 266274 | 0 |  |  | Recurring | Cost Savings | 60
PRJ024 |  |  | 4 |  |  |  |  | 285039 | 0 |  |  | Recurring | Cost Savings | 60
PRJ025 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 60
PRJ025 |  |  | 1 |  |  |  |  | 557802 | 0 |  |  | Recurring | Cost Savings | 80
PRJ025 |  |  | 2 |  |  |  |  | 570031 | 0 |  |  | Recurring | Cost Savings | 70
PRJ025 |  |  | 3 |  |  |  |  | 508780 | 0 |  |  | Recurring | Cost Savings | 70
PRJ025 |  |  | 4 |  |  |  |  | 485411 | 0 |  |  | Recurring | Cost Savings | 90
PRJ026 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 70
PRJ026 |  |  | 1 |  |  |  |  | 1692598 | 0 |  |  | Recurring | Cost Savings | 80
PRJ026 |  |  | 2 |  |  |  |  | 1603427 | 0 |  |  | Recurring | Cost Savings | 70
PRJ026 |  |  | 3 |  |  |  |  | 1394812 | 0 |  |  | Recurring | Cost Savings | 60
PRJ026 |  |  | 4 |  |  |  |  | 1447654 | 0 |  |  | Recurring | Cost Savings | 70
PRJ027 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 80
PRJ027 |  |  | 1 |  |  |  |  | 0 | 2283746 |  |  | One-Off | Compliance | 90
PRJ027 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 80
PRJ027 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 80
PRJ027 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 60
PRJ028 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 90
PRJ028 |  |  | 1 |  |  |  |  | 0 | 573194 |  |  | One-Off | Risk Avoidance | 60
PRJ028 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 90
PRJ028 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 90
PRJ028 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 70
PRJ029 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 70
PRJ029 |  |  | 1 |  |  |  |  | 0 | 1457637 |  |  | One-Off | Cost Savings | 80
PRJ029 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 80
PRJ029 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 90
PRJ029 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Cost Savings | 90
PRJ030 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 80
PRJ030 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ030 |  |  | 2 |  |  |  |  | 0 | 603368 |  |  | One-Off | Compliance | 70
PRJ030 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 60
PRJ030 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ031 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 90
PRJ031 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 60
PRJ031 |  |  | 2 |  |  |  |  | 0 | 1005938 |  |  | One-Off | Productivity | 90
PRJ031 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 90
PRJ031 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 60
PRJ032 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 90
PRJ032 |  |  | 1 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 60
PRJ032 |  |  | 2 |  |  |  |  | 0 | 4965523 |  |  | One-Off | Revenue Uplift | 60
PRJ032 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 80
PRJ032 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 60
PRJ033 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Risk Avoidance | 70
PRJ033 |  |  | 1 |  |  |  |  | 234403 | 0 |  |  | Recurring | Risk Avoidance | 60
PRJ033 |  |  | 2 |  |  |  |  | 223983 | 0 |  |  | Recurring | Risk Avoidance | 60
PRJ033 |  |  | 3 |  |  |  |  | 276791 | 0 |  |  | Recurring | Risk Avoidance | 90
PRJ033 |  |  | 4 |  |  |  |  | 206353 | 0 |  |  | Recurring | Risk Avoidance | 60
PRJ034 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Productivity | 90
PRJ034 |  |  | 1 |  |  |  |  | 655615 | 0 |  |  | Recurring | Productivity | 60
PRJ034 |  |  | 2 |  |  |  |  | 618701 | 0 |  |  | Recurring | Productivity | 90
PRJ034 |  |  | 3 |  |  |  |  | 650026 | 0 |  |  | Recurring | Productivity | 60
PRJ034 |  |  | 4 |  |  |  |  | 654609 | 0 |  |  | Recurring | Productivity | 60
PRJ035 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Cost Savings | 60
PRJ035 |  |  | 1 |  |  |  |  | 1237968 | 0 |  |  | Recurring | Cost Savings | 70
PRJ035 |  |  | 2 |  |  |  |  | 1113471 | 0 |  |  | Recurring | Cost Savings | 80
PRJ035 |  |  | 3 |  |  |  |  | 1084946 | 0 |  |  | Recurring | Cost Savings | 70
PRJ035 |  |  | 4 |  |  |  |  | 944283 | 0 |  |  | Recurring | Cost Savings | 90
PRJ036 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 80
PRJ036 |  |  | 1 |  |  |  |  | 0 | 3306307 |  |  | One-Off | Productivity | 70
PRJ036 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 60
PRJ036 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 70
PRJ036 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Productivity | 60
PRJ037 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | Recurring | Revenue Uplift | 80
PRJ037 |  |  | 1 |  |  |  |  | 559351 | 0 |  |  | Recurring | Revenue Uplift | 80
PRJ037 |  |  | 2 |  |  |  |  | 587763 | 0 |  |  | Recurring | Revenue Uplift | 60
PRJ037 |  |  | 3 |  |  |  |  | 631939 | 0 |  |  | Recurring | Revenue Uplift | 70
PRJ037 |  |  | 4 |  |  |  |  | 594096 | 0 |  |  | Recurring | Revenue Uplift | 80
PRJ038 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 60
PRJ038 |  |  | 1 |  |  |  |  | 0 | 722882 |  |  | One-Off | Risk Avoidance | 90
PRJ038 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 80
PRJ038 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 70
PRJ038 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Risk Avoidance | 80
PRJ039 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 70
PRJ039 |  |  | 1 |  |  |  |  | 0 | 2030910 |  |  | One-Off | Revenue Uplift | 70
PRJ039 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 60
PRJ039 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 90
PRJ039 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Revenue Uplift | 70
PRJ040 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ040 |  |  | 1 |  |  |  |  | 0 | 1873752 |  |  | One-Off | Compliance | 80
PRJ040 |  |  | 2 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ040 |  |  | 3 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70
PRJ040 |  |  | 4 |  |  |  |  | 0 | 0 |  |  | One-Off | Compliance | 70

## Benefits
Benefit ID | Project ID | Project Name | Description | Category | Target Value | Realised Value | Benefits Remaining | Realisation % | Owner | Start Date | End Date | Status
BEN001 | PRJ001 |  | Process cycle-time reduction | Cost Reduction | 569626 | 250989 |  |  | Carlos Diaz |  |  | At Risk
BEN002 | PRJ001 |  | Risk loss avoidance | Compliance | 497551 | 28353 |  |  | Alex Brown |  |  | At Risk
BEN003 | PRJ002 |  | Regulatory compliance achievement | Customer Experience | 1527159 | 400095 |  |  | Jane Doe |  |  | Realised
BEN004 | PRJ002 |  | Risk loss avoidance | Customer Experience | 1098404 | 371599 |  |  | Mike Johnson |  |  | Planned
BEN005 | PRJ002 |  | Risk loss avoidance | Cost Reduction | 493679 | 309250 |  |  | Sarah Lee |  |  | At Risk
BEN006 | PRJ003 |  | Process cycle-time reduction | Productivity Improvement | 1185604 | 776392 |  |  | Alex Brown |  |  | Planned
BEN007 | PRJ003 |  | Revenue growth from new channel | Risk Reduction | 660591 | 239910 |  |  | John Smith |  |  | Realised
BEN008 | PRJ004 |  | Process cycle-time reduction | Customer Experience | 957187 | 289792 |  |  | Mike Johnson |  |  | Planned
BEN009 | PRJ004 |  | Customer NPS uplift | Revenue Increase | 441175 | 72200 |  |  | Mike Johnson |  |  | Planned
BEN010 | PRJ005 |  | Headcount cost avoidance | Productivity Improvement | 1860551 | 128167 |  |  | John Smith |  |  | Realised
BEN011 | PRJ005 |  | Process cycle-time reduction | Compliance | 473628 | 109157 |  |  | Carlos Diaz |  |  | In Progress
BEN012 | PRJ006 |  | Customer NPS uplift | Compliance | 1247665 | 120407 |  |  | Alex Brown |  |  | Realised
BEN013 | PRJ006 |  | Risk loss avoidance | Customer Experience | 635506 | 154201 |  |  | Carlos Diaz |  |  | Planned
BEN014 | PRJ006 |  | Revenue growth from new channel | Customer Experience | 996808 | 357707 |  |  | Jane Doe |  |  | At Risk
BEN015 | PRJ007 |  | Risk loss avoidance | Compliance | 1080068 | 594234 |  |  | Carlos Diaz |  |  | Planned
BEN016 | PRJ008 |  | Customer NPS uplift | Customer Experience | 1707023 | 512372 |  |  | Jane Doe |  |  | Planned
BEN017 | PRJ008 |  | Revenue growth from new channel | Productivity Improvement | 811930 | 328228 |  |  | Priya Patel |  |  | Realised
BEN018 | PRJ009 |  | Risk loss avoidance | Compliance | 528432 | 157475 |  |  | Alex Brown |  |  | Planned
BEN019 | PRJ009 |  | Revenue growth from new channel | Cost Reduction | 1178397 | 26568 |  |  | Mike Johnson |  |  | At Risk
BEN020 | PRJ010 |  | Regulatory compliance achievement | Customer Experience | 487989 | 133438 |  |  | Jane Doe |  |  | Realised
BEN021 | PRJ010 |  | Process cycle-time reduction | Revenue Increase | 1182079 | 373625 |  |  | Jane Doe |  |  | In Progress
BEN022 | PRJ011 |  | Headcount cost avoidance | Cost Reduction | 1670302 | 705460 |  |  | Jane Doe |  |  | Realised
BEN023 | PRJ012 |  | Headcount cost avoidance | Customer Experience | 542775 | 250599 |  |  | John Smith |  |  | Planned
BEN024 | PRJ013 |  | Risk loss avoidance | Cost Reduction | 720867 | 459098 |  |  | John Smith |  |  | At Risk
BEN025 | PRJ014 |  | Revenue growth from new channel | Cost Reduction | 1511971 | 411702 |  |  | Carlos Diaz |  |  | At Risk
BEN026 | PRJ014 |  | Revenue growth from new channel | Risk Reduction | 1654003 | 769698 |  |  | Alex Brown |  |  | In Progress
BEN027 | PRJ015 |  | Revenue growth from new channel | Revenue Increase | 1461867 | 469653 |  |  | Jane Doe |  |  | At Risk
BEN028 | PRJ015 |  | Process cycle-time reduction | Risk Reduction | 1249212 | 215849 |  |  | Sarah Lee |  |  | Planned
BEN029 | PRJ015 |  | Risk loss avoidance | Productivity Improvement | 1500852 | 302479 |  |  | Priya Patel |  |  | In Progress
BEN030 | PRJ016 |  | Customer NPS uplift | Customer Experience | 573356 | 361200 |  |  | Sarah Lee |  |  | In Progress
BEN031 | PRJ016 |  | Customer NPS uplift | Revenue Increase | 1427192 | 95442 |  |  | Jane Doe |  |  | Realised
BEN032 | PRJ017 |  | Customer NPS uplift | Cost Reduction | 1840963 | 899551 |  |  | Sarah Lee |  |  | Planned
BEN033 | PRJ017 |  | Headcount cost avoidance | Risk Reduction | 1991101 | 106670 |  |  | Carlos Diaz |  |  | At Risk
BEN034 | PRJ017 |  | Headcount cost avoidance | Customer Experience | 413194 | 59979 |  |  | John Smith |  |  | At Risk
BEN035 | PRJ018 |  | Revenue growth from new channel | Customer Experience | 752950 | 210479 |  |  | John Smith |  |  | Planned
BEN036 | PRJ018 |  | Customer NPS uplift | Compliance | 1447289 | 138269 |  |  | Sarah Lee |  |  | Planned
BEN037 | PRJ019 |  | Risk loss avoidance | Cost Reduction | 1142014 | 193692 |  |  | Sarah Lee |  |  | In Progress
BEN038 | PRJ020 |  | Headcount cost avoidance | Risk Reduction | 1253278 | 155489 |  |  | Priya Patel |  |  | Planned
BEN039 | PRJ021 |  | Revenue growth from new channel | Customer Experience | 1550819 | 735349 |  |  | Mike Johnson |  |  | Planned
BEN040 | PRJ021 |  | Risk loss avoidance | Compliance | 1796107 | 669246 |  |  | John Smith |  |  | Planned
BEN041 | PRJ021 |  | Headcount cost avoidance | Risk Reduction | 842175 | 181764 |  |  | John Smith |  |  | In Progress
BEN042 | PRJ022 |  | Headcount cost avoidance | Revenue Increase | 811825 | 135557 |  |  | Sarah Lee |  |  | Realised
BEN043 | PRJ023 |  | Headcount cost avoidance | Compliance | 1391923 | 61551 |  |  | Jane Doe |  |  | At Risk
BEN044 | PRJ024 |  | Regulatory compliance achievement | Compliance | 304599 | 69753 |  |  | Jane Doe |  |  | At Risk
BEN045 | PRJ024 |  | Revenue growth from new channel | Revenue Increase | 1883954 | 159312 |  |  | Mike Johnson |  |  | Planned
BEN046 | PRJ024 |  | Risk loss avoidance | Cost Reduction | 864065 | 191276 |  |  | Sarah Lee |  |  | Realised
BEN047 | PRJ025 |  | Revenue growth from new channel | Customer Experience | 1285428 | 39536 |  |  | Mike Johnson |  |  | Planned
BEN048 | PRJ025 |  | Regulatory compliance achievement | Cost Reduction | 1453809 | 805238 |  |  | Mike Johnson |  |  | Realised
BEN049 | PRJ025 |  | Customer NPS uplift | Compliance | 1964690 | 957631 |  |  | Jane Doe |  |  | Realised
BEN050 | PRJ026 |  | Regulatory compliance achievement | Risk Reduction | 1016048 | 238338 |  |  | Sarah Lee |  |  | In Progress
BEN051 | PRJ026 |  | Headcount cost avoidance | Cost Reduction | 1056498 | 521107 |  |  | John Smith |  |  | Realised
BEN052 | PRJ026 |  | Revenue growth from new channel | Risk Reduction | 549153 | 164718 |  |  | John Smith |  |  | Realised
BEN053 | PRJ027 |  | Revenue growth from new channel | Compliance | 663568 | 70451 |  |  | John Smith |  |  | At Risk
BEN054 | PRJ027 |  | Process cycle-time reduction | Productivity Improvement | 1504586 | 346180 |  |  | Priya Patel |  |  | At Risk
BEN055 | PRJ028 |  | Revenue growth from new channel | Compliance | 1644150 | 863813 |  |  | Mike Johnson |  |  | In Progress
BEN056 | PRJ028 |  | Customer NPS uplift | Cost Reduction | 1124692 | 713777 |  |  | Carlos Diaz |  |  | In Progress
BEN057 | PRJ028 |  | Process cycle-time reduction | Cost Reduction | 1255320 | 335221 |  |  | Sarah Lee |  |  | Planned
BEN058 | PRJ029 |  | Customer NPS uplift | Cost Reduction | 232971 | 31387 |  |  | Jane Doe |  |  | In Progress
BEN059 | PRJ029 |  | Revenue growth from new channel | Cost Reduction | 1225998 | 713353 |  |  | Alex Brown |  |  | At Risk
BEN060 | PRJ030 |  | Risk loss avoidance | Cost Reduction | 411902 | 56956 |  |  | Alex Brown |  |  | Realised
BEN061 | PRJ030 |  | Revenue growth from new channel | Productivity Improvement | 1195201 | 809639 |  |  | Carlos Diaz |  |  | Realised
BEN062 | PRJ031 |  | Risk loss avoidance | Risk Reduction | 817663 | 269419 |  |  | Alex Brown |  |  | At Risk
BEN063 | PRJ031 |  | Headcount cost avoidance | Productivity Improvement | 137641 | 36749 |  |  | Alex Brown |  |  | In Progress
BEN064 | PRJ032 |  | Process cycle-time reduction | Customer Experience | 822855 | 176168 |  |  | Alex Brown |  |  | Planned
BEN065 | PRJ032 |  | Revenue growth from new channel | Cost Reduction | 733145 | 366869 |  |  | Jane Doe |  |  | Realised
BEN066 | PRJ033 |  | Risk loss avoidance | Compliance | 868655 | 252843 |  |  | Mike Johnson |  |  | Realised
BEN067 | PRJ033 |  | Risk loss avoidance | Revenue Increase | 1317993 | 542771 |  |  | John Smith |  |  | In Progress
BEN068 | PRJ034 |  | Customer NPS uplift | Productivity Improvement | 1549607 | 1038187 |  |  | Alex Brown |  |  | Realised
BEN069 | PRJ035 |  | Risk loss avoidance | Compliance | 209639 | 56547 |  |  | Jane Doe |  |  | Planned
BEN070 | PRJ035 |  | Customer NPS uplift | Compliance | 1850790 | 468231 |  |  | John Smith |  |  | In Progress
BEN071 | PRJ035 |  | Customer NPS uplift | Cost Reduction | 596528 | 190191 |  |  | Mike Johnson |  |  | In Progress
BEN072 | PRJ036 |  | Customer NPS uplift | Customer Experience | 321788 | 20792 |  |  | Sarah Lee |  |  | Planned
BEN073 | PRJ037 |  | Revenue growth from new channel | Customer Experience | 1828903 | 1121491 |  |  | Mike Johnson |  |  | At Risk
BEN074 | PRJ037 |  | Customer NPS uplift | Revenue Increase | 1213552 | 623466 |  |  | John Smith |  |  | Realised
BEN075 | PRJ037 |  | Revenue growth from new channel | Compliance | 1647033 | 310161 |  |  | Sarah Lee |  |  | Planned
BEN076 | PRJ038 |  | Headcount cost avoidance | Compliance | 1651140 | 1825 |  |  | Sarah Lee |  |  | Realised
BEN077 | PRJ039 |  | Revenue growth from new channel | Compliance | 918804 | 113455 |  |  | Jane Doe |  |  | In Progress
BEN078 | PRJ039 |  | Regulatory compliance achievement | Cost Reduction | 1054966 | 81408 |  |  | Jane Doe |  |  | In Progress
BEN079 | PRJ039 |  | Risk loss avoidance | Customer Experience | 1637439 | 219940 |  |  | Priya Patel |  |  | In Progress
BEN080 | PRJ040 |  | Process cycle-time reduction | Revenue Increase | 656939 | 173701 |  |  | Mike Johnson |  |  | In Progress

## Decisions
Decision ID | Type | Project ID | Program | Description | Required By | Owner | Due Date | Priority | Status | Outcome | Approval Date
DEC001 | General |  |  | Approve full project funding | CIO | Mike Johnson | 2026-05-04 |  | Closed
DEC002 | Project | PRJ007 |  | Approve architecture pattern | CIO | Sarah Lee | 2026-07-23 |  | Closed
DEC003 | SteerCo | PRJ032 |  | Defer benefits realisation date | COO | Alex Brown | 2026-07-15 |  | Approved
DEC004 | Architecture | PRJ021 |  | Cut scope of MVP | CMO | Sarah Lee | 2026-04-06 |  | Open
DEC005 | Architecture | PRJ007 |  | Re-baseline schedule | CMO | Priya Patel | 2026-04-03 |  | Open
DEC006 | Program | PRJ034 |  | Accept residual risk | CFO | Mike Johnson | 2026-06-05 |  | Closed
DEC007 | General | PRJ033 |  | Accept residual risk | CFO | John Smith | 2026-06-26 |  | Approved
DEC008 | Architecture | PRJ003 |  | Accept residual risk | CMO | Jane Doe | 2026-01-06 |  | Rejected
DEC009 | Program | PRJ023 |  | Re-baseline schedule | CIO | Priya Patel | 2026-04-14 |  | Approved
DEC010 | Funding | PRJ010 |  | Choose vendor for cloud migration | CMO | Carlos Diaz | 2026-06-06 |  | Approved
DEC011 | General | PRJ011 |  | Approve full project funding | CMO | Priya Patel | 2026-08-03 |  | In Review
DEC012 | Funding | PRJ011 |  | Approve full project funding | CMO | Priya Patel | 2026-03-05 |  | In Review
DEC013 | Risk | PRJ018 |  | Accept residual risk | COO | Priya Patel | 2026-03-26 |  | Open
DEC014 | Portfolio | PRJ035 |  | Approve full project funding | COO | Carlos Diaz | 2026-06-21 |  | Closed
DEC015 | Program |  |  | Re-baseline schedule | CMO | Priya Patel | 2026-07-17 |  | Closed
DEC016 | Risk | PRJ015 |  | Cut scope of MVP | CIO | Mike Johnson | 2026-08-09 |  | Open
DEC017 | Architecture | PRJ038 |  | Accept residual risk | CIO | Alex Brown | 2026-01-24 |  | In Review
DEC018 | Architecture | PRJ025 |  | Cut scope of MVP | CIO | Alex Brown | 2026-08-08 |  | In Review
DEC019 | Risk | PRJ028 |  | Defer benefits realisation date | COO | Carlos Diaz | 2026-08-06 |  | In Review
DEC020 | Funding | PRJ007 |  | Approve full project funding | CTO | Carlos Diaz | 2026-05-15 |  | Approved
DEC021 | SteerCo | PRJ015 |  | Accept residual risk | CMO | Jane Doe | 2026-02-08 |  | Approved
DEC022 | Project | PRJ039 |  | Cut scope of MVP | CTO | Priya Patel | 2026-02-08 |  | Approved
DEC023 | General |  |  | Re-baseline schedule | COO | Priya Patel | 2026-08-07 |  | Open
DEC024 | Architecture | PRJ010 |  | Defer benefits realisation date | CFO | Priya Patel | 2026-07-28 |  | Open
DEC025 | Portfolio | PRJ032 |  | Cut scope of MVP | CFO | John Smith | 2026-08-11 |  | Rejected
DEC026 | Risk |  |  | Cut scope of MVP | CMO | Sarah Lee | 2026-03-29 |  | Closed
DEC027 | SteerCo | PRJ019 |  | Accept residual risk | CTO | Sarah Lee | 2026-07-07 |  | In Review
DEC028 | Project | PRJ020 |  | Accept residual risk | CFO | Alex Brown | 2026-03-25 |  | Rejected
DEC029 | General | PRJ019 |  | Choose vendor for cloud migration | CFO | Carlos Diaz | 2026-06-29 |  | In Review
DEC030 | Project | PRJ024 |  | Accept residual risk | CFO | Sarah Lee | 2026-07-09 |  | In Review
DEC031 | Program | PRJ023 |  | Choose vendor for cloud migration | CIO | John Smith | 2026-01-16 |  | Approved
DEC032 | Risk | PRJ010 |  | Choose vendor for cloud migration | CIO | John Smith | 2026-06-02 |  | Rejected
DEC033 | SteerCo | PRJ039 |  | Accept residual risk | CMO | Carlos Diaz | 2026-05-07 |  | Open
DEC034 | General |  |  | Cut scope of MVP | CMO | Mike Johnson | 2026-07-20 |  | Open
DEC035 | Program | PRJ008 |  | Accept residual risk | CTO | Jane Doe | 2026-01-31 |  | Closed
DEC036 | General | PRJ018 |  | Defer benefits realisation date | CTO | Jane Doe | 2026-05-28 |  | Rejected
DEC037 | Risk | PRJ020 |  | Approve full project funding | COO | John Smith | 2026-06-16 |  | Closed
DEC038 | Risk | PRJ002 |  | Approve architecture pattern | CTO | Carlos Diaz | 2026-02-18 |  | Rejected
DEC039 | Program | PRJ014 |  | Choose vendor for cloud migration | CTO | Priya Patel | 2026-01-18 |  | Open
DEC040 | General | PRJ021 |  | Approve full project funding | CFO | Alex Brown | 2026-05-24 |  | In Review

## Actions
Action ID | Project ID | Description | Owner | Due Date | Priority | Status | Comments
ACT001 | PRJ017 | Close out stage gate evidence | Carlos Diaz | 2026-01-07 | High | Complete
ACT002 | PRJ033 | Publish SteerCo pack | Mike Johnson | 2026-01-06 | Low | Overdue
ACT003 | PRJ001 | Update risk register | Mike Johnson | 2026-01-28 | High | Overdue
ACT004 | PRJ035 | Resolve blocker on environment | Jane Doe | 2026-04-27 | Low | Overdue
ACT005 | PRJ021 | Schedule architecture review | Mike Johnson | 2026-04-20 | Low | Complete
ACT006 | PRJ014 | Submit funding paper | John Smith | 2026-05-02 | Low | Complete
ACT007 | PRJ016 | Confirm vendor SOW | Jane Doe | 2026-07-13 | High | Overdue
ACT008 | PRJ009 | Schedule architecture review | Alex Brown | 2026-03-02 | High | Overdue
ACT009 | PRJ018 | Update risk register | Priya Patel | 2026-05-16 | Low | Overdue
ACT010 | PRJ036 | Publish SteerCo pack | Mike Johnson | 2026-04-03 | Medium | Overdue
ACT011 | PRJ026 | Resolve blocker on environment | John Smith | 2026-05-31 | Medium | Overdue
ACT012 | PRJ010 | Schedule architecture review | Jane Doe | 2026-06-07 | High | Overdue
ACT013 | PRJ018 | Submit funding paper | Priya Patel | 2026-05-26 | Low | Complete
ACT014 | PRJ024 | Schedule architecture review | Priya Patel | 2026-02-03 | Low | Complete
ACT015 | PRJ039 | Update risk register | Sarah Lee | 2026-07-14 | High | Complete
ACT016 | PRJ025 | Confirm vendor SOW | Alex Brown | 2026-03-06 | High | Overdue
ACT017 | PRJ008 | Schedule architecture review | John Smith | 2026-01-04 | Low | Overdue
ACT018 | PRJ005 | Publish SteerCo pack | Priya Patel | 2026-05-05 | High | Overdue
ACT019 | PRJ018 | Update risk register | Carlos Diaz | 2026-03-18 | High | Overdue
ACT020 | PRJ007 | Resolve blocker on environment | Jane Doe | 2026-02-24 | Medium | Overdue
ACT021 | PRJ012 | Schedule architecture review | Priya Patel | 2026-01-11 | Medium | Overdue
ACT022 | PRJ007 | Schedule architecture review | Mike Johnson | 2026-05-15 | Low | Overdue
ACT023 | PRJ036 | Publish SteerCo pack | Alex Brown | 2026-05-11 | High | Overdue
ACT024 | PRJ021 | Close out stage gate evidence | Sarah Lee | 2025-12-28 | High | Overdue
ACT025 | PRJ035 | Schedule architecture review | Alex Brown | 2026-03-14 | Medium | Complete
ACT026 | PRJ009 | Publish SteerCo pack | John Smith | 2026-04-17 | Low | Complete
ACT027 | PRJ010 | Submit funding paper | Jane Doe | 2026-04-26 | High | Complete
ACT028 | PRJ018 | Confirm vendor SOW | Priya Patel | 2026-03-22 | Low | Complete
ACT029 | PRJ016 | Submit funding paper | Alex Brown | 2026-03-20 | Medium | Complete
ACT030 | PRJ012 | Resolve blocker on environment | Mike Johnson | 2026-06-14 | Medium | Overdue
ACT031 | PRJ018 | Resolve blocker on environment | Alex Brown | 2026-04-23 | Low | Overdue
ACT032 | PRJ020 | Submit funding paper | Carlos Diaz | 2026-07-12 | High | Overdue
ACT033 | PRJ021 | Close out stage gate evidence | John Smith | 2026-03-04 | Low | Overdue
ACT034 | PRJ016 | Confirm vendor SOW | Jane Doe | 2026-01-05 | Low | Overdue
ACT035 | PRJ019 | Schedule architecture review | Sarah Lee | 2025-12-30 | High | Overdue
ACT036 | PRJ033 | Submit funding paper | Jane Doe | 2026-04-03 | Medium | Complete
ACT037 | PRJ035 | Submit funding paper | John Smith | 2026-04-22 | Medium | Complete
ACT038 | PRJ013 | Close out stage gate evidence | Priya Patel | 2025-12-19 | High | Complete
ACT039 | PRJ035 | Submit funding paper | Mike Johnson | 2026-06-16 | High | Overdue
ACT040 | PRJ034 | Submit funding paper | Alex Brown | 2026-06-23 | High | Complete
ACT041 | PRJ011 | Submit funding paper | Carlos Diaz | 2026-05-20 | Low | Overdue
ACT042 | PRJ005 | Publish SteerCo pack | Carlos Diaz | 2026-02-11 | High | Overdue
ACT043 | PRJ004 | Resolve blocker on environment | Sarah Lee | 2026-04-26 | Medium | Overdue
ACT044 | PRJ008 | Publish SteerCo pack | Priya Patel | 2026-01-28 | High | Overdue
ACT045 | PRJ019 | Publish SteerCo pack | Sarah Lee | 2026-05-03 | Medium | Overdue
ACT046 | PRJ001 | Submit funding paper | Priya Patel | 2026-02-21 | Low | Overdue
ACT047 | PRJ020 | Submit funding paper | Alex Brown | 2026-03-26 | High | Overdue
ACT048 | PRJ032 | Confirm vendor SOW | Mike Johnson | 2026-04-13 | High | Complete
ACT049 | PRJ022 | Publish SteerCo pack | Mike Johnson | 2026-05-22 | High | Overdue
ACT050 | PRJ012 | Resolve blocker on environment | Mike Johnson | 2025-12-17 | High | Overdue
ACT051 | PRJ032 | Update risk register | John Smith | 2026-01-10 | Low | Overdue
ACT052 | PRJ027 | Confirm vendor SOW | Sarah Lee | 2026-04-26 | High | Overdue
ACT053 | PRJ017 | Update risk register | Sarah Lee | 2026-01-24 | Medium | Complete
ACT054 | PRJ024 | Resolve blocker on environment | Jane Doe | 2026-03-21 | Low | Overdue
ACT055 | PRJ007 | Resolve blocker on environment | Priya Patel | 2026-07-11 | Medium | Overdue
ACT056 | PRJ023 | Submit funding paper | Sarah Lee | 2026-01-26 | High | Overdue
ACT057 | PRJ013 | Confirm vendor SOW | Jane Doe | 2026-03-17 | Medium | Complete
ACT058 | PRJ026 | Resolve blocker on environment | Priya Patel | 2025-12-26 | Medium | Overdue
ACT059 | PRJ013 | Resolve blocker on environment | Priya Patel | 2025-12-24 | Medium | Overdue
ACT060 | PRJ032 | Schedule architecture review | Sarah Lee | 2026-01-15 | Low | Overdue

## Milestones
Project ID | Milestone | Planned Date | Forecast Date | Actual Date | Status | Owner | Source | _Key
PRJ001 | Discovery | [5 empty] | StageGate
PRJ001 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ001 | Design | [5 empty] | StageGate
PRJ001 | Business Case / Full Funding | [5 empty] | StageGate
PRJ001 | Build | [5 empty] | StageGate
PRJ001 | Testing | [5 empty] | StageGate
PRJ001 | Deployment | [5 empty] | StageGate
PRJ001 | Handover | [5 empty] | StageGate
PRJ002 | Discovery | [5 empty] | StageGate
PRJ002 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ002 | Design | [5 empty] | StageGate
PRJ002 | Business Case / Full Funding | [5 empty] | StageGate
PRJ002 | Build | [5 empty] | StageGate
PRJ002 | Testing | [5 empty] | StageGate
PRJ002 | Deployment | [5 empty] | StageGate
PRJ002 | Handover | [5 empty] | StageGate
PRJ003 | Discovery | [5 empty] | StageGate
PRJ003 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ003 | Design | [5 empty] | StageGate
PRJ003 | Business Case / Full Funding | [5 empty] | StageGate
PRJ003 | Build | [5 empty] | StageGate
PRJ003 | Testing | [5 empty] | StageGate
PRJ003 | Deployment | [5 empty] | StageGate
PRJ003 | Handover | [5 empty] | StageGate
PRJ004 | Discovery | [5 empty] | StageGate
PRJ004 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ004 | Design | [5 empty] | StageGate
PRJ004 | Business Case / Full Funding | [5 empty] | StageGate
PRJ004 | Build | [5 empty] | StageGate
PRJ004 | Testing | [5 empty] | StageGate
PRJ004 | Deployment | [5 empty] | StageGate
PRJ004 | Handover | [5 empty] | StageGate
PRJ005 | Discovery | [5 empty] | StageGate
PRJ005 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ005 | Design | [5 empty] | StageGate
PRJ005 | Business Case / Full Funding | [5 empty] | StageGate
PRJ005 | Build | [5 empty] | StageGate
PRJ005 | Testing | [5 empty] | StageGate
PRJ005 | Deployment | [5 empty] | StageGate
PRJ005 | Handover | [5 empty] | StageGate
PRJ006 | Discovery | [5 empty] | StageGate
PRJ006 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ006 | Design | [5 empty] | StageGate
PRJ006 | Business Case / Full Funding | [5 empty] | StageGate
PRJ006 | Build | [5 empty] | StageGate
PRJ006 | Testing | [5 empty] | StageGate
PRJ006 | Deployment | [5 empty] | StageGate
PRJ006 | Handover | [5 empty] | StageGate
PRJ007 | Discovery | [5 empty] | StageGate
PRJ007 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ007 | Design | [5 empty] | StageGate
PRJ007 | Business Case / Full Funding | [5 empty] | StageGate
PRJ007 | Build | [5 empty] | StageGate
PRJ007 | Testing | [5 empty] | StageGate
PRJ007 | Deployment | [5 empty] | StageGate
PRJ007 | Handover | [5 empty] | StageGate
PRJ008 | Discovery | [5 empty] | StageGate
PRJ008 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ008 | Design | [5 empty] | StageGate
PRJ008 | Business Case / Full Funding | [5 empty] | StageGate
PRJ008 | Build | [5 empty] | StageGate
PRJ008 | Testing | [5 empty] | StageGate
PRJ008 | Deployment | [5 empty] | StageGate
PRJ008 | Handover | [5 empty] | StageGate
PRJ009 | Discovery | [5 empty] | StageGate
PRJ009 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ009 | Design | [5 empty] | StageGate
PRJ009 | Business Case / Full Funding | [5 empty] | StageGate
PRJ009 | Build | [5 empty] | StageGate
PRJ009 | Testing | [5 empty] | StageGate
PRJ009 | Deployment | [5 empty] | StageGate
PRJ009 | Handover | [5 empty] | StageGate
PRJ010 | Discovery | [5 empty] | StageGate
PRJ010 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ010 | Design | [5 empty] | StageGate
PRJ010 | Business Case / Full Funding | [5 empty] | StageGate
PRJ010 | Build | [5 empty] | StageGate
PRJ010 | Testing | [5 empty] | StageGate
PRJ010 | Deployment | [5 empty] | StageGate
PRJ010 | Handover | [5 empty] | StageGate
PRJ011 | Discovery | [5 empty] | StageGate
PRJ011 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ011 | Design | [5 empty] | StageGate
PRJ011 | Business Case / Full Funding | [5 empty] | StageGate
PRJ011 | Build | [5 empty] | StageGate
PRJ011 | Testing | [5 empty] | StageGate
PRJ011 | Deployment | [5 empty] | StageGate
PRJ011 | Handover | [5 empty] | StageGate
PRJ012 | Discovery | [5 empty] | StageGate
PRJ012 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ012 | Design | [5 empty] | StageGate
PRJ012 | Business Case / Full Funding | [5 empty] | StageGate
PRJ012 | Build | [5 empty] | StageGate
PRJ012 | Testing | [5 empty] | StageGate
PRJ012 | Deployment | [5 empty] | StageGate
PRJ012 | Handover | [5 empty] | StageGate
PRJ013 | Discovery | [5 empty] | StageGate
PRJ013 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ013 | Design | [5 empty] | StageGate
PRJ013 | Business Case / Full Funding | [5 empty] | StageGate
PRJ013 | Build | [5 empty] | StageGate
PRJ013 | Testing | [5 empty] | StageGate
PRJ013 | Deployment | [5 empty] | StageGate
PRJ013 | Handover | [5 empty] | StageGate
PRJ014 | Discovery | [5 empty] | StageGate
PRJ014 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ014 | Design | [5 empty] | StageGate
PRJ014 | Business Case / Full Funding | [5 empty] | StageGate
PRJ014 | Build | [5 empty] | StageGate
PRJ014 | Testing | [5 empty] | StageGate
PRJ014 | Deployment | [5 empty] | StageGate
PRJ014 | Handover | [5 empty] | StageGate
PRJ015 | Discovery | [5 empty] | StageGate
PRJ015 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ015 | Design | [5 empty] | StageGate
PRJ015 | Business Case / Full Funding | [5 empty] | StageGate
PRJ015 | Build | [5 empty] | StageGate
PRJ015 | Testing | [5 empty] | StageGate
PRJ015 | Deployment | [5 empty] | StageGate
PRJ015 | Handover | [5 empty] | StageGate
PRJ016 | Discovery | [5 empty] | StageGate
PRJ016 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ016 | Design | [5 empty] | StageGate
PRJ016 | Business Case / Full Funding | [5 empty] | StageGate
PRJ016 | Build | [5 empty] | StageGate
PRJ016 | Testing | [5 empty] | StageGate
PRJ016 | Deployment | [5 empty] | StageGate
PRJ016 | Handover | [5 empty] | StageGate
PRJ017 | Discovery | [5 empty] | StageGate
PRJ017 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ017 | Design | [5 empty] | StageGate
PRJ017 | Business Case / Full Funding | [5 empty] | StageGate
PRJ017 | Build | [5 empty] | StageGate
PRJ017 | Testing | [5 empty] | StageGate
PRJ017 | Deployment | [5 empty] | StageGate
PRJ017 | Handover | [5 empty] | StageGate
PRJ018 | Discovery | [5 empty] | StageGate
PRJ018 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ018 | Design | [5 empty] | StageGate
PRJ018 | Business Case / Full Funding | [5 empty] | StageGate
PRJ018 | Build | [5 empty] | StageGate
PRJ018 | Testing | [5 empty] | StageGate
PRJ018 | Deployment | [5 empty] | StageGate
PRJ018 | Handover | [5 empty] | StageGate
PRJ019 | Discovery | [5 empty] | StageGate
PRJ019 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ019 | Design | [5 empty] | StageGate
PRJ019 | Business Case / Full Funding | [5 empty] | StageGate
PRJ019 | Build | [5 empty] | StageGate
PRJ019 | Testing | [5 empty] | StageGate
PRJ019 | Deployment | [5 empty] | StageGate
PRJ019 | Handover | [5 empty] | StageGate
PRJ020 | Discovery | [5 empty] | StageGate
PRJ020 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ020 | Design | [5 empty] | StageGate
PRJ020 | Business Case / Full Funding | [5 empty] | StageGate
PRJ020 | Build | [5 empty] | StageGate
PRJ020 | Testing | [5 empty] | StageGate
PRJ020 | Deployment | [5 empty] | StageGate
PRJ020 | Handover | [5 empty] | StageGate
PRJ021 | Discovery | [5 empty] | StageGate
PRJ021 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ021 | Design | [5 empty] | StageGate
PRJ021 | Business Case / Full Funding | [5 empty] | StageGate
PRJ021 | Build | [5 empty] | StageGate
PRJ021 | Testing | [5 empty] | StageGate
PRJ021 | Deployment | [5 empty] | StageGate
PRJ021 | Handover | [5 empty] | StageGate
PRJ022 | Discovery | [5 empty] | StageGate
PRJ022 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ022 | Design | [5 empty] | StageGate
PRJ022 | Business Case / Full Funding | [5 empty] | StageGate
PRJ022 | Build | [5 empty] | StageGate
PRJ022 | Testing | [5 empty] | StageGate
PRJ022 | Deployment | [5 empty] | StageGate
PRJ022 | Handover | [5 empty] | StageGate
PRJ023 | Discovery | [5 empty] | StageGate
PRJ023 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ023 | Design | [5 empty] | StageGate
PRJ023 | Business Case / Full Funding | [5 empty] | StageGate
PRJ023 | Build | [5 empty] | StageGate
PRJ023 | Testing | [5 empty] | StageGate
PRJ023 | Deployment | [5 empty] | StageGate
PRJ023 | Handover | [5 empty] | StageGate
PRJ024 | Discovery | [5 empty] | StageGate
PRJ024 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ024 | Design | [5 empty] | StageGate
PRJ024 | Business Case / Full Funding | [5 empty] | StageGate
PRJ024 | Build | [5 empty] | StageGate
PRJ024 | Testing | [5 empty] | StageGate
PRJ024 | Deployment | [5 empty] | StageGate
PRJ024 | Handover | [5 empty] | StageGate
PRJ025 | Discovery | [5 empty] | StageGate
PRJ025 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ025 | Design | [5 empty] | StageGate
PRJ025 | Business Case / Full Funding | [5 empty] | StageGate
PRJ025 | Build | [5 empty] | StageGate
PRJ025 | Testing | [5 empty] | StageGate
PRJ025 | Deployment | [5 empty] | StageGate
PRJ025 | Handover | [5 empty] | StageGate
PRJ026 | Discovery | [5 empty] | StageGate
PRJ026 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ026 | Design | [5 empty] | StageGate
PRJ026 | Business Case / Full Funding | [5 empty] | StageGate
PRJ026 | Build | [5 empty] | StageGate
PRJ026 | Testing | [5 empty] | StageGate
PRJ026 | Deployment | [5 empty] | StageGate
PRJ026 | Handover | [5 empty] | StageGate
PRJ027 | Discovery | [5 empty] | StageGate
PRJ027 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ027 | Design | [5 empty] | StageGate
PRJ027 | Business Case / Full Funding | [5 empty] | StageGate
PRJ027 | Build | [5 empty] | StageGate
PRJ027 | Testing | [5 empty] | StageGate
PRJ027 | Deployment | [5 empty] | StageGate
PRJ027 | Handover | [5 empty] | StageGate
PRJ028 | Discovery | [5 empty] | StageGate
PRJ028 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ028 | Design | [5 empty] | StageGate
PRJ028 | Business Case / Full Funding | [5 empty] | StageGate
PRJ028 | Build | [5 empty] | StageGate
PRJ028 | Testing | [5 empty] | StageGate
PRJ028 | Deployment | [5 empty] | StageGate
PRJ028 | Handover | [5 empty] | StageGate
PRJ029 | Discovery | [5 empty] | StageGate
PRJ029 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ029 | Design | [5 empty] | StageGate
PRJ029 | Business Case / Full Funding | [5 empty] | StageGate
PRJ029 | Build | [5 empty] | StageGate
PRJ029 | Testing | [5 empty] | StageGate
PRJ029 | Deployment | [5 empty] | StageGate
PRJ029 | Handover | [5 empty] | StageGate
PRJ030 | Discovery | [5 empty] | StageGate
PRJ030 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ030 | Design | [5 empty] | StageGate
PRJ030 | Business Case / Full Funding | [5 empty] | StageGate
PRJ030 | Build | [5 empty] | StageGate
PRJ030 | Testing | [5 empty] | StageGate
PRJ030 | Deployment | [5 empty] | StageGate
PRJ030 | Handover | [5 empty] | StageGate
PRJ031 | Discovery | [5 empty] | StageGate
PRJ031 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ031 | Design | [5 empty] | StageGate
PRJ031 | Business Case / Full Funding | [5 empty] | StageGate
PRJ031 | Build | [5 empty] | StageGate
PRJ031 | Testing | [5 empty] | StageGate
PRJ031 | Deployment | [5 empty] | StageGate
PRJ031 | Handover | [5 empty] | StageGate
PRJ032 | Discovery | [5 empty] | StageGate
PRJ032 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ032 | Design | [5 empty] | StageGate
PRJ032 | Business Case / Full Funding | [5 empty] | StageGate
PRJ032 | Build | [5 empty] | StageGate
PRJ032 | Testing | [5 empty] | StageGate
PRJ032 | Deployment | [5 empty] | StageGate
PRJ032 | Handover | [5 empty] | StageGate
PRJ033 | Discovery | [5 empty] | StageGate
PRJ033 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ033 | Design | [5 empty] | StageGate
PRJ033 | Business Case / Full Funding | [5 empty] | StageGate
PRJ033 | Build | [5 empty] | StageGate
PRJ033 | Testing | [5 empty] | StageGate
PRJ033 | Deployment | [5 empty] | StageGate
PRJ033 | Handover | [5 empty] | StageGate
PRJ034 | Discovery | [5 empty] | StageGate
PRJ034 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ034 | Design | [5 empty] | StageGate
PRJ034 | Business Case / Full Funding | [5 empty] | StageGate
PRJ034 | Build | [5 empty] | StageGate
PRJ034 | Testing | [5 empty] | StageGate
PRJ034 | Deployment | [5 empty] | StageGate
PRJ034 | Handover | [5 empty] | StageGate
PRJ035 | Discovery | [5 empty] | StageGate
PRJ035 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ035 | Design | [5 empty] | StageGate
PRJ035 | Business Case / Full Funding | [5 empty] | StageGate
PRJ035 | Build | [5 empty] | StageGate
PRJ035 | Testing | [5 empty] | StageGate
PRJ035 | Deployment | [5 empty] | StageGate
PRJ035 | Handover | [5 empty] | StageGate
PRJ036 | Discovery | [5 empty] | StageGate
PRJ036 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ036 | Design | [5 empty] | StageGate
PRJ036 | Business Case / Full Funding | [5 empty] | StageGate
PRJ036 | Build | [5 empty] | StageGate
PRJ036 | Testing | [5 empty] | StageGate
PRJ036 | Deployment | [5 empty] | StageGate
PRJ036 | Handover | [5 empty] | StageGate
PRJ037 | Discovery | [5 empty] | StageGate
PRJ037 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ037 | Design | [5 empty] | StageGate
PRJ037 | Business Case / Full Funding | [5 empty] | StageGate
PRJ037 | Build | [5 empty] | StageGate
PRJ037 | Testing | [5 empty] | StageGate
PRJ037 | Deployment | [5 empty] | StageGate
PRJ037 | Handover | [5 empty] | StageGate
PRJ038 | Discovery | [5 empty] | StageGate
PRJ038 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ038 | Design | [5 empty] | StageGate
PRJ038 | Business Case / Full Funding | [5 empty] | StageGate
PRJ038 | Build | [5 empty] | StageGate
PRJ038 | Testing | [5 empty] | StageGate
PRJ038 | Deployment | [5 empty] | StageGate
PRJ038 | Handover | [5 empty] | StageGate
PRJ039 | Discovery | [5 empty] | StageGate
PRJ039 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ039 | Design | [5 empty] | StageGate
PRJ039 | Business Case / Full Funding | [5 empty] | StageGate
PRJ039 | Build | [5 empty] | StageGate
PRJ039 | Testing | [5 empty] | StageGate
PRJ039 | Deployment | [5 empty] | StageGate
PRJ039 | Handover | [5 empty] | StageGate
PRJ040 | Discovery | [5 empty] | StageGate
PRJ040 | Business Case / Seed Funding | [5 empty] | StageGate
PRJ040 | Design | [5 empty] | StageGate
PRJ040 | Business Case / Full Funding | [5 empty] | StageGate
PRJ040 | Build | [5 empty] | StageGate
PRJ040 | Testing | [5 empty] | StageGate
PRJ040 | Deployment | [5 empty] | StageGate
PRJ040 | Handover | [5 empty] | StageGate

## PortfolioMovements
Movement ID | Project ID | Project Name | From Category | To Category | Moved By | Moved On | Reason
MV001 | PRJ009 | ERP Modernisation | CAPEX | IT Strategic | sponsor | 2026-01-06 | Promoted from unfunded to IT strategic
MV002 | PRJ009 | ERP Modernisation | Business Strategic | IT Strategic | admin | 2025-08-06 | Reclassified following strategy review
MV003 | PRJ023 | Workforce Portal | Business Strategic | Unfunded | admin | 2025-07-18 | De-funded; moved to unfunded backlog
MV004 | PRJ028 | Mobile App 2 | Business Strategic | CAPEX | governance | 2025-09-17 | De-funded; moved to unfunded backlog
MV005 | PRJ032 | Compliance Hub | Business Strategic | CAPEX | admin | 2025-12-10 | Reclassified following strategy review
MV006 | PRJ033 | Risk Platform | IT Strategic | Business Strategic | governance | 2026-01-17 | Funding approved — move to CAPEX
MV007 | PRJ017 | App Modernisation | IT Strategic | Unfunded | governance | 2025-08-24 | Promoted from unfunded to IT strategic
MV008 | PRJ007 | CRM Upgrade | IT Strategic | Business Strategic | sponsor | 2025-12-13 | Reclassified following strategy review
MV009 | PRJ015 | Service Desk | Business Strategic | IT Strategic | governance | 2025-07-14 | De-funded; moved to unfunded backlog
MV010 | PRJ013 | API Gateway | IT Strategic | CAPEX | admin | 2025-12-09 | Reclassified following strategy review

## Prioritisation
Project ID | Project Name | Strategic Alignment (1-5) | Benefit Value (1-5) | Risk Reduction (1-5) | Compliance (1-5) | Complexity (1-5) | Score
PRJ027 |  | 4 | 5 | 5 | 3 | 3
PRJ011 |  | 3 | 5 | 5 | 5 | 3
PRJ037 |  | 4 | 3 | 5 | 5 | 2
PRJ034 |  | 4 | 5 | 3 | 3 | 1
PRJ024 |  | 4 | 5 | 4 | 4 | 5
PRJ039 |  | 5 | 4 | 2 | 4 | 2
PRJ003 |  | 4 | 1 | 5 | 4 | 1
PRJ016 |  | 3 | 4 | 2 | 5 | 2
PRJ040 |  | 4 | 3 | 2 | 4 | 1
PRJ036 |  | 3 | 1 | 5 | 5 | 1
PRJ018 |  | 3 | 5 | 3 | 3 | 4
PRJ020 |  | 5 | 5 | 1 | 2 | 5
PRJ005 |  | 3 | 4 | 2 | 3 | 1
PRJ026 |  | 5 | 2 | 5 | 1 | 5
PRJ028 |  | 2 | 3 | 3 | 5 | 1
PRJ038 |  | 4 | 2 | 3 | 3 | 2
PRJ033 |  | 3 | 1 | 5 | 3 | 2
PRJ009 |  | 3 | 3 | 3 | 1 | 1
PRJ023 |  | 5 | 1 | 2 | 4 | 5
PRJ010 |  | 1 | 5 | 2 | 3 | 3
PRJ012 |  | 2 | 3 | 2 | 5 | 4
PRJ007 |  | 2 | 3 | 4 | 3 | 5
PRJ015 |  | 1 | 1 | 5 | 5 | 3
PRJ004 |  | 3 | 1 | 3 | 3 | 3
PRJ029 |  | 2 | 2 | 1 | 5 | 2
PRJ014 |  | 1 | 5 | 2 | 2 | 4
PRJ002 |  | 3 | 2 | 2 | 3 | 4
PRJ030 |  | 3 | 1 | 2 | 3 | 2
PRJ008 |  | 1 | 4 | 2 | 3 | 4
PRJ025 |  | 3 | 2 | 2 | 1 | 2
PRJ022 |  | 1 | 2 | 4 | 4 | 5
PRJ035 |  | 1 | 3 | 2 | 3 | 2
PRJ019 |  | 1 | 4 | 1 | 4 | 4
PRJ021 |  | 3 | 2 | 3 | 1 | 5
PRJ032 |  | 1 | 1 | 3 | 5 | 3
PRJ013 |  | 1 | 1 | 2 | 5 | 1
PRJ001 |  | 1 | 1 | 4 | 4 | 5
PRJ031 |  | 3 | 1 | 2 | 2 | 5
PRJ017 |  | 1 | 2 | 2 | 4 | 5
PRJ006 |  | 2 | 1 | 1 | 1 | 3

## Config
Category | Value | Display Order | Active
Status | Active | 1
Status | Active | 2
Status | Active | 3
Status | Completed | 4
Status | Pipeline | 5
Status | On Hold | 6
Status | Cancelled | 7
RAG | Green | 1
RAG | Amber | 2
RAG | Red | 3
Priority | P1 - Critical | 1
Priority | P2 - High | 2
Priority | P3 - Medium | 3
Priority | P4 - Low | 4
Investment Type | Run | 1
Investment Type | Grow | 2
Investment Type | Transform | 3
Delivery Method | Waterfall | 1
Delivery Method | Agile | 2
Delivery Method | Hybrid | 3
Funding Type | CAPEX | 1
Funding Type | OPEX | 2
Funding Type | Mixed | 3
Funding Type | Unfunded | 4
Portfolio Category | Business Strategic | 1
Portfolio Category | IT Strategic | 2
Portfolio Category | CAPEX | 3
Portfolio Category | Unfunded | 4
Governance Channel | Channel A (<$200K) | 1
Governance Channel | Channel B (>$200K) | 2
Program | Digital Transformation | 1
Program | Cyber Security | 2
Program | Cloud Migration | 3
Program | Data & AI | 4
Program | Customer Experience | 5
Theme | Infrastructure | 1
Theme | Digital & Applications | 2
Theme | Data & Analytics | 3
Theme | Cyber Security | 4
Theme | Business Transformation | 5
Business Unit | Retail | 1
Business Unit | Wholesale | 2
Business Unit | Operations | 3
Business Unit | Technology | 4
Business Unit | Finance | 5
Business Unit | HR | 6
Business Unit | Marketing | 7
Sponsor | CIO | 1
Sponsor | CFO | 2
Sponsor | COO | 3
Sponsor | CMO | 4
Sponsor | CTO | 5
Financial Year | FY25 | 1
Financial Year | FY25-26 | 2
Financial Year | FY26 | 3
Financial Year | FY26-27 | 4
Financial Year | FY27 | 5
Financial Year | FY27-28 | 6
Financial Year | FY28 | 7
Financial Year | FY28-29 | 8
Financial Year | FY29 | 9
Financial Year | FY29-30 | 10
Financial Year | FY30 | 11
Stage (Channel A) | Discovery | 1
Stage (Channel A) | Business Case / Full Funding | 2
Stage (Channel A) | Design | 3
Stage (Channel A) | Build | 4
Stage (Channel A) | Testing | 5
Stage (Channel A) | Deployment | 6
Stage (Channel A) | Handover | 7
Stage (Channel B) | Discovery | 1
Stage (Channel B) | Business Case / Seed Funding | 2
Stage (Channel B) | Design | 3
Stage (Channel B) | Business Case / Full Funding | 4
Stage (Channel B) | Build | 5
Stage (Channel B) | Testing | 6
Stage (Channel B) | Deployment | 7
Stage (Channel B) | Handover | 8
Gate Status | Not Started | 1
Gate Status | In Progress | 2
Gate Status | Pending Approval | 3
Gate Status | Approved | 4
Gate Status | Rejected | 5
Gate Status | Complete | 6
Gate Status | On Hold | 7
Gate Outcome |  | 1
Gate Outcome | Proceed | 2
Gate Outcome | Conditional | 3
Gate Outcome | Rework | 4
Gate Outcome | Held | 5
Decision Status | Open | 1
Decision Status | In Review | 2
Decision Status | Approved | 3
Decision Status | Rejected | 4
Decision Status | Closed | 5
Decision Type | Project | 1
Decision Type | Program | 2
Decision Type | Portfolio | 3
Decision Type | Funding | 4
Decision Type | SteerCo | 5
Decision Type | Architecture | 6
Decision Type | Risk | 7
Decision Type | General | 8
Action Status | Open | 1
Action Status | In Progress | 2
Action Status | Complete | 3
Action Status | Overdue | 4
Risk Probability | Low | 1
Risk Probability | Medium | 2
Risk Probability | High | 3
Risk Impact | Low | 1
Risk Impact | Medium | 2
Risk Impact | High | 3
Risk Impact | Critical | 4
Risk Status | Open | 1
Risk Status | Mitigated | 2
Risk Status | Closed | 3
RAID Type | Risk | 1
RAID Type | Issue | 2
RAID Type | Assumption | 3
RAID Type | Dependency | 4
Benefit Status | Planned | 1
Benefit Status | In Progress | 2
Benefit Status | Realised | 3
Benefit Status | At Risk | 4
Benefit Category | Cost Savings | 1
Benefit Category | Revenue Uplift | 2
Benefit Category | Productivity | 3
Benefit Category | Risk Avoidance | 4
Benefit Category | Compliance | 5
Benefit Type | Recurring | 1
Benefit Type | One-Off | 2
Dependency Type | Finish-Start | 1
Dependency Type | Start-Start | 2
Dependency Type | Blocks | 3
Dependency Type | Shared Resource | 4
Dependency Status | Healthy | 1
Dependency Status | At Risk | 2
Dependency Status | Blocked | 3
Skill | PM | 1
Skill | BA | 2
Skill | Dev | 3
Skill | QA | 4
Skill | DevOps | 5
Skill | Data | 6
Skill | Security | 7
Skill | UX | 8
Skill | Architect | 9
Resource Role | Project Manager | 1
Resource Role | Developer | 2
Resource Role | Tester | 3
Resource Role | Analyst | 4
Resource Role | Architect | 5
Milestone | Discovery | 1
Milestone | Business Case / Seed Funding | 2
Milestone | Design | 3
Milestone | Business Case / Full Funding | 4
Milestone | Build | 5
Milestone | Testing | 6
Milestone | Deployment | 7
Milestone | Handover | 8
Pipeline Decision | New | 1
Pipeline Decision | Under Review | 2
Pipeline Decision | Approved | 3
Pipeline Decision | Rejected | 4
Pipeline Decision | Parked | 5

## ConfigRules
Key | Value | Type | Description
GOV_CHANNEL_THRESHOLD | 200000 | currency | Approved $ at/below which a project is Channel A
SCHEDULE_AMBER_VARIANCE | -0.05 | ratio | Schedule variance worse than this → Amber
SCHEDULE_RED_VARIANCE | -0.1 | ratio | Schedule variance worse than this → Red
FINANCIAL_AMBER_VARIANCE | 0.05 | ratio | (Forecast-Approved)/Approved above → Amber
FINANCIAL_RED_VARIANCE | 0.1 | ratio | (Forecast-Approved)/Approved above → Red
BENEFIT_GREEN_THRESHOLD | 0.7 | ratio | Benefit realisation ≥ → Green
BENEFIT_AMBER_THRESHOLD | 0.3 | ratio | Benefit realisation ≥ → Amber (else Red)
DELIVERY_AMBER_DAYS_LATE | 1 | int | Stage gate days late ≥ → Amber
DELIVERY_RED_DAYS_LATE | 15 | int | Stage gate days late ≥ → Red
UPCOMING_GATE_WINDOW_DAYS | 30 | int | Window for 'upcoming stage gates' KPI
PRIORITY_SCORE_WEIGHT_STRAT | 0.3 | ratio | Prioritisation: strategic weight
PRIORITY_SCORE_WEIGHT_BENEFIT | 0.25 | ratio | Prioritisation: benefit weight
PRIORITY_SCORE_WEIGHT_RISK | 0.2 | ratio | Prioritisation: risk-reduction weight
PRIORITY_SCORE_WEIGHT_COMPL | 0.15 | ratio | Prioritisation: compliance weight
PRIORITY_SCORE_WEIGHT_CPLX | 0.1 | ratio | Prioritisation: complexity penalty
CURRENCY_SYMBOL | $ | text | Symbol shown in KPI cards

## Sprints
Sprint ID | Project ID | Project Name | Sprint # | Sprint Name | Start Date | End Date | Points Committed | Points Completed | Stories Committed | Stories Completed | Status | Team
SP0001 | PRJ001 |  | 1 | PRJ001 Sprint 1 |  |  | 37 | 39 | 7 | 7 | Complete | Alex Brown
SP0002 | PRJ001 |  | 2 | PRJ001 Sprint 2 |  |  | 37 | 30 | 7 | 6 | Complete | Alex Brown
SP0003 | PRJ001 |  | 3 | PRJ001 Sprint 3 |  |  | 38 | 41 | 7 | 8 | Complete | Alex Brown
SP0004 | PRJ001 |  | 4 | PRJ001 Sprint 4 |  |  | 37 | 34 | 7 | 6 | Complete | Alex Brown
SP0005 | PRJ001 |  | 5 | PRJ001 Sprint 5 |  |  | 32 | 29 | 6 | 5 | Complete | Alex Brown
SP0006 | PRJ001 |  | 6 | PRJ001 Sprint 6 |  |  | 37 | 30 | 7 | 6 | Complete | Alex Brown
SP0007 | PRJ001 |  | 7 | PRJ001 Sprint 7 |  |  | 44 | 38 | 8 | 7 | Complete | Alex Brown
SP0008 | PRJ001 |  | 8 | PRJ001 Sprint 8 |  |  | 34 | 26 | 6 | 5 | Complete | Alex Brown
SP0009 | PRJ002 |  | 1 | PRJ002 Sprint 1 |  |  | 32 | 27 | 6 | 5 | Complete | Carlos Diaz
SP0010 | PRJ002 |  | 2 | PRJ002 Sprint 2 |  |  | 33 | 33 | 6 | 6 | Complete | Carlos Diaz
SP0011 | PRJ002 |  | 3 | PRJ002 Sprint 3 |  |  | 22 | 26 | 4 | 5 | Complete | Carlos Diaz
SP0012 | PRJ002 |  | 4 | PRJ002 Sprint 4 |  |  | 23 | 11 | 4 | 2 | Complete | Carlos Diaz
SP0013 | PRJ002 |  | 5 | PRJ002 Sprint 5 |  |  | 22 | 22 | 4 | 4 | Complete | Carlos Diaz
SP0014 | PRJ002 |  | 6 | PRJ002 Sprint 6 |  |  | 31 | 19 | 6 | 3 | Complete | Carlos Diaz
SP0015 | PRJ002 |  | 7 | PRJ002 Sprint 7 |  |  | 22 | 10 | 4 | 2 | Complete | Carlos Diaz
SP0016 | PRJ002 |  | 8 | PRJ002 Sprint 8 |  |  | 20 | 12 | 4 | 2 | Complete | Carlos Diaz
SP0017 | PRJ003 |  | 1 | PRJ003 Sprint 1 |  |  | 26 | 22 | 5 | 4 | Complete | Carlos Diaz
SP0018 | PRJ003 |  | 2 | PRJ003 Sprint 2 |  |  | 28 | 16 | 5 | 3 | Complete | Carlos Diaz
SP0019 | PRJ003 |  | 3 | PRJ003 Sprint 3 |  |  | 24 | 15 | 4 | 3 | Complete | Carlos Diaz
SP0020 | PRJ003 |  | 4 | PRJ003 Sprint 4 |  |  | 41 | 39 | 8 | 7 | Complete | Carlos Diaz
SP0021 | PRJ003 |  | 5 | PRJ003 Sprint 5 |  |  | 26 | 20 | 5 | 4 | Complete | Carlos Diaz
SP0022 | PRJ003 |  | 6 | PRJ003 Sprint 6 |  |  | 28 | 31 | 5 | 6 | Complete | Carlos Diaz
SP0023 | PRJ003 |  | 7 | PRJ003 Sprint 7 |  |  | 42 | 44 | 8 | 8 | Complete | Carlos Diaz
SP0024 | PRJ003 |  | 8 | PRJ003 Sprint 8 |  |  | 29 | 26 | 5 | 5 | Complete | Carlos Diaz
SP0025 | PRJ005 |  | 1 | PRJ005 Sprint 1 |  |  | 42 | 34 | 8 | 6 | Complete | Priya Patel
SP0026 | PRJ005 |  | 2 | PRJ005 Sprint 2 |  |  | 34 | 23 | 6 | 4 | Complete | Priya Patel
SP0027 | PRJ005 |  | 3 | PRJ005 Sprint 3 |  |  | 44 | 40 | 8 | 8 | Complete | Priya Patel
SP0028 | PRJ005 |  | 4 | PRJ005 Sprint 4 |  |  | 44 | 35 | 8 | 7 | Complete | Priya Patel
SP0029 | PRJ005 |  | 5 | PRJ005 Sprint 5 |  |  | 27 | 16 | 5 | 3 | Complete | Priya Patel
SP0030 | PRJ005 |  | 6 | PRJ005 Sprint 6 |  |  | 30 | 35 | 6 | 7 | Complete | Priya Patel
SP0031 | PRJ005 |  | 7 | PRJ005 Sprint 7 |  |  | 36 | 27 | 7 | 5 | Complete | Priya Patel
SP0032 | PRJ005 |  | 8 | PRJ005 Sprint 8 |  |  | 43 | 44 | 8 | 8 | Complete | Priya Patel
SP0033 | PRJ008 |  | 1 | PRJ008 Sprint 1 |  |  | 21 | 16 | 4 | 3 | Complete | Carlos Diaz
SP0034 | PRJ008 |  | 2 | PRJ008 Sprint 2 |  |  | 21 | 16 | 4 | 3 | Complete | Carlos Diaz
SP0035 | PRJ008 |  | 3 | PRJ008 Sprint 3 |  |  | 34 | 34 | 6 | 6 | Complete | Carlos Diaz
SP0036 | PRJ008 |  | 4 | PRJ008 Sprint 4 |  |  | 25 | 24 | 5 | 4 | Complete | Carlos Diaz
SP0037 | PRJ008 |  | 5 | PRJ008 Sprint 5 |  |  | 30 | 25 | 6 | 5 | Complete | Carlos Diaz
SP0038 | PRJ008 |  | 6 | PRJ008 Sprint 6 |  |  | 33 | 24 | 6 | 4 | Complete | Carlos Diaz
SP0039 | PRJ008 |  | 7 | PRJ008 Sprint 7 |  |  | 36 | 29 | 7 | 5 | Complete | Carlos Diaz
SP0040 | PRJ008 |  | 8 | PRJ008 Sprint 8 |  |  | 24 | 19 | 4 | 3 | Complete | Carlos Diaz
SP0041 | PRJ009 |  | 1 | PRJ009 Sprint 1 |  |  | 29 | 28 | 5 | 5 | Complete | Jane Doe
SP0042 | PRJ009 |  | 2 | PRJ009 Sprint 2 |  |  | 22 | 20 | 4 | 4 | Complete | Jane Doe
SP0043 | PRJ009 |  | 3 | PRJ009 Sprint 3 |  |  | 23 | 22 | 4 | 4 | Complete | Jane Doe
SP0044 | PRJ009 |  | 4 | PRJ009 Sprint 4 |  |  | 22 | 11 | 4 | 2 | Complete | Jane Doe
SP0045 | PRJ009 |  | 5 | PRJ009 Sprint 5 |  |  | 24 | 17 | 4 | 3 | Complete | Jane Doe
SP0046 | PRJ009 |  | 6 | PRJ009 Sprint 6 |  |  | 33 | 37 | 6 | 7 | Complete | Jane Doe
SP0047 | PRJ009 |  | 7 | PRJ009 Sprint 7 |  |  | 30 | 23 | 6 | 4 | Complete | Jane Doe
SP0048 | PRJ009 |  | 8 | PRJ009 Sprint 8 |  |  | 33 | 25 | 6 | 5 | Complete | Jane Doe
SP0049 | PRJ010 |  | 1 | PRJ010 Sprint 1 |  |  | 54 | 51 | 10 | 10 | Complete | Priya Patel
SP0050 | PRJ010 |  | 2 | PRJ010 Sprint 2 |  |  | 56 | 47 | 11 | 9 | Complete | Priya Patel
SP0051 | PRJ010 |  | 3 | PRJ010 Sprint 3 |  |  | 53 | 56 | 10 | 11 | Complete | Priya Patel
SP0052 | PRJ010 |  | 4 | PRJ010 Sprint 4 |  |  | 56 | 52 | 11 | 10 | Complete | Priya Patel
SP0053 | PRJ010 |  | 5 | PRJ010 Sprint 5 |  |  | 47 | 35 | 9 | 7 | Complete | Priya Patel
SP0054 | PRJ010 |  | 6 | PRJ010 Sprint 6 |  |  | 49 | 41 | 9 | 8 | Complete | Priya Patel
SP0055 | PRJ010 |  | 7 | PRJ010 Sprint 7 |  |  | 55 | 47 | 11 | 9 | Complete | Priya Patel
SP0056 | PRJ010 |  | 8 | PRJ010 Sprint 8 |  |  | 57 | 59 | 11 | 11 | Complete | Priya Patel
SP0057 | PRJ011 |  | 1 | PRJ011 Sprint 1 |  |  | 55 | 45 | 11 | 9 | Complete | Jane Doe
SP0058 | PRJ011 |  | 2 | PRJ011 Sprint 2 |  |  | 43 | 44 | 8 | 8 | Complete | Jane Doe
SP0059 | PRJ011 |  | 3 | PRJ011 Sprint 3 |  |  | 48 | 40 | 9 | 8 | Complete | Jane Doe
SP0060 | PRJ011 |  | 4 | PRJ011 Sprint 4 |  |  | 42 | 40 | 8 | 8 | Complete | Jane Doe
SP0061 | PRJ011 |  | 5 | PRJ011 Sprint 5 |  |  | 44 | 37 | 8 | 7 | Complete | Jane Doe
SP0062 | PRJ011 |  | 6 | PRJ011 Sprint 6 |  |  | 52 | 51 | 10 | 10 | Complete | Jane Doe
SP0063 | PRJ011 |  | 7 | PRJ011 Sprint 7 |  |  | 50 | 53 | 10 | 10 | Complete | Jane Doe
SP0064 | PRJ011 |  | 8 | PRJ011 Sprint 8 |  |  | 53 | 56 | 10 | 11 | Complete | Jane Doe
SP0065 | PRJ013 |  | 1 | PRJ013 Sprint 1 |  |  | 52 | 50 | 10 | 10 | Complete | Priya Patel
SP0066 | PRJ013 |  | 2 | PRJ013 Sprint 2 |  |  | 43 | 38 | 8 | 7 | Complete | Priya Patel
SP0067 | PRJ013 |  | 3 | PRJ013 Sprint 3 |  |  | 51 | 52 | 10 | 10 | Complete | Priya Patel
SP0068 | PRJ013 |  | 4 | PRJ013 Sprint 4 |  |  | 56 | 59 | 11 | 11 | Complete | Priya Patel
SP0069 | PRJ013 |  | 5 | PRJ013 Sprint 5 |  |  | 56 | 61 | 11 | 12 | Complete | Priya Patel
SP0070 | PRJ013 |  | 6 | PRJ013 Sprint 6 |  |  | 54 | 59 | 10 | 11 | Complete | Priya Patel
SP0071 | PRJ013 |  | 7 | PRJ013 Sprint 7 |  |  | 56 | 51 | 11 | 10 | Complete | Priya Patel
SP0072 | PRJ013 |  | 8 | PRJ013 Sprint 8 |  |  | 51 | 41 | 10 | 8 | Complete | Priya Patel
SP0073 | PRJ014 |  | 1 | PRJ014 Sprint 1 |  |  | 48 | 52 | 9 | 10 | Complete | Alex Brown
SP0074 | PRJ014 |  | 2 | PRJ014 Sprint 2 |  |  | 53 | 48 | 10 | 9 | Complete | Alex Brown
SP0075 | PRJ014 |  | 3 | PRJ014 Sprint 3 |  |  | 37 | 32 | 7 | 6 | Complete | Alex Brown
SP0076 | PRJ014 |  | 4 | PRJ014 Sprint 4 |  |  | 46 | 34 | 9 | 6 | Complete | Alex Brown
SP0077 | PRJ014 |  | 5 | PRJ014 Sprint 5 |  |  | 41 | 29 | 8 | 5 | Complete | Alex Brown
SP0078 | PRJ014 |  | 6 | PRJ014 Sprint 6 |  |  | 46 | 51 | 9 | 10 | Complete | Alex Brown
SP0079 | PRJ014 |  | 7 | PRJ014 Sprint 7 |  |  | 50 | 42 | 10 | 8 | Complete | Alex Brown
SP0080 | PRJ014 |  | 8 | PRJ014 Sprint 8 |  |  | 38 | 27 | 7 | 5 | Complete | Alex Brown
SP0081 | PRJ015 |  | 1 | PRJ015 Sprint 1 |  |  | 57 | 56 | 11 | 11 | Complete | John Smith
SP0082 | PRJ015 |  | 2 | PRJ015 Sprint 2 |  |  | 50 | 47 | 10 | 9 | Complete | John Smith
SP0083 | PRJ015 |  | 3 | PRJ015 Sprint 3 |  |  | 60 | 52 | 12 | 10 | Complete | John Smith
SP0084 | PRJ015 |  | 4 | PRJ015 Sprint 4 |  |  | 63 | 64 | 12 | 12 | Complete | John Smith
SP0085 | PRJ015 |  | 5 | PRJ015 Sprint 5 |  |  | 53 | 47 | 10 | 9 | Complete | John Smith
SP0086 | PRJ015 |  | 6 | PRJ015 Sprint 6 |  |  | 53 | 42 | 10 | 8 | Complete | John Smith
SP0087 | PRJ015 |  | 7 | PRJ015 Sprint 7 |  |  | 50 | 41 | 10 | 8 | Complete | John Smith
SP0088 | PRJ015 |  | 8 | PRJ015 Sprint 8 |  |  | 50 | 50 | 10 | 10 | Complete | John Smith
SP0089 | PRJ016 |  | 1 | PRJ016 Sprint 1 |  |  | 40 | 41 | 8 | 8 | Complete | John Smith
SP0090 | PRJ016 |  | 2 | PRJ016 Sprint 2 |  |  | 51 | 40 | 10 | 8 | Complete | John Smith
SP0091 | PRJ016 |  | 3 | PRJ016 Sprint 3 |  |  | 43 | 33 | 8 | 6 | Complete | John Smith
SP0092 | PRJ016 |  | 4 | PRJ016 Sprint 4 |  |  | 55 | 48 | 11 | 9 | Complete | John Smith
SP0093 | PRJ016 |  | 5 | PRJ016 Sprint 5 |  |  | 40 | 32 | 8 | 6 | Complete | John Smith
SP0094 | PRJ016 |  | 6 | PRJ016 Sprint 6 |  |  | 51 | 43 | 10 | 8 | Complete | John Smith
SP0095 | PRJ016 |  | 7 | PRJ016 Sprint 7 |  |  | 42 | 37 | 8 | 7 | Complete | John Smith
SP0096 | PRJ016 |  | 8 | PRJ016 Sprint 8 |  |  | 42 | 30 | 8 | 6 | Complete | John Smith
SP0097 | PRJ017 |  | 1 | PRJ017 Sprint 1 |  |  | 48 | 40 | 9 | 8 | Complete | Priya Patel
SP0098 | PRJ017 |  | 2 | PRJ017 Sprint 2 |  |  | 40 | 43 | 8 | 8 | Complete | Priya Patel
SP0099 | PRJ017 |  | 3 | PRJ017 Sprint 3 |  |  | 39 | 43 | 7 | 8 | Complete | Priya Patel
SP0100 | PRJ017 |  | 4 | PRJ017 Sprint 4 |  |  | 44 | 47 | 8 | 9 | Complete | Priya Patel
SP0101 | PRJ017 |  | 5 | PRJ017 Sprint 5 |  |  | 48 | 46 | 9 | 9 | Complete | Priya Patel
SP0102 | PRJ017 |  | 6 | PRJ017 Sprint 6 |  |  | 49 | 37 | 9 | 7 | Complete | Priya Patel
SP0103 | PRJ017 |  | 7 | PRJ017 Sprint 7 |  |  | 44 | 35 | 8 | 7 | Complete | Priya Patel
SP0104 | PRJ017 |  | 8 | PRJ017 Sprint 8 |  |  | 39 | 28 | 7 | 5 | Complete | Priya Patel
SP0105 | PRJ020 |  | 1 | PRJ020 Sprint 1 |  |  | 46 | 39 | 9 | 7 | Complete | Carlos Diaz
SP0106 | PRJ020 |  | 2 | PRJ020 Sprint 2 |  |  | 61 | 54 | 12 | 10 | Complete | Carlos Diaz
SP0107 | PRJ020 |  | 3 | PRJ020 Sprint 3 |  |  | 45 | 45 | 9 | 9 | Complete | Carlos Diaz
SP0108 | PRJ020 |  | 4 | PRJ020 Sprint 4 |  |  | 58 | 60 | 11 | 12 | Complete | Carlos Diaz
SP0109 | PRJ020 |  | 5 | PRJ020 Sprint 5 |  |  | 62 | 58 | 12 | 11 | Complete | Carlos Diaz
SP0110 | PRJ020 |  | 6 | PRJ020 Sprint 6 |  |  | 63 | 67 | 12 | 13 | Complete | Carlos Diaz
SP0111 | PRJ020 |  | 7 | PRJ020 Sprint 7 |  |  | 54 | 49 | 10 | 9 | Complete | Carlos Diaz
SP0112 | PRJ020 |  | 8 | PRJ020 Sprint 8 |  |  | 58 | 51 | 11 | 10 | Complete | Carlos Diaz
SP0113 | PRJ022 |  | 1 | PRJ022 Sprint 1 |  |  | 27 | 31 | 5 | 6 | Complete | Priya Patel
SP0114 | PRJ022 |  | 2 | PRJ022 Sprint 2 |  |  | 37 | 29 | 7 | 5 | Complete | Priya Patel
SP0115 | PRJ022 |  | 3 | PRJ022 Sprint 3 |  |  | 31 | 31 | 6 | 6 | Complete | Priya Patel
SP0116 | PRJ022 |  | 4 | PRJ022 Sprint 4 |  |  | 26 | 21 | 5 | 4 | Complete | Priya Patel
SP0117 | PRJ022 |  | 5 | PRJ022 Sprint 5 |  |  | 37 | 30 | 7 | 6 | Complete | Priya Patel
SP0118 | PRJ022 |  | 6 | PRJ022 Sprint 6 |  |  | 42 | 32 | 8 | 6 | Complete | Priya Patel
SP0119 | PRJ022 |  | 7 | PRJ022 Sprint 7 |  |  | 39 | 42 | 7 | 8 | Complete | Priya Patel
SP0120 | PRJ022 |  | 8 | PRJ022 Sprint 8 |  |  | 35 | 35 | 7 | 7 | Complete | Priya Patel
SP0121 | PRJ023 |  | 1 | PRJ023 Sprint 1 |  |  | 55 | 48 | 11 | 9 | Complete | Jane Doe
SP0122 | PRJ023 |  | 2 | PRJ023 Sprint 2 |  |  | 44 | 43 | 8 | 8 | Complete | Jane Doe
SP0123 | PRJ023 |  | 3 | PRJ023 Sprint 3 |  |  | 56 | 50 | 11 | 10 | Complete | Jane Doe
SP0124 | PRJ023 |  | 4 | PRJ023 Sprint 4 |  |  | 51 | 42 | 10 | 8 | Complete | Jane Doe
SP0125 | PRJ023 |  | 5 | PRJ023 Sprint 5 |  |  | 46 | 36 | 9 | 7 | Complete | Jane Doe
SP0126 | PRJ023 |  | 6 | PRJ023 Sprint 6 |  |  | 54 | 52 | 10 | 10 | Complete | Jane Doe
SP0127 | PRJ023 |  | 7 | PRJ023 Sprint 7 |  |  | 43 | 38 | 8 | 7 | Complete | Jane Doe
SP0128 | PRJ023 |  | 8 | PRJ023 Sprint 8 |  |  | 52 | 45 | 10 | 9 | Complete | Jane Doe
SP0129 | PRJ024 |  | 1 | PRJ024 Sprint 1 |  |  | 37 | 27 | 7 | 5 | Complete | Jane Doe
SP0130 | PRJ024 |  | 2 | PRJ024 Sprint 2 |  |  | 40 | 28 | 8 | 5 | Complete | Jane Doe
SP0131 | PRJ024 |  | 3 | PRJ024 Sprint 3 |  |  | 43 | 37 | 8 | 7 | Complete | Jane Doe
SP0132 | PRJ024 |  | 4 | PRJ024 Sprint 4 |  |  | 51 | 45 | 10 | 9 | Complete | Jane Doe
SP0133 | PRJ024 |  | 5 | PRJ024 Sprint 5 |  |  | 35 | 30 | 7 | 6 | Complete | Jane Doe
SP0134 | PRJ024 |  | 6 | PRJ024 Sprint 6 |  |  | 42 | 32 | 8 | 6 | Complete | Jane Doe
SP0135 | PRJ024 |  | 7 | PRJ024 Sprint 7 |  |  | 52 | 41 | 10 | 8 | Complete | Jane Doe
SP0136 | PRJ024 |  | 8 | PRJ024 Sprint 8 |  |  | 52 | 55 | 10 | 11 | Complete | Jane Doe
SP0137 | PRJ025 |  | 1 | PRJ025 Sprint 1 |  |  | 19 | 17 | 3 | 3 | Complete | Sarah Lee
SP0138 | PRJ025 |  | 2 | PRJ025 Sprint 2 |  |  | 20 | 17 | 4 | 3 | Complete | Sarah Lee
SP0139 | PRJ025 |  | 3 | PRJ025 Sprint 3 |  |  | 18 | 17 | 3 | 3 | Complete | Sarah Lee
SP0140 | PRJ025 |  | 4 | PRJ025 Sprint 4 |  |  | 27 | 27 | 5 | 5 | Complete | Sarah Lee
SP0141 | PRJ025 |  | 5 | PRJ025 Sprint 5 |  |  | 34 | 28 | 6 | 5 | Complete | Sarah Lee
SP0142 | PRJ025 |  | 6 | PRJ025 Sprint 6 |  |  | 28 | 28 | 5 | 5 | Complete | Sarah Lee
SP0143 | PRJ025 |  | 7 | PRJ025 Sprint 7 |  |  | 29 | 21 | 5 | 4 | Complete | Sarah Lee
SP0144 | PRJ025 |  | 8 | PRJ025 Sprint 8 |  |  | 21 | 19 | 4 | 3 | Complete | Sarah Lee
SP0145 | PRJ026 |  | 1 | PRJ026 Sprint 1 |  |  | 46 | 37 | 9 | 7 | Complete | Carlos Diaz
SP0146 | PRJ026 |  | 2 | PRJ026 Sprint 2 |  |  | 46 | 38 | 9 | 7 | Complete | Carlos Diaz
SP0147 | PRJ026 |  | 3 | PRJ026 Sprint 3 |  |  | 30 | 30 | 6 | 6 | Complete | Carlos Diaz
SP0148 | PRJ026 |  | 4 | PRJ026 Sprint 4 |  |  | 45 | 34 | 9 | 6 | Complete | Carlos Diaz
SP0149 | PRJ026 |  | 5 | PRJ026 Sprint 5 |  |  | 39 | 32 | 7 | 6 | Complete | Carlos Diaz
SP0150 | PRJ026 |  | 6 | PRJ026 Sprint 6 |  |  | 34 | 36 | 6 | 7 | Complete | Carlos Diaz
SP0151 | PRJ026 |  | 7 | PRJ026 Sprint 7 |  |  | 32 | 22 | 6 | 4 | Complete | Carlos Diaz
SP0152 | PRJ026 |  | 8 | PRJ026 Sprint 8 |  |  | 37 | 31 | 7 | 6 | Complete | Carlos Diaz
SP0153 | PRJ029 |  | 1 | PRJ029 Sprint 1 |  |  | 46 | 39 | 9 | 7 | Complete | John Smith
SP0154 | PRJ029 |  | 2 | PRJ029 Sprint 2 |  |  | 58 | 62 | 11 | 12 | Complete | John Smith
SP0155 | PRJ029 |  | 3 | PRJ029 Sprint 3 |  |  | 58 | 56 | 11 | 11 | Complete | John Smith
SP0156 | PRJ029 |  | 4 | PRJ029 Sprint 4 |  |  | 56 | 48 | 11 | 9 | Complete | John Smith
SP0157 | PRJ029 |  | 5 | PRJ029 Sprint 5 |  |  | 52 | 49 | 10 | 9 | Complete | John Smith
SP0158 | PRJ029 |  | 6 | PRJ029 Sprint 6 |  |  | 53 | 54 | 10 | 10 | Complete | John Smith
SP0159 | PRJ029 |  | 7 | PRJ029 Sprint 7 |  |  | 43 | 43 | 8 | 8 | Complete | John Smith
SP0160 | PRJ029 |  | 8 | PRJ029 Sprint 8 |  |  | 49 | 43 | 9 | 8 | Complete | John Smith
SP0161 | PRJ032 |  | 1 | PRJ032 Sprint 1 |  |  | 38 | 30 | 7 | 6 | Complete | Carlos Diaz
SP0162 | PRJ032 |  | 2 | PRJ032 Sprint 2 |  |  | 54 | 57 | 10 | 11 | Complete | Carlos Diaz
SP0163 | PRJ032 |  | 3 | PRJ032 Sprint 3 |  |  | 39 | 27 | 7 | 5 | Complete | Carlos Diaz
SP0164 | PRJ032 |  | 4 | PRJ032 Sprint 4 |  |  | 40 | 37 | 8 | 7 | Complete | Carlos Diaz
SP0165 | PRJ032 |  | 5 | PRJ032 Sprint 5 |  |  | 53 | 43 | 10 | 8 | Complete | Carlos Diaz
SP0166 | PRJ032 |  | 6 | PRJ032 Sprint 6 |  |  | 51 | 42 | 10 | 8 | Complete | Carlos Diaz
SP0167 | PRJ032 |  | 7 | PRJ032 Sprint 7 |  |  | 50 | 48 | 10 | 9 | Complete | Carlos Diaz
SP0168 | PRJ032 |  | 8 | PRJ032 Sprint 8 |  |  | 41 | 38 | 8 | 7 | Complete | Carlos Diaz
SP0169 | PRJ033 |  | 1 | PRJ033 Sprint 1 |  |  | 24 | 20 | 4 | 4 | Complete | Priya Patel
SP0170 | PRJ033 |  | 2 | PRJ033 Sprint 2 |  |  | 40 | 39 | 8 | 7 | Complete | Priya Patel
SP0171 | PRJ033 |  | 3 | PRJ033 Sprint 3 |  |  | 33 | 23 | 6 | 4 | Complete | Priya Patel
SP0172 | PRJ033 |  | 4 | PRJ033 Sprint 4 |  |  | 24 | 17 | 4 | 3 | Complete | Priya Patel
SP0173 | PRJ033 |  | 5 | PRJ033 Sprint 5 |  |  | 36 | 32 | 7 | 6 | Complete | Priya Patel
SP0174 | PRJ033 |  | 6 | PRJ033 Sprint 6 |  |  | 37 | 33 | 7 | 6 | Complete | Priya Patel
SP0175 | PRJ033 |  | 7 | PRJ033 Sprint 7 |  |  | 36 | 28 | 7 | 5 | Complete | Priya Patel
SP0176 | PRJ033 |  | 8 | PRJ033 Sprint 8 |  |  | 25 | 28 | 5 | 5 | Complete | Priya Patel
SP0177 | PRJ034 |  | 1 | PRJ034 Sprint 1 |  |  | 29 | 26 | 5 | 5 | Complete | Jane Doe
SP0178 | PRJ034 |  | 2 | PRJ034 Sprint 2 |  |  | 30 | 31 | 6 | 6 | Complete | Jane Doe
SP0179 | PRJ034 |  | 3 | PRJ034 Sprint 3 |  |  | 22 | 24 | 4 | 4 | Complete | Jane Doe
SP0180 | PRJ034 |  | 4 | PRJ034 Sprint 4 |  |  | 29 | 33 | 5 | 6 | Complete | Jane Doe
SP0181 | PRJ034 |  | 5 | PRJ034 Sprint 5 |  |  | 28 | 27 | 5 | 5 | Complete | Jane Doe
SP0182 | PRJ034 |  | 6 | PRJ034 Sprint 6 |  |  | 20 | 21 | 4 | 4 | Complete | Jane Doe
SP0183 | PRJ034 |  | 7 | PRJ034 Sprint 7 |  |  | 34 | 36 | 6 | 7 | Complete | Jane Doe
SP0184 | PRJ034 |  | 8 | PRJ034 Sprint 8 |  |  | 26 | 15 | 5 | 3 | Complete | Jane Doe
SP0185 | PRJ035 |  | 1 | PRJ035 Sprint 1 |  |  | 37 | 32 | 7 | 6 | Complete | Jane Doe
SP0186 | PRJ035 |  | 2 | PRJ035 Sprint 2 |  |  | 53 | 41 | 10 | 8 | Complete | Jane Doe
SP0187 | PRJ035 |  | 3 | PRJ035 Sprint 3 |  |  | 40 | 31 | 8 | 6 | Complete | Jane Doe
SP0188 | PRJ035 |  | 4 | PRJ035 Sprint 4 |  |  | 45 | 45 | 9 | 9 | Complete | Jane Doe
SP0189 | PRJ035 |  | 5 | PRJ035 Sprint 5 |  |  | 41 | 41 | 8 | 8 | Complete | Jane Doe
SP0190 | PRJ035 |  | 6 | PRJ035 Sprint 6 |  |  | 38 | 33 | 7 | 6 | Complete | Jane Doe
SP0191 | PRJ035 |  | 7 | PRJ035 Sprint 7 |  |  | 48 | 50 | 9 | 10 | Complete | Jane Doe
SP0192 | PRJ035 |  | 8 | PRJ035 Sprint 8 |  |  | 38 | 37 | 7 | 7 | Complete | Jane Doe
SP0193 | PRJ036 |  | 1 | PRJ036 Sprint 1 |  |  | 45 | 50 | 9 | 10 | Complete | Jane Doe
SP0194 | PRJ036 |  | 2 | PRJ036 Sprint 2 |  |  | 45 | 36 | 9 | 7 | Complete | Jane Doe
SP0195 | PRJ036 |  | 3 | PRJ036 Sprint 3 |  |  | 33 | 26 | 6 | 5 | Complete | Jane Doe
SP0196 | PRJ036 |  | 4 | PRJ036 Sprint 4 |  |  | 34 | 34 | 6 | 6 | Complete | Jane Doe
SP0197 | PRJ036 |  | 5 | PRJ036 Sprint 5 |  |  | 44 | 38 | 8 | 7 | Complete | Jane Doe
SP0198 | PRJ036 |  | 6 | PRJ036 Sprint 6 |  |  | 43 | 41 | 8 | 8 | Complete | Jane Doe
SP0199 | PRJ036 |  | 7 | PRJ036 Sprint 7 |  |  | 33 | 31 | 6 | 6 | Complete | Jane Doe
SP0200 | PRJ036 |  | 8 | PRJ036 Sprint 8 |  |  | 41 | 44 | 8 | 8 | Complete | Jane Doe
SP0201 | PRJ037 |  | 1 | PRJ037 Sprint 1 |  |  | 38 | 29 | 7 | 5 | Complete | John Smith
SP0202 | PRJ037 |  | 2 | PRJ037 Sprint 2 |  |  | 31 | 33 | 6 | 6 | Complete | John Smith
SP0203 | PRJ037 |  | 3 | PRJ037 Sprint 3 |  |  | 24 | 29 | 4 | 5 | Complete | John Smith
SP0204 | PRJ037 |  | 4 | PRJ037 Sprint 4 |  |  | 27 | 30 | 5 | 6 | Complete | John Smith
SP0205 | PRJ037 |  | 5 | PRJ037 Sprint 5 |  |  | 27 | 21 | 5 | 4 | Complete | John Smith
SP0206 | PRJ037 |  | 6 | PRJ037 Sprint 6 |  |  | 33 | 22 | 6 | 4 | Complete | John Smith
SP0207 | PRJ037 |  | 7 | PRJ037 Sprint 7 |  |  | 35 | 24 | 7 | 4 | Complete | John Smith
SP0208 | PRJ037 |  | 8 | PRJ037 Sprint 8 |  |  | 34 | 35 | 6 | 7 | Complete | John Smith
SP0209 | PRJ038 |  | 1 | PRJ038 Sprint 1 |  |  | 38 | 27 | 7 | 5 | Complete | Jane Doe
SP0210 | PRJ038 |  | 2 | PRJ038 Sprint 2 |  |  | 38 | 26 | 7 | 5 | Complete | Jane Doe
SP0211 | PRJ038 |  | 3 | PRJ038 Sprint 3 |  |  | 45 | 41 | 9 | 8 | Complete | Jane Doe
SP0212 | PRJ038 |  | 4 | PRJ038 Sprint 4 |  |  | 40 | 33 | 8 | 6 | Complete | Jane Doe
SP0213 | PRJ038 |  | 5 | PRJ038 Sprint 5 |  |  | 34 | 26 | 6 | 5 | Complete | Jane Doe
SP0214 | PRJ038 |  | 6 | PRJ038 Sprint 6 |  |  | 34 | 30 | 6 | 6 | Complete | Jane Doe
SP0215 | PRJ038 |  | 7 | PRJ038 Sprint 7 |  |  | 44 | 34 | 8 | 6 | Complete | Jane Doe
SP0216 | PRJ038 |  | 8 | PRJ038 Sprint 8 |  |  | 41 | 43 | 8 | 8 | Complete | Jane Doe

## Releases
Release ID | Project ID | Project Name | Release Name | Version | Type | Planned Date | Actual Date | Status | Owner | Environment | Notes
REL0001 | PRJ001 |  | Customer Portal R1 | 1.0.0 | Patch | 2025-05-03 | 2025-05-04 | Delivered | Alex Brown | Production
REL0002 | PRJ001 |  | Customer Portal R2 | 2.0.0 | Major | 2025-07-20 | 2025-07-16 | Delivered | Alex Brown | UAT
REL0003 | PRJ001 |  | Customer Portal R3 | 3.0.0 | Patch | 2025-10-07 | 2025-10-12 | Delivered | Alex Brown | Production
REL0004 | PRJ001 |  | Customer Portal R4 | 4.0.0 | Patch | 2025-12-24 | 2025-12-25 | Delivered | Alex Brown | UAT
REL0005 | PRJ002 |  | Cloud Migration R1 | 1.0.0 | Minor | 2025-04-30 | 2025-05-10 | Delivered | Carlos Diaz | Staging
REL0006 | PRJ002 |  | Cloud Migration R2 | 2.0.0 | Patch | 2025-06-09 | 2025-06-17 | Delivered | Carlos Diaz | Staging
REL0007 | PRJ002 |  | Cloud Migration R3 | 3.0.0 | Major | 2025-07-19 | 2025-07-26 | Delivered | Carlos Diaz | Staging
REL0008 | PRJ002 |  | Cloud Migration R4 | 4.0.0 | Major | 2025-08-28 | 2025-08-29 | Delivered | Carlos Diaz | Staging
REL0009 | PRJ003 |  | Data Platform R1 | 1.0.0 | Patch | 2025-09-06 | 2025-09-11 | Delivered | Carlos Diaz | Production
REL0010 | PRJ003 |  | Data Platform R2 | 2.0.0 | Hotfix | 2026-02-03 | 2026-02-02 | Delivered | Carlos Diaz | Production
REL0011 | PRJ004 |  | AI Assistant R1 | 1.0.0 | Major | 2026-01-01 | 2026-01-06 | Delivered | Jane Doe | Staging
REL0012 | PRJ004 |  | AI Assistant R2 | 2.0.0 | Patch | 2026-04-04 | 2026-04-12 | Delivered | Jane Doe | Staging
REL0013 | PRJ004 |  | AI Assistant R3 | 3.0.0 | Hotfix | 2026-07-05 | 2026-06-30 | Delivered | Jane Doe | Production
REL0014 | PRJ004 |  | AI Assistant R4 | 4.0.0 | Hotfix | 2026-10-06 |  | Planned | Jane Doe | Staging
REL0015 | PRJ005 |  | Network Refresh R1 | 1.0.0 | Minor | 2026-04-19 | 2026-04-15 | Delivered | Priya Patel | Staging
REL0016 | PRJ006 |  | Cyber Security Program R1 | 1.0.0 | Minor | 2025-08-04 | 2025-08-12 | Delivered | Alex Brown | Staging
REL0017 | PRJ006 |  | Cyber Security Program R2 | 2.0.0 | Minor | 2025-12-19 | 2025-12-26 | Delivered | Alex Brown | UAT
REL0018 | PRJ007 |  | CRM Upgrade R1 | 1.0.0 | Major | 2025-11-26 | 2025-11-27 | Delivered | Alex Brown | UAT
REL0019 | PRJ007 |  | CRM Upgrade R2 | 2.0.0 | Major | 2026-06-10 | 2026-06-16 | Delivered | Alex Brown | UAT
REL0020 | PRJ008 |  | Mobile App R1 | 1.0.0 | Hotfix | 2025-06-01 | 2025-05-30 | Delivered | Carlos Diaz | Staging
REL0021 | PRJ008 |  | Mobile App R2 | 2.0.0 | Hotfix | 2025-07-01 | 2025-07-10 | Delivered | Carlos Diaz | UAT
REL0022 | PRJ008 |  | Mobile App R3 | 3.0.0 | Patch | 2025-07-31 | 2025-08-06 | Delivered | Carlos Diaz | Staging
REL0023 | PRJ009 |  | ERP Modernisation R1 | 1.0.0 | Major | 2026-02-19 | 2026-02-24 | Delivered | Jane Doe | Production
REL0024 | PRJ009 |  | ERP Modernisation R2 | 2.0.0 | Hotfix | 2026-04-10 | 2026-04-19 | Delivered | Jane Doe | UAT
REL0025 | PRJ009 |  | ERP Modernisation R3 | 3.0.0 | Minor | 2026-05-30 | 2026-05-30 | Delivered | Jane Doe | Staging
REL0026 | PRJ009 |  | ERP Modernisation R4 | 4.0.0 | Hotfix | 2026-07-19 |  | In Progress | Jane Doe | UAT
REL0027 | PRJ010 |  | Workforce Enablement R1 | 1.0.0 | Patch | 2025-05-05 | 2025-05-13 | Delivered | Priya Patel | Staging
REL0028 | PRJ010 |  | Workforce Enablement R2 | 2.0.0 | Major | 2025-08-01 | 2025-07-30 | Delivered | Priya Patel | Production
REL0029 | PRJ010 |  | Workforce Enablement R3 | 3.0.0 | Major | 2025-10-28 | 2025-10-25 | Delivered | Priya Patel | Staging
REL0030 | PRJ011 |  | IoT Initiative R1 | 1.0.0 | Hotfix | 2025-12-25 | 2025-12-23 | Delivered | Jane Doe | Staging
REL0031 | PRJ011 |  | IoT Initiative R2 | 2.0.0 | Hotfix | 2026-01-22 | 2026-01-20 | Delivered | Jane Doe | Staging
REL0032 | PRJ011 |  | IoT Initiative R3 | 3.0.0 | Patch | 2026-02-19 | 2026-02-15 | Delivered | Jane Doe | UAT
REL0033 | PRJ011 |  | IoT Initiative R4 | 4.0.0 | Minor | 2026-03-19 | 2026-03-20 | Delivered | Jane Doe | UAT
REL0034 | PRJ012 |  | Analytics Platform R1 | 1.0.0 | Minor | 2026-01-15 | 2026-01-13 | Delivered | Jane Doe | UAT
REL0035 | PRJ012 |  | Analytics Platform R2 | 2.0.0 | Patch | 2026-04-29 | 2026-04-27 | Delivered | Jane Doe | UAT
REL0036 | PRJ012 |  | Analytics Platform R3 | 3.0.0 | Hotfix | 2026-08-10 |  | In Progress | Jane Doe | Staging
REL0037 | PRJ012 |  | Analytics Platform R4 | 4.0.0 | Hotfix | 2026-11-22 |  | Planned | Jane Doe | Production
REL0038 | PRJ013 |  | API Gateway R1 | 1.0.0 | Patch | 2026-03-29 | 2026-03-31 | Delivered | Priya Patel | UAT
REL0039 | PRJ013 |  | API Gateway R2 | 2.0.0 | Patch | 2026-07-21 |  | In Progress | Priya Patel | UAT
REL0040 | PRJ013 |  | API Gateway R3 | 3.0.0 | Hotfix | 2026-11-12 |  | Planned | Priya Patel | Staging
REL0041 | PRJ014 |  | Identity Mgmt R1 | 1.0.0 | Hotfix | 2025-06-16 | 2025-06-11 | Delivered | Alex Brown | Production
REL0042 | PRJ014 |  | Identity Mgmt R2 | 2.0.0 | Major | 2025-10-25 | 2025-10-20 | Delivered | Alex Brown | Production
REL0043 | PRJ015 |  | Service Desk R1 | 1.0.0 | Patch | 2025-08-23 | 2025-08-28 | Delivered | John Smith | Production
REL0044 | PRJ015 |  | Service Desk R2 | 2.0.0 | Minor | 2025-11-12 | 2025-11-20 | Delivered | John Smith | Staging
REL0045 | PRJ015 |  | Service Desk R3 | 3.0.0 | Minor | 2026-02-01 | 2026-02-08 | Delivered | John Smith | Staging
REL0046 | PRJ016 |  | Infrastructure Upg R1 | 1.0.0 | Hotfix | 2026-02-11 | 2026-02-07 | Delivered | John Smith | Production
REL0047 | PRJ016 |  | Infrastructure Upg R2 | 2.0.0 | Minor | 2026-04-24 | 2026-05-01 | Delivered | John Smith | UAT
REL0048 | PRJ016 |  | Infrastructure Upg R3 | 3.0.0 | Minor | 2026-07-05 | 2026-07-10 | Delivered | John Smith | UAT
REL0049 | PRJ016 |  | Infrastructure Upg R4 | 4.0.0 | Minor | 2026-09-15 |  | Planned | John Smith | Production
REL0050 | PRJ017 |  | App Modernisation R1 | 1.0.0 | Hotfix | 2025-07-05 | 2025-07-03 | Delivered | Priya Patel | Staging
REL0051 | PRJ017 |  | App Modernisation R2 | 2.0.0 | Minor | 2025-11-20 | 2025-11-23 | Delivered | Priya Patel | UAT
REL0052 | PRJ018 |  | RPA Program R1 | 1.0.0 | Major | 2026-02-27 | 2026-02-24 | Delivered | Carlos Diaz | Production
REL0053 | PRJ018 |  | RPA Program R2 | 2.0.0 | Major | 2026-07-01 | 2026-07-09 | Delivered | Carlos Diaz | Staging
REL0054 | PRJ019 |  | Vendor Mgmt R1 | 1.0.0 | Major | 2025-10-07 | 2025-10-02 | Delivered | Carlos Diaz | Staging
REL0055 | PRJ019 |  | Vendor Mgmt R2 | 2.0.0 | Major | 2026-04-21 | 2026-04-28 | Delivered | Carlos Diaz | Staging
REL0056 | PRJ020 |  | Process Automation R1 | 1.0.0 | Patch | 2025-05-29 | 2025-06-07 | Delivered | Carlos Diaz | Production
REL0057 | PRJ020 |  | Process Automation R2 | 2.0.0 | Minor | 2025-07-02 | 2025-07-04 | Delivered | Carlos Diaz | UAT
REL0058 | PRJ021 |  | Data Warehouse R1 | 1.0.0 | Hotfix | 2025-03-09 | 2025-03-11 | Delivered | Alex Brown | UAT
REL0059 | PRJ021 |  | Data Warehouse R2 | 2.0.0 | Patch | 2025-04-26 | 2025-04-22 | Delivered | Alex Brown | Production
REL0060 | PRJ022 |  | DevOps Tools R1 | 1.0.0 | Major | 2025-07-12 | 2025-07-07 | Delivered | Priya Patel | Production
REL0061 | PRJ022 |  | DevOps Tools R2 | 2.0.0 | Major | 2025-10-12 | 2025-10-21 | Delivered | Priya Patel | Production
REL0062 | PRJ023 |  | Workforce Portal R1 | 1.0.0 | Patch | 2026-03-19 | 2026-03-23 | Delivered | Jane Doe | Production
REL0063 | PRJ023 |  | Workforce Portal R2 | 2.0.0 | Major | 2026-07-24 |  | In Progress | Jane Doe | Production
REL0064 | PRJ024 |  | Process Mining R1 | 1.0.0 | Minor | 2026-02-26 | 2026-03-04 | Delivered | Jane Doe | UAT
REL0065 | PRJ024 |  | Process Mining R2 | 2.0.0 | Hotfix | 2026-05-20 | 2026-05-18 | Delivered | Jane Doe | Production
REL0066 | PRJ024 |  | Process Mining R3 | 3.0.0 | Hotfix | 2026-08-11 |  | In Progress | Jane Doe | Production
REL0067 | PRJ024 |  | Process Mining R4 | 4.0.0 | Hotfix | 2026-11-02 |  | Planned | Jane Doe | Staging
REL0068 | PRJ025 |  | Customer Insights R1 | 1.0.0 | Hotfix | 2026-07-11 | 2026-07-12 | Delivered | Sarah Lee | UAT
REL0069 | PRJ026 |  | ERP Modernisation 2 R1 | 1.0.0 | Minor | 2025-12-02 | 2025-12-11 | Delivered | Carlos Diaz | Production
REL0070 | PRJ026 |  | ERP Modernisation 2 R2 | 2.0.0 | Major | 2026-02-17 | 2026-02-21 | Delivered | Carlos Diaz | Production
REL0071 | PRJ026 |  | ERP Modernisation 2 R3 | 3.0.0 | Major | 2026-05-05 | 2026-05-01 | Delivered | Carlos Diaz | UAT
REL0072 | PRJ027 |  | Cyber Program R1 | 1.0.0 | Major | 2025-07-09 | 2025-07-19 | Delivered | Mike Johnson | Production
REL0073 | PRJ027 |  | Cyber Program R2 | 2.0.0 | Major | 2025-09-19 | 2025-09-22 | Delivered | Mike Johnson | Production
REL0074 | PRJ027 |  | Cyber Program R3 | 3.0.0 | Major | 2025-11-29 | 2025-11-24 | Delivered | Mike Johnson | Staging
REL0075 | PRJ028 |  | Mobile App 2 R1 | 1.0.0 | Patch | 2025-07-13 | 2025-07-14 | Delivered | Carlos Diaz | Production
REL0076 | PRJ028 |  | Mobile App 2 R2 | 2.0.0 | Major | 2026-01-20 | 2026-01-21 | Delivered | Carlos Diaz | UAT
REL0077 | PRJ029 |  | Analytics Platform 2 R1 | 1.0.0 | Major | 2026-03-16 | 2026-03-18 | Delivered | John Smith | Staging
REL0078 | PRJ029 |  | Analytics Platform 2 R2 | 2.0.0 | Patch | 2026-07-15 | 2026-07-14 | Delivered | John Smith | UAT
REL0079 | PRJ030 |  | Service Desk 2 R1 | 1.0.0 | Major | 2025-08-21 | 2025-08-22 | Delivered | Jane Doe | UAT
REL0080 | PRJ030 |  | Service Desk 2 R2 | 2.0.0 | Hotfix | 2025-12-02 | 2025-12-06 | Delivered | Jane Doe | Staging
REL0081 | PRJ030 |  | Service Desk 2 R3 | 3.0.0 | Hotfix | 2026-03-16 | 2026-03-26 | Delivered | Jane Doe | Staging
REL0082 | PRJ030 |  | Service Desk 2 R4 | 4.0.0 | Minor | 2026-06-27 | 2026-07-04 | Delivered | Jane Doe | UAT
REL0083 | PRJ031 |  | Quality Mgmt R1 | 1.0.0 | Patch | 2026-01-23 | 2026-01-24 | Delivered | Carlos Diaz | UAT
REL0084 | PRJ031 |  | Quality Mgmt R2 | 2.0.0 | Patch | 2026-06-21 | 2026-06-19 | Delivered | Carlos Diaz | Production
REL0085 | PRJ032 |  | Compliance Hub R1 | 1.0.0 | Hotfix | 2026-06-09 | 2026-06-19 | Delivered | Carlos Diaz | UAT
REL0086 | PRJ032 |  | Compliance Hub R2 | 2.0.0 | Hotfix | 2026-11-28 |  | Planned | Carlos Diaz | Staging
REL0087 | PRJ033 |  | Risk Platform R1 | 1.0.0 | Major | 2026-04-07 | 2026-04-12 | Delivered | Priya Patel | Staging
REL0088 | PRJ033 |  | Risk Platform R2 | 2.0.0 | Hotfix | 2026-08-22 |  | Planned | Priya Patel | UAT
REL0089 | PRJ033 |  | Risk Platform R3 | 3.0.0 | Minor | 2027-01-05 |  | Planned | Priya Patel | Staging
REL0090 | PRJ034 |  | Treasury Sys R1 | 1.0.0 | Major | 2026-02-25 | 2026-03-03 | Delivered | Jane Doe | UAT
REL0091 | PRJ034 |  | Treasury Sys R2 | 2.0.0 | Major | 2026-06-13 | 2026-06-13 | Delivered | Jane Doe | Staging
REL0092 | PRJ034 |  | Treasury Sys R3 | 3.0.0 | Patch | 2026-09-29 |  | Planned | Jane Doe | Staging
REL0093 | PRJ035 |  | Payroll Cloud R1 | 1.0.0 | Patch | 2025-07-31 | 2025-08-04 | Delivered | Jane Doe | UAT
REL0094 | PRJ035 |  | Payroll Cloud R2 | 2.0.0 | Major | 2025-10-28 | 2025-10-23 | Delivered | Jane Doe | Production
REL0095 | PRJ035 |  | Payroll Cloud R3 | 3.0.0 | Hotfix | 2026-01-24 | 2026-01-29 | Delivered | Jane Doe | Production
REL0096 | PRJ035 |  | Payroll Cloud R4 | 4.0.0 | Minor | 2026-04-23 | 2026-04-29 | Delivered | Jane Doe | Production
REL0097 | PRJ036 |  | HR Self-Service R1 | 1.0.0 | Patch | 2025-07-17 | 2025-07-23 | Delivered | Jane Doe | Production
REL0098 | PRJ036 |  | HR Self-Service R2 | 2.0.0 | Major | 2025-09-24 | 2025-09-29 | Delivered | Jane Doe | Production
REL0099 | PRJ037 |  | SAP S/4HANA R1 | 1.0.0 | Patch | 2025-05-02 | 2025-04-27 | Delivered | John Smith | Production
REL0100 | PRJ037 |  | SAP S/4HANA R2 | 2.0.0 | Patch | 2025-06-29 | 2025-07-08 | Delivered | John Smith | Production
REL0101 | PRJ037 |  | SAP S/4HANA R3 | 3.0.0 | Hotfix | 2025-08-25 | 2025-08-22 | Delivered | John Smith | UAT
REL0102 | PRJ038 |  | Salesforce CRM R1 | 1.0.0 | Major | 2025-10-21 | 2025-10-22 | Delivered | Jane Doe | Staging
REL0103 | PRJ038 |  | Salesforce CRM R2 | 2.0.0 | Major | 2025-12-02 | 2025-12-05 | Delivered | Jane Doe | Staging
REL0104 | PRJ039 |  | M365 Rollout R1 | 1.0.0 | Patch | 2025-12-08 | 2025-12-16 | Delivered | Jane Doe | UAT
REL0105 | PRJ039 |  | M365 Rollout R2 | 2.0.0 | Minor | 2026-01-01 | 2026-01-02 | Delivered | Jane Doe | Production
REL0106 | PRJ039 |  | M365 Rollout R3 | 3.0.0 | Hotfix | 2026-01-25 | 2026-02-04 | Delivered | Jane Doe | Production
REL0107 | PRJ039 |  | M365 Rollout R4 | 4.0.0 | Hotfix | 2026-02-18 | 2026-02-21 | Delivered | Jane Doe | Production
REL0108 | PRJ040 |  | Zero-Trust Net R1 | 1.0.0 | Minor | 2025-09-14 | 2025-09-23 | Delivered | Alex Brown | Staging

## Programs
Program | Owner | Sponsor | Budget | Forecast | Start FY | End FY | Status | Notes
Digital Transformation | Mike Johnson | CTO | 20682756 | 19929607 | FY25 | FY26 | Active
Cyber Security | Sarah Lee | CFO | 23048795 | 25365239 | FY25 | FY27 | Active
Cloud Migration | Alex Brown | CIO | 19629127 | 19663839 | FY25 | FY27 | Active
Data & AI | Mike Johnson | CIO | 15462956 | 14369534 | FY25 | FY27 | Active
Customer Experience | Priya Patel | CTO | 10175226 | 10299815 | FY25 | FY26 | Active

## PhaseFinancials
Project ID | Stage | Planned Start | Planned End | Actual Start | Actual End | Phase Budget | Phase Forecast | Phase Actual Spend | Status | Notes
PRJ001 | Discovery | 2025-02-14 | 2025-04-04 | 2025-02-14 | 2025-04-04 | 324221 | 371877 | 310352 | Complete
PRJ001 | Business Case / Seed Funding | 2025-04-04 | 2025-05-23 | 2025-04-04 | 2025-05-23 | 324221 | 314848 | 286522 | Complete
PRJ001 | Design | 2025-05-23 | 2025-07-11 | 2025-05-23 | 2025-07-11 | 324221 | 324448 | 304969 | Complete
PRJ001 | Business Case / Full Funding | 2025-07-11 | 2025-08-29 | 2025-07-11 | 2025-08-29 | 324221 | 366210 | 13318 | Complete
PRJ001 | Build | 2025-08-29 | 2025-10-17 | 2025-08-29 | 2025-10-17 | 324221 | 344061 | 23644 | Complete
PRJ001 | Testing | 2025-10-17 | 2025-12-05 | 2025-10-17 | 2025-12-05 | 324221 | 299509 | 273201 | Complete
PRJ001 | Deployment | 2025-12-05 | 2026-01-23 | 2025-12-05 | 2026-01-23 | 324221 | 350422 | 93508 | Complete
PRJ001 | Handover | 2026-01-23 | 2026-03-13 | 2026-01-23 | 2026-03-13 | 324221 | 352889 | 136290 | Complete
PRJ002 | Discovery | 2025-03-21 | 2025-04-15 | 2025-03-21 | 2025-04-15 | 231489 | 240544 | 76121 | Complete
PRJ002 | Business Case / Seed Funding | 2025-04-15 | 2025-05-10 | 2025-04-15 | 2025-05-10 | 231489 | 243777 | 95604 | Complete
PRJ002 | Design | 2025-05-10 | 2025-06-04 | 2025-05-10 | 2025-06-04 | 231489 | 248646 | 110492 | Complete
PRJ002 | Business Case / Full Funding | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 231489 | 257455 | 235080 | Complete
PRJ002 | Build | 2025-06-29 | 2025-07-24 | 2025-06-29 | 2025-07-24 | 231489 | 215367 | 90883 | Complete
PRJ002 | Testing | 2025-07-24 | 2025-08-18 | 2025-07-24 | 2025-08-18 | 231489 | 244104 | 7119 | Complete
PRJ002 | Deployment | 2025-08-18 | 2025-09-12 | 2025-08-18 | 2025-09-12 | 231489 | 211109 | 2527 | Complete
PRJ002 | Handover | 2025-09-12 | 2025-10-07 | 2025-09-12 | 2025-10-07 | 231489 | 214425 | 78475 | Complete
PRJ003 | Discovery | 2025-04-09 | 2025-06-04 | 2025-04-09 | 2025-06-04 | 486894 | 521901 | 222738 | Complete
PRJ003 | Business Case / Seed Funding | 2025-06-04 | 2025-07-30 | 2025-06-04 | 2025-07-30 | 486894 | 458921 | 97728 | Complete
PRJ003 | Design | 2025-07-30 | 2025-09-24 | 2025-07-30 | 2025-09-24 | 486894 | 548033 | 188585 | Complete
PRJ003 | Business Case / Full Funding | 2025-09-24 | 2025-11-19 | 2025-09-24 | 2025-11-19 | 486894 | 548106 | 505904 | Complete
PRJ003 | Build | 2025-11-19 | 2026-01-14 | 2025-11-19 | 2026-01-14 | 486894 | 551908 | 443763 | Complete
PRJ003 | Testing | 2026-01-14 | 2026-03-11 | 2026-01-14 | 2026-03-11 | 486894 | 469815 | 401294 | Complete
PRJ003 | Deployment | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 486894 | 451692 | 484217 | Complete
PRJ003 | Handover | 2026-05-06 | 2026-07-01 | 2026-05-06 | 2026-07-01 | 486894 | 447339 | 168366 | Complete
PRJ004 | Discovery | 2025-10-01 | 2025-11-27 | 2025-10-01 | 2025-11-27 | 192963 | 203227 | 164619 | Complete
PRJ004 | Business Case / Seed Funding | 2025-11-27 | 2026-01-23 | 2025-11-27 | 2026-01-23 | 192963 | 186688 | 34513 | Complete
PRJ004 | Design | 2026-01-23 | 2026-03-21 | 2026-01-23 | 2026-03-21 | 192963 | 180313 | 93342 | Complete
PRJ004 | Business Case / Full Funding | 2026-03-21 | 2026-05-17 | 2026-03-21 | 2026-05-17 | 192963 | 179759 | 174630 | Complete
PRJ004 | Build | 2026-05-17 | 2026-07-13 | 2026-05-17 | 2026-07-13 | 192963 | 209994 | 179878 | Complete
PRJ004 | Testing | 2026-07-13 | 2026-09-08 | 2026-07-13 |  | 192963 | 220260 | 83738 | In Progress
PRJ004 | Deployment | 2026-09-08 | 2026-11-04 |  |  | 192963 | 195220 | 0 | Planned
PRJ004 | Handover | 2026-11-04 | 2026-12-31 |  |  | 192963 | 179570 | 0 | Planned
PRJ005 | Discovery | 2025-07-22 | 2025-09-27 | 2025-07-22 | 2025-09-27 | 208068 | 214705 | 126251 | Complete
PRJ005 | Business Case / Seed Funding | 2025-09-27 | 2025-12-03 | 2025-09-27 | 2025-12-03 | 208068 | 221658 | 213304 | Complete
PRJ005 | Design | 2025-12-03 | 2026-02-08 | 2025-12-03 | 2026-02-08 | 208068 | 204006 | 159673 | Complete
PRJ005 | Business Case / Full Funding | 2026-02-08 | 2026-04-16 | 2026-02-08 | 2026-04-16 | 208068 | 199008 | 57635 | Complete
PRJ005 | Build | 2026-04-16 | 2026-06-22 | 2026-04-16 | 2026-06-22 | 208068 | 202670 | 18088 | Complete
PRJ005 | Testing | 2026-06-22 | 2026-08-28 | 2026-06-22 |  | 208068 | 216313 | 190698 | In Progress
PRJ005 | Deployment | 2026-08-28 | 2026-11-03 |  |  | 208068 | 221565 | 0 | Planned
PRJ005 | Handover | 2026-11-03 | 2027-01-09 |  |  | 208068 | 225508 | 0 | Planned
PRJ006 | Discovery | 2025-03-20 | 2025-05-10 | 2025-03-20 | 2025-05-10 | 207208 | 197153 | 16974 | Complete
PRJ006 | Business Case / Seed Funding | 2025-05-10 | 2025-06-30 | 2025-05-10 | 2025-06-30 | 207208 | 236826 | 13112 | Complete
PRJ006 | Design | 2025-06-30 | 2025-08-20 | 2025-06-30 | 2025-08-20 | 207208 | 187167 | 47024 | Complete
PRJ006 | Business Case / Full Funding | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-10-10 | 207208 | 228887 | 40885 | Complete
PRJ006 | Build | 2025-10-10 | 2025-11-30 | 2025-10-10 | 2025-11-30 | 207208 | 191902 | 45398 | Complete
PRJ006 | Testing | 2025-11-30 | 2026-01-20 | 2025-11-30 | 2026-01-20 | 207208 | 217077 | 114799 | Complete
PRJ006 | Deployment | 2026-01-20 | 2026-03-12 | 2026-01-20 | 2026-03-12 | 207208 | 230957 | 165458 | Complete
PRJ006 | Handover | 2026-03-12 | 2026-05-02 | 2026-03-12 | 2026-05-02 | 207208 | 202640 | 98781 | Complete
PRJ007 | Discovery | 2025-05-15 | 2025-07-27 | 2025-05-15 | 2025-07-27 | 443834 | 416538 | 235115 | Complete
PRJ007 | Business Case / Seed Funding | 2025-07-27 | 2025-10-08 | 2025-07-27 | 2025-10-08 | 443834 | 500881 | 101959 | Complete
PRJ007 | Design | 2025-10-08 | 2025-12-20 | 2025-10-08 | 2025-12-20 | 443834 | 439800 | 454406 | Complete
PRJ007 | Business Case / Full Funding | 2025-12-20 | 2026-03-03 | 2025-12-20 | 2026-03-03 | 443834 | 495747 | 239288 | Complete
PRJ007 | Build | 2026-03-03 | 2026-05-15 | 2026-03-03 | 2026-05-15 | 443834 | 486001 | 87591 | Complete
PRJ007 | Testing | 2026-05-15 | 2026-07-27 | 2026-05-15 |  | 443834 | 430279 | 76520 | In Progress
PRJ007 | Deployment | 2026-07-27 | 2026-10-08 |  |  | 443834 | 433532 | 0 | Planned
PRJ007 | Handover | 2026-10-08 | 2026-12-20 |  |  | 443834 | 495966 | 0 | Planned
PRJ008 | Discovery | 2025-05-03 | 2025-05-17 | 2025-05-03 | 2025-05-17 | 460266 | 488846 | 71182 | Complete
PRJ008 | Business Case / Seed Funding | 2025-05-17 | 2025-05-31 | 2025-05-17 | 2025-05-31 | 460266 | 515060 | 360055 | Complete
PRJ008 | Design | 2025-05-31 | 2025-06-14 | 2025-05-31 | 2025-06-14 | 460266 | 441920 | 432099 | Complete
PRJ008 | Business Case / Full Funding | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-06-28 | 460266 | 435760 | 13815 | Complete
PRJ008 | Build | 2025-06-28 | 2025-07-12 | 2025-06-28 | 2025-07-12 | 460266 | 490400 | 218752 | Complete
PRJ008 | Testing | 2025-07-12 | 2025-07-26 | 2025-07-12 | 2025-07-26 | 460266 | 444798 | 447965 | Complete
PRJ008 | Deployment | 2025-07-26 | 2025-08-09 | 2025-07-26 | 2025-08-09 | 460266 | 423912 | 208522 | Complete
PRJ008 | Handover | 2025-08-09 | 2025-08-23 | 2025-08-09 | 2025-08-23 | 460266 | 431570 | 242698 | Complete
PRJ009 | Discovery | 2026-01-01 | 2026-02-01 | 2026-01-01 | 2026-02-01 | 141715 | 145539 | 7910 | Complete
PRJ009 | Business Case / Seed Funding | 2026-02-01 | 2026-03-04 | 2026-02-01 | 2026-03-04 | 141715 | 137201 | 14555 | Complete
PRJ009 | Design | 2026-03-04 | 2026-04-04 | 2026-03-04 | 2026-04-04 | 141715 | 150523 | 108922 | Complete
PRJ009 | Business Case / Full Funding | 2026-04-04 | 2026-05-05 | 2026-04-04 | 2026-05-05 | 141715 | 142515 | 43748 | Complete
PRJ009 | Build | 2026-05-05 | 2026-06-05 | 2026-05-05 | 2026-06-05 | 141715 | 141811 | 88395 | Complete
PRJ009 | Testing | 2026-06-05 | 2026-07-06 | 2026-06-05 | 2026-07-06 | 141715 | 146305 | 73451 | Complete
PRJ009 | Deployment | 2026-07-06 | 2026-08-06 | 2026-07-06 |  | 141715 | 142904 | 101357 | In Progress
PRJ009 | Handover | 2026-08-06 | 2026-09-06 |  |  | 141715 | 150443 | 0 | Planned
PRJ010 | Discovery | 2025-02-06 | 2025-03-22 | 2025-02-06 | 2025-03-22 | 299364 | 341199 | 69021 | Complete
PRJ010 | Business Case / Seed Funding | 2025-03-22 | 2025-05-05 | 2025-03-22 | 2025-05-05 | 299364 | 273405 | 11218 | Complete
PRJ010 | Design | 2025-05-05 | 2025-06-18 | 2025-05-05 | 2025-06-18 | 299364 | 289349 | 20698 | Complete
PRJ010 | Business Case / Full Funding | 2025-06-18 | 2025-08-01 | 2025-06-18 | 2025-08-01 | 299364 | 276989 | 71185 | Complete
PRJ010 | Build | 2025-08-01 | 2025-09-14 | 2025-08-01 | 2025-09-14 | 299364 | 315846 | 225007 | Complete
PRJ010 | Testing | 2025-09-14 | 2025-10-28 | 2025-09-14 | 2025-10-28 | 299364 | 298759 | 31843 | Complete
PRJ010 | Deployment | 2025-10-28 | 2025-12-11 | 2025-10-28 | 2025-12-11 | 299364 | 324356 | 276464 | Complete
PRJ010 | Handover | 2025-12-11 | 2026-01-24 | 2025-12-11 | 2026-01-24 | 299364 | 289505 | 64660 | Complete
PRJ011 | Discovery | 2025-11-27 | 2025-12-14 | 2025-11-27 | 2025-12-14 | 58484 | 64124 | 21347 | Complete
PRJ011 | Business Case / Seed Funding | 2025-12-14 | 2025-12-31 | 2025-12-14 | 2025-12-31 | 58484 | 56846 | 36618 | Complete
PRJ011 | Design | 2025-12-31 | 2026-01-17 | 2025-12-31 | 2026-01-17 | 58484 | 63366 | 5787 | Complete
PRJ011 | Business Case / Full Funding | 2026-01-17 | 2026-02-03 | 2026-01-17 | 2026-02-03 | 58484 | 59993 | 43015 | Complete
PRJ011 | Build | 2026-02-03 | 2026-02-20 | 2026-02-03 | 2026-02-20 | 58484 | 59606 | 18749 | Complete
PRJ011 | Testing | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 58484 | 65892 | 14653 | Complete
PRJ011 | Deployment | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 58484 | 57243 | 4265 | Complete
PRJ011 | Handover | 2026-03-26 | 2026-04-12 | 2026-03-26 | 2026-04-12 | 58484 | 55375 | 55259 | Complete
PRJ012 | Discovery | 2025-10-04 | 2025-12-07 | 2025-10-04 | 2025-12-07 | 238031 | 222668 | 3183 | Complete
PRJ012 | Business Case / Seed Funding | 2025-12-07 | 2026-02-09 | 2025-12-07 | 2026-02-09 | 238031 | 242470 | 83491 | Complete
PRJ012 | Design | 2026-02-09 | 2026-04-14 | 2026-02-09 | 2026-04-14 | 238031 | 224792 | 65940 | Complete
PRJ012 | Business Case / Full Funding | 2026-04-14 | 2026-06-17 | 2026-04-14 | 2026-06-17 | 238031 | 218809 | 169755 | Complete
PRJ012 | Build | 2026-06-17 | 2026-08-20 | 2026-06-17 |  | 238031 | 264993 | 148461 | In Progress
PRJ012 | Testing | 2026-08-20 | 2026-10-23 |  |  | 238031 | 271923 | 0 | Planned
PRJ012 | Deployment | 2026-10-23 | 2026-12-26 |  |  | 238031 | 248931 | 0 | Planned
PRJ012 | Handover | 2026-12-26 | 2027-02-28 |  |  | 238031 | 243286 | 0 | Planned
PRJ013 | Discovery | 2025-12-05 | 2026-01-31 | 2025-12-05 | 2026-01-31 | 492838 | 474050 | 56605 | Complete
PRJ013 | Business Case / Seed Funding | 2026-01-31 | 2026-03-29 | 2026-01-31 | 2026-03-29 | 492838 | 544454 | 293549 | Complete
PRJ013 | Design | 2026-03-29 | 2026-05-25 | 2026-03-29 | 2026-05-25 | 492838 | 565583 | 432282 | Complete
PRJ013 | Business Case / Full Funding | 2026-05-25 | 2026-07-21 | 2026-05-25 |  | 492838 | 508272 | 86577 | In Progress
PRJ013 | Build | 2026-07-21 | 2026-09-16 |  |  | 492838 | 461615 | 0 | Planned
PRJ013 | Testing | 2026-09-16 | 2026-11-12 |  |  | 492838 | 455125 | 0 | Planned
PRJ013 | Deployment | 2026-11-12 | 2027-01-08 |  |  | 492838 | 481084 | 0 | Planned
PRJ013 | Handover | 2027-01-08 | 2027-03-06 |  |  | 492838 | 534259 | 0 | Planned
PRJ014 | Discovery | 2025-02-05 | 2025-03-26 | 2025-02-05 | 2025-03-26 | 297287 | 301197 | 229373 | Complete
PRJ014 | Business Case / Seed Funding | 2025-03-26 | 2025-05-14 | 2025-03-26 | 2025-05-14 | 297287 | 341121 | 80329 | Complete
PRJ014 | Design | 2025-05-14 | 2025-07-02 | 2025-05-14 | 2025-07-02 | 297287 | 303715 | 113713 | Complete
PRJ014 | Business Case / Full Funding | 2025-07-02 | 2025-08-20 | 2025-07-02 | 2025-08-20 | 297287 | 268566 | 110073 | Complete
PRJ014 | Build | 2025-08-20 | 2025-10-08 | 2025-08-20 | 2025-10-08 | 297287 | 320338 | 278243 | Complete
PRJ014 | Testing | 2025-10-08 | 2025-11-26 | 2025-10-08 | 2025-11-26 | 297287 | 325122 | 267500 | Complete
PRJ014 | Deployment | 2025-11-26 | 2026-01-14 | 2025-11-26 | 2026-01-14 | 297287 | 334608 | 185962 | Complete
PRJ014 | Handover | 2026-01-14 | 2026-03-04 | 2026-01-14 | 2026-03-04 | 297287 | 275939 | 214068 | Complete
PRJ015 | Discovery | 2025-06-03 | 2025-07-13 | 2025-06-03 | 2025-07-13 | 166730 | 180411 | 3629 | Complete
PRJ015 | Business Case / Seed Funding | 2025-07-13 | 2025-08-22 | 2025-07-13 | 2025-08-22 | 166730 | 190849 | 149904 | Complete
PRJ015 | Design | 2025-08-22 | 2025-10-01 | 2025-08-22 | 2025-10-01 | 166730 | 177541 | 24795 | Complete
PRJ015 | Business Case / Full Funding | 2025-10-01 | 2025-11-10 | 2025-10-01 | 2025-11-10 | 166730 | 170808 | 42781 | Complete
PRJ015 | Build | 2025-11-10 | 2025-12-20 | 2025-11-10 | 2025-12-20 | 166730 | 180945 | 170391 | Complete
PRJ015 | Testing | 2025-12-20 | 2026-01-29 | 2025-12-20 | 2026-01-29 | 166730 | 165039 | 130314 | Complete
PRJ015 | Deployment | 2026-01-29 | 2026-03-10 | 2026-01-29 | 2026-03-10 | 166730 | 158137 | 167156 | Complete
PRJ015 | Handover | 2026-03-10 | 2026-04-19 | 2026-03-10 | 2026-04-19 | 166730 | 176681 | 169019 | Complete
PRJ016 | Discovery | 2025-12-01 | 2026-01-15 | 2025-12-01 | 2026-01-15 | 441921 | 494636 | 314976 | Complete
PRJ016 | Business Case / Seed Funding | 2026-01-15 | 2026-03-01 | 2026-01-15 | 2026-03-01 | 441921 | 497075 | 208469 | Complete
PRJ016 | Design | 2026-03-01 | 2026-04-15 | 2026-03-01 | 2026-04-15 | 441921 | 503603 | 244494 | Complete
PRJ016 | Business Case / Full Funding | 2026-04-15 | 2026-05-30 | 2026-04-15 | 2026-05-30 | 441921 | 427041 | 315099 | Complete
PRJ016 | Build | 2026-05-30 | 2026-07-14 | 2026-05-30 | 2026-07-14 | 441921 | 495835 | 181443 | Complete
PRJ016 | Testing | 2026-07-14 | 2026-08-28 | 2026-07-14 |  | 441921 | 443832 | 461207 | In Progress
PRJ016 | Deployment | 2026-08-28 | 2026-10-12 |  |  | 441921 | 431903 | 0 | Planned
PRJ016 | Handover | 2026-10-12 | 2026-11-26 |  |  | 441921 | 402270 | 0 | Planned
PRJ017 | Discovery | 2025-02-17 | 2025-04-09 | 2025-02-17 | 2025-04-09 | 362336 | 373213 | 130600 | Complete
PRJ017 | Business Case / Seed Funding | 2025-04-09 | 2025-05-30 | 2025-04-09 | 2025-05-30 | 362336 | 381573 | 164911 | Complete
PRJ017 | Design | 2025-05-30 | 2025-07-20 | 2025-05-30 | 2025-07-20 | 362336 | 367321 | 368337 | Complete
PRJ017 | Business Case / Full Funding | 2025-07-20 | 2025-09-09 | 2025-07-20 | 2025-09-09 | 362336 | 397876 | 109726 | Complete
PRJ017 | Build | 2025-09-09 | 2025-10-30 | 2025-09-09 | 2025-10-30 | 362336 | 413921 | 189818 | Complete
PRJ017 | Testing | 2025-10-30 | 2025-12-20 | 2025-10-30 | 2025-12-20 | 362336 | 388200 | 177412 | Complete
PRJ017 | Deployment | 2025-12-20 | 2026-02-09 | 2025-12-20 | 2026-02-09 | 362336 | 339711 | 367773 | Complete
PRJ017 | Handover | 2026-02-09 | 2026-04-01 | 2026-02-09 | 2026-04-01 | 362336 | 382608 | 252743 | Complete
PRJ018 | Discovery | 2025-10-26 | 2025-12-11 | 2025-10-26 | 2025-12-11 | 220997 | 215674 | 66890 | Complete
PRJ018 | Business Case / Seed Funding | 2025-12-11 | 2026-01-26 | 2025-12-11 | 2026-01-26 | 220997 | 243085 | 3618 | Complete
PRJ018 | Design | 2026-01-26 | 2026-03-13 | 2026-01-26 | 2026-03-13 | 220997 | 201160 | 65673 | Complete
PRJ018 | Business Case / Full Funding | 2026-03-13 | 2026-04-28 | 2026-03-13 | 2026-04-28 | 220997 | 231664 | 12343 | Complete
PRJ018 | Build | 2026-04-28 | 2026-06-13 | 2026-04-28 | 2026-06-13 | 220997 | 215794 | 99855 | Complete
PRJ018 | Testing | 2026-06-13 | 2026-07-29 | 2026-06-13 |  | 220997 | 235376 | 149 | In Progress
PRJ018 | Deployment | 2026-07-29 | 2026-09-13 |  |  | 220997 | 212789 | 0 | Planned
PRJ018 | Handover | 2026-09-13 | 2026-10-29 |  |  | 220997 | 218247 | 0 | Planned
PRJ019 | Discovery | 2025-03-25 | 2025-06-06 | 2025-03-25 | 2025-06-06 | 62612 | 60785 | 56473 | Complete
PRJ019 | Business Case / Seed Funding | 2025-06-06 | 2025-08-18 | 2025-06-06 | 2025-08-18 | 62612 | 66765 | 50548 | Complete
PRJ019 | Design | 2025-08-18 | 2025-10-30 | 2025-08-18 | 2025-10-30 | 62612 | 58777 | 5654 | Complete
PRJ019 | Business Case / Full Funding | 2025-10-30 | 2026-01-11 | 2025-10-30 | 2026-01-11 | 62612 | 60587 | 65474 | Complete
PRJ019 | Build | 2026-01-11 | 2026-03-25 | 2026-01-11 | 2026-03-25 | 62612 | 59430 | 38474 | Complete
PRJ019 | Testing | 2026-03-25 | 2026-06-06 | 2026-03-25 | 2026-06-06 | 62612 | 57614 | 14388 | Complete
PRJ019 | Deployment | 2026-06-06 | 2026-08-18 | 2026-06-06 |  | 62612 | 63757 | 23314 | In Progress
PRJ019 | Handover | 2026-08-18 | 2026-10-30 |  |  | 62612 | 69056 | 0 | Planned
PRJ020 | Discovery | 2025-04-25 | 2025-05-07 | 2025-04-25 | 2025-05-07 | 437681 | 463619 | 194195 | Complete
PRJ020 | Business Case / Seed Funding | 2025-05-07 | 2025-05-19 | 2025-05-07 | 2025-05-19 | 437681 | 499712 | 45101 | Complete
PRJ020 | Design | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-31 | 437681 | 422500 | 138799 | Complete
PRJ020 | Business Case / Full Funding | 2025-05-31 | 2025-06-12 | 2025-05-31 | 2025-06-12 | 437681 | 427914 | 259152 | Complete
PRJ020 | Build | 2025-06-12 | 2025-06-24 | 2025-06-12 | 2025-06-24 | 437681 | 468201 | 148201 | Complete
PRJ020 | Testing | 2025-06-24 | 2025-07-06 | 2025-06-24 | 2025-07-06 | 437681 | 457176 | 314031 | Complete
PRJ020 | Deployment | 2025-07-06 | 2025-07-18 | 2025-07-06 | 2025-07-18 | 437681 | 415743 | 62359 | Complete
PRJ020 | Handover | 2025-07-18 | 2025-07-30 | 2025-07-18 | 2025-07-30 | 437681 | 454563 | 138358 | Complete
PRJ021 | Discovery | 2025-01-20 | 2025-02-07 | 2025-01-20 | 2025-02-07 | 490810 | 452233 | 292031 | Complete
PRJ021 | Business Case / Seed Funding | 2025-02-07 | 2025-02-25 | 2025-02-07 | 2025-02-25 | 490810 | 518826 | 281294 | Complete
PRJ021 | Design | 2025-02-25 | 2025-03-15 | 2025-02-25 | 2025-03-15 | 490810 | 487861 | 451407 | Complete
PRJ021 | Business Case / Full Funding | 2025-03-15 | 2025-04-02 | 2025-03-15 | 2025-04-02 | 490810 | 495337 | 71433 | Complete
PRJ021 | Build | 2025-04-02 | 2025-04-20 | 2025-04-02 | 2025-04-20 | 490810 | 495952 | 161439 | Complete
PRJ021 | Testing | 2025-04-20 | 2025-05-08 | 2025-04-20 | 2025-05-08 | 490810 | 556442 | 367238 | Complete
PRJ021 | Deployment | 2025-05-08 | 2025-05-26 | 2025-05-08 | 2025-05-26 | 490810 | 499201 | 220400 | Complete
PRJ021 | Handover | 2025-05-26 | 2025-06-13 | 2025-05-26 | 2025-06-13 | 490810 | 493327 | 211427 | Complete
PRJ022 | Discovery | 2025-04-11 | 2025-05-15 | 2025-04-11 | 2025-05-15 | 358033 | 324707 | 210113 | Complete
PRJ022 | Business Case / Seed Funding | 2025-05-15 | 2025-06-18 | 2025-05-15 | 2025-06-18 | 358033 | 407933 | 158238 | Complete
PRJ022 | Design | 2025-06-18 | 2025-07-22 | 2025-06-18 | 2025-07-22 | 358033 | 389885 | 231278 | Complete
PRJ022 | Business Case / Full Funding | 2025-07-22 | 2025-08-25 | 2025-07-22 | 2025-08-25 | 358033 | 349296 | 91219 | Complete
PRJ022 | Build | 2025-08-25 | 2025-09-28 | 2025-08-25 | 2025-09-28 | 358033 | 368076 | 47847 | Complete
PRJ022 | Testing | 2025-09-28 | 2025-11-01 | 2025-09-28 | 2025-11-01 | 358033 | 370857 | 212619 | Complete
PRJ022 | Deployment | 2025-11-01 | 2025-12-05 | 2025-11-01 | 2025-12-05 | 358033 | 348486 | 283957 | Complete
PRJ022 | Handover | 2025-12-05 | 2026-01-08 | 2025-12-05 | 2026-01-08 | 358033 | 357376 | 151480 | Complete
PRJ023 | Discovery | 2025-11-12 | 2025-12-29 | 2025-11-12 | 2025-12-29 | 352389 | 317675 | 298775 | Complete
PRJ023 | Business Case / Seed Funding | 2025-12-29 | 2026-02-14 | 2025-12-29 | 2026-02-14 | 352389 | 394227 | 170286 | Complete
PRJ023 | Design | 2026-02-14 | 2026-04-02 | 2026-02-14 | 2026-04-02 | 352389 | 321938 | 20237 | Complete
PRJ023 | Business Case / Full Funding | 2026-04-02 | 2026-05-19 | 2026-04-02 | 2026-05-19 | 352389 | 390262 | 240461 | Complete
PRJ023 | Build | 2026-05-19 | 2026-07-05 | 2026-05-19 | 2026-07-05 | 352389 | 346529 | 36038 | Complete
PRJ023 | Testing | 2026-07-05 | 2026-08-21 | 2026-07-05 |  | 352389 | 342749 | 178147 | In Progress
PRJ023 | Deployment | 2026-08-21 | 2026-10-07 |  |  | 352389 | 346338 | 0 | Planned
PRJ023 | Handover | 2026-10-07 | 2026-11-23 |  |  | 352389 | 322512 | 0 | Planned
PRJ024 | Discovery | 2025-12-06 | 2026-01-26 | 2025-12-06 | 2026-01-26 | 116679 | 126611 | 82625 | Complete
PRJ024 | Business Case / Seed Funding | 2026-01-26 | 2026-03-18 | 2026-01-26 | 2026-03-18 | 116679 | 126579 | 6496 | Complete
PRJ024 | Design | 2026-03-18 | 2026-05-08 | 2026-03-18 | 2026-05-08 | 116679 | 110993 | 17661 | Complete
PRJ024 | Business Case / Full Funding | 2026-05-08 | 2026-06-28 | 2026-05-08 | 2026-06-28 | 116679 | 126609 | 60681 | Complete
PRJ024 | Build | 2026-06-28 | 2026-08-18 | 2026-06-28 |  | 116679 | 111532 | 82780 | In Progress
PRJ024 | Testing | 2026-08-18 | 2026-10-08 |  |  | 116679 | 129872 | 0 | Planned
PRJ024 | Deployment | 2026-10-08 | 2026-11-28 |  |  | 116679 | 113788 | 0 | Planned
PRJ024 | Handover | 2026-11-28 | 2027-01-18 |  |  | 116679 | 114080 | 0 | Planned
PRJ025 | Discovery | 2025-12-02 | 2026-01-26 | 2025-12-02 | 2026-01-26 | 234515 | 269057 | 1588 | Complete
PRJ025 | Business Case / Seed Funding | 2026-01-26 | 2026-03-22 | 2026-01-26 | 2026-03-22 | 234515 | 239496 | 169358 | Complete
PRJ025 | Design | 2026-03-22 | 2026-05-16 | 2026-03-22 | 2026-05-16 | 234515 | 217789 | 9 | Complete
PRJ025 | Business Case / Full Funding | 2026-05-16 | 2026-07-10 | 2026-05-16 | 2026-07-10 | 234515 | 246463 | 29804 | Complete
PRJ025 | Build | 2026-07-10 | 2026-09-03 | 2026-07-10 |  | 234515 | 216743 | 50306 | In Progress
PRJ025 | Testing | 2026-09-03 | 2026-10-28 |  |  | 234515 | 238839 | 0 | Planned
PRJ025 | Deployment | 2026-10-28 | 2026-12-22 |  |  | 234515 | 259886 | 0 | Planned
PRJ025 | Handover | 2026-12-22 | 2027-02-15 |  |  | 234515 | 237084 | 0 | Planned
PRJ026 | Discovery | 2025-09-16 | 2025-10-24 | 2025-09-16 | 2025-10-24 | 337944 | 308852 | 43224 | Complete
PRJ026 | Business Case / Seed Funding | 2025-10-24 | 2025-12-01 | 2025-10-24 | 2025-12-01 | 337944 | 338329 | 348701 | Complete
PRJ026 | Design | 2025-12-01 | 2026-01-08 | 2025-12-01 | 2026-01-08 | 337944 | 373451 | 298677 | Complete
PRJ026 | Business Case / Full Funding | 2026-01-08 | 2026-02-15 | 2026-01-08 | 2026-02-15 | 337944 | 350340 | 291568 | Complete
PRJ026 | Build | 2026-02-15 | 2026-03-25 | 2026-02-15 | 2026-03-25 | 337944 | 361712 | 304920 | Complete
PRJ026 | Testing | 2026-03-25 | 2026-05-02 | 2026-03-25 | 2026-05-02 | 337944 | 356291 | 153417 | Complete
PRJ026 | Deployment | 2026-05-02 | 2026-06-09 | 2026-05-02 | 2026-06-09 | 337944 | 357899 | 65577 | Complete
PRJ026 | Handover | 2026-06-09 | 2026-07-17 | 2026-06-09 |  | 337944 | 373306 | 233296 | In Progress
PRJ027 | Discovery | 2025-04-29 | 2025-06-03 | 2025-04-29 | 2025-06-03 | 226938 | 213933 | 176727 | Complete
PRJ027 | Business Case / Seed Funding | 2025-06-03 | 2025-07-08 | 2025-06-03 | 2025-07-08 | 226938 | 235260 | 113461 | Complete
PRJ027 | Design | 2025-07-08 | 2025-08-12 | 2025-07-08 | 2025-08-12 | 226938 | 220699 | 159064 | Complete
PRJ027 | Business Case / Full Funding | 2025-08-12 | 2025-09-16 | 2025-08-12 | 2025-09-16 | 226938 | 258658 | 117466 | Complete
PRJ027 | Build | 2025-09-16 | 2025-10-21 | 2025-09-16 | 2025-10-21 | 226938 | 242126 | 93214 | Complete
PRJ027 | Testing | 2025-10-21 | 2025-11-25 | 2025-10-21 | 2025-11-25 | 226938 | 243825 | 25576 | Complete
PRJ027 | Deployment | 2025-11-25 | 2025-12-30 | 2025-11-25 | 2025-12-30 | 226938 | 227896 | 101231 | Complete
PRJ027 | Handover | 2025-12-30 | 2026-02-03 | 2025-12-30 | 2026-02-03 | 226938 | 205831 | 108916 | Complete
PRJ028 | Discovery | 2025-01-04 | 2025-03-16 | 2025-01-04 | 2025-03-16 | 202370 | 210678 | 2342 | Complete
PRJ028 | Business Case / Seed Funding | 2025-03-16 | 2025-05-26 | 2025-03-16 | 2025-05-26 | 202370 | 197450 | 137078 | Complete
PRJ028 | Design | 2025-05-26 | 2025-08-05 | 2025-05-26 | 2025-08-05 | 202370 | 227323 | 131717 | Complete
PRJ028 | Business Case / Full Funding | 2025-08-05 | 2025-10-15 | 2025-08-05 | 2025-10-15 | 202370 | 184290 | 192739 | Complete
PRJ028 | Build | 2025-10-15 | 2025-12-25 | 2025-10-15 | 2025-12-25 | 202370 | 230843 | 99425 | Complete
PRJ028 | Testing | 2025-12-25 | 2026-03-06 | 2025-12-25 | 2026-03-06 | 202370 | 218715 | 58839 | Complete
PRJ028 | Deployment | 2026-03-06 | 2026-05-16 | 2026-03-06 | 2026-05-16 | 202370 | 231802 | 76017 | Complete
PRJ028 | Handover | 2026-05-16 | 2026-07-26 | 2026-05-16 |  | 202370 | 225432 | 106925 | In Progress
PRJ029 | Discovery | 2025-11-15 | 2025-12-30 | 2025-11-15 | 2025-12-30 | 249250 | 246062 | 184828 | Complete
PRJ029 | Business Case / Seed Funding | 2025-12-30 | 2026-02-13 | 2025-12-30 | 2026-02-13 | 249250 | 248666 | 16427 | Complete
PRJ029 | Design | 2026-02-13 | 2026-03-30 | 2026-02-13 | 2026-03-30 | 249250 | 265198 | 92088 | Complete
PRJ029 | Business Case / Full Funding | 2026-03-30 | 2026-05-14 | 2026-03-30 | 2026-05-14 | 249250 | 269141 | 88797 | Complete
PRJ029 | Build | 2026-05-14 | 2026-06-28 | 2026-05-14 | 2026-06-28 | 249250 | 268890 | 205889 | Complete
PRJ029 | Testing | 2026-06-28 | 2026-08-12 | 2026-06-28 |  | 249250 | 241670 | 199584 | In Progress
PRJ029 | Deployment | 2026-08-12 | 2026-09-26 |  |  | 249250 | 243202 | 0 | Planned
PRJ029 | Handover | 2026-09-26 | 2026-11-10 |  |  | 249250 | 248872 | 0 | Planned
PRJ030 | Discovery | 2025-05-10 | 2025-07-13 | 2025-05-10 | 2025-07-13 | 139326 | 157305 | 94378 | Complete
PRJ030 | Business Case / Seed Funding | 2025-07-13 | 2025-09-15 | 2025-07-13 | 2025-09-15 | 139326 | 138509 | 69014 | Complete
PRJ030 | Design | 2025-09-15 | 2025-11-18 | 2025-09-15 | 2025-11-18 | 139326 | 148347 | 84270 | Complete
PRJ030 | Business Case / Full Funding | 2025-11-18 | 2026-01-21 | 2025-11-18 | 2026-01-21 | 139326 | 157697 | 113435 | Complete
PRJ030 | Build | 2026-01-21 | 2026-03-26 | 2026-01-21 | 2026-03-26 | 139326 | 143695 | 18933 | Complete
PRJ030 | Testing | 2026-03-26 | 2026-05-29 | 2026-03-26 | 2026-05-29 | 139326 | 136682 | 139738 | Complete
PRJ030 | Deployment | 2026-05-29 | 2026-08-01 | 2026-05-29 |  | 139326 | 137518 | 90332 | In Progress
PRJ030 | Handover | 2026-08-01 | 2026-10-04 |  |  | 139326 | 139458 | 0 | Planned
PRJ031 | Discovery | 2025-08-27 | 2025-10-22 | 2025-08-27 | 2025-10-22 | 109688 | 99952 | 98131 | Complete
PRJ031 | Business Case / Seed Funding | 2025-10-22 | 2025-12-17 | 2025-10-22 | 2025-12-17 | 109688 | 103085 | 11119 | Complete
PRJ031 | Design | 2025-12-17 | 2026-02-11 | 2025-12-17 | 2026-02-11 | 109688 | 101632 | 107598 | Complete
PRJ031 | Business Case / Full Funding | 2026-02-11 | 2026-04-08 | 2026-02-11 | 2026-04-08 | 109688 | 111784 | 87521 | Complete
PRJ031 | Build | 2026-04-08 | 2026-06-03 | 2026-04-08 | 2026-06-03 | 109688 | 125630 | 93124 | Complete
PRJ031 | Testing | 2026-06-03 | 2026-07-29 | 2026-06-03 |  | 109688 | 118810 | 27252 | In Progress
PRJ031 | Deployment | 2026-07-29 | 2026-09-23 |  |  | 109688 | 123394 | 0 | Planned
PRJ031 | Handover | 2026-09-23 | 2026-11-18 |  |  | 109688 | 103491 | 0 | Planned
PRJ032 | Discovery | 2025-12-20 | 2026-02-22 | 2025-12-20 | 2026-02-22 | 465332 | 522623 | 369290 | Complete
PRJ032 | Business Case / Seed Funding | 2026-02-22 | 2026-04-27 | 2026-02-22 | 2026-04-27 | 465332 | 467666 | 31451 | Complete
PRJ032 | Design | 2026-04-27 | 2026-06-30 | 2026-04-27 | 2026-06-30 | 465332 | 489984 | 55932 | Complete
PRJ032 | Business Case / Full Funding | 2026-06-30 | 2026-09-02 | 2026-06-30 |  | 465332 | 517310 | 35610 | In Progress
PRJ032 | Build | 2026-09-02 | 2026-11-05 |  |  | 465332 | 507602 | 0 | Planned
PRJ032 | Testing | 2026-11-05 | 2027-01-08 |  |  | 465332 | 489359 | 0 | Planned
PRJ032 | Deployment | 2027-01-08 | 2027-03-13 |  |  | 465332 | 516598 | 0 | Planned
PRJ032 | Handover | 2027-03-13 | 2027-05-16 |  |  | 465332 | 526239 | 0 | Planned
PRJ033 | Discovery | 2025-11-22 | 2026-01-29 | 2025-11-22 | 2026-01-29 | 193153 | 189346 | 141709 | Complete
PRJ033 | Business Case / Seed Funding | 2026-01-29 | 2026-04-07 | 2026-01-29 | 2026-04-07 | 193153 | 192073 | 200554 | Complete
PRJ033 | Design | 2026-04-07 | 2026-06-14 | 2026-04-07 | 2026-06-14 | 193153 | 201545 | 40508 | Complete
PRJ033 | Business Case / Full Funding | 2026-06-14 | 2026-08-21 | 2026-06-14 |  | 193153 | 186030 | 88733 | In Progress
PRJ033 | Build | 2026-08-21 | 2026-10-28 |  |  | 193153 | 187653 | 0 | Planned
PRJ033 | Testing | 2026-10-28 | 2027-01-04 |  |  | 193153 | 183553 | 0 | Planned
PRJ033 | Deployment | 2027-01-04 | 2027-03-13 |  |  | 193153 | 181665 | 0 | Planned
PRJ033 | Handover | 2027-03-13 | 2027-05-20 |  |  | 193153 | 213137 | 0 | Planned
PRJ034 | Discovery | 2025-11-09 | 2026-01-02 | 2025-11-09 | 2026-01-02 | 169624 | 186954 | 34249 | Complete
PRJ034 | Business Case / Seed Funding | 2026-01-02 | 2026-02-25 | 2026-01-02 | 2026-02-25 | 169624 | 177346 | 112048 | Complete
PRJ034 | Design | 2026-02-25 | 2026-04-20 | 2026-02-25 | 2026-04-20 | 169624 | 181016 | 36251 | Complete
PRJ034 | Business Case / Full Funding | 2026-04-20 | 2026-06-13 | 2026-04-20 | 2026-06-13 | 169624 | 187010 | 159099 | Complete
PRJ034 | Build | 2026-06-13 | 2026-08-06 | 2026-06-13 |  | 169624 | 167909 | 72672 | In Progress
PRJ034 | Testing | 2026-08-06 | 2026-09-29 |  |  | 169624 | 175839 | 0 | Planned
PRJ034 | Deployment | 2026-09-29 | 2026-11-22 |  |  | 169624 | 155713 | 0 | Planned
PRJ034 | Handover | 2026-11-22 | 2027-01-15 |  |  | 169624 | 160519 | 0 | Planned
PRJ035 | Discovery | 2025-05-04 | 2025-06-28 | 2025-05-04 | 2025-06-28 | 441552 | 477978 | 422362 | Complete
PRJ035 | Business Case / Seed Funding | 2025-06-28 | 2025-08-22 | 2025-06-28 | 2025-08-22 | 441552 | 468292 | 230042 | Complete
PRJ035 | Design | 2025-08-22 | 2025-10-16 | 2025-08-22 | 2025-10-16 | 441552 | 489285 | 264441 | Complete
PRJ035 | Business Case / Full Funding | 2025-10-16 | 2025-12-10 | 2025-10-16 | 2025-12-10 | 441552 | 449692 | 163247 | Complete
PRJ035 | Build | 2025-12-10 | 2026-02-03 | 2025-12-10 | 2026-02-03 | 441552 | 465670 | 259029 | Complete
PRJ035 | Testing | 2026-02-03 | 2026-03-30 | 2026-02-03 | 2026-03-30 | 441552 | 412617 | 31135 | Complete
PRJ035 | Deployment | 2026-03-30 | 2026-05-24 | 2026-03-30 | 2026-05-24 | 441552 | 444589 | 174380 | Complete
PRJ035 | Handover | 2026-05-24 | 2026-07-18 | 2026-05-24 |  | 441552 | 405220 | 36230 | In Progress
PRJ036 | Discovery | 2025-05-09 | 2025-06-04 | 2025-05-09 | 2025-06-04 | 282318 | 309307 | 88405 | Complete
PRJ036 | Business Case / Seed Funding | 2025-06-04 | 2025-06-30 | 2025-06-04 | 2025-06-30 | 282318 | 262410 | 68350 | Complete
PRJ036 | Design | 2025-06-30 | 2025-07-26 | 2025-06-30 | 2025-07-26 | 282318 | 296539 | 98096 | Complete
PRJ036 | Business Case / Full Funding | 2025-07-26 | 2025-08-21 | 2025-07-26 | 2025-08-21 | 282318 | 269898 | 278831 | Complete
PRJ036 | Build | 2025-08-21 | 2025-09-16 | 2025-08-21 | 2025-09-16 | 282318 | 319180 | 74518 | Complete
PRJ036 | Testing | 2025-09-16 | 2025-10-12 | 2025-09-16 | 2025-10-12 | 282318 | 303723 | 20144 | Complete
PRJ036 | Deployment | 2025-10-12 | 2025-11-07 | 2025-10-12 | 2025-11-07 | 282318 | 315594 | 286982 | Complete
PRJ036 | Handover | 2025-11-07 | 2025-12-03 | 2025-11-07 | 2025-12-03 | 282318 | 259364 | 170555 | Complete
PRJ037 | Discovery | 2025-03-06 | 2025-04-03 | 2025-03-06 | 2025-04-03 | 150462 | 167509 | 147212 | Complete
PRJ037 | Business Case / Seed Funding | 2025-04-03 | 2025-05-01 | 2025-04-03 | 2025-05-01 | 150462 | 154225 | 63071 | Complete
PRJ037 | Design | 2025-05-01 | 2025-05-29 | 2025-05-01 | 2025-05-29 | 150462 | 137547 | 110197 | Complete
PRJ037 | Business Case / Full Funding | 2025-05-29 | 2025-06-26 | 2025-05-29 | 2025-06-26 | 150462 | 139586 | 74408 | Complete
PRJ037 | Build | 2025-06-26 | 2025-07-24 | 2025-06-26 | 2025-07-24 | 150462 | 169924 | 41558 | Complete
PRJ037 | Testing | 2025-07-24 | 2025-08-21 | 2025-07-24 | 2025-08-21 | 150462 | 136543 | 53406 | Complete
PRJ037 | Deployment | 2025-08-21 | 2025-09-18 | 2025-08-21 | 2025-09-18 | 150462 | 145229 | 52852 | Complete
PRJ037 | Handover | 2025-09-18 | 2025-10-16 | 2025-09-18 | 2025-10-16 | 150462 | 164182 | 22006 | Complete
PRJ038 | Discovery | 2025-09-09 | 2025-09-24 | 2025-09-09 | 2025-09-24 | 227228 | 235584 | 175095 | Complete
PRJ038 | Business Case / Seed Funding | 2025-09-24 | 2025-10-09 | 2025-09-24 | 2025-10-09 | 227228 | 257005 | 158265 | Complete
PRJ038 | Design | 2025-10-09 | 2025-10-24 | 2025-10-09 | 2025-10-24 | 227228 | 254398 | 56216 | Complete
PRJ038 | Business Case / Full Funding | 2025-10-24 | 2025-11-08 | 2025-10-24 | 2025-11-08 | 227228 | 208648 | 226183 | Complete
PRJ038 | Build | 2025-11-08 | 2025-11-23 | 2025-11-08 | 2025-11-23 | 227228 | 255878 | 167750 | Complete
PRJ038 | Testing | 2025-11-23 | 2025-12-08 | 2025-11-23 | 2025-12-08 | 227228 | 247996 | 8437 | Complete
PRJ038 | Deployment | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-23 | 227228 | 260237 | 226638 | Complete
PRJ038 | Handover | 2025-12-23 | 2026-01-07 | 2025-12-23 | 2026-01-07 | 227228 | 238485 | 146120 | Complete
PRJ039 | Discovery | 2025-11-14 | 2025-11-29 | 2025-11-14 | 2025-11-29 | 390651 | 359457 | 226185 | Complete
PRJ039 | Business Case / Seed Funding | 2025-11-29 | 2025-12-14 | 2025-11-29 | 2025-12-14 | 390651 | 444033 | 110958 | Complete
PRJ039 | Design | 2025-12-14 | 2025-12-29 | 2025-12-14 | 2025-12-29 | 390651 | 355662 | 14603 | Complete
PRJ039 | Business Case / Full Funding | 2025-12-29 | 2026-01-13 | 2025-12-29 | 2026-01-13 | 390651 | 401160 | 266757 | Complete
PRJ039 | Build | 2026-01-13 | 2026-01-28 | 2026-01-13 | 2026-01-28 | 390651 | 393729 | 124457 | Complete
PRJ039 | Testing | 2026-01-28 | 2026-02-12 | 2026-01-28 | 2026-02-12 | 390651 | 434583 | 398479 | Complete
PRJ039 | Deployment | 2026-02-12 | 2026-02-27 | 2026-02-12 | 2026-02-27 | 390651 | 353680 | 22706 | Complete
PRJ039 | Handover | 2026-02-27 | 2026-03-14 | 2026-02-27 | 2026-03-14 | 390651 | 427139 | 332808 | Complete
PRJ040 | Discovery | 2025-02-06 | 2025-04-02 | 2025-02-06 | 2025-04-02 | 211652 | 218753 | 191188 | Complete
PRJ040 | Business Case / Seed Funding | 2025-04-02 | 2025-05-27 | 2025-04-02 | 2025-05-27 | 211652 | 226571 | 163992 | Complete
PRJ040 | Design | 2025-05-27 | 2025-07-21 | 2025-05-27 | 2025-07-21 | 211652 | 219721 | 11587 | Complete
PRJ040 | Business Case / Full Funding | 2025-07-21 | 2025-09-14 | 2025-07-21 | 2025-09-14 | 211652 | 231002 | 154551 | Complete
PRJ040 | Build | 2025-09-14 | 2025-11-08 | 2025-09-14 | 2025-11-08 | 211652 | 213225 | 94857 | Complete
PRJ040 | Testing | 2025-11-08 | 2026-01-02 | 2025-11-08 | 2026-01-02 | 211652 | 197777 | 97328 | Complete
PRJ040 | Deployment | 2026-01-02 | 2026-02-26 | 2026-01-02 | 2026-02-26 | 211652 | 237958 | 218354 | Complete
PRJ040 | Handover | 2026-02-26 | 2026-04-22 | 2026-02-26 | 2026-04-22 | 211652 | 209944 | 43035 | Complete

## ProjectBrief
Project ID | Portfolio / Workstream | Sponsor | Business Owner | Business Solution Manager | Strategic Alignment | Background and Context | Opportunity / Problem Statement | Objective | In Scope | Out of Scope | Assumptions & Constraints | Key Metrics / Success Measures | Approval Type | Funding Ask | Funding Source | Resource Ask | Estimate Commentary | P&L Benefits Commentary | Delivery Milestones | Project Risks | Dependencies
PRJ001
PRJ002
PRJ003
PRJ004
PRJ005
PRJ006
PRJ007
PRJ008
PRJ009
PRJ010
PRJ011
PRJ012
PRJ013
PRJ014
PRJ015
PRJ016
PRJ017
PRJ018
PRJ019
PRJ020
PRJ021
PRJ022
PRJ023
PRJ024
PRJ025
PRJ026
PRJ027
PRJ028
PRJ029
PRJ030
PRJ031
PRJ032
PRJ033
PRJ034
PRJ035
PRJ036
PRJ037
PRJ038
PRJ039
PRJ040

## ProjectLinks
Project ID | Title | Type | URL | Added By | Added On

## _Stages (hidden)
Discovery
Business Case / Seed Funding
Design
Business Case / Full Funding
Build
Testing
Deployment
Handover

## FYAllocation
Project ID | Project Name | FY | Budget % | Forecast % | Budget Amount | Forecast Amount | Notes
PRJ001 | Customer Portal | FY25 | 50 | 50 | 1296882 | 1203668 | Auto-split from Projects.Financial Year — edit to revise
PRJ001 | Customer Portal | FY26 | 50 | 50 | 1296882 | 1203668 | Auto-split from Projects.Financial Year — edit to revise
PRJ002 | Cloud Migration | FY25 | 100 | 100 | 1851915 | 2065964 | Auto-split from Projects.Financial Year — edit to revise
PRJ003 | Data Platform | FY25 | 50 | 50 | 1947576 | 2220804 | Auto-split from Projects.Financial Year — edit to revise
PRJ003 | Data Platform | FY26 | 50 | 50 | 1947576 | 2220804 | Auto-split from Projects.Financial Year — edit to revise
PRJ004 | AI Assistant | FY25 | 33.3 | 33.3 | 514569 | 606074 | Auto-split from Projects.Financial Year — edit to revise
PRJ004 | AI Assistant | FY26 | 33.3 | 33.3 | 514569 | 606074 | Auto-split from Projects.Financial Year — edit to revise
PRJ004 | AI Assistant | FY27 | 33.3 | 33.3 | 514569 | 606074 | Auto-split from Projects.Financial Year — edit to revise
PRJ005 | Network Refresh | FY25 | 33.3 | 33.3 | 554848 | 581765 | Auto-split from Projects.Financial Year — edit to revise
PRJ005 | Network Refresh | FY26 | 33.3 | 33.3 | 554848 | 581765 | Auto-split from Projects.Financial Year — edit to revise
PRJ005 | Network Refresh | FY27 | 33.3 | 33.3 | 554848 | 581765 | Auto-split from Projects.Financial Year — edit to revise
PRJ006 | Cyber Security Program | FY25 | 50 | 50 | 828831 | 852316 | Auto-split from Projects.Financial Year — edit to revise
PRJ006 | Cyber Security Program | FY26 | 50 | 50 | 828831 | 852316 | Auto-split from Projects.Financial Year — edit to revise
PRJ007 | CRM Upgrade | FY25 | 50 | 50 | 1775338 | 1720411 | Auto-split from Projects.Financial Year — edit to revise
PRJ007 | CRM Upgrade | FY26 | 50 | 50 | 1775338 | 1720411 | Auto-split from Projects.Financial Year — edit to revise
PRJ008 | Mobile App | FY25 | 100 | 100 | 3682125 | 3273975 | Auto-split from Projects.Financial Year — edit to revise
PRJ009 | ERP Modernisation | FY26 | 100 | 100 | 1133721 | 1047705 | Auto-split from Projects.Financial Year — edit to revise
PRJ010 | Workforce Enablement | FY25 | 50 | 50 | 1197458 | 1042514 | Auto-split from Projects.Financial Year — edit to revise
PRJ010 | Workforce Enablement | FY26 | 50 | 50 | 1197458 | 1042514 | Auto-split from Projects.Financial Year — edit to revise
PRJ011 | IoT Initiative | FY25 | 50 | 50 | 233936 | 232505 | Auto-split from Projects.Financial Year — edit to revise
PRJ011 | IoT Initiative | FY26 | 50 | 50 | 233936 | 232505 | Auto-split from Projects.Financial Year — edit to revise
PRJ012 | Analytics Platform | FY25 | 33.3 | 33.3 | 634750 | 719049 | Auto-split from Projects.Financial Year — edit to revise
PRJ012 | Analytics Platform | FY26 | 33.3 | 33.3 | 634750 | 719049 | Auto-split from Projects.Financial Year — edit to revise
PRJ012 | Analytics Platform | FY27 | 33.3 | 33.3 | 634750 | 719049 | Auto-split from Projects.Financial Year — edit to revise
PRJ013 | API Gateway | FY25 | 33.3 | 33.3 | 1314235 | 1326395 | Auto-split from Projects.Financial Year — edit to revise
PRJ013 | API Gateway | FY26 | 33.3 | 33.3 | 1314235 | 1326395 | Auto-split from Projects.Financial Year — edit to revise
PRJ013 | API Gateway | FY27 | 33.3 | 33.3 | 1314235 | 1326395 | Auto-split from Projects.Financial Year — edit to revise
PRJ014 | Identity Mgmt | FY25 | 50 | 50 | 1189146 | 1076298 | Auto-split from Projects.Financial Year — edit to revise
PRJ014 | Identity Mgmt | FY26 | 50 | 50 | 1189146 | 1076298 | Auto-split from Projects.Financial Year — edit to revise
PRJ015 | Service Desk | FY25 | 50 | 50 | 666921 | 640220 | Auto-split from Projects.Financial Year — edit to revise
PRJ015 | Service Desk | FY26 | 50 | 50 | 666921 | 640220 | Auto-split from Projects.Financial Year — edit to revise
PRJ016 | Infrastructure Upg | FY25 | 50 | 50 | 1767685 | 1600128 | Auto-split from Projects.Financial Year — edit to revise
PRJ016 | Infrastructure Upg | FY26 | 50 | 50 | 1767685 | 1600128 | Auto-split from Projects.Financial Year — edit to revise
PRJ017 | App Modernisation | FY25 | 50 | 50 | 1449344 | 1365854 | Auto-split from Projects.Financial Year — edit to revise
PRJ017 | App Modernisation | FY26 | 50 | 50 | 1449344 | 1365854 | Auto-split from Projects.Financial Year — edit to revise
PRJ018 | RPA Program | FY25 | 50 | 50 | 883990 | 1024621 | Auto-split from Projects.Financial Year — edit to revise
PRJ018 | RPA Program | FY26 | 50 | 50 | 883990 | 1024621 | Auto-split from Projects.Financial Year — edit to revise
PRJ019 | Vendor Mgmt | FY25 | 50 | 50 | 250448 | 248502 | Auto-split from Projects.Financial Year — edit to revise
PRJ019 | Vendor Mgmt | FY26 | 50 | 50 | 250448 | 248502 | Auto-split from Projects.Financial Year — edit to revise
PRJ020 | Process Automation | FY25 | 100 | 100 | 3501450 | 3976966 | Auto-split from Projects.Financial Year — edit to revise
PRJ021 | Data Warehouse | FY25 | 100 | 100 | 3926484 | 3496022 | Auto-split from Projects.Financial Year — edit to revise
PRJ022 | DevOps Tools | FY25 | 50 | 50 | 1432132 | 1487208 | Auto-split from Projects.Financial Year — edit to revise
PRJ022 | DevOps Tools | FY26 | 50 | 50 | 1432132 | 1487208 | Auto-split from Projects.Financial Year — edit to revise
PRJ023 | Workforce Portal | FY25 | 50 | 50 | 1409556 | 1526162 | Auto-split from Projects.Financial Year — edit to revise
PRJ023 | Workforce Portal | FY26 | 50 | 50 | 1409556 | 1526162 | Auto-split from Projects.Financial Year — edit to revise
PRJ024 | Process Mining | FY25 | 33.3 | 33.3 | 311145 | 351161 | Auto-split from Projects.Financial Year — edit to revise
PRJ024 | Process Mining | FY26 | 33.3 | 33.3 | 311145 | 351161 | Auto-split from Projects.Financial Year — edit to revise
PRJ024 | Process Mining | FY27 | 33.3 | 33.3 | 311145 | 351161 | Auto-split from Projects.Financial Year — edit to revise
PRJ025 | Customer Insights | FY25 | 33.3 | 33.3 | 625374 | 688800 | Auto-split from Projects.Financial Year — edit to revise
PRJ025 | Customer Insights | FY26 | 33.3 | 33.3 | 625374 | 688800 | Auto-split from Projects.Financial Year — edit to revise
PRJ025 | Customer Insights | FY27 | 33.3 | 33.3 | 625374 | 688800 | Auto-split from Projects.Financial Year — edit to revise
PRJ026 | ERP Modernisation 2 | FY25 | 50 | 50 | 1351776 | 1598494 | Auto-split from Projects.Financial Year — edit to revise
PRJ026 | ERP Modernisation 2 | FY26 | 50 | 50 | 1351776 | 1598494 | Auto-split from Projects.Financial Year — edit to revise
PRJ027 | Cyber Program | FY25 | 50 | 50 | 907752 | 878292 | Auto-split from Projects.Financial Year — edit to revise
PRJ027 | Cyber Program | FY26 | 50 | 50 | 907752 | 878292 | Auto-split from Projects.Financial Year — edit to revise
PRJ028 | Mobile App 2 | FY25 | 50 | 50 | 809480 | 693592 | Auto-split from Projects.Financial Year — edit to revise
PRJ028 | Mobile App 2 | FY26 | 50 | 50 | 809480 | 693592 | Auto-split from Projects.Financial Year — edit to revise
PRJ029 | Analytics Platform 2 | FY25 | 50 | 50 | 997002 | 1125964 | Auto-split from Projects.Financial Year — edit to revise
PRJ029 | Analytics Platform 2 | FY26 | 50 | 50 | 997002 | 1125964 | Auto-split from Projects.Financial Year — edit to revise
PRJ030 | Service Desk 2 | FY25 | 50 | 50 | 557305 | 539541 | Auto-split from Projects.Financial Year — edit to revise
PRJ030 | Service Desk 2 | FY26 | 50 | 50 | 557305 | 539541 | Auto-split from Projects.Financial Year — edit to revise
PRJ031 | Quality Mgmt | FY25 | 50 | 50 | 438754 | 392324 | Auto-split from Projects.Financial Year — edit to revise
PRJ031 | Quality Mgmt | FY26 | 50 | 50 | 438754 | 392324 | Auto-split from Projects.Financial Year — edit to revise
PRJ032 | Compliance Hub | FY25 | 33.3 | 33.3 | 1240887 | 1217753 | Auto-split from Projects.Financial Year — edit to revise
PRJ032 | Compliance Hub | FY26 | 33.3 | 33.3 | 1240887 | 1217753 | Auto-split from Projects.Financial Year — edit to revise
PRJ032 | Compliance Hub | FY27 | 33.3 | 33.3 | 1240887 | 1217753 | Auto-split from Projects.Financial Year — edit to revise
PRJ033 | Risk Platform | FY25 | 33.3 | 33.3 | 515075 | 590972 | Auto-split from Projects.Financial Year — edit to revise
PRJ033 | Risk Platform | FY26 | 33.3 | 33.3 | 515075 | 590972 | Auto-split from Projects.Financial Year — edit to revise
PRJ033 | Risk Platform | FY27 | 33.3 | 33.3 | 515075 | 590972 | Auto-split from Projects.Financial Year — edit to revise
PRJ034 | Treasury Sys | FY25 | 33.3 | 33.3 | 452329 | 428639 | Auto-split from Projects.Financial Year — edit to revise
PRJ034 | Treasury Sys | FY26 | 33.3 | 33.3 | 452329 | 428639 | Auto-split from Projects.Financial Year — edit to revise
PRJ034 | Treasury Sys | FY27 | 33.3 | 33.3 | 452329 | 428639 | Auto-split from Projects.Financial Year — edit to revise
PRJ035 | Payroll Cloud | FY25 | 50 | 50 | 1766210 | 1619384 | Auto-split from Projects.Financial Year — edit to revise
PRJ035 | Payroll Cloud | FY26 | 50 | 50 | 1766210 | 1619384 | Auto-split from Projects.Financial Year — edit to revise
PRJ036 | HR Self-Service | FY25 | 100 | 100 | 2258545 | 2354840 | Auto-split from Projects.Financial Year — edit to revise
PRJ037 | SAP S/4HANA | FY25 | 100 | 100 | 1203695 | 1118978 | Auto-split from Projects.Financial Year — edit to revise
PRJ038 | Salesforce CRM | FY25 | 50 | 50 | 908914 | 1071948 | Auto-split from Projects.Financial Year — edit to revise
PRJ038 | Salesforce CRM | FY26 | 50 | 50 | 908914 | 1071948 | Auto-split from Projects.Financial Year — edit to revise
PRJ039 | M365 Rollout | FY25 | 50 | 50 | 1562602 | 1490838 | Auto-split from Projects.Financial Year — edit to revise
PRJ039 | M365 Rollout | FY26 | 50 | 50 | 1562602 | 1490838 | Auto-split from Projects.Financial Year — edit to revise
PRJ040 | Zero-Trust Net | FY25 | 50 | 50 | 846610 | 729290 | Auto-split from Projects.Financial Year — edit to revise
PRJ040 | Zero-Trust Net | FY26 | 50 | 50 | 846610 | 729290 | Auto-split from Projects.Financial Year — edit to revise