## Projects
Project ID | Project Name | Program | Theme | Portfolio Category | Business Unit | Sponsor | Delivery Lead | PM | Priority | Investment Type | Delivery Method | Funding Type | Governance Channel | Financial Year | Start Date | End Date | Go Live Date | Progress % | Approved Funding | CAPEX | OPEX | Total Funding | Actual Spend | Forecast At Completion | Remaining Budget | Forecast Variance | Contingency | Benefits Forecast | Benefits Realised | Benefits Remaining | Benefit Realisation % | Budget | Actual Cost | Forecast | Status | RAG
PRJ001 | Customer Portal | Digital Transformation | Digital & Applications | Business Strategic | Wholesale | CTO | Alex Brown | John Smith | P2 - High | Transform | Hybrid | CAPEX | Channel B (>$200K) | FY25-26 | 2025-02-14 | 2026-03-13 | 2026-02-14 | 74 | 2593765 | 1319588 | 1274177 | 2593765 | 937070 | 2407335 | 1656695 | 186430 | 259376 | 6550938 | 2659810 | 3891128 | 0.40602 | 2593765 | 937070 | 2407335 | Completed | Green
PRJ002 | Cloud Migration | Digital Transformation | Cyber Security | CAPEX | Retail | COO | Carlos Diaz | Mike Johnson | P3 - Medium | Run | Agile | CAPEX | Channel B (>$200K) | FY25 | 2025-03-21 | 2025-10-07 | 2025-08-20 | 40 | 1851915 | 1106272 | 745643 | 1851915 | 1714568 | 2065964 | 137347 | -214049 | 185192 | 2754514 | 698458 | 2056056 | 0.25357 | 1851915 | 1714568 | 2065964 | Pipeline | Green
PRJ003 | Data Platform | Cyber Security | Data & Analytics | Business Strategic | Retail | CFO | Carlos Diaz | John Smith | P4 - Low | Grow | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-04-09 | 2026-07-03 | 2026-06-29 | 78 | 3895151 | 2463632 | 1431519 | 3895151 | 2432283 | 4441608 | 1462868 | -546457 | 389515 | 9010791 | 4658796 | 4351995 | 0.51702 | 3895151 | 2432283 | 4441608 | Active | Green
PRJ004 | AI Assistant | Data & AI | Data & Analytics | IT Strategic | HR | CTO | Jane Doe | Priya Patel | P3 - Medium | Run | Waterfall | OPEX | Channel B (>$200K) | FY25-27 | 2025-10-01 | 2027-01-07 | 2026-12-23 | 26 | 1543706 | 885049 | 658657 | 1543706 | 545899 | 1818222 | 997807 | -274516 | 154371 | 3653124 | 1335139 | 2317985 | 0.36548 | 1543706 | 545899 | 1818222 | Active | Green
PRJ005 | Network Refresh | Cyber Security | Data & Analytics | Unfunded | Wholesale | CFO | Priya Patel | Alex Brown | P3 - Medium | Transform | Hybrid | Unfunded | Channel B (>$200K) | FY25-27 | 2025-07-22 | 2027-01-15 | 2026-11-18 | 68 | 1664543 | 870832 | 793711 | 1664543 | 1610411 | 1745295 | 54132 | -80752 | 166454 | 4148450 | 529242 | 3619208 | 0.12758 | 1664543 | 1610411 | 1745295 | Completed | Amber
PRJ006 | Cyber Security Program | Customer Experience | Infrastructure | Unfunded | Technology | CMO | Alex Brown | Sarah Lee | P3 - Medium | Transform | Waterfall | Unfunded | Channel B (>$200K) | FY25-26 | 2025-03-20 | 2026-05-05 | 2026-04-25 | 19 | 1657662 | 956077 | 701585 | 1657662 | 1736667 | 1704631 | -79005 | -46969 | 165766 | 2260449 | 63902 | 2196547 | 0.02827 | 1657662 | 1736667 | 1704631 | Active | Red
PRJ007 | CRM Upgrade | Digital Transformation | Data & Analytics | IT Strategic | Marketing | CTO | Alex Brown | Jane Doe | P2 - High | Grow | Waterfall | Mixed | Channel B (>$200K) | FY25-26 | 2025-05-15 | 2026-12-23 | 2026-11-21 | 5 | 3550675 | 2708481 | 842194 | 3550675 | 2947660 | 3440822 | 603015 | 109853 | 355068 | 6136632 | 582334 | 5554298 | 0.094895 | 3550675 | 2947660 | 3440822 | Pipeline | Amber
PRJ008 | Mobile App | Data & AI | Infrastructure | Business Strategic | Marketing | CTO | Carlos Diaz | Jane Doe | P2 - High | Transform | Agile | CAPEX | Channel B (>$200K) | FY25 | 2025-05-03 | 2025-08-30 | 2025-08-15 | 44 | 3682125 | 2612949 | 1069176 | 3682125 | 2077364 | 3273975 | 1604761 | 408150 | 368212 | 6824323 | 4034491 | 2789832 | 0.59119 | 3682125 | 2077364 | 3273975 | Pipeline | Green
PRJ009 | ERP Modernisation | Customer Experience | Cyber Security | CAPEX | Retail | CFO | Jane Doe | John Smith | P3 - Medium | Run | Hybrid | OPEX | Channel B (>$200K) | FY26 | 2026-01-01 | 2026-09-07 | 2026-08-13 | 30 | 1133721 | 913044 | 220677 | 1133721 | 569106 | 1047705 | 564615 | 86016 | 113372 | 2461006 | 1077819 | 1383187 | 0.43796 | 1133721 | 569106 | 1047705 | Pipeline | Green
PRJ010 | Workforce Enablement | Data & AI | Digital & Applications | CAPEX | Finance | CFO | Priya Patel | Alex Brown | P4 - Low | Run | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-02-06 | 2026-01-25 | 2026-01-10 | 47 | 2394916 | 1203486 | 1191430 | 2394916 | 1849950 | 2085028 | 544966 | 309888 | 239492 | 3164452 | 59643 | 3104809 | 0.018848 | 2394916 | 1849950 | 2085028 | Completed | Green
PRJ011 | IoT Initiative | Cloud Migration | Infrastructure | Unfunded | Wholesale | CFO | Jane Doe | Alex Brown | P4 - Low | Run | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-11-27 | 2026-04-16 | 2026-04-13 | 88 | 467871 | 341847 | 126024 | 467871 | 204264 | 465010 | 263607 | 2861 | 46787 | 1288941 | 41894 | 1247047 | 0.032503 | 467871 | 204264 | 465010 | Active | Green
PRJ012 | Analytics Platform | Cyber Security | Cyber Security | Business Strategic | Technology | CMO | Jane Doe | Carlos Diaz | P4 - Low | Run | Waterfall | CAPEX | Channel B (>$200K) | FY25-27 | 2025-10-04 | 2027-03-06 | 2027-03-06 | 88 | 1904249 | 1534958 | 369291 | 1904249 | 326799 | 2157148 | 1577450 | -252899 | 190425 | 5219052 | 306594 | 4912458 | 0.058745 | 1904249 | 326799 | 2157148 | Completed | Green
PRJ013 | API Gateway | Cloud Migration | Digital & Applications | IT Strategic | Retail | CTO | Priya Patel | Alex Brown | P1 - Critical | Transform | Agile | CAPEX | Channel B (>$200K) | FY25-27 | 2025-12-05 | 2027-03-07 | 2027-02-04 | 76 | 3942704 | 2337318 | 1605386 | 3942704 | 3331061 | 3979186 | 611643 | -36482 | 394270 | 7733273 | 4441919 | 3291354 | 0.57439 | 3942704 | 3331061 | 3979186 | Active | Green
PRJ014 | Identity Mgmt | Digital Transformation | Business Transformation | IT Strategic | Wholesale | CTO | Alex Brown | John Smith | P1 - Critical | Grow | Hybrid | OPEX | Channel B (>$200K) | FY25-26 | 2025-02-05 | 2026-03-06 | 2026-03-02 | 28 | 2378293 | 1607720 | 770573 | 2378293 | 2164446 | 2152596 | 213847 | 225697 | 237829 | 6966976 | 334881 | 6632095 | 0.048067 | 2378293 | 2164446 | 2152596 | Pipeline | Amber
PRJ015 | Service Desk | Data & AI | Business Transformation | Business Strategic | Finance | CIO | John Smith | Alex Brown | P2 - High | Transform | Agile | CAPEX | Channel B (>$200K) | FY25-26 | 2025-06-03 | 2026-04-23 | 2026-04-03 | 87 | 1333842 | 788658 | 545184 | 1333842 | 982027 | 1280441 | 351815 | 53401 | 133384 | 2238328 | 175769 | 2062559 | 0.078527 | 1333842 | 982027 | 1280441 | Active | Green
PRJ016 | Infrastructure Upg | Digital Transformation | Digital & Applications | CAPEX | Operations | CIO | John Smith | Priya Patel | P2 - High | Grow | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-12-01 | 2026-11-26 | 2026-11-26 | 83 | 3535370 | 2855676 | 679694 | 3535370 | 1594631 | 3200257 | 1940739 | 335113 | 353537 | 9548118 | 4030489 | 5517629 | 0.42212 | 3535370 | 1594631 | 3200257 | Pipeline | Green
PRJ017 | App Modernisation | Digital Transformation | Data & Analytics | CAPEX | Marketing | CFO | Priya Patel | Mike Johnson | P2 - High | Transform | Agile | CAPEX | Channel B (>$200K) | FY25-26 | 2025-02-17 | 2026-04-07 | 2026-03-11 | 11 | 2898688 | 1655902 | 1242786 | 2898688 | 2036404 | 2731707 | 862284 | 166981 | 289869 | 6027408 | 3274099 | 2753309 | 0.5432 | 2898688 | 2036404 | 2731707 | Pipeline | Red
PRJ018 | RPA Program | Cyber Security | Infrastructure | Unfunded | Operations | COO | Carlos Diaz | Carlos Diaz | P1 - Critical | Grow | Waterfall | Unfunded | Channel B (>$200K) | FY25-26 | 2025-10-26 | 2026-11-02 | 2026-10-24 | 52 | 1767979 | 889973 | 878006 | 1767979 | 303176 | 2049242 | 1464803 | -281263 | 176798 | 4998203 | 1636183 | 3362020 | 0.32735 | 1767979 | 303176 | 2049242 | Active | Red
PRJ019 | Vendor Mgmt | Digital Transformation | Digital & Applications | IT Strategic | HR | COO | Carlos Diaz | Sarah Lee | P2 - High | Grow | Waterfall | OPEX | Channel B (>$200K) | FY25-26 | 2025-03-25 | 2026-11-04 | 2026-09-14 | 35 | 500895 | 387212 | 113683 | 500895 | 470805 | 497004 | 30090 | 3891 | 50090 | 1160669 | 107631 | 1053038 | 0.092732 | 500895 | 470805 | 497004 | Active | Amber
PRJ020 | Process Automation | Cloud Migration | Data & Analytics | IT Strategic | Marketing | CIO | Carlos Diaz | Mike Johnson | P3 - Medium | Transform | Hybrid | OPEX | Channel B (>$200K) | FY25 | 2025-04-25 | 2025-08-05 | 2025-06-24 | 34 | 3501450 | 2802937 | 698513 | 3501450 | 1090044 | 3976966 | 2411406 | -475516 | 350145 | 7102852 | 1300635 | 5802217 | 0.18311 | 3501450 | 1090044 | 3976966 | Completed | Red
PRJ021 | Data Warehouse | Cloud Migration | Data & Analytics | Unfunded | Technology | CTO | Alex Brown | John Smith | P4 - Low | Transform | Waterfall | Unfunded | Channel B (>$200K) | FY25 | 2025-01-20 | 2025-06-14 | 2025-05-07 | 38 | 3926484 | 2700147 | 1226337 | 3926484 | 3896153 | 3496022 | 30331 | 430462 | 392648 | 11570253 | 1239645 | 10330608 | 0.10714 | 3926484 | 3896153 | 3496022 | Active | Green
PRJ022 | DevOps Tools | Cloud Migration | Business Transformation | Business Strategic | Operations | CIO | Priya Patel | Mike Johnson | P3 - Medium | Transform | Agile | Mixed | Channel B (>$200K) | FY25-26 | 2025-04-11 | 2026-01-12 | 2025-12-16 | 90 | 2864263 | 1433827 | 1430436 | 2864263 | 2804962 | 2974417 | 59301 | -110154 | 286426 | 7146262 | 3181302 | 3964960 | 0.44517 | 2864263 | 2804962 | 2974417 | Active | Amber
PRJ023 | Workforce Portal | Customer Experience | Infrastructure | Unfunded | Operations | COO | Jane Doe | Sarah Lee | P3 - Medium | Grow | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-11-12 | 2026-11-28 | 2026-11-09 | 27 | 2819113 | 1956589 | 862524 | 2819113 | 795689 | 3052325 | 2023424 | -233212 | 281911 | 5306872 | 2382153 | 2924719 | 0.44888 | 2819113 | 795689 | 3052325 | Completed | Red
PRJ024 | Process Mining | Cyber Security | Data & Analytics | CAPEX | Wholesale | CFO | Jane Doe | John Smith | P1 - Critical | Run | Agile | CAPEX | Channel B (>$200K) | FY25-27 | 2025-12-06 | 2027-01-24 | 2026-12-16 | 70 | 933435 | 621308 | 312127 | 933435 | 892478 | 1053483 | 40957 | -120048 | 93344 | 1405235 | 71495 | 1333740 | 0.050878 | 933435 | 892478 | 1053483 | Pipeline | Green
PRJ025 | Customer Insights | Cyber Security | Digital & Applications | Business Strategic | Marketing | CTO | Sarah Lee | John Smith | P2 - High | Run | Agile | OPEX | Channel B (>$200K) | FY25-27 | 2025-12-02 | 2027-02-17 | 2027-02-17 | 23 | 1876123 | 1519937 | 356186 | 1876123 | 1213640 | 2066401 | 662483 | -190278 | 187612 | 3548051 | 850793 | 2697258 | 0.23979 | 1876123 | 1213640 | 2066401 | Active | Amber
PRJ026 | ERP Modernisation 2 | Cyber Security | Cyber Security | Unfunded | Technology | COO | Carlos Diaz | Jane Doe | P3 - Medium | Transform | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-09-16 | 2026-07-21 | 2026-05-29 | 97 | 2703553 | 2286563 | 416990 | 2703553 | 1799700 | 3196989 | 903853 | -493436 | 270355 | 7582295 | 2787186 | 4795109 | 0.36759 | 2703553 | 1799700 | 3196989 | Active | Green
PRJ027 | Cyber Program | Cyber Security | Infrastructure | IT Strategic | Technology | CMO | Mike Johnson | Alex Brown | P4 - Low | Grow | Waterfall | Mixed | Channel B (>$200K) | FY25-26 | 2025-04-29 | 2026-02-09 | 2025-12-27 | 24 | 1815503 | 1361156 | 454347 | 1815503 | 585988 | 1756584 | 1229515 | 58919 | 181550 | 5096931 | 246419 | 4850512 | 0.048347 | 1815503 | 585988 | 1756584 | Active | Amber
PRJ028 | Mobile App 2 | Data & AI | Business Transformation | CAPEX | HR | CTO | Carlos Diaz | Alex Brown | P2 - High | Grow | Waterfall | OPEX | Channel B (>$200K) | FY25-26 | 2025-01-04 | 2026-07-30 | 2026-07-08 | 66 | 1618960 | 1245674 | 373286 | 1618960 | 1616951 | 1387184 | 2009 | 231776 | 161896 | 4509098 | 1557507 | 2951591 | 0.34541 | 1618960 | 1616951 | 1387184 | Active | Amber
PRJ029 | Analytics Platform 2 | Customer Experience | Business Transformation | Unfunded | HR | CIO | John Smith | Priya Patel | P4 - Low | Run | Agile | Unfunded | Channel B (>$200K) | FY25-26 | 2025-11-15 | 2026-11-13 | 2026-11-12 | 21 | 1994004 | 1268386 | 725618 | 1994004 | 1466450 | 2251928 | 527554 | -257924 | 199400 | 4992042 | 2517504 | 2474538 | 0.5043 | 1994004 | 1466450 | 2251928 | Active | Green
PRJ030 | Service Desk 2 | Digital Transformation | Business Transformation | Unfunded | Retail | COO | Jane Doe | Priya Patel | P1 - Critical | Transform | Waterfall | Unfunded | Channel B (>$200K) | FY25-26 | 2025-05-10 | 2026-10-09 | 2026-10-04 | 58 | 1114610 | 685010 | 429600 | 1114610 | 592933 | 1079082 | 521677 | 35528 | 111461 | 3102352 | 517950 | 2584402 | 0.16695 | 1114610 | 592933 | 1079082 | Active | Green
PRJ031 | Quality Mgmt | Customer Experience | Business Transformation | CAPEX | HR | CIO | Carlos Diaz | Carlos Diaz | P2 - High | Grow | Waterfall | CAPEX | Channel B (>$200K) | FY25-26 | 2025-08-27 | 2026-11-18 | 2026-11-02 | 32 | 877507 | 445013 | 432494 | 877507 | 214781 | 784647 | 662726 | 92860 | 87751 | 2110427 | 714130 | 1396297 | 0.33838 | 877507 | 214781 | 784647 | Pipeline | Green
PRJ032 | Compliance Hub | Cloud Migration | Business Transformation | IT Strategic | Marketing | CIO | Carlos Diaz | Alex Brown | P1 - Critical | Grow | Hybrid | CAPEX | Channel B (>$200K) | FY25-27 | 2025-12-20 | 2027-05-19 | 2027-04-09 | 80 | 3722660 | 2611553 | 1111107 | 3722660 | 3583525 | 3653260 | 139135 | 69400 | 372266 | 10775787 | 1282296 | 9493491 | 0.119 | 3722660 | 3583525 | 3653260 | Completed | Red
PRJ033 | Risk Platform | Cyber Security | Cyber Security | Unfunded | Wholesale | CTO | Priya Patel | Mike Johnson | P4 - Low | Grow | Agile | Unfunded | Channel B (>$200K) | FY25-27 | 2025-11-22 | 2027-05-22 | 2027-03-30 | 51 | 1545226 | 1046251 | 498975 | 1545226 | 655438 | 1772917 | 889788 | -227691 | 154523 | 4141508 | 262254 | 3879254 | 0.063323 | 1545226 | 655438 | 1772917 | Pipeline | Green
PRJ034 | Treasury Sys | Data & AI | Data & Analytics | CAPEX | Wholesale | CMO | Jane Doe | Mike Johnson | P3 - Medium | Grow | Agile | CAPEX | Channel B (>$200K) | FY25-27 | 2025-11-09 | 2027-01-15 | 2026-12-22 | 77 | 1356988 | 795091 | 561897 | 1356988 | 1340556 | 1285916 | 16432 | 71072 | 135699 | 2729505 | 1229057 | 1500448 | 0.45029 | 1356988 | 1340556 | 1285916 | Pipeline | Red
PRJ035 | Payroll Cloud | Data & AI | Infrastructure | Unfunded | Retail | COO | Jane Doe | Sarah Lee | P2 - High | Grow | Hybrid | Unfunded | Channel B (>$200K) | FY25-26 | 2025-05-04 | 2026-07-21 | 2026-06-21 | 76 | 3532419 | 2453360 | 1079059 | 3532419 | 2086939 | 3238768 | 1445480 | 293651 | 353242 | 5773530 | 1407915 | 4365615 | 0.24386 | 3532419 | 2086939 | 3238768 | Active | Amber
PRJ036 | HR Self-Service | Digital Transformation | Business Transformation | IT Strategic | Marketing | CFO | Jane Doe | Jane Doe | P4 - Low | Grow | Hybrid | OPEX | Channel B (>$200K) | FY25 | 2025-05-09 | 2025-12-03 | 2025-11-26 | 44 | 2258545 | 1401010 | 857535 | 2258545 | 2364245 | 2354840 | -105700 | -96295 | 225854 | 4140498 | 1127239 | 3013259 | 0.27225 | 2258545 | 2364245 | 2354840 | Pipeline | Amber
PRJ037 | SAP S/4HANA | Cloud Migration | Digital & Applications | Business Strategic | HR | CMO | John Smith | Carlos Diaz | P1 - Critical | Transform | Agile | Mixed | Channel B (>$200K) | FY25 | 2025-03-06 | 2025-10-22 | 2025-10-20 | 73 | 1203695 | 644198 | 559497 | 1203695 | 342345 | 1118978 | 861350 | 84717 | 120370 | 1833221 | 15562 | 1817659 | 0.0084889 | 1203695 | 342345 | 1118978 | Completed | Amber
PRJ038 | Salesforce CRM | Cyber Security | Business Transformation | Business Strategic | Operations | CIO | Jane Doe | John Smith | P4 - Low | Transform | Hybrid | CAPEX | Channel B (>$200K) | FY25-26 | 2025-09-09 | 2026-01-14 | 2025-12-09 | 56 | 1817828 | 1026214 | 791614 | 1817828 | 270507 | 2143896 | 1547321 | -326068 | 181783 | 3744567 | 1847080 | 1897487 | 0.49327 | 1817828 | 270507 | 2143896 | Pipeline | Green
PRJ039 | M365 Rollout | Cyber Security | Data & Analytics | Business Strategic | HR | CIO | Jane Doe | Jane Doe | P2 - High | Transform | Waterfall | CAPEX | Channel B (>$200K) | FY25-26 | 2025-11-14 | 2026-03-14 | 2026-02-03 | 77 | 3125205 | 1978668 | 1146537 | 3125205 | 3009820 | 2981676 | 115385 | 143529 | 312520 | 7060917 | 1816759 | 5244158 | 0.2573 | 3125205 | 3009820 | 2981676 | Active | Green
PRJ040 | Zero-Trust Net | Customer Experience | Digital & Applications | CAPEX | Technology | CIO | Alex Brown | Jane Doe | P2 - High | Grow | Waterfall | Mixed | Channel B (>$200K) | FY25-26 | 2025-02-06 | 2026-04-23 | 2026-04-09 | 63 | 1693219 | 1255149 | 438070 | 1693219 | 925203 | 1458579 | 768016 | 234640 | 169322 | 2909947 | 493617 | 2416330 | 0.16963 | 1693219 | 925203 | 1458579 | Active | Green

## Roadmap
Project ID | Month | Year | Phase | Status
PRJ001 | Mar | 2025 | Design | Completed
PRJ001 | Apr | 2025 | Build | Completed
PRJ001 | May | 2025 | Deploy | Completed
PRJ001 | Jun | 2025 | Deploy | Completed
PRJ001 | Jul | 2025 | Build | Completed
PRJ001 | Aug | 2025 | Test | Completed
PRJ001 | Sep | 2025 | Discovery | Completed
PRJ001 | Oct | 2025 | Test | Completed
PRJ001 | Nov | 2025 | Build | Completed
PRJ001 | Dec | 2025 | Test | Completed
PRJ001 | Jan | 2026 | Build | Completed
PRJ001 | Feb | 2026 | Deploy | Completed
PRJ001 | Mar | 2026 | Deploy | Completed
PRJ002 | Apr | 2025 | Test | Pipeline
PRJ002 | May | 2025 | Test | Pipeline
PRJ002 | Jun | 2025 | Discovery | Pipeline
PRJ002 | Jul | 2025 | Deploy | Pipeline
PRJ002 | Aug | 2025 | Discovery | Pipeline
PRJ002 | Sep | 2025 | Test | Pipeline
PRJ002 | Oct | 2025 | Build | Pipeline
PRJ003 | May | 2025 | Deploy | Active
PRJ003 | Jun | 2025 | Build | Active
PRJ003 | Jul | 2025 | Discovery | Active
PRJ003 | Aug | 2025 | Discovery | Active
PRJ003 | Sep | 2025 | Design | Active
PRJ003 | Oct | 2025 | Deploy | Active
PRJ003 | Nov | 2025 | Deploy | Active
PRJ003 | Dec | 2025 | Discovery | Active
PRJ003 | Jan | 2026 | Build | Active
PRJ003 | Feb | 2026 | Deploy | Active
PRJ003 | Mar | 2026 | Discovery | Active
PRJ003 | Apr | 2026 | Design | Active
PRJ003 | May | 2026 | Test | Active
PRJ003 | Jun | 2026 | Deploy | Active
PRJ003 | Jul | 2026 | Test | Active
PRJ004 | Oct | 2025 | Build | Active
PRJ004 | Nov | 2025 | Design | Active
PRJ004 | Dec | 2025 | Deploy | Active
PRJ004 | Jan | 2026 | Test | Active
PRJ004 | Feb | 2026 | Test | Active
PRJ004 | Mar | 2026 | Discovery | Active
PRJ004 | Apr | 2026 | Test | Active
PRJ004 | May | 2026 | Build | Active
PRJ004 | Jun | 2026 | Test | Active
PRJ004 | Jul | 2026 | Build | Active
PRJ004 | Aug | 2026 | Build | Active
PRJ004 | Sep | 2026 | Discovery | Active
PRJ004 | Oct | 2026 | Design | Active
PRJ004 | Nov | 2026 | Build | Active
PRJ004 | Dec | 2026 | Test | Active
PRJ004 | Jan | 2027 | Test | Active
PRJ005 | Aug | 2025 | Build | Completed
PRJ005 | Sep | 2025 | Test | Completed
PRJ005 | Oct | 2025 | Deploy | Completed
PRJ005 | Nov | 2025 | Discovery | Completed
PRJ005 | Dec | 2025 | Test | Completed
PRJ005 | Jan | 2026 | Discovery | Completed
PRJ005 | Feb | 2026 | Build | Completed
PRJ005 | Mar | 2026 | Build | Completed
PRJ005 | Apr | 2026 | Build | Completed
PRJ005 | May | 2026 | Discovery | Completed
PRJ005 | Jun | 2026 | Test | Completed
PRJ005 | Jul | 2026 | Deploy | Completed
PRJ005 | Aug | 2026 | Discovery | Completed
PRJ005 | Sep | 2026 | Deploy | Completed
PRJ005 | Oct | 2026 | Test | Completed
PRJ005 | Nov | 2026 | Test | Completed
PRJ005 | Dec | 2026 | Discovery | Completed
PRJ005 | Jan | 2027 | Design | Completed
PRJ006 | Apr | 2025 | Deploy | Active
PRJ006 | May | 2025 | Build | Active
PRJ006 | Jun | 2025 | Deploy | Active
PRJ006 | Jul | 2025 | Test | Active
PRJ006 | Aug | 2025 | Test | Active
PRJ006 | Sep | 2025 | Discovery | Active
PRJ006 | Oct | 2025 | Design | Active
PRJ006 | Nov | 2025 | Build | Active
PRJ006 | Dec | 2025 | Deploy | Active
PRJ006 | Jan | 2026 | Design | Active
PRJ006 | Feb | 2026 | Build | Active
PRJ006 | Mar | 2026 | Test | Active
PRJ006 | Apr | 2026 | Test | Active
PRJ006 | May | 2026 | Discovery | Active
PRJ007 | Jun | 2025 | Discovery | Pipeline
PRJ007 | Jul | 2025 | Deploy | Pipeline
PRJ007 | Aug | 2025 | Design | Pipeline
PRJ007 | Sep | 2025 | Design | Pipeline
PRJ007 | Oct | 2025 | Build | Pipeline
PRJ007 | Nov | 2025 | Deploy | Pipeline
PRJ007 | Dec | 2025 | Discovery | Pipeline
PRJ007 | Jan | 2026 | Deploy | Pipeline
PRJ007 | Feb | 2026 | Test | Pipeline
PRJ007 | Mar | 2026 | Discovery | Pipeline
PRJ007 | Apr | 2026 | Design | Pipeline
PRJ007 | May | 2026 | Discovery | Pipeline
PRJ007 | Jun | 2026 | Test | Pipeline
PRJ007 | Jul | 2026 | Discovery | Pipeline
PRJ007 | Aug | 2026 | Design | Pipeline
PRJ007 | Sep | 2026 | Test | Pipeline
PRJ007 | Oct | 2026 | Build | Pipeline
PRJ007 | Nov | 2026 | Deploy | Pipeline
PRJ007 | Dec | 2026 | Build | Pipeline
PRJ008 | Jun | 2025 | Test | Pipeline
PRJ008 | Jul | 2025 | Test | Pipeline
PRJ008 | Aug | 2025 | Test | Pipeline
PRJ009 | Jan | 2026 | Design | Pipeline
PRJ009 | Feb | 2026 | Test | Pipeline
PRJ009 | Mar | 2026 | Deploy | Pipeline
PRJ009 | Apr | 2026 | Design | Pipeline
PRJ009 | May | 2026 | Test | Pipeline
PRJ009 | Jun | 2026 | Design | Pipeline
PRJ009 | Jul | 2026 | Deploy | Pipeline
PRJ009 | Aug | 2026 | Deploy | Pipeline
PRJ009 | Sep | 2026 | Design | Pipeline
PRJ010 | Mar | 2025 | Discovery | Completed
PRJ010 | Apr | 2025 | Build | Completed
PRJ010 | May | 2025 | Test | Completed
PRJ010 | Jun | 2025 | Build | Completed
PRJ010 | Jul | 2025 | Deploy | Completed
PRJ010 | Aug | 2025 | Build | Completed
PRJ010 | Sep | 2025 | Discovery | Completed
PRJ010 | Oct | 2025 | Build | Completed
PRJ010 | Nov | 2025 | Build | Completed
PRJ010 | Dec | 2025 | Deploy | Completed
PRJ010 | Jan | 2026 | Deploy | Completed
PRJ011 | Dec | 2025 | Test | Active
PRJ011 | Jan | 2026 | Design | Active
PRJ011 | Feb | 2026 | Test | Active
PRJ011 | Mar | 2026 | Deploy | Active
PRJ011 | Apr | 2026 | Test | Active
PRJ012 | Nov | 2025 | Build | Completed
PRJ012 | Dec | 2025 | Build | Completed
PRJ012 | Jan | 2026 | Deploy | Completed
PRJ012 | Feb | 2026 | Deploy | Completed
PRJ012 | Mar | 2026 | Test | Completed
PRJ012 | Apr | 2026 | Test | Completed
PRJ012 | May | 2026 | Build | Completed
PRJ012 | Jun | 2026 | Design | Completed
PRJ012 | Jul | 2026 | Design | Completed
PRJ012 | Aug | 2026 | Deploy | Completed
PRJ012 | Sep | 2026 | Test | Completed
PRJ012 | Oct | 2026 | Design | Completed
PRJ012 | Nov | 2026 | Test | Completed
PRJ012 | Dec | 2026 | Discovery | Completed
PRJ012 | Jan | 2027 | Build | Completed
PRJ012 | Feb | 2027 | Test | Completed
PRJ012 | Mar | 2027 | Test | Completed
PRJ013 | Jan | 2026 | Test | Active
PRJ013 | Feb | 2026 | Design | Active
PRJ013 | Mar | 2026 | Test | Active
PRJ013 | Apr | 2026 | Discovery | Active
PRJ013 | May | 2026 | Design | Active
PRJ013 | Jun | 2026 | Deploy | Active
PRJ013 | Jul | 2026 | Deploy | Active
PRJ013 | Aug | 2026 | Build | Active
PRJ013 | Sep | 2026 | Discovery | Active
PRJ013 | Oct | 2026 | Test | Active
PRJ013 | Nov | 2026 | Discovery | Active
PRJ013 | Dec | 2026 | Deploy | Active
PRJ013 | Jan | 2027 | Test | Active
PRJ013 | Feb | 2027 | Discovery | Active
PRJ013 | Mar | 2027 | Design | Active
PRJ014 | Mar | 2025 | Test | Pipeline
PRJ014 | Apr | 2025 | Design | Pipeline
PRJ014 | May | 2025 | Discovery | Pipeline
PRJ014 | Jun | 2025 | Test | Pipeline
PRJ014 | Jul | 2025 | Build | Pipeline
PRJ014 | Aug | 2025 | Build | Pipeline
PRJ014 | Sep | 2025 | Deploy | Pipeline
PRJ014 | Oct | 2025 | Test | Pipeline
PRJ014 | Nov | 2025 | Discovery | Pipeline
PRJ014 | Dec | 2025 | Build | Pipeline
PRJ014 | Jan | 2026 | Deploy | Pipeline
PRJ014 | Feb | 2026 | Test | Pipeline
PRJ014 | Mar | 2026 | Build | Pipeline
PRJ015 | Jul | 2025 | Test | Active
PRJ015 | Aug | 2025 | Deploy | Active
PRJ015 | Sep | 2025 | Discovery | Active
PRJ015 | Oct | 2025 | Deploy | Active
PRJ015 | Nov | 2025 | Discovery | Active
PRJ015 | Dec | 2025 | Design | Active
PRJ015 | Jan | 2026 | Build | Active
PRJ015 | Feb | 2026 | Design | Active
PRJ015 | Mar | 2026 | Discovery | Active
PRJ015 | Apr | 2026 | Test | Active
PRJ016 | Dec | 2025 | Discovery | Pipeline
PRJ016 | Jan | 2026 | Discovery | Pipeline
PRJ016 | Feb | 2026 | Test | Pipeline
PRJ016 | Mar | 2026 | Design | Pipeline
PRJ016 | Apr | 2026 | Build | Pipeline
PRJ016 | May | 2026 | Discovery | Pipeline
PRJ016 | Jun | 2026 | Discovery | Pipeline
PRJ016 | Jul | 2026 | Build | Pipeline
PRJ016 | Aug | 2026 | Discovery | Pipeline
PRJ016 | Sep | 2026 | Build | Pipeline
PRJ016 | Oct | 2026 | Build | Pipeline
PRJ016 | Nov | 2026 | Build | Pipeline
PRJ017 | Mar | 2025 | Test | Pipeline
PRJ017 | Apr | 2025 | Design | Pipeline
PRJ017 | May | 2025 | Design | Pipeline
PRJ017 | Jun | 2025 | Deploy | Pipeline
PRJ017 | Jul | 2025 | Test | Pipeline
PRJ017 | Aug | 2025 | Deploy | Pipeline
PRJ017 | Sep | 2025 | Design | Pipeline
PRJ017 | Oct | 2025 | Design | Pipeline
PRJ017 | Nov | 2025 | Design | Pipeline
PRJ017 | Dec | 2025 | Discovery | Pipeline
PRJ017 | Jan | 2026 | Deploy | Pipeline
PRJ017 | Feb | 2026 | Test | Pipeline
PRJ017 | Mar | 2026 | Deploy | Pipeline
PRJ017 | Apr | 2026 | Design | Pipeline
PRJ018 | Nov | 2025 | Test | Active
PRJ018 | Dec | 2025 | Deploy | Active
PRJ018 | Jan | 2026 | Design | Active
PRJ018 | Feb | 2026 | Design | Active
PRJ018 | Mar | 2026 | Test | Active
PRJ018 | Apr | 2026 | Build | Active
PRJ018 | May | 2026 | Test | Active
PRJ018 | Jun | 2026 | Build | Active
PRJ018 | Jul | 2026 | Discovery | Active
PRJ018 | Aug | 2026 | Test | Active
PRJ018 | Sep | 2026 | Build | Active
PRJ018 | Oct | 2026 | Deploy | Active
PRJ018 | Nov | 2026 | Design | Active
PRJ019 | Apr | 2025 | Discovery | Active
PRJ019 | May | 2025 | Test | Active
PRJ019 | Jun | 2025 | Build | Active
PRJ019 | Jul | 2025 | Deploy | Active
PRJ019 | Aug | 2025 | Build | Active
PRJ019 | Sep | 2025 | Test | Active
PRJ019 | Oct | 2025 | Build | Active
PRJ019 | Nov | 2025 | Test | Active
PRJ019 | Dec | 2025 | Build | Active
PRJ019 | Jan | 2026 | Design | Active
PRJ019 | Feb | 2026 | Test | Active
PRJ019 | Mar | 2026 | Test | Active
PRJ019 | Apr | 2026 | Discovery | Active
PRJ019 | May | 2026 | Design | Active
PRJ019 | Jun | 2026 | Test | Active
PRJ019 | Jul | 2026 | Deploy | Active
PRJ019 | Aug | 2026 | Build | Active
PRJ019 | Sep | 2026 | Deploy | Active
PRJ019 | Oct | 2026 | Build | Active
PRJ019 | Nov | 2026 | Build | Active
PRJ020 | May | 2025 | Discovery | Completed
PRJ020 | Jun | 2025 | Test | Completed
PRJ020 | Jul | 2025 | Build | Completed
PRJ020 | Aug | 2025 | Discovery | Completed
PRJ021 | Feb | 2025 | Deploy | Active
PRJ021 | Mar | 2025 | Discovery | Active
PRJ021 | Apr | 2025 | Deploy | Active
PRJ021 | May | 2025 | Test | Active
PRJ021 | Jun | 2025 | Build | Active
PRJ022 | May | 2025 | Design | Active
PRJ022 | Jun | 2025 | Deploy | Active
PRJ022 | Jul | 2025 | Build | Active
PRJ022 | Aug | 2025 | Design | Active
PRJ022 | Sep | 2025 | Design | Active
PRJ022 | Oct | 2025 | Deploy | Active
PRJ022 | Nov | 2025 | Build | Active
PRJ022 | Dec | 2025 | Design | Active
PRJ022 | Jan | 2026 | Discovery | Active
PRJ023 | Dec | 2025 | Discovery | Completed
PRJ023 | Jan | 2026 | Build | Completed
PRJ023 | Feb | 2026 | Test | Completed
PRJ023 | Mar | 2026 | Discovery | Completed
PRJ023 | Apr | 2026 | Deploy | Completed
PRJ023 | May | 2026 | Build | Completed
PRJ023 | Jun | 2026 | Design | Completed
PRJ023 | Jul | 2026 | Discovery | Completed
PRJ023 | Aug | 2026 | Build | Completed
PRJ023 | Sep | 2026 | Build | Completed
PRJ023 | Oct | 2026 | Test | Completed
PRJ023 | Nov | 2026 | Design | Completed
PRJ024 | Jan | 2026 | Design | Pipeline
PRJ024 | Feb | 2026 | Design | Pipeline
PRJ024 | Mar | 2026 | Deploy | Pipeline
PRJ024 | Apr | 2026 | Build | Pipeline
PRJ024 | May | 2026 | Deploy | Pipeline
PRJ024 | Jun | 2026 | Deploy | Pipeline
PRJ024 | Jul | 2026 | Build | Pipeline
PRJ024 | Aug | 2026 | Design | Pipeline
PRJ024 | Sep | 2026 | Build | Pipeline
PRJ024 | Oct | 2026 | Test | Pipeline
PRJ024 | Nov | 2026 | Build | Pipeline
PRJ024 | Dec | 2026 | Build | Pipeline
PRJ024 | Jan | 2027 | Discovery | Pipeline
PRJ025 | Jan | 2026 | Test | Active
PRJ025 | Feb | 2026 | Discovery | Active
PRJ025 | Mar | 2026 | Design | Active
PRJ025 | Apr | 2026 | Design | Active
PRJ025 | May | 2026 | Test | Active
PRJ025 | Jun | 2026 | Deploy | Active
PRJ025 | Jul | 2026 | Build | Active
PRJ025 | Aug | 2026 | Discovery | Active
PRJ025 | Sep | 2026 | Test | Active
PRJ025 | Oct | 2026 | Discovery | Active
PRJ025 | Nov | 2026 | Build | Active
PRJ025 | Dec | 2026 | Deploy | Active
PRJ025 | Jan | 2027 | Discovery | Active
PRJ025 | Feb | 2027 | Test | Active
PRJ026 | Oct | 2025 | Build | Active
PRJ026 | Nov | 2025 | Build | Active
PRJ026 | Dec | 2025 | Deploy | Active
PRJ026 | Jan | 2026 | Test | Active
PRJ026 | Feb | 2026 | Build | Active
PRJ026 | Mar | 2026 | Discovery | Active
PRJ026 | Apr | 2026 | Design | Active
PRJ026 | May | 2026 | Test | Active
PRJ026 | Jun | 2026 | Discovery | Active
PRJ026 | Jul | 2026 | Deploy | Active
PRJ027 | May | 2025 | Deploy | Active
PRJ027 | Jun | 2025 | Build | Active
PRJ027 | Jul | 2025 | Deploy | Active
PRJ027 | Aug | 2025 | Design | Active
PRJ027 | Sep | 2025 | Discovery | Active
PRJ027 | Oct | 2025 | Test | Active
PRJ027 | Nov | 2025 | Build | Active
PRJ027 | Dec | 2025 | Test | Active
PRJ027 | Jan | 2026 | Discovery | Active
PRJ027 | Feb | 2026 | Design | Active
PRJ028 | Feb | 2025 | Discovery | Active
PRJ028 | Mar | 2025 | Discovery | Active
PRJ028 | Apr | 2025 | Build | Active
PRJ028 | May | 2025 | Test | Active
PRJ028 | Jun | 2025 | Discovery | Active
PRJ028 | Jul | 2025 | Discovery | Active
PRJ028 | Aug | 2025 | Design | Active
PRJ028 | Sep | 2025 | Deploy | Active
PRJ028 | Oct | 2025 | Design | Active
PRJ028 | Nov | 2025 | Test | Active
PRJ028 | Dec | 2025 | Test | Active
PRJ028 | Jan | 2026 | Build | Active
PRJ028 | Feb | 2026 | Deploy | Active
PRJ028 | Mar | 2026 | Test | Active
PRJ028 | Apr | 2026 | Deploy | Active
PRJ028 | May | 2026 | Design | Active
PRJ028 | Jun | 2026 | Test | Active
PRJ028 | Jul | 2026 | Discovery | Active
PRJ029 | Dec | 2025 | Test | Active
PRJ029 | Jan | 2026 | Deploy | Active
PRJ029 | Feb | 2026 | Test | Active
PRJ029 | Mar | 2026 | Build | Active
PRJ029 | Apr | 2026 | Discovery | Active
PRJ029 | May | 2026 | Build | Active
PRJ029 | Jun | 2026 | Design | Active
PRJ029 | Jul | 2026 | Test | Active
PRJ029 | Aug | 2026 | Test | Active
PRJ029 | Sep | 2026 | Design | Active
PRJ029 | Oct | 2026 | Build | Active
PRJ029 | Nov | 2026 | Discovery | Active
PRJ030 | Jun | 2025 | Build | Active
PRJ030 | Jul | 2025 | Deploy | Active
PRJ030 | Aug | 2025 | Build | Active
PRJ030 | Sep | 2025 | Discovery | Active
PRJ030 | Oct | 2025 | Test | Active
PRJ030 | Nov | 2025 | Build | Active
PRJ030 | Dec | 2025 | Design | Active
PRJ030 | Jan | 2026 | Discovery | Active
PRJ030 | Feb | 2026 | Test | Active
PRJ030 | Mar | 2026 | Discovery | Active
PRJ030 | Apr | 2026 | Design | Active
PRJ030 | May | 2026 | Deploy | Active
PRJ030 | Jun | 2026 | Discovery | Active
PRJ030 | Jul | 2026 | Discovery | Active
PRJ030 | Aug | 2026 | Build | Active
PRJ030 | Sep | 2026 | Design | Active
PRJ030 | Oct | 2026 | Design | Active
PRJ031 | Sep | 2025 | Deploy | Pipeline
PRJ031 | Oct | 2025 | Design | Pipeline
PRJ031 | Nov | 2025 | Discovery | Pipeline
PRJ031 | Dec | 2025 | Deploy | Pipeline
PRJ031 | Jan | 2026 | Design | Pipeline
PRJ031 | Feb | 2026 | Deploy | Pipeline
PRJ031 | Mar | 2026 | Design | Pipeline
PRJ031 | Apr | 2026 | Design | Pipeline
PRJ031 | May | 2026 | Build | Pipeline
PRJ031 | Jun | 2026 | Design | Pipeline
PRJ031 | Jul | 2026 | Deploy | Pipeline
PRJ031 | Aug | 2026 | Discovery | Pipeline
PRJ031 | Sep | 2026 | Build | Pipeline
PRJ031 | Oct | 2026 | Design | Pipeline
PRJ031 | Nov | 2026 | Design | Pipeline
PRJ032 | Jan | 2026 | Deploy | Completed
PRJ032 | Feb | 2026 | Build | Completed
PRJ032 | Mar | 2026 | Design | Completed
PRJ032 | Apr | 2026 | Discovery | Completed
PRJ032 | May | 2026 | Discovery | Completed
PRJ032 | Jun | 2026 | Design | Completed
PRJ032 | Jul | 2026 | Discovery | Completed
PRJ032 | Aug | 2026 | Build | Completed
PRJ032 | Sep | 2026 | Design | Completed
PRJ032 | Oct | 2026 | Deploy | Completed
PRJ032 | Nov | 2026 | Build | Completed
PRJ032 | Dec | 2026 | Discovery | Completed
PRJ032 | Jan | 2027 | Design | Completed
PRJ032 | Feb | 2027 | Build | Completed
PRJ032 | Mar | 2027 | Discovery | Completed
PRJ032 | Apr | 2027 | Design | Completed
PRJ032 | May | 2027 | Test | Completed
PRJ033 | Dec | 2025 | Deploy | Pipeline
PRJ033 | Jan | 2026 | Discovery | Pipeline
PRJ033 | Feb | 2026 | Discovery | Pipeline
PRJ033 | Mar | 2026 | Test | Pipeline
PRJ033 | Apr | 2026 | Test | Pipeline
PRJ033 | May | 2026 | Build | Pipeline
PRJ033 | Jun | 2026 | Deploy | Pipeline
PRJ033 | Jul | 2026 | Deploy | Pipeline
PRJ033 | Aug | 2026 | Discovery | Pipeline
PRJ033 | Sep | 2026 | Test | Pipeline
PRJ033 | Oct | 2026 | Deploy | Pipeline
PRJ033 | Nov | 2026 | Design | Pipeline
PRJ033 | Dec | 2026 | Deploy | Pipeline
PRJ033 | Jan | 2027 | Discovery | Pipeline
PRJ033 | Feb | 2027 | Deploy | Pipeline
PRJ033 | Mar | 2027 | Build | Pipeline
PRJ033 | Apr | 2027 | Test | Pipeline
PRJ033 | May | 2027 | Discovery | Pipeline
PRJ034 | Dec | 2025 | Discovery | Pipeline
PRJ034 | Jan | 2026 | Test | Pipeline
PRJ034 | Feb | 2026 | Test | Pipeline
PRJ034 | Mar | 2026 | Test | Pipeline
PRJ034 | Apr | 2026 | Discovery | Pipeline
PRJ034 | May | 2026 | Test | Pipeline
PRJ034 | Jun | 2026 | Test | Pipeline
PRJ034 | Jul | 2026 | Discovery | Pipeline
PRJ034 | Aug | 2026 | Discovery | Pipeline
PRJ034 | Sep | 2026 | Build | Pipeline
PRJ034 | Oct | 2026 | Deploy | Pipeline
PRJ034 | Nov | 2026 | Design | Pipeline
PRJ034 | Dec | 2026 | Discovery | Pipeline
PRJ034 | Jan | 2027 | Design | Pipeline
PRJ035 | Jun | 2025 | Build | Active
PRJ035 | Jul | 2025 | Deploy | Active
PRJ035 | Aug | 2025 | Deploy | Active
PRJ035 | Sep | 2025 | Deploy | Active
PRJ035 | Oct | 2025 | Build | Active
PRJ035 | Nov | 2025 | Test | Active
PRJ035 | Dec | 2025 | Deploy | Active
PRJ035 | Jan | 2026 | Deploy | Active
PRJ035 | Feb | 2026 | Build | Active
PRJ035 | Mar | 2026 | Test | Active
PRJ035 | Apr | 2026 | Deploy | Active
PRJ035 | May | 2026 | Deploy | Active
PRJ035 | Jun | 2026 | Test | Active
PRJ035 | Jul | 2026 | Discovery | Active
PRJ036 | Jun | 2025 | Discovery | Pipeline
PRJ036 | Jul | 2025 | Deploy | Pipeline
PRJ036 | Aug | 2025 | Design | Pipeline
PRJ036 | Sep | 2025 | Test | Pipeline
PRJ036 | Oct | 2025 | Test | Pipeline
PRJ036 | Nov | 2025 | Design | Pipeline
PRJ036 | Dec | 2025 | Test | Pipeline
PRJ037 | Apr | 2025 | Build | Completed
PRJ037 | May | 2025 | Test | Completed
PRJ037 | Jun | 2025 | Test | Completed
PRJ037 | Jul | 2025 | Test | Completed
PRJ037 | Aug | 2025 | Discovery | Completed
PRJ037 | Sep | 2025 | Build | Completed
PRJ037 | Oct | 2025 | Test | Completed
PRJ038 | Oct | 2025 | Build | Pipeline
PRJ038 | Nov | 2025 | Build | Pipeline
PRJ038 | Dec | 2025 | Build | Pipeline
PRJ038 | Jan | 2026 | Design | Pipeline
PRJ039 | Dec | 2025 | Test | Active
PRJ039 | Jan | 2026 | Discovery | Active
PRJ039 | Feb | 2026 | Discovery | Active
PRJ039 | Mar | 2026 | Discovery | Active
PRJ040 | Mar | 2025 | Discovery | Active
PRJ040 | Apr | 2025 | Test | Active
PRJ040 | May | 2025 | Discovery | Active
PRJ040 | Jun | 2025 | Build | Active
PRJ040 | Jul | 2025 | Design | Active
PRJ040 | Aug | 2025 | Deploy | Active
PRJ040 | Sep | 2025 | Discovery | Active
PRJ040 | Oct | 2025 | Deploy | Active
PRJ040 | Nov | 2025 | Deploy | Active
PRJ040 | Dec | 2025 | Deploy | Active
PRJ040 | Jan | 2026 | Build | Active
PRJ040 | Feb | 2026 | Discovery | Active
PRJ040 | Mar | 2026 | Test | Active
PRJ040 | Apr | 2026 | Build | Active

## Risks
Risk ID | Project ID | Description | Probability | Impact | Velocity | Owner | Mitigation Plan | Status
R001 | PRJ028 | Vendor delay impacting milestone | Medium | High | Medium | John Smith | Increase staffing | Open
R002 | PRJ010 | Stakeholder alignment risk | Low | Low | Medium | Carlos Diaz | Increase staffing | Mitigated
R003 | PRJ008 | Scope creep | High | Medium | Medium | Carlos Diaz | Increase staffing | Open
R004 | PRJ039 | Scope creep | Low | Medium | Medium | Priya Patel | Rebaseline budget | Mitigated
R005 | PRJ023 | Vendor delay impacting milestone | Low | Medium | Fast | Priya Patel | Patch & monitoring | Open
R006 | PRJ010 | Vendor delay impacting milestone | Low | Medium | Medium | Sarah Lee | Patch & monitoring | Mitigated
R007 | PRJ011 | Integration risk | Medium | High | Fast | Alex Brown | Add buffer | Open
R008 | PRJ010 | Resource shortage | High | Low | Fast | John Smith | Rebaseline budget | Closed
R009 | PRJ028 | Stakeholder alignment risk | High | Critical | Medium | Mike Johnson | Engage vendor | Open
R010 | PRJ023 | Regulatory change | Low | High | Fast | Priya Patel | Increase staffing | Closed
R011 | PRJ034 | Scope creep | Low | Medium | Medium | Alex Brown | Add buffer | Open
R012 | PRJ014 | Scope creep | Low | Medium | Medium | Mike Johnson | Rebaseline budget | Open
R013 | PRJ001 | Stakeholder alignment risk | High | Critical | Slow | Jane Doe | Patch & monitoring | Open
R014 | PRJ033 | Technology obsolescence | High | High | Slow | Sarah Lee | Stakeholder workshop | Open
R015 | PRJ028 | Vendor delay impacting milestone | Medium | Low | Medium | Alex Brown | Patch & monitoring | Closed
R016 | PRJ027 | Scope creep | Low | Critical | Slow | Mike Johnson | Engage vendor | Closed
R017 | PRJ024 | Budget overrun forecast | Medium | Low | Slow | Sarah Lee | Increase staffing | Closed
R018 | PRJ034 | Budget overrun forecast | Medium | High | Fast | Mike Johnson | Engage vendor | Mitigated
R019 | PRJ011 | Budget overrun forecast | High | Low | Fast | Alex Brown | Engage vendor | Mitigated
R020 | PRJ023 | Resource shortage | Low | Low | Slow | Mike Johnson | Engage vendor | Open
R021 | PRJ039 | Resource shortage | High | Low | Slow | Carlos Diaz | Stakeholder workshop | Closed
R022 | PRJ030 | Stakeholder alignment risk | High | High | Fast | Mike Johnson | Engage vendor | Closed
R023 | PRJ005 | Stakeholder alignment risk | Medium | High | Medium | Alex Brown | Add buffer | Mitigated
R024 | PRJ033 | Budget overrun forecast | Medium | Critical | Medium | John Smith | Add buffer | Mitigated
R025 | PRJ019 | Budget overrun forecast | High | Low | Fast | Alex Brown | Increase staffing | Closed
R026 | PRJ030 | Technology obsolescence | High | Low | Medium | Carlos Diaz | Increase staffing | Open
R027 | PRJ021 | Stakeholder alignment risk | High | Medium | Slow | Sarah Lee | Add buffer | Mitigated
R028 | PRJ006 | Technology obsolescence | High | Medium | Slow | Jane Doe | Stakeholder workshop | Closed
R029 | PRJ029 | Technology obsolescence | High | Medium | Medium | Mike Johnson | Rebaseline budget | Closed
R030 | PRJ027 | Integration risk | High | Low | Fast | Priya Patel | Rebaseline budget | Open
R031 | PRJ022 | Budget overrun forecast | High | Critical | Medium | Mike Johnson | Stakeholder workshop | Open
R032 | PRJ022 | Budget overrun forecast | High | Medium | Medium | Mike Johnson | Stakeholder workshop | Closed
R033 | PRJ009 | Budget overrun forecast | Medium | Critical | Fast | Carlos Diaz | Rebaseline budget | Open
R034 | PRJ034 | Budget overrun forecast | High | Critical | Fast | Mike Johnson | Add buffer | Mitigated
R035 | PRJ020 | Resource shortage | Low | High | Medium | Jane Doe | Engage vendor | Open
R036 | PRJ010 | Budget overrun forecast | Medium | Low | Fast | Carlos Diaz | Increase staffing | Open
R037 | PRJ022 | Resource shortage | High | Critical | Slow | Jane Doe | Engage vendor | Open
R038 | PRJ029 | Vendor delay impacting milestone | Medium | High | Fast | Priya Patel | Engage vendor | Closed
R039 | PRJ040 | Scope creep | High | Critical | Slow | Alex Brown | Engage vendor | Mitigated
R040 | PRJ031 | Cyber security vulnerability detected | Medium | Critical | Medium | Carlos Diaz | Rebaseline budget | Closed
R041 | PRJ033 | Technology obsolescence | Medium | Medium | Slow | Carlos Diaz | Increase staffing | Open
R042 | PRJ017 | Vendor delay impacting milestone | High | Critical | Medium | Alex Brown | Add buffer | Open
R043 | PRJ019 | Budget overrun forecast | Low | High | Medium | Alex Brown | Engage vendor | Closed
R044 | PRJ006 | Cyber security vulnerability detected | Medium | High | Slow | Sarah Lee | Add buffer | Closed
R045 | PRJ033 | Integration risk | Low | Critical | Slow | Mike Johnson | Engage vendor | Open
R046 | PRJ021 | Budget overrun forecast | High | High | Slow | Jane Doe | Add buffer | Mitigated
R047 | PRJ031 | Resource shortage | High | Critical | Medium | Alex Brown | Add buffer | Open
R048 | PRJ002 | Scope creep | Low | Medium | Fast | Priya Patel | Increase staffing | Closed
R049 | PRJ008 | Scope creep | Low | High | Slow | John Smith | Engage vendor | Closed
R050 | PRJ040 | Stakeholder alignment risk | Low | Low | Medium | Alex Brown | Increase staffing | Open
R051 | PRJ033 | Cyber security vulnerability detected | High | Medium | Medium | Sarah Lee | Add buffer | Mitigated
R052 | PRJ016 | Regulatory change | Low | Low | Fast | Mike Johnson | Add buffer | Open
R053 | PRJ025 | Stakeholder alignment risk | Low | Critical | Medium | Mike Johnson | Stakeholder workshop | Open
R054 | PRJ023 | Budget overrun forecast | Medium | Medium | Fast | Priya Patel | Stakeholder workshop | Open
R055 | PRJ038 | Integration risk | Low | Low | Medium | Alex Brown | Rebaseline budget | Open
R056 | PRJ030 | Stakeholder alignment risk | High | Medium | Slow | John Smith | Stakeholder workshop | Closed
R057 | PRJ003 | Scope creep | Low | Low | Slow | John Smith | Rebaseline budget | Mitigated
R058 | PRJ033 | Regulatory change | High | Critical | Medium | John Smith | Stakeholder workshop | Open
R059 | PRJ019 | Integration risk | Low | High | Medium | John Smith | Rebaseline budget | Closed
R060 | PRJ026 | Stakeholder alignment risk | Medium | High | Slow | Sarah Lee | Stakeholder workshop | Closed

## RAID
RAID ID | Project ID | Type | Description | Probability | Impact | RAG | Owner | Target Resolution Date | Mitigation | Status
RAID001 | PRJ024 | Assumption | Regulatory deadline | Low | Critical | Green | Sarah Lee | 2026-08-02 | Contingency plan | Closed
RAID002 | PRJ019 | Assumption | Cloud provider outage risk | Low | High | Red | Mike Johnson | 2026-05-18 | Re-baseline | Closed
RAID003 | PRJ028 | Issue | Staff turnover | Medium | High | Amber | John Smith | 2026-09-03 | Vendor escalation | Closed
RAID004 | PRJ028 | Assumption | Staff turnover | Low | Low | Red | Priya Patel | 2026-06-12 | Vendor escalation | Closed
RAID005 | PRJ011 | Risk | Test data not available | High | Critical | Green | Jane Doe | 2026-03-18 | Contingency plan | Closed
RAID006 | PRJ024 | Assumption | Depends on procurement signoff | High | Low | Red | Jane Doe | 2026-08-21 | Re-baseline | In Progress
RAID007 | PRJ024 | Dependency | Regulatory deadline | Low | Medium | Red | Mike Johnson | 2026-06-10 | Vendor escalation | Closed
RAID008 | PRJ018 | Issue | Cloud provider outage risk | Low | Medium | Amber | Alex Brown | 2026-06-08 | Add buffer | Open
RAID009 | PRJ017 | Assumption | Staff turnover | Medium | Medium | Red | Mike Johnson | 2026-08-25 | Re-baseline | Open
RAID010 | PRJ008 | Issue | Regulatory deadline | Low | Critical | Green | Priya Patel | 2026-06-22 | Active monitoring | Closed
RAID011 | PRJ021 | Assumption | Staff turnover | Low | High | Amber | Carlos Diaz | 2026-04-10 | Contingency plan | In Progress
RAID012 | PRJ033 | Issue | Cloud provider outage risk | Low | Medium | Green | Carlos Diaz | 2026-07-05 | Active monitoring | In Progress
RAID013 | PRJ036 | Assumption | Depends on procurement signoff | High | Medium | Red | John Smith | 2026-03-17 | Vendor escalation | In Progress
RAID014 | PRJ031 | Dependency | Regulatory deadline | Medium | Low | Green | Mike Johnson | 2026-08-12 | Active monitoring | In Progress
RAID015 | PRJ030 | Assumption | Test data not available | High | Medium | Green | Sarah Lee | 2026-07-07 | Active monitoring | Open
RAID016 | PRJ034 | Issue | Assumes API contract stable | Low | Medium | Amber | Priya Patel | 2026-04-27 | Vendor escalation | Closed
RAID017 | PRJ019 | Risk | Assumes API contract stable | Low | High | Green | Priya Patel | 2026-05-17 | Add buffer | Closed
RAID018 | PRJ006 | Issue | Vendor licence cost rise | High | Medium | Green | Priya Patel | 2026-08-07 | Add buffer | In Progress
RAID019 | PRJ037 | Risk | Regulatory deadline | Low | Low | Green | Priya Patel | 2026-09-14 | Add buffer | In Progress
RAID020 | PRJ014 | Dependency | Vendor licence cost rise | High | Low | Amber | Priya Patel | 2026-07-18 | Vendor escalation | Closed
RAID021 | PRJ020 | Dependency | Test data not available | High | Critical | Amber | Sarah Lee | 2026-03-19 | Active monitoring | Open
RAID022 | PRJ029 | Dependency | Depends on procurement signoff | Medium | Medium | Amber | Alex Brown | 2026-04-06 | Vendor escalation | Closed
RAID023 | PRJ021 | Assumption | Depends on procurement signoff | Low | High | Red | Alex Brown | 2026-03-28 | Vendor escalation | Open
RAID024 | PRJ030 | Risk | Assumes API contract stable | Medium | Medium | Green | John Smith | 2026-03-13 | Vendor escalation | In Progress
RAID025 | PRJ040 | Dependency | Test data not available | Low | High | Red | Priya Patel | 2026-05-20 | Contingency plan | Open
RAID026 | PRJ032 | Dependency | Depends on procurement signoff | Medium | Critical | Green | John Smith | 2026-06-09 | Add buffer | In Progress
RAID027 | PRJ016 | Issue | Vendor licence cost rise | Medium | Low | Green | Mike Johnson | 2026-07-05 | Add buffer | Closed
RAID028 | PRJ031 | Assumption | Vendor licence cost rise | Low | Low | Amber | Jane Doe | 2026-10-12 | Vendor escalation | Closed
RAID029 | PRJ024 | Dependency | Assumes API contract stable | Low | Critical | Green | Alex Brown | 2026-07-22 | Contingency plan | In Progress
RAID030 | PRJ036 | Assumption | Cloud provider outage risk | Medium | Critical | Red | Mike Johnson | 2026-09-28 | Add buffer | Closed
RAID031 | PRJ040 | Risk | Test data not available | Low | Critical | Amber | Carlos Diaz | 2026-05-26 | Add buffer | In Progress
RAID032 | PRJ010 | Issue | Vendor licence cost rise | High | Critical | Red | John Smith | 2026-03-12 | Active monitoring | Open
RAID033 | PRJ022 | Dependency | Vendor licence cost rise | Medium | Medium | Red | Alex Brown | 2026-04-05 | Vendor escalation | Closed
RAID034 | PRJ021 | Issue | Depends on procurement signoff | High | High | Red | Mike Johnson | 2026-07-08 | Add buffer | Closed
RAID035 | PRJ032 | Assumption | Depends on procurement signoff | Low | High | Amber | Priya Patel | 2026-03-29 | Re-baseline | Closed
RAID036 | PRJ020 | Risk | Vendor licence cost rise | Medium | High | Red | Carlos Diaz | 2026-09-15 | Add buffer | Closed
RAID037 | PRJ015 | Risk | Vendor licence cost rise | Medium | Medium | Red | Priya Patel | 2026-09-01 | Add buffer | In Progress
RAID038 | PRJ010 | Issue | Cloud provider outage risk | High | Low | Green | John Smith | 2026-06-21 | Vendor escalation | In Progress
RAID039 | PRJ010 | Dependency | Staff turnover | Low | Critical | Red | Carlos Diaz | 2026-08-04 | Re-baseline | Closed
RAID040 | PRJ004 | Issue | Vendor licence cost rise | Low | High | Red | Sarah Lee | 2026-07-13 | Re-baseline | In Progress
RAID041 | PRJ012 | Dependency | Vendor licence cost rise | Medium | High | Red | Carlos Diaz | 2026-10-09 | Vendor escalation | Closed
RAID042 | PRJ031 | Issue | Test data not available | Medium | High | Green | Mike Johnson | 2026-09-14 | Vendor escalation | Closed
RAID043 | PRJ014 | Dependency | Assumes API contract stable | Medium | High | Red | Carlos Diaz | 2026-09-01 | Vendor escalation | In Progress
RAID044 | PRJ008 | Dependency | Depends on procurement signoff | Medium | Medium | Amber | John Smith | 2026-05-13 | Active monitoring | In Progress
RAID045 | PRJ029 | Assumption | Staff turnover | Medium | Medium | Green | Carlos Diaz | 2026-07-16 | Vendor escalation | Closed
RAID046 | PRJ018 | Issue | Cloud provider outage risk | High | Medium | Green | John Smith | 2026-08-19 | Add buffer | Open
RAID047 | PRJ015 | Risk | Cloud provider outage risk | Medium | High | Red | Sarah Lee | 2026-03-26 | Contingency plan | Open
RAID048 | PRJ036 | Issue | Depends on procurement signoff | High | Critical | Amber | Priya Patel | 2026-04-21 | Vendor escalation | In Progress
RAID049 | PRJ019 | Risk | Regulatory deadline | Low | Medium | Red | Priya Patel | 2026-09-02 | Active monitoring | Open
RAID050 | PRJ027 | Issue | Cloud provider outage risk | Medium | Critical | Green | Priya Patel | 2026-10-10 | Vendor escalation | Open
RAID051 | PRJ001 | Assumption | Vendor licence cost rise | High | Low | Amber | Mike Johnson | 2026-06-25 | Add buffer | Closed
RAID052 | PRJ032 | Issue | Regulatory deadline | High | Critical | Amber | Jane Doe | 2026-09-24 | Active monitoring | In Progress
RAID053 | PRJ011 | Dependency | Staff turnover | Medium | Medium | Green | Priya Patel | 2026-05-26 | Vendor escalation | Closed
RAID054 | PRJ013 | Issue | Vendor licence cost rise | High | Critical | Amber | Alex Brown | 2026-05-23 | Active monitoring | In Progress
RAID055 | PRJ007 | Issue | Test data not available | Medium | High | Green | John Smith | 2026-05-06 | Re-baseline | Open
RAID056 | PRJ029 | Assumption | Assumes API contract stable | Medium | Low | Amber | Priya Patel | 2026-06-01 | Contingency plan | Open
RAID057 | PRJ008 | Dependency | Assumes API contract stable | Low | Critical | Red | Alex Brown | 2026-10-23 | Vendor escalation | Closed
RAID058 | PRJ008 | Assumption | Assumes API contract stable | High | Medium | Green | Jane Doe | 2026-07-01 | Contingency plan | In Progress
RAID059 | PRJ039 | Assumption | Depends on procurement signoff | High | Critical | Red | Carlos Diaz | 2026-08-18 | Contingency plan | Open
RAID060 | PRJ039 | Risk | Vendor licence cost rise | Medium | High | Green | Alex Brown | 2026-03-29 | Active monitoring | Closed
RAID061 | PRJ033 | Issue | Vendor licence cost rise | High | Medium | Green | Mike Johnson | 2026-10-05 | Add buffer | In Progress
RAID062 | PRJ008 | Issue | Staff turnover | High | Critical | Green | Alex Brown | 2026-06-23 | Active monitoring | In Progress
RAID063 | PRJ009 | Dependency | Depends on procurement signoff | High | Low | Red | Sarah Lee | 2026-08-20 | Vendor escalation | Closed
RAID064 | PRJ002 | Dependency | Assumes API contract stable | Low | Medium | Red | John Smith | 2026-03-12 | Re-baseline | In Progress
RAID065 | PRJ005 | Risk | Cloud provider outage risk | Medium | Low | Amber | Sarah Lee | 2026-04-16 | Contingency plan | Closed
RAID066 | PRJ027 | Assumption | Depends on procurement signoff | Medium | Critical | Amber | John Smith | 2026-08-22 | Add buffer | Open
RAID067 | PRJ023 | Risk | Test data not available | High | Critical | Red | Jane Doe | 2026-09-03 | Contingency plan | Open
RAID068 | PRJ002 | Assumption | Depends on procurement signoff | High | Critical | Red | Sarah Lee | 2026-09-27 | Contingency plan | Open
RAID069 | PRJ030 | Assumption | Test data not available | Medium | Medium | Red | Carlos Diaz | 2026-03-29 | Active monitoring | Closed
RAID070 | PRJ027 | Risk | Test data not available | Low | Low | Green | Alex Brown | 2026-03-09 | Re-baseline | Closed
RAID071 | PRJ004 | Issue | Staff turnover | Low | Critical | Amber | Jane Doe | 2026-07-17 | Contingency plan | Open
RAID072 | PRJ009 | Assumption | Test data not available | High | High | Red | Alex Brown | 2026-09-14 | Vendor escalation | Open
RAID073 | PRJ020 | Issue | Staff turnover | High | Medium | Amber | Mike Johnson | 2026-05-10 | Active monitoring | Closed
RAID074 | PRJ038 | Issue | Staff turnover | High | Critical | Red | Sarah Lee | 2026-03-13 | Vendor escalation | Closed
RAID075 | PRJ025 | Assumption | Staff turnover | Medium | Critical | Green | Mike Johnson | 2026-06-05 | Contingency plan | Closed
RAID076 | PRJ031 | Issue | Regulatory deadline | Low | High | Red | Jane Doe | 2026-09-23 | Re-baseline | Open
RAID077 | PRJ036 | Dependency | Depends on procurement signoff | High | Medium | Amber | Jane Doe | 2026-05-05 | Contingency plan | In Progress
RAID078 | PRJ006 | Dependency | Regulatory deadline | Medium | Low | Red | Priya Patel | 2026-09-29 | Contingency plan | Open
RAID079 | PRJ018 | Dependency | Staff turnover | High | Low | Green | Jane Doe | 2026-09-22 | Add buffer | Closed
RAID080 | PRJ036 | Issue | Depends on procurement signoff | Low | High | Amber | John Smith | 2026-04-24 | Contingency plan | Closed

## StageGates
Project ID | Project Name | Governance Channel | Stage | Next Gate | Gate Status | Status | Gate Owner | Planned Gate Date | Actual Gate Date | Gate Outcome | Gate Comments | Checklist Complete % | Days Late | _Key
PRJ001 | Customer Portal | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-02-14 | 2025-03-01 | Conditional | Approved with conditions | 100 | 15 | PRJ001¦Discovery
PRJ001 | Customer Portal | Channel B (>$200K) | Business Case / Seed Funding | Design | Pending Approval | In Progress | CTO | 2025-04-15 |  |  | Awaiting sponsor sign-off | 89 | 0 | PRJ001¦Business Case / Seed Funding
PRJ001 | Customer Portal | Channel B (>$200K) | Design | Business Case / Full Funding | Not Started | Not Started | CTO | 2025-06-14 |  |  | On track | 0 | 0 | PRJ001¦Design
PRJ001 | Customer Portal | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CTO | 2025-08-13 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ001¦Business Case / Full Funding
PRJ001 | Customer Portal | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CTO | 2025-10-12 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ001¦Build
PRJ001 | Customer Portal | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CTO | 2025-12-11 |  |  | On track | 0 | 0 | PRJ001¦Testing
PRJ001 | Customer Portal | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CTO | 2026-02-09 |  |  |  | 0 | 0 | PRJ001¦Deployment
PRJ001 | Customer Portal | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2026-04-10 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ001¦Handover
PRJ002 | Cloud Migration | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-03-21 | 2025-03-29 | Rework | On track | 100 | 8 | PRJ002¦Discovery
PRJ002 | Cloud Migration | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2025-05-20 | 2025-05-07 | Conditional | Approved with conditions | 100 | 0 | PRJ002¦Business Case / Seed Funding
PRJ002 | Cloud Migration | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2025-07-19 | 2025-07-05 | Rework | On track | 100 | 0 | PRJ002¦Design
PRJ002 | Cloud Migration | Channel B (>$200K) | Business Case / Full Funding | Build | Pending Approval | In Progress | COO | 2025-09-17 |  |  | Approved with conditions | 61 | 0 | PRJ002¦Business Case / Full Funding
PRJ002 | Cloud Migration | Channel B (>$200K) | Build | Testing | Not Started | Not Started | COO | 2025-11-16 |  |  | On track | 0 | 0 | PRJ002¦Build
PRJ002 | Cloud Migration | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | COO | 2026-01-15 |  |  | Approved with conditions | 0 | 0 | PRJ002¦Testing
PRJ002 | Cloud Migration | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | COO | 2026-03-16 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ002¦Deployment
PRJ002 | Cloud Migration | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2026-05-15 |  |  | On track | 0 | 0 | PRJ002¦Handover
PRJ003 | Data Platform | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-04-09 | 2025-04-23 | Conditional | Awaiting sponsor sign-off | 100 | 14 | PRJ003¦Discovery
PRJ003 | Data Platform | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2025-06-08 | 2025-06-03 | Conditional | On track | 100 | 0 | PRJ003¦Business Case / Seed Funding
PRJ003 | Data Platform | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2025-08-07 | 2025-08-03 | Proceed |  | 100 | 0 | PRJ003¦Design
PRJ003 | Data Platform | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CFO | 2025-10-06 | 2025-09-25 | Proceed |  | 100 | 0 | PRJ003¦Business Case / Full Funding
PRJ003 | Data Platform | Channel B (>$200K) | Build | Testing | Approved | Complete | CFO | 2025-12-05 | 2025-12-16 | Conditional | Approved with conditions | 100 | 11 | PRJ003¦Build
PRJ003 | Data Platform | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CFO | 2026-02-03 | 2026-01-23 | Conditional |  | 100 | 0 | PRJ003¦Testing
PRJ003 | Data Platform | Channel B (>$200K) | Deployment | Handover | Approved | Complete | CFO | 2026-04-04 | 2026-04-02 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ003¦Deployment
PRJ003 | Data Platform | Channel B (>$200K) | Handover | Handover | In Progress | In Progress | CFO | 2026-06-03 |  |  | On track | 41 | 0 | PRJ003¦Handover
PRJ004 | AI Assistant | Channel B (>$200K) | Discovery | Business Case / Seed Funding | In Progress | In Progress | CTO | 2025-10-01 |  |  |  | 41 | 0 | PRJ004¦Discovery
PRJ004 | AI Assistant | Channel B (>$200K) | Business Case / Seed Funding | Design | Not Started | Not Started | CTO | 2025-11-30 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ004¦Business Case / Seed Funding
PRJ004 | AI Assistant | Channel B (>$200K) | Design | Business Case / Full Funding | Not Started | Not Started | CTO | 2026-01-29 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ004¦Design
PRJ004 | AI Assistant | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CTO | 2026-03-30 |  |  | On track | 0 | 0 | PRJ004¦Business Case / Full Funding
PRJ004 | AI Assistant | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CTO | 2026-05-29 |  |  |  | 0 | 0 | PRJ004¦Build
PRJ004 | AI Assistant | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CTO | 2026-07-28 |  |  | Approved with conditions | 0 | 0 | PRJ004¦Testing
PRJ004 | AI Assistant | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CTO | 2026-09-26 |  |  | Approved with conditions | 0 | 0 | PRJ004¦Deployment
PRJ004 | AI Assistant | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2026-11-25 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ004¦Handover
PRJ005 | Network Refresh | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-07-22 | 2025-07-24 | Held |  | 100 | 2 | PRJ005¦Discovery
PRJ005 | Network Refresh | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2025-09-20 | 2025-09-28 | Held | On track | 100 | 8 | PRJ005¦Business Case / Seed Funding
PRJ005 | Network Refresh | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2025-11-19 | 2025-12-10 | Conditional | Approved with conditions | 100 | 21 | PRJ005¦Design
PRJ005 | Network Refresh | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CFO | 2026-01-18 | 2026-01-22 | Proceed |  | 100 | 4 | PRJ005¦Business Case / Full Funding
PRJ005 | Network Refresh | Channel B (>$200K) | Build | Testing | Approved | Complete | CFO | 2026-03-19 | 2026-03-09 | Held | On track | 100 | 0 | PRJ005¦Build
PRJ005 | Network Refresh | Channel B (>$200K) | Testing | Deployment | In Progress | In Progress | CFO | 2026-05-18 |  |  |  | 80 | 0 | PRJ005¦Testing
PRJ005 | Network Refresh | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CFO | 2026-07-17 |  |  | Approved with conditions | 0 | 0 | PRJ005¦Deployment
PRJ005 | Network Refresh | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2026-09-15 |  |  | On track | 0 | 0 | PRJ005¦Handover
PRJ006 | Cyber Security Program | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CMO | 2025-03-20 | 2025-04-15 | Rework |  | 100 | 26 | PRJ006¦Discovery
PRJ006 | Cyber Security Program | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CMO | 2025-05-19 | 2025-06-06 | Proceed | Approved with conditions | 100 | 18 | PRJ006¦Business Case / Seed Funding
PRJ006 | Cyber Security Program | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CMO | 2025-07-18 | 2025-07-16 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ006¦Design
PRJ006 | Cyber Security Program | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CMO | 2025-09-16 | 2025-09-03 | Proceed | Awaiting sponsor sign-off | 100 | 0 | PRJ006¦Business Case / Full Funding
PRJ006 | Cyber Security Program | Channel B (>$200K) | Build | Testing | Approved | Complete | CMO | 2025-11-15 | 2025-12-04 | Proceed | Approved with conditions | 100 | 19 | PRJ006¦Build
PRJ006 | Cyber Security Program | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CMO | 2026-01-14 | 2026-01-19 | Proceed | Approved with conditions | 100 | 5 | PRJ006¦Testing
PRJ006 | Cyber Security Program | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | CMO | 2026-03-15 |  |  | On track | 44 | 0 | PRJ006¦Deployment
PRJ006 | Cyber Security Program | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CMO | 2026-05-14 |  |  | Approved with conditions | 0 | 0 | PRJ006¦Handover
PRJ007 | CRM Upgrade | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-05-15 | 2025-06-05 | Held | Awaiting sponsor sign-off | 100 | 21 | PRJ007¦Discovery
PRJ007 | CRM Upgrade | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2025-07-14 | 2025-07-23 | Conditional |  | 100 | 9 | PRJ007¦Business Case / Seed Funding
PRJ007 | CRM Upgrade | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2025-09-12 | 2025-09-29 | Rework |  | 100 | 17 | PRJ007¦Design
PRJ007 | CRM Upgrade | Channel B (>$200K) | Business Case / Full Funding | Build | In Progress | In Progress | CTO | 2025-11-11 |  |  | Approved with conditions | 93 | 0 | PRJ007¦Business Case / Full Funding
PRJ007 | CRM Upgrade | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CTO | 2026-01-10 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ007¦Build
PRJ007 | CRM Upgrade | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CTO | 2026-03-11 |  |  | On track | 0 | 0 | PRJ007¦Testing
PRJ007 | CRM Upgrade | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CTO | 2026-05-10 |  |  |  | 0 | 0 | PRJ007¦Deployment
PRJ007 | CRM Upgrade | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2026-07-09 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ007¦Handover
PRJ008 | Mobile App | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-05-03 | 2025-05-19 | Conditional | Awaiting sponsor sign-off | 100 | 16 | PRJ008¦Discovery
PRJ008 | Mobile App | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2025-07-02 | 2025-07-22 | Held | On track | 100 | 20 | PRJ008¦Business Case / Seed Funding
PRJ008 | Mobile App | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2025-08-31 | 2025-08-27 | Held |  | 100 | 0 | PRJ008¦Design
PRJ008 | Mobile App | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CTO | 2025-10-30 | 2025-11-23 | Rework | Approved with conditions | 100 | 24 | PRJ008¦Business Case / Full Funding
PRJ008 | Mobile App | Channel B (>$200K) | Build | Testing | Approved | Complete | CTO | 2025-12-29 | 2026-01-28 | Proceed |  | 100 | 30 | PRJ008¦Build
PRJ008 | Mobile App | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CTO | 2026-02-27 | 2026-03-01 | Conditional | On track | 100 | 2 | PRJ008¦Testing
PRJ008 | Mobile App | Channel B (>$200K) | Deployment | Handover | Approved | Complete | CTO | 2026-04-28 | 2026-05-28 | Conditional | On track | 100 | 30 | PRJ008¦Deployment
PRJ008 | Mobile App | Channel B (>$200K) | Handover | Handover | In Progress | In Progress | CTO | 2026-06-27 |  |  |  | 45 | 0 | PRJ008¦Handover
PRJ009 | ERP Modernisation | Channel B (>$200K) | Discovery | Business Case / Seed Funding | In Progress | In Progress | CFO | 2026-01-01 |  |  | Awaiting sponsor sign-off | 88 | 0 | PRJ009¦Discovery
PRJ009 | ERP Modernisation | Channel B (>$200K) | Business Case / Seed Funding | Design | Not Started | Not Started | CFO | 2026-03-02 |  |  |  | 0 | 0 | PRJ009¦Business Case / Seed Funding
PRJ009 | ERP Modernisation | Channel B (>$200K) | Design | Business Case / Full Funding | Not Started | Not Started | CFO | 2026-05-01 |  |  |  | 0 | 0 | PRJ009¦Design
PRJ009 | ERP Modernisation | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CFO | 2026-06-30 |  |  | On track | 0 | 0 | PRJ009¦Business Case / Full Funding
PRJ009 | ERP Modernisation | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CFO | 2026-08-29 |  |  | On track | 0 | 0 | PRJ009¦Build
PRJ009 | ERP Modernisation | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CFO | 2026-10-28 |  |  |  | 0 | 0 | PRJ009¦Testing
PRJ009 | ERP Modernisation | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CFO | 2026-12-27 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ009¦Deployment
PRJ009 | ERP Modernisation | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2027-02-25 |  |  |  | 0 | 0 | PRJ009¦Handover
PRJ010 | Workforce Enablement | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-02-06 | 2025-02-15 | Proceed | Awaiting sponsor sign-off | 100 | 9 | PRJ010¦Discovery
PRJ010 | Workforce Enablement | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2025-04-07 | 2025-04-18 | Held |  | 100 | 11 | PRJ010¦Business Case / Seed Funding
PRJ010 | Workforce Enablement | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2025-06-06 | 2025-06-26 | Conditional | Approved with conditions | 100 | 20 | PRJ010¦Design
PRJ010 | Workforce Enablement | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CFO | 2025-08-05 | 2025-09-02 | Held | Approved with conditions | 100 | 28 | PRJ010¦Business Case / Full Funding
PRJ010 | Workforce Enablement | Channel B (>$200K) | Build | Testing | Approved | Complete | CFO | 2025-10-04 | 2025-09-27 | Rework | Awaiting sponsor sign-off | 100 | 0 | PRJ010¦Build
PRJ010 | Workforce Enablement | Channel B (>$200K) | Testing | Deployment | In Progress | In Progress | CFO | 2025-12-03 |  |  | Approved with conditions | 44 | 0 | PRJ010¦Testing
PRJ010 | Workforce Enablement | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CFO | 2026-02-01 |  |  | On track | 0 | 0 | PRJ010¦Deployment
PRJ010 | Workforce Enablement | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2026-04-02 |  |  | On track | 0 | 0 | PRJ010¦Handover
PRJ011 | IoT Initiative | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-11-27 | 2025-12-12 | Proceed | Awaiting sponsor sign-off | 100 | 15 | PRJ011¦Discovery
PRJ011 | IoT Initiative | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2026-01-26 | 2026-01-27 | Conditional | On track | 100 | 1 | PRJ011¦Business Case / Seed Funding
PRJ011 | IoT Initiative | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2026-03-27 | 2026-04-19 | Conditional | On track | 100 | 23 | PRJ011¦Design
PRJ011 | IoT Initiative | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CFO | 2026-05-26 | 2026-05-17 | Conditional | Awaiting sponsor sign-off | 100 | 0 | PRJ011¦Business Case / Full Funding
PRJ011 | IoT Initiative | Channel B (>$200K) | Build | Testing | In Progress | In Progress | CFO | 2026-07-25 |  |  | Awaiting sponsor sign-off | 93 | 0 | PRJ011¦Build
PRJ011 | IoT Initiative | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CFO | 2026-09-23 |  |  | On track | 0 | 0 | PRJ011¦Testing
PRJ011 | IoT Initiative | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CFO | 2026-11-22 |  |  | On track | 0 | 0 | PRJ011¦Deployment
PRJ011 | IoT Initiative | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2027-01-21 |  |  | On track | 0 | 0 | PRJ011¦Handover
PRJ012 | Analytics Platform | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CMO | 2025-10-04 | 2025-10-08 | Rework | Approved with conditions | 100 | 4 | PRJ012¦Discovery
PRJ012 | Analytics Platform | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CMO | 2025-12-03 | 2025-12-18 | Rework | Approved with conditions | 100 | 15 | PRJ012¦Business Case / Seed Funding
PRJ012 | Analytics Platform | Channel B (>$200K) | Design | Business Case / Full Funding | In Progress | In Progress | CMO | 2026-02-01 |  |  | Awaiting sponsor sign-off | 87 | 0 | PRJ012¦Design
PRJ012 | Analytics Platform | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CMO | 2026-04-02 |  |  | On track | 0 | 0 | PRJ012¦Business Case / Full Funding
PRJ012 | Analytics Platform | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CMO | 2026-06-01 |  |  | Approved with conditions | 0 | 0 | PRJ012¦Build
PRJ012 | Analytics Platform | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CMO | 2026-07-31 |  |  | On track | 0 | 0 | PRJ012¦Testing
PRJ012 | Analytics Platform | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CMO | 2026-09-29 |  |  | On track | 0 | 0 | PRJ012¦Deployment
PRJ012 | Analytics Platform | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CMO | 2026-11-28 |  |  |  | 0 | 0 | PRJ012¦Handover
PRJ013 | API Gateway | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-12-05 | 2025-12-27 | Conditional |  | 100 | 22 | PRJ013¦Discovery
PRJ013 | API Gateway | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2026-02-03 | 2026-02-17 | Conditional | On track | 100 | 14 | PRJ013¦Business Case / Seed Funding
PRJ013 | API Gateway | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2026-04-04 | 2026-04-07 | Proceed | On track | 100 | 3 | PRJ013¦Design
PRJ013 | API Gateway | Channel B (>$200K) | Business Case / Full Funding | Build | In Progress | In Progress | CTO | 2026-06-03 |  |  | Approved with conditions | 80 | 0 | PRJ013¦Business Case / Full Funding
PRJ013 | API Gateway | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CTO | 2026-08-02 |  |  | Approved with conditions | 0 | 0 | PRJ013¦Build
PRJ013 | API Gateway | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CTO | 2026-10-01 |  |  | Approved with conditions | 0 | 0 | PRJ013¦Testing
PRJ013 | API Gateway | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CTO | 2026-11-30 |  |  | On track | 0 | 0 | PRJ013¦Deployment
PRJ013 | API Gateway | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2027-01-29 |  |  |  | 0 | 0 | PRJ013¦Handover
PRJ014 | Identity Mgmt | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-02-05 | 2025-02-28 | Held | On track | 100 | 23 | PRJ014¦Discovery
PRJ014 | Identity Mgmt | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2025-04-06 | 2025-04-25 | Held |  | 100 | 19 | PRJ014¦Business Case / Seed Funding
PRJ014 | Identity Mgmt | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2025-06-05 | 2025-06-13 | Proceed |  | 100 | 8 | PRJ014¦Design
PRJ014 | Identity Mgmt | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CTO | 2025-08-04 | 2025-08-04 | Rework | Approved with conditions | 100 | 0 | PRJ014¦Business Case / Full Funding
PRJ014 | Identity Mgmt | Channel B (>$200K) | Build | Testing | Approved | Complete | CTO | 2025-10-03 | 2025-10-29 | Proceed | On track | 100 | 26 | PRJ014¦Build
PRJ014 | Identity Mgmt | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CTO | 2025-12-02 | 2025-12-08 | Held |  | 100 | 6 | PRJ014¦Testing
PRJ014 | Identity Mgmt | Channel B (>$200K) | Deployment | Handover | Approved | Complete | CTO | 2026-01-31 | 2026-01-16 | Proceed | Awaiting sponsor sign-off | 100 | 0 | PRJ014¦Deployment
PRJ014 | Identity Mgmt | Channel B (>$200K) | Handover | Handover | Pending Approval | In Progress | CTO | 2026-04-01 |  |  | On track | 63 | 0 | PRJ014¦Handover
PRJ015 | Service Desk | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-06-03 | 2025-06-17 | Conditional | Awaiting sponsor sign-off | 100 | 14 | PRJ015¦Discovery
PRJ015 | Service Desk | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2025-08-02 | 2025-07-19 | Held |  | 100 | 0 | PRJ015¦Business Case / Seed Funding
PRJ015 | Service Desk | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CIO | 2025-10-01 | 2025-10-04 | Held |  | 100 | 3 | PRJ015¦Design
PRJ015 | Service Desk | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CIO | 2025-11-30 | 2025-11-22 | Conditional | Awaiting sponsor sign-off | 100 | 0 | PRJ015¦Business Case / Full Funding
PRJ015 | Service Desk | Channel B (>$200K) | Build | Testing | Approved | Complete | CIO | 2026-01-29 | 2026-02-02 | Rework | On track | 100 | 4 | PRJ015¦Build
PRJ015 | Service Desk | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CIO | 2026-03-30 | 2026-03-28 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ015¦Testing
PRJ015 | Service Desk | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | CIO | 2026-05-29 |  |  | On track | 86 | 0 | PRJ015¦Deployment
PRJ015 | Service Desk | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2026-07-28 |  |  | On track | 0 | 0 | PRJ015¦Handover
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-12-01 | 2025-11-20 | Rework |  | 100 | 0 | PRJ016¦Discovery
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2026-01-30 | 2026-03-01 | Proceed |  | 100 | 30 | PRJ016¦Business Case / Seed Funding
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CIO | 2026-03-31 | 2026-04-06 | Proceed | Approved with conditions | 100 | 6 | PRJ016¦Design
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CIO | 2026-05-30 | 2026-05-30 | Conditional | Approved with conditions | 100 | 0 | PRJ016¦Business Case / Full Funding
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Build | Testing | Approved | Complete | CIO | 2026-07-29 | 2026-08-04 | Held | On track | 100 | 6 | PRJ016¦Build
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Testing | Deployment | In Progress | In Progress | CIO | 2026-09-27 |  |  | Approved with conditions | 51 | 0 | PRJ016¦Testing
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-11-26 |  |  | On track | 0 | 0 | PRJ016¦Deployment
PRJ016 | Infrastructure Upg | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2027-01-25 |  |  |  | 0 | 0 | PRJ016¦Handover
PRJ017 | App Modernisation | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-02-17 | 2025-03-02 | Held | On track | 100 | 13 | PRJ017¦Discovery
PRJ017 | App Modernisation | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2025-04-18 | 2025-04-03 | Conditional | Approved with conditions | 100 | 0 | PRJ017¦Business Case / Seed Funding
PRJ017 | App Modernisation | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2025-06-17 | 2025-06-19 | Proceed |  | 100 | 2 | PRJ017¦Design
PRJ017 | App Modernisation | Channel B (>$200K) | Business Case / Full Funding | Build | Pending Approval | In Progress | CFO | 2025-08-16 |  |  | Awaiting sponsor sign-off | 60 | 0 | PRJ017¦Business Case / Full Funding
PRJ017 | App Modernisation | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CFO | 2025-10-15 |  |  | On track | 0 | 0 | PRJ017¦Build
PRJ017 | App Modernisation | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CFO | 2025-12-14 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ017¦Testing
PRJ017 | App Modernisation | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CFO | 2026-02-12 |  |  | On track | 0 | 0 | PRJ017¦Deployment
PRJ017 | App Modernisation | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2026-04-13 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ017¦Handover
PRJ018 | RPA Program | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-10-26 | 2025-11-19 | Held |  | 100 | 24 | PRJ018¦Discovery
PRJ018 | RPA Program | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2025-12-25 | 2026-01-01 | Rework | On track | 100 | 7 | PRJ018¦Business Case / Seed Funding
PRJ018 | RPA Program | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2026-02-23 | 2026-03-19 | Conditional | Awaiting sponsor sign-off | 100 | 24 | PRJ018¦Design
PRJ018 | RPA Program | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | COO | 2026-04-24 | 2026-05-18 | Proceed | Approved with conditions | 100 | 24 | PRJ018¦Business Case / Full Funding
PRJ018 | RPA Program | Channel B (>$200K) | Build | Testing | Approved | Complete | COO | 2026-06-23 | 2026-06-28 | Proceed | Approved with conditions | 100 | 5 | PRJ018¦Build
PRJ018 | RPA Program | Channel B (>$200K) | Testing | Deployment | Approved | Complete | COO | 2026-08-22 | 2026-08-26 | Proceed | Approved with conditions | 100 | 4 | PRJ018¦Testing
PRJ018 | RPA Program | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | COO | 2026-10-21 |  |  | On track | 66 | 0 | PRJ018¦Deployment
PRJ018 | RPA Program | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2026-12-20 |  |  | Approved with conditions | 0 | 0 | PRJ018¦Handover
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-03-25 | 2025-04-06 | Conditional | On track | 100 | 12 | PRJ019¦Discovery
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2025-05-24 | 2025-06-18 | Conditional | Approved with conditions | 100 | 25 | PRJ019¦Business Case / Seed Funding
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2025-07-23 | 2025-08-08 | Rework | Approved with conditions | 100 | 16 | PRJ019¦Design
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | COO | 2025-09-21 | 2025-09-17 | Rework | On track | 100 | 0 | PRJ019¦Business Case / Full Funding
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Build | Testing | Approved | Complete | COO | 2025-11-20 | 2025-12-14 | Proceed | Awaiting sponsor sign-off | 100 | 24 | PRJ019¦Build
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Testing | Deployment | Approved | Complete | COO | 2026-01-19 | 2026-01-04 | Held | Approved with conditions | 100 | 0 | PRJ019¦Testing
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Deployment | Handover | In Progress | In Progress | COO | 2026-03-20 |  |  | On track | 66 | 0 | PRJ019¦Deployment
PRJ019 | Vendor Mgmt | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2026-05-19 |  |  | On track | 0 | 0 | PRJ019¦Handover
PRJ020 | Process Automation | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-04-25 | 2025-05-25 | Held | On track | 100 | 30 | PRJ020¦Discovery
PRJ020 | Process Automation | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2025-06-24 | 2025-06-19 | Proceed |  | 100 | 0 | PRJ020¦Business Case / Seed Funding
PRJ020 | Process Automation | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CIO | 2025-08-23 | 2025-08-22 | Rework |  | 100 | 0 | PRJ020¦Design
PRJ020 | Process Automation | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CIO | 2025-10-22 | 2025-10-24 | Conditional | Awaiting sponsor sign-off | 100 | 2 | PRJ020¦Business Case / Full Funding
PRJ020 | Process Automation | Channel B (>$200K) | Build | Testing | Approved | Complete | CIO | 2025-12-21 | 2025-12-16 | Held | On track | 100 | 0 | PRJ020¦Build
PRJ020 | Process Automation | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CIO | 2026-02-19 | 2026-03-11 | Proceed |  | 100 | 20 | PRJ020¦Testing
PRJ020 | Process Automation | Channel B (>$200K) | Deployment | Handover | In Progress | In Progress | CIO | 2026-04-20 |  |  |  | 88 | 0 | PRJ020¦Deployment
PRJ020 | Process Automation | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2026-06-19 |  |  | Approved with conditions | 0 | 0 | PRJ020¦Handover
PRJ021 | Data Warehouse | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-01-20 | 2025-01-11 | Conditional | Awaiting sponsor sign-off | 100 | 0 | PRJ021¦Discovery
PRJ021 | Data Warehouse | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2025-03-21 | 2025-03-08 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ021¦Business Case / Seed Funding
PRJ021 | Data Warehouse | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2025-05-20 | 2025-05-27 | Proceed | On track | 100 | 7 | PRJ021¦Design
PRJ021 | Data Warehouse | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CTO | 2025-07-19 | 2025-07-11 | Conditional | Approved with conditions | 100 | 0 | PRJ021¦Business Case / Full Funding
PRJ021 | Data Warehouse | Channel B (>$200K) | Build | Testing | Approved | Complete | CTO | 2025-09-17 | 2025-10-09 | Rework | On track | 100 | 22 | PRJ021¦Build
PRJ021 | Data Warehouse | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CTO | 2025-11-16 | 2025-11-11 | Conditional | Approved with conditions | 100 | 0 | PRJ021¦Testing
PRJ021 | Data Warehouse | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | CTO | 2026-01-15 |  |  | Awaiting sponsor sign-off | 74 | 0 | PRJ021¦Deployment
PRJ021 | Data Warehouse | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2026-03-16 |  |  | Approved with conditions | 0 | 0 | PRJ021¦Handover
PRJ022 | DevOps Tools | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-04-11 | 2025-05-11 | Rework | Awaiting sponsor sign-off | 100 | 30 | PRJ022¦Discovery
PRJ022 | DevOps Tools | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2025-06-10 | 2025-07-01 | Rework |  | 100 | 21 | PRJ022¦Business Case / Seed Funding
PRJ022 | DevOps Tools | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CIO | 2025-08-09 | 2025-08-02 | Held |  | 100 | 0 | PRJ022¦Design
PRJ022 | DevOps Tools | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CIO | 2025-10-08 | 2025-10-10 | Conditional | Approved with conditions | 100 | 2 | PRJ022¦Business Case / Full Funding
PRJ022 | DevOps Tools | Channel B (>$200K) | Build | Testing | Approved | Complete | CIO | 2025-12-07 | 2025-12-07 | Conditional | Awaiting sponsor sign-off | 100 | 0 | PRJ022¦Build
PRJ022 | DevOps Tools | Channel B (>$200K) | Testing | Deployment | In Progress | In Progress | CIO | 2026-02-05 |  |  | On track | 49 | 0 | PRJ022¦Testing
PRJ022 | DevOps Tools | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-04-06 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ022¦Deployment
PRJ022 | DevOps Tools | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2026-06-05 |  |  | On track | 0 | 0 | PRJ022¦Handover
PRJ023 | Workforce Portal | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-11-12 | 2025-11-25 | Proceed |  | 100 | 13 | PRJ023¦Discovery
PRJ023 | Workforce Portal | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2026-01-11 | 2026-01-21 | Rework | Awaiting sponsor sign-off | 100 | 10 | PRJ023¦Business Case / Seed Funding
PRJ023 | Workforce Portal | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2026-03-12 | 2026-03-26 | Held | Awaiting sponsor sign-off | 100 | 14 | PRJ023¦Design
PRJ023 | Workforce Portal | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | COO | 2026-05-11 | 2026-06-02 | Proceed |  | 100 | 22 | PRJ023¦Business Case / Full Funding
PRJ023 | Workforce Portal | Channel B (>$200K) | Build | Testing | Approved | Complete | COO | 2026-07-10 | 2026-07-24 | Rework |  | 100 | 14 | PRJ023¦Build
PRJ023 | Workforce Portal | Channel B (>$200K) | Testing | Deployment | Approved | Complete | COO | 2026-09-08 | 2026-09-27 | Held | Approved with conditions | 100 | 19 | PRJ023¦Testing
PRJ023 | Workforce Portal | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | COO | 2026-11-07 |  |  | On track | 57 | 0 | PRJ023¦Deployment
PRJ023 | Workforce Portal | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2027-01-06 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ023¦Handover
PRJ024 | Process Mining | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-12-06 | 2025-12-26 | Conditional | On track | 100 | 20 | PRJ024¦Discovery
PRJ024 | Process Mining | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2026-02-04 | 2026-02-10 | Proceed |  | 100 | 6 | PRJ024¦Business Case / Seed Funding
PRJ024 | Process Mining | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2026-04-05 | 2026-03-27 | Held |  | 100 | 0 | PRJ024¦Design
PRJ024 | Process Mining | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CFO | 2026-06-04 | 2026-05-27 | Conditional | On track | 100 | 0 | PRJ024¦Business Case / Full Funding
PRJ024 | Process Mining | Channel B (>$200K) | Build | Testing | Approved | Complete | CFO | 2026-08-03 | 2026-08-17 | Proceed | On track | 100 | 14 | PRJ024¦Build
PRJ024 | Process Mining | Channel B (>$200K) | Testing | Deployment | Pending Approval | In Progress | CFO | 2026-10-02 |  |  | Awaiting sponsor sign-off | 50 | 0 | PRJ024¦Testing
PRJ024 | Process Mining | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CFO | 2026-12-01 |  |  |  | 0 | 0 | PRJ024¦Deployment
PRJ024 | Process Mining | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2027-01-30 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ024¦Handover
PRJ025 | Customer Insights | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-12-02 | 2025-11-22 | Rework | Approved with conditions | 100 | 0 | PRJ025¦Discovery
PRJ025 | Customer Insights | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2026-01-31 | 2026-01-19 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ025¦Business Case / Seed Funding
PRJ025 | Customer Insights | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2026-04-01 | 2026-04-30 | Conditional | On track | 100 | 29 | PRJ025¦Design
PRJ025 | Customer Insights | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CTO | 2026-05-31 | 2026-06-26 | Proceed |  | 100 | 26 | PRJ025¦Business Case / Full Funding
PRJ025 | Customer Insights | Channel B (>$200K) | Build | Testing | Pending Approval | In Progress | CTO | 2026-07-30 |  |  | On track | 44 | 0 | PRJ025¦Build
PRJ025 | Customer Insights | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CTO | 2026-09-28 |  |  | Approved with conditions | 0 | 0 | PRJ025¦Testing
PRJ025 | Customer Insights | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CTO | 2026-11-27 |  |  | On track | 0 | 0 | PRJ025¦Deployment
PRJ025 | Customer Insights | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2027-01-26 |  |  |  | 0 | 0 | PRJ025¦Handover
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-09-16 | 2025-09-08 | Held | Approved with conditions | 100 | 0 | PRJ026¦Discovery
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2025-11-15 | 2025-11-30 | Proceed | Approved with conditions | 100 | 15 | PRJ026¦Business Case / Seed Funding
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2026-01-14 | 2026-01-23 | Proceed |  | 100 | 9 | PRJ026¦Design
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | COO | 2026-03-15 | 2026-03-06 | Rework | Awaiting sponsor sign-off | 100 | 0 | PRJ026¦Business Case / Full Funding
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Build | Testing | Approved | Complete | COO | 2026-05-14 | 2026-05-18 | Conditional | On track | 100 | 4 | PRJ026¦Build
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Testing | Deployment | Pending Approval | In Progress | COO | 2026-07-13 |  |  |  | 73 | 0 | PRJ026¦Testing
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | COO | 2026-09-11 |  |  |  | 0 | 0 | PRJ026¦Deployment
PRJ026 | ERP Modernisation 2 | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2026-11-10 |  |  | Approved with conditions | 0 | 0 | PRJ026¦Handover
PRJ027 | Cyber Program | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CMO | 2025-04-29 | 2025-05-06 | Conditional | Approved with conditions | 100 | 7 | PRJ027¦Discovery
PRJ027 | Cyber Program | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CMO | 2025-06-28 | 2025-07-09 | Held | Approved with conditions | 100 | 11 | PRJ027¦Business Case / Seed Funding
PRJ027 | Cyber Program | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CMO | 2025-08-27 | 2025-08-17 | Proceed | Approved with conditions | 100 | 0 | PRJ027¦Design
PRJ027 | Cyber Program | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CMO | 2025-10-26 | 2025-10-18 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ027¦Business Case / Full Funding
PRJ027 | Cyber Program | Channel B (>$200K) | Build | Testing | Approved | Complete | CMO | 2025-12-25 | 2026-01-06 | Rework | Approved with conditions | 100 | 12 | PRJ027¦Build
PRJ027 | Cyber Program | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CMO | 2026-02-23 | 2026-02-23 | Rework |  | 100 | 0 | PRJ027¦Testing
PRJ027 | Cyber Program | Channel B (>$200K) | Deployment | Handover | Approved | Complete | CMO | 2026-04-24 | 2026-04-24 | Rework |  | 100 | 0 | PRJ027¦Deployment
PRJ027 | Cyber Program | Channel B (>$200K) | Handover | Handover | In Progress | In Progress | CMO | 2026-06-23 |  |  | Approved with conditions | 73 | 0 | PRJ027¦Handover
PRJ028 | Mobile App 2 | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-01-04 | 2025-01-14 | Rework |  | 100 | 10 | PRJ028¦Discovery
PRJ028 | Mobile App 2 | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2025-03-05 | 2025-03-05 | Held | On track | 100 | 0 | PRJ028¦Business Case / Seed Funding
PRJ028 | Mobile App 2 | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2025-05-04 | 2025-04-26 | Conditional | On track | 100 | 0 | PRJ028¦Design
PRJ028 | Mobile App 2 | Channel B (>$200K) | Business Case / Full Funding | Build | Pending Approval | In Progress | CTO | 2025-07-03 |  |  |  | 63 | 0 | PRJ028¦Business Case / Full Funding
PRJ028 | Mobile App 2 | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CTO | 2025-09-01 |  |  | Approved with conditions | 0 | 0 | PRJ028¦Build
PRJ028 | Mobile App 2 | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CTO | 2025-10-31 |  |  | On track | 0 | 0 | PRJ028¦Testing
PRJ028 | Mobile App 2 | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CTO | 2025-12-30 |  |  | Approved with conditions | 0 | 0 | PRJ028¦Deployment
PRJ028 | Mobile App 2 | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CTO | 2026-02-28 |  |  |  | 0 | 0 | PRJ028¦Handover
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Pending Approval | In Progress | CIO | 2025-11-15 |  |  |  | 56 | 0 | PRJ029¦Discovery
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Business Case / Seed Funding | Design | Not Started | Not Started | CIO | 2026-01-14 |  |  |  | 0 | 0 | PRJ029¦Business Case / Seed Funding
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Design | Business Case / Full Funding | Not Started | Not Started | CIO | 2026-03-15 |  |  | On track | 0 | 0 | PRJ029¦Design
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CIO | 2026-05-14 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ029¦Business Case / Full Funding
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CIO | 2026-07-13 |  |  | On track | 0 | 0 | PRJ029¦Build
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CIO | 2026-09-11 |  |  | On track | 0 | 0 | PRJ029¦Testing
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-11-10 |  |  | Approved with conditions | 0 | 0 | PRJ029¦Deployment
PRJ029 | Analytics Platform 2 | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2027-01-09 |  |  |  | 0 | 0 | PRJ029¦Handover
PRJ030 | Service Desk 2 | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-05-10 | 2025-04-30 | Conditional | Approved with conditions | 100 | 0 | PRJ030¦Discovery
PRJ030 | Service Desk 2 | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2025-07-09 | 2025-07-28 | Rework | On track | 100 | 19 | PRJ030¦Business Case / Seed Funding
PRJ030 | Service Desk 2 | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2025-09-07 | 2025-09-29 | Proceed | Awaiting sponsor sign-off | 100 | 22 | PRJ030¦Design
PRJ030 | Service Desk 2 | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | COO | 2025-11-06 | 2025-12-05 | Held | Approved with conditions | 100 | 29 | PRJ030¦Business Case / Full Funding
PRJ030 | Service Desk 2 | Channel B (>$200K) | Build | Testing | Pending Approval | In Progress | COO | 2026-01-05 |  |  |  | 67 | 0 | PRJ030¦Build
PRJ030 | Service Desk 2 | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | COO | 2026-03-06 |  |  | On track | 0 | 0 | PRJ030¦Testing
PRJ030 | Service Desk 2 | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | COO | 2026-05-05 |  |  |  | 0 | 0 | PRJ030¦Deployment
PRJ030 | Service Desk 2 | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2026-07-04 |  |  | Approved with conditions | 0 | 0 | PRJ030¦Handover
PRJ031 | Quality Mgmt | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-08-27 | 2025-08-12 | Conditional |  | 100 | 0 | PRJ031¦Discovery
PRJ031 | Quality Mgmt | Channel B (>$200K) | Business Case / Seed Funding | Design | In Progress | In Progress | CIO | 2025-10-26 |  |  | Awaiting sponsor sign-off | 73 | 0 | PRJ031¦Business Case / Seed Funding
PRJ031 | Quality Mgmt | Channel B (>$200K) | Design | Business Case / Full Funding | Not Started | Not Started | CIO | 2025-12-25 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ031¦Design
PRJ031 | Quality Mgmt | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CIO | 2026-02-23 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ031¦Business Case / Full Funding
PRJ031 | Quality Mgmt | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CIO | 2026-04-24 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ031¦Build
PRJ031 | Quality Mgmt | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CIO | 2026-06-23 |  |  |  | 0 | 0 | PRJ031¦Testing
PRJ031 | Quality Mgmt | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-08-22 |  |  | On track | 0 | 0 | PRJ031¦Deployment
PRJ031 | Quality Mgmt | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2026-10-21 |  |  |  | 0 | 0 | PRJ031¦Handover
PRJ032 | Compliance Hub | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-12-20 | 2026-01-19 | Proceed | On track | 100 | 30 | PRJ032¦Discovery
PRJ032 | Compliance Hub | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2026-02-18 | 2026-03-04 | Rework |  | 100 | 14 | PRJ032¦Business Case / Seed Funding
PRJ032 | Compliance Hub | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CIO | 2026-04-19 | 2026-05-05 | Conditional | Awaiting sponsor sign-off | 100 | 16 | PRJ032¦Design
PRJ032 | Compliance Hub | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CIO | 2026-06-18 | 2026-06-13 | Rework |  | 100 | 0 | PRJ032¦Business Case / Full Funding
PRJ032 | Compliance Hub | Channel B (>$200K) | Build | Testing | Pending Approval | In Progress | CIO | 2026-08-17 |  |  | Approved with conditions | 87 | 0 | PRJ032¦Build
PRJ032 | Compliance Hub | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CIO | 2026-10-16 |  |  |  | 0 | 0 | PRJ032¦Testing
PRJ032 | Compliance Hub | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-12-15 |  |  |  | 0 | 0 | PRJ032¦Deployment
PRJ032 | Compliance Hub | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2027-02-13 |  |  |  | 0 | 0 | PRJ032¦Handover
PRJ033 | Risk Platform | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CTO | 2025-11-22 | 2025-11-30 | Held | Approved with conditions | 100 | 8 | PRJ033¦Discovery
PRJ033 | Risk Platform | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CTO | 2026-01-21 | 2026-01-17 | Proceed | On track | 100 | 0 | PRJ033¦Business Case / Seed Funding
PRJ033 | Risk Platform | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CTO | 2026-03-22 | 2026-03-21 | Rework | Approved with conditions | 100 | 0 | PRJ033¦Design
PRJ033 | Risk Platform | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CTO | 2026-05-21 | 2026-06-01 | Rework | Awaiting sponsor sign-off | 100 | 11 | PRJ033¦Business Case / Full Funding
PRJ033 | Risk Platform | Channel B (>$200K) | Build | Testing | Approved | Complete | CTO | 2026-07-20 | 2026-07-09 | Rework |  | 100 | 0 | PRJ033¦Build
PRJ033 | Risk Platform | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CTO | 2026-09-18 | 2026-10-05 | Proceed | Approved with conditions | 100 | 17 | PRJ033¦Testing
PRJ033 | Risk Platform | Channel B (>$200K) | Deployment | Handover | Approved | Complete | CTO | 2026-11-17 | 2026-11-16 | Proceed | On track | 100 | 0 | PRJ033¦Deployment
PRJ033 | Risk Platform | Channel B (>$200K) | Handover | Handover | In Progress | In Progress | CTO | 2027-01-16 |  |  | Awaiting sponsor sign-off | 89 | 0 | PRJ033¦Handover
PRJ034 | Treasury Sys | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CMO | 2025-11-09 | 2025-11-14 | Proceed | On track | 100 | 5 | PRJ034¦Discovery
PRJ034 | Treasury Sys | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CMO | 2026-01-08 | 2025-12-24 | Rework | Approved with conditions | 100 | 0 | PRJ034¦Business Case / Seed Funding
PRJ034 | Treasury Sys | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CMO | 2026-03-09 | 2026-03-12 | Rework | Approved with conditions | 100 | 3 | PRJ034¦Design
PRJ034 | Treasury Sys | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CMO | 2026-05-08 | 2026-05-22 | Rework | On track | 100 | 14 | PRJ034¦Business Case / Full Funding
PRJ034 | Treasury Sys | Channel B (>$200K) | Build | Testing | Pending Approval | In Progress | CMO | 2026-07-07 |  |  | Approved with conditions | 40 | 0 | PRJ034¦Build
PRJ034 | Treasury Sys | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CMO | 2026-09-05 |  |  |  | 0 | 0 | PRJ034¦Testing
PRJ034 | Treasury Sys | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CMO | 2026-11-04 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ034¦Deployment
PRJ034 | Treasury Sys | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CMO | 2027-01-03 |  |  |  | 0 | 0 | PRJ034¦Handover
PRJ035 | Payroll Cloud | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | COO | 2025-05-04 | 2025-04-19 | Held | Awaiting sponsor sign-off | 100 | 0 | PRJ035¦Discovery
PRJ035 | Payroll Cloud | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | COO | 2025-07-03 | 2025-06-24 | Conditional | Approved with conditions | 100 | 0 | PRJ035¦Business Case / Seed Funding
PRJ035 | Payroll Cloud | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | COO | 2025-09-01 | 2025-09-12 | Held |  | 100 | 11 | PRJ035¦Design
PRJ035 | Payroll Cloud | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | COO | 2025-10-31 | 2025-10-25 | Rework |  | 100 | 0 | PRJ035¦Business Case / Full Funding
PRJ035 | Payroll Cloud | Channel B (>$200K) | Build | Testing | Approved | Complete | COO | 2025-12-30 | 2025-12-17 | Conditional | On track | 100 | 0 | PRJ035¦Build
PRJ035 | Payroll Cloud | Channel B (>$200K) | Testing | Deployment | In Progress | In Progress | COO | 2026-02-28 |  |  | On track | 87 | 0 | PRJ035¦Testing
PRJ035 | Payroll Cloud | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | COO | 2026-04-29 |  |  |  | 0 | 0 | PRJ035¦Deployment
PRJ035 | Payroll Cloud | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | COO | 2026-06-28 |  |  | Approved with conditions | 0 | 0 | PRJ035¦Handover
PRJ036 | HR Self-Service | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CFO | 2025-05-09 | 2025-04-28 | Proceed | On track | 100 | 0 | PRJ036¦Discovery
PRJ036 | HR Self-Service | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CFO | 2025-07-08 | 2025-08-04 | Conditional | Approved with conditions | 100 | 27 | PRJ036¦Business Case / Seed Funding
PRJ036 | HR Self-Service | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CFO | 2025-09-06 | 2025-09-09 | Rework | Awaiting sponsor sign-off | 100 | 3 | PRJ036¦Design
PRJ036 | HR Self-Service | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CFO | 2025-11-05 | 2025-11-15 | Rework | Awaiting sponsor sign-off | 100 | 10 | PRJ036¦Business Case / Full Funding
PRJ036 | HR Self-Service | Channel B (>$200K) | Build | Testing | Approved | Complete | CFO | 2026-01-04 | 2026-01-17 | Rework | Approved with conditions | 100 | 13 | PRJ036¦Build
PRJ036 | HR Self-Service | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CFO | 2026-03-05 | 2026-02-22 | Conditional | Approved with conditions | 100 | 0 | PRJ036¦Testing
PRJ036 | HR Self-Service | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | CFO | 2026-05-04 |  |  | Approved with conditions | 46 | 0 | PRJ036¦Deployment
PRJ036 | HR Self-Service | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CFO | 2026-07-03 |  |  | On track | 0 | 0 | PRJ036¦Handover
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CMO | 2025-03-06 | 2025-03-11 | Held |  | 100 | 5 | PRJ037¦Discovery
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CMO | 2025-05-05 | 2025-05-24 | Rework | Approved with conditions | 100 | 19 | PRJ037¦Business Case / Seed Funding
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CMO | 2025-07-04 | 2025-07-17 | Rework | On track | 100 | 13 | PRJ037¦Design
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CMO | 2025-09-02 | 2025-09-03 | Proceed |  | 100 | 1 | PRJ037¦Business Case / Full Funding
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Build | Testing | Approved | Complete | CMO | 2025-11-01 | 2025-10-27 | Rework |  | 100 | 0 | PRJ037¦Build
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CMO | 2025-12-31 | 2025-12-29 | Rework | Approved with conditions | 100 | 0 | PRJ037¦Testing
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Deployment | Handover | Approved | Complete | CMO | 2026-03-01 | 2026-02-19 | Conditional | Awaiting sponsor sign-off | 100 | 0 | PRJ037¦Deployment
PRJ037 | SAP S/4HANA | Channel B (>$200K) | Handover | Handover | Pending Approval | In Progress | CMO | 2026-04-30 |  |  | Awaiting sponsor sign-off | 56 | 0 | PRJ037¦Handover
PRJ038 | Salesforce CRM | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-09-09 | 2025-08-26 | Held | On track | 100 | 0 | PRJ038¦Discovery
PRJ038 | Salesforce CRM | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2025-11-08 | 2025-11-28 | Conditional |  | 100 | 20 | PRJ038¦Business Case / Seed Funding
PRJ038 | Salesforce CRM | Channel B (>$200K) | Design | Business Case / Full Funding | Pending Approval | In Progress | CIO | 2026-01-07 |  |  | Approved with conditions | 47 | 0 | PRJ038¦Design
PRJ038 | Salesforce CRM | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CIO | 2026-03-08 |  |  |  | 0 | 0 | PRJ038¦Business Case / Full Funding
PRJ038 | Salesforce CRM | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CIO | 2026-05-07 |  |  | Approved with conditions | 0 | 0 | PRJ038¦Build
PRJ038 | Salesforce CRM | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CIO | 2026-07-06 |  |  | On track | 0 | 0 | PRJ038¦Testing
PRJ038 | Salesforce CRM | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-09-04 |  |  |  | 0 | 0 | PRJ038¦Deployment
PRJ038 | Salesforce CRM | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2026-11-03 |  |  | Awaiting sponsor sign-off | 0 | 0 | PRJ038¦Handover
PRJ039 | M365 Rollout | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-11-14 | 2025-10-31 | Proceed | Approved with conditions | 100 | 0 | PRJ039¦Discovery
PRJ039 | M365 Rollout | Channel B (>$200K) | Business Case / Seed Funding | Design | In Progress | In Progress | CIO | 2026-01-13 |  |  | Approved with conditions | 45 | 0 | PRJ039¦Business Case / Seed Funding
PRJ039 | M365 Rollout | Channel B (>$200K) | Design | Business Case / Full Funding | Not Started | Not Started | CIO | 2026-03-14 |  |  |  | 0 | 0 | PRJ039¦Design
PRJ039 | M365 Rollout | Channel B (>$200K) | Business Case / Full Funding | Build | Not Started | Not Started | CIO | 2026-05-13 |  |  | On track | 0 | 0 | PRJ039¦Business Case / Full Funding
PRJ039 | M365 Rollout | Channel B (>$200K) | Build | Testing | Not Started | Not Started | CIO | 2026-07-12 |  |  | Approved with conditions | 0 | 0 | PRJ039¦Build
PRJ039 | M365 Rollout | Channel B (>$200K) | Testing | Deployment | Not Started | Not Started | CIO | 2026-09-10 |  |  | On track | 0 | 0 | PRJ039¦Testing
PRJ039 | M365 Rollout | Channel B (>$200K) | Deployment | Handover | Not Started | Not Started | CIO | 2026-11-09 |  |  | On track | 0 | 0 | PRJ039¦Deployment
PRJ039 | M365 Rollout | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2027-01-08 |  |  | On track | 0 | 0 | PRJ039¦Handover
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Discovery | Business Case / Seed Funding | Approved | Complete | CIO | 2025-02-06 | 2025-02-02 | Rework | Approved with conditions | 100 | 0 | PRJ040¦Discovery
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Business Case / Seed Funding | Design | Approved | Complete | CIO | 2025-04-07 | 2025-04-03 | Rework | Awaiting sponsor sign-off | 100 | 0 | PRJ040¦Business Case / Seed Funding
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Design | Business Case / Full Funding | Approved | Complete | CIO | 2025-06-06 | 2025-06-19 | Conditional |  | 100 | 13 | PRJ040¦Design
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Business Case / Full Funding | Build | Approved | Complete | CIO | 2025-08-05 | 2025-08-29 | Conditional | Awaiting sponsor sign-off | 100 | 24 | PRJ040¦Business Case / Full Funding
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Build | Testing | Approved | Complete | CIO | 2025-10-04 | 2025-10-20 | Held | On track | 100 | 16 | PRJ040¦Build
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Testing | Deployment | Approved | Complete | CIO | 2025-12-03 | 2025-11-21 | Proceed | Awaiting sponsor sign-off | 100 | 0 | PRJ040¦Testing
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Deployment | Handover | Pending Approval | In Progress | CIO | 2026-02-01 |  |  | On track | 52 | 0 | PRJ040¦Deployment
PRJ040 | Zero-Trust Net | Channel B (>$200K) | Handover | Handover | Not Started | Not Started | CIO | 2026-04-02 |  |  | Approved with conditions | 0 | 0 | PRJ040¦Handover

## Financials
Project ID | Month | CAPEX | OPEX | Actual | Forecast | Variance | Planned Value | Earned Value
PRJ001 | Jan | 109965.6667 | 106181.4167 | 261933 | 301306 | 39373 | 251156 | 195289
PRJ001 | Feb | 109965.6667 | 106181.4167 | 231778 | 225033 | -6745 | 192576 | 147431
PRJ001 | Mar | 109965.6667 | 106181.4167 | 174362 | 182142 | 7780 | 135066 | 165831
PRJ001 | Apr | 109965.6667 | 106181.4167 | 272440 | 283263 | 10823 | 203135 | 213717
PRJ001 | May | 109965.6667 | 106181.4167 | 237193 | 204783 | -32410 | 223895 | 154098
PRJ001 | Jun | 109965.6667 | 106181.4167 | 222203 | 317214 | 95011 | 276980 | 191631
PRJ001 | Jul | 109965.6667 | 106181.4167 | 245586 | 292094 | 46508 | 208528 | 227833
PRJ001 | Aug | 109965.6667 | 106181.4167 | 239886 | 257711 | 17825 | 271464 | 259232
PRJ001 | Sep | 109965.6667 | 106181.4167 | 164832 | 179916 | 15084 | 165087 | 134079
PRJ001 | Oct | 109965.6667 | 106181.4167 | 175825 | 157796 | -18029 | 137163 | 147237
PRJ001 | Nov | 109965.6667 | 106181.4167 | 227590 | 270516 | 42926 | 274054 | 288863
PRJ001 | Dec | 109965.6667 | 106181.4167 | 291696 | 322783 | 31087 | 247640 | 276531
PRJ002 | Jan | 92189.3333 | 62136.9167 | 90038 | 112009 | 21971 | 99705 | 117449
PRJ002 | Feb | 92189.3333 | 62136.9167 | 194030 | 198009 | 3979 | 208543 | 184132
PRJ002 | Mar | 92189.3333 | 62136.9167 | 150645 | 221694 | 71049 | 176779 | 152997
PRJ002 | Apr | 92189.3333 | 62136.9167 | 143262 | 168928 | 25666 | 147024 | 112397
PRJ002 | May | 92189.3333 | 62136.9167 | 140984 | 240376 | 99392 | 225186 | 225828
PRJ002 | Jun | 92189.3333 | 62136.9167 | 141736 | 124067 | -17669 | 125912 | 92231
PRJ002 | Jul | 92189.3333 | 62136.9167 | 185760 | 164296 | -21464 | 167790 | 152441
PRJ002 | Aug | 92189.3333 | 62136.9167 | 136745 | 179635 | 42890 | 151856 | 131156
PRJ002 | Sep | 92189.3333 | 62136.9167 | 69148 | 94453 | 25305 | 86663 | 83175
PRJ002 | Oct | 92189.3333 | 62136.9167 | 127592 | 135243 | 7651 | 130937 | 138204
PRJ002 | Nov | 92189.3333 | 62136.9167 | 122553 | 165200 | 42647 | 174324 | 129142
PRJ002 | Dec | 92189.3333 | 62136.9167 | 105554 | 156157 | 50603 | 144984 | 147917
PRJ003 | Jan | 205302.6667 | 119293.25 | 246820 | 400266 | 153446 | 352250 | 302762
PRJ003 | Feb | 205302.6667 | 119293.25 | 191842 | 315504 | 123662 | 233702 | 180038
PRJ003 | Mar | 205302.6667 | 119293.25 | 215485 | 245450 | 29965 | 214893 | 160400
PRJ003 | Apr | 205302.6667 | 119293.25 | 155226 | 259102 | 103876 | 240477 | 164323
PRJ003 | May | 205302.6667 | 119293.25 | 214757 | 306212 | 91455 | 264408 | 195386
PRJ003 | Jun | 205302.6667 | 119293.25 | 140201 | 173015 | 32814 | 182088 | 135960
PRJ003 | Jul | 205302.6667 | 119293.25 | 281245 | 278907 | -2338 | 274688 | 203699
PRJ003 | Aug | 205302.6667 | 119293.25 | 319411 | 374893 | 55482 | 346630 | 268023
PRJ003 | Sep | 205302.6667 | 119293.25 | 219420 | 239819 | 20399 | 183684 | 165785
PRJ003 | Oct | 205302.6667 | 119293.25 | 348332 | 404205 | 55873 | 376863 | 360982
PRJ003 | Nov | 205302.6667 | 119293.25 | 322568 | 317967 | -4601 | 304740 | 246739
PRJ003 | Dec | 205302.6667 | 119293.25 | 273940 | 293508 | 19568 | 280505 | 263358
PRJ004 | Jan | 73754.0833 | 54888.0833 | 97924 | 161584 | 63660 | 123799 | 147410
PRJ004 | Feb | 73754.0833 | 54888.0833 | 119620 | 181451 | 61831 | 179974 | 139656
PRJ004 | Mar | 73754.0833 | 54888.0833 | 175239 | 166179 | -9060 | 169227 | 166386
PRJ004 | Apr | 73754.0833 | 54888.0833 | 72332 | 88892 | 16560 | 77455 | 70936
PRJ004 | May | 73754.0833 | 54888.0833 | 156706 | 177183 | 20477 | 151959 | 131649
PRJ004 | Jun | 73754.0833 | 54888.0833 | 105284 | 122028 | 16744 | 105908 | 88714
PRJ004 | Jul | 73754.0833 | 54888.0833 | 75910 | 86245 | 10335 | 77166 | 65885
PRJ004 | Aug | 73754.0833 | 54888.0833 | 82638 | 129400 | 46762 | 110691 | 112653
PRJ004 | Sep | 73754.0833 | 54888.0833 | 122877 | 115596 | -7281 | 99676 | 105649
PRJ004 | Oct | 73754.0833 | 54888.0833 | 110719 | 200408 | 89689 | 156177 | 129233
PRJ004 | Nov | 73754.0833 | 54888.0833 | 90091 | 155062 | 64971 | 114764 | 137361
PRJ004 | Dec | 73754.0833 | 54888.0833 | 104571 | 142927 | 38356 | 132240 | 96098
PRJ005 | Jan | 72569.3333 | 66142.5833 | 135086 | 151706 | 16620 | 135499 | 129231
PRJ005 | Feb | 72569.3333 | 66142.5833 | 88599 | 120394 | 31795 | 96992 | 110288
PRJ005 | Mar | 72569.3333 | 66142.5833 | 94069 | 149703 | 55634 | 130679 | 94531
PRJ005 | Apr | 72569.3333 | 66142.5833 | 155419 | 158059 | 2640 | 157440 | 130895
PRJ005 | May | 72569.3333 | 66142.5833 | 76086 | 122810 | 46724 | 113621 | 82981
PRJ005 | Jun | 72569.3333 | 66142.5833 | 132771 | 161214 | 28443 | 167728 | 154138
PRJ005 | Jul | 72569.3333 | 66142.5833 | 109632 | 130009 | 20377 | 126378 | 136262
PRJ005 | Aug | 72569.3333 | 66142.5833 | 163712 | 168669 | 4957 | 153782 | 106024
PRJ005 | Sep | 72569.3333 | 66142.5833 | 106838 | 199355 | 92517 | 164286 | 148552
PRJ005 | Oct | 72569.3333 | 66142.5833 | 86884 | 84616 | -2268 | 86092 | 74279
PRJ005 | Nov | 72569.3333 | 66142.5833 | 96804 | 120387 | 23583 | 111678 | 108870
PRJ005 | Dec | 72569.3333 | 66142.5833 | 101218 | 159778 | 58560 | 144947 | 145700
PRJ006 | Jan | 79673.0833 | 58465.4167 | 123678 | 133263 | 9585 | 112343 | 85531
PRJ006 | Feb | 79673.0833 | 58465.4167 | 190963 | 178836 | -12127 | 174562 | 177291
PRJ006 | Mar | 79673.0833 | 58465.4167 | 99885 | 114337 | 14452 | 97685 | 93605
PRJ006 | Apr | 79673.0833 | 58465.4167 | 146223 | 167983 | 21760 | 144777 | 155337
PRJ006 | May | 79673.0833 | 58465.4167 | 90698 | 103797 | 13099 | 107542 | 94659
PRJ006 | Jun | 79673.0833 | 58465.4167 | 90092 | 130943 | 40851 | 121229 | 121943
PRJ006 | Jul | 79673.0833 | 58465.4167 | 155717 | 169032 | 13315 | 148498 | 102387
PRJ006 | Aug | 79673.0833 | 58465.4167 | 61501 | 92935 | 31434 | 80328 | 56771
PRJ006 | Sep | 79673.0833 | 58465.4167 | 92086 | 141250 | 49164 | 135539 | 103255
PRJ006 | Oct | 79673.0833 | 58465.4167 | 110439 | 147223 | 36784 | 146729 | 119201
PRJ006 | Nov | 79673.0833 | 58465.4167 | 184643 | 158061 | -26582 | 168408 | 137806
PRJ006 | Dec | 79673.0833 | 58465.4167 | 120243 | 146619 | 26376 | 155821 | 105119
PRJ007 | Jan | 225706.75 | 70182.8333 | 196291 | 249973 | 53682 | 197802 | 161202
PRJ007 | Feb | 225706.75 | 70182.8333 | 307262 | 385177 | 77915 | 304194 | 310907
PRJ007 | Mar | 225706.75 | 70182.8333 | 164941 | 158475 | -6466 | 160282 | 133863
PRJ007 | Apr | 225706.75 | 70182.8333 | 296183 | 345522 | 49339 | 287512 | 321938
PRJ007 | May | 225706.75 | 70182.8333 | 165907 | 235515 | 69608 | 190355 | 172825
PRJ007 | Jun | 225706.75 | 70182.8333 | 327855 | 369186 | 41331 | 296896 | 306555
PRJ007 | Jul | 225706.75 | 70182.8333 | 185842 | 245786 | 59944 | 195612 | 218176
PRJ007 | Aug | 225706.75 | 70182.8333 | 227159 | 247232 | 20073 | 204453 | 225103
PRJ007 | Sep | 225706.75 | 70182.8333 | 416792 | 392642 | -24150 | 332295 | 388445
PRJ007 | Oct | 225706.75 | 70182.8333 | 273901 | 414869 | 140968 | 316865 | 342709
PRJ007 | Nov | 225706.75 | 70182.8333 | 229429 | 311248 | 81819 | 236510 | 278438
PRJ007 | Dec | 225706.75 | 70182.8333 | 151833 | 279366 | 127533 | 226766 | 209506
PRJ008 | Jan | 217745.75 | 89098 | 177179 | 218094 | 40915 | 199331 | 173096
PRJ008 | Feb | 217745.75 | 89098 | 227604 | 242557 | 14953 | 231876 | 215128
PRJ008 | Mar | 217745.75 | 89098 | 177956 | 294826 | 116870 | 218520 | 236227
PRJ008 | Apr | 217745.75 | 89098 | 123583 | 179691 | 56108 | 158932 | 133435
PRJ008 | May | 217745.75 | 89098 | 271529 | 277840 | 6311 | 230492 | 227827
PRJ008 | Jun | 217745.75 | 89098 | 215651 | 253800 | 38149 | 263280 | 271290
PRJ008 | Jul | 217745.75 | 89098 | 266388 | 364302 | 97914 | 356334 | 351233
PRJ008 | Aug | 217745.75 | 89098 | 141882 | 227456 | 85574 | 170360 | 155788
PRJ008 | Sep | 217745.75 | 89098 | 118194 | 185503 | 67309 | 183153 | 138289
PRJ008 | Oct | 217745.75 | 89098 | 315956 | 294132 | -21824 | 313148 | 279246
PRJ008 | Nov | 217745.75 | 89098 | 182118 | 234738 | 52620 | 216999 | 141712
PRJ008 | Dec | 217745.75 | 89098 | 277871 | 395974 | 118103 | 296610 | 261866
PRJ009 | Jan | 76087 | 18389.75 | 117100 | 139244 | 22144 | 104203 | 111279
PRJ009 | Feb | 76087 | 18389.75 | 46922 | 69310 | 22388 | 63383 | 63573
PRJ009 | Mar | 76087 | 18389.75 | 80716 | 101130 | 20414 | 82339 | 89290
PRJ009 | Apr | 76087 | 18389.75 | 85788 | 145716 | 59928 | 106065 | 98577
PRJ009 | May | 76087 | 18389.75 | 42056 | 59776 | 17720 | 51969 | 50382
PRJ009 | Jun | 76087 | 18389.75 | 110533 | 108352 | -2181 | 88071 | 82141
PRJ009 | Jul | 76087 | 18389.75 | 95222 | 98423 | 3201 | 88910 | 89050
PRJ009 | Aug | 76087 | 18389.75 | 80842 | 105464 | 24622 | 74565 | 78836
PRJ009 | Sep | 76087 | 18389.75 | 76729 | 83566 | 6837 | 60951 | 59581
PRJ009 | Oct | 76087 | 18389.75 | 52145 | 79711 | 27566 | 77458 | 63499
PRJ009 | Nov | 76087 | 18389.75 | 73608 | 74447 | 839 | 71452 | 57292
PRJ009 | Dec | 76087 | 18389.75 | 60621 | 60554 | -67 | 57728 | 53829
PRJ010 | Jan | 100290.5 | 99285.8333 | 98176 | 114790 | 16614 | 93694 | 87427
PRJ010 | Feb | 100290.5 | 99285.8333 | 201274 | 185485 | -15789 | 151793 | 129013
PRJ010 | Mar | 100290.5 | 99285.8333 | 182868 | 204656 | 21788 | 187200 | 178143
PRJ010 | Apr | 100290.5 | 99285.8333 | 132659 | 183878 | 51219 | 180265 | 183959
PRJ010 | May | 100290.5 | 99285.8333 | 172042 | 164878 | -7164 | 150657 | 118701
PRJ010 | Jun | 100290.5 | 99285.8333 | 159007 | 256149 | 97142 | 203785 | 236531
PRJ010 | Jul | 100290.5 | 99285.8333 | 182855 | 199187 | 16332 | 151634 | 141342
PRJ010 | Aug | 100290.5 | 99285.8333 | 246738 | 301534 | 54796 | 245550 | 238180
PRJ010 | Sep | 100290.5 | 99285.8333 | 177572 | 215865 | 38293 | 169272 | 203642
PRJ010 | Oct | 100290.5 | 99285.8333 | 198049 | 262071 | 64022 | 193707 | 192775
PRJ010 | Nov | 100290.5 | 99285.8333 | 147467 | 195111 | 47644 | 181437 | 148942
PRJ010 | Dec | 100290.5 | 99285.8333 | 249271 | 256961 | 7690 | 201386 | 232185
PRJ011 | Jan | 28487.25 | 10502 | 34599 | 52062 | 17463 | 48783 | 46675
PRJ011 | Feb | 28487.25 | 10502 | 36451 | 38135 | 1684 | 34921 | 30178
PRJ011 | Mar | 28487.25 | 10502 | 23679 | 31337 | 7658 | 29690 | 31535
PRJ011 | Apr | 28487.25 | 10502 | 40960 | 51615 | 10655 | 41562 | 31066
PRJ011 | May | 28487.25 | 10502 | 30609 | 36883 | 6274 | 30546 | 31087
PRJ011 | Jun | 28487.25 | 10502 | 47565 | 51209 | 3644 | 42031 | 28349
PRJ011 | Jul | 28487.25 | 10502 | 21470 | 33359 | 11889 | 25527 | 21921
PRJ011 | Aug | 28487.25 | 10502 | 33508 | 34518 | 1010 | 33700 | 21726
PRJ011 | Sep | 28487.25 | 10502 | 45249 | 47474 | 2225 | 42577 | 39251
PRJ011 | Oct | 28487.25 | 10502 | 37681 | 41766 | 4085 | 32568 | 32882
PRJ011 | Nov | 28487.25 | 10502 | 53872 | 57150 | 3278 | 43090 | 41008
PRJ011 | Dec | 28487.25 | 10502 | 20485 | 24647 | 4162 | 21919 | 20974
PRJ012 | Jan | 127913.1667 | 30774.25 | 201041 | 236940 | 35899 | 197887 | 183096
PRJ012 | Feb | 127913.1667 | 30774.25 | 155617 | 196708 | 41091 | 195078 | 140558
PRJ012 | Mar | 127913.1667 | 30774.25 | 92571 | 118224 | 25653 | 106977 | 76539
PRJ012 | Apr | 127913.1667 | 30774.25 | 123892 | 174425 | 50533 | 134525 | 107088
PRJ012 | May | 127913.1667 | 30774.25 | 130264 | 128763 | -1501 | 113915 | 97280
PRJ012 | Jun | 127913.1667 | 30774.25 | 162311 | 160257 | -2054 | 138092 | 110204
PRJ012 | Jul | 127913.1667 | 30774.25 | 83713 | 107159 | 23446 | 84792 | 71333
PRJ012 | Aug | 127913.1667 | 30774.25 | 91188 | 111544 | 20356 | 111068 | 94904
PRJ012 | Sep | 127913.1667 | 30774.25 | 253202 | 209468 | -43734 | 216802 | 180694
PRJ012 | Oct | 127913.1667 | 30774.25 | 194795 | 243818 | 49023 | 200345 | 155819
PRJ012 | Nov | 127913.1667 | 30774.25 | 178874 | 233493 | 54619 | 193228 | 217584
PRJ012 | Dec | 127913.1667 | 30774.25 | 196317 | 198274 | 1957 | 158552 | 188065
PRJ013 | Jan | 194776.5 | 133782.1667 | 290574 | 254795 | -35779 | 268160 | 220530
PRJ013 | Feb | 194776.5 | 133782.1667 | 163155 | 190760 | 27605 | 169754 | 134284
PRJ013 | Mar | 194776.5 | 133782.1667 | 243993 | 293409 | 49416 | 244934 | 220206
PRJ013 | Apr | 194776.5 | 133782.1667 | 302728 | 453864 | 151136 | 387465 | 284002
PRJ013 | May | 194776.5 | 133782.1667 | 247100 | 293397 | 46297 | 237679 | 197743
PRJ013 | Jun | 194776.5 | 133782.1667 | 264690 | 293123 | 28433 | 302990 | 263854
PRJ013 | Jul | 194776.5 | 133782.1667 | 363747 | 389196 | 25449 | 349686 | 233962
PRJ013 | Aug | 194776.5 | 133782.1667 | 356886 | 350380 | -6506 | 293607 | 325511
PRJ013 | Sep | 194776.5 | 133782.1667 | 281329 | 307980 | 26651 | 274172 | 197928
PRJ013 | Oct | 194776.5 | 133782.1667 | 302991 | 395733 | 92742 | 287702 | 302316
PRJ013 | Nov | 194776.5 | 133782.1667 | 432841 | 445683 | 12842 | 444162 | 368564
PRJ013 | Dec | 194776.5 | 133782.1667 | 174055 | 303083 | 129028 | 262139 | 282754
PRJ014 | Jan | 133976.6667 | 64214.4167 | 197701 | 185330 | -12371 | 165888 | 161347
PRJ014 | Feb | 133976.6667 | 64214.4167 | 126522 | 197458 | 70936 | 149403 | 119781
PRJ014 | Mar | 133976.6667 | 64214.4167 | 267663 | 295690 | 28027 | 260661 | 204723
PRJ014 | Apr | 133976.6667 | 64214.4167 | 121288 | 176961 | 55673 | 180897 | 152141
PRJ014 | May | 133976.6667 | 64214.4167 | 140696 | 140283 | -413 | 140115 | 145596
PRJ014 | Jun | 133976.6667 | 64214.4167 | 154942 | 166586 | 11644 | 156420 | 140961
PRJ014 | Jul | 133976.6667 | 64214.4167 | 136975 | 151621 | 14646 | 142877 | 115853
PRJ014 | Aug | 133976.6667 | 64214.4167 | 230756 | 211193 | -19563 | 214138 | 215169
PRJ014 | Sep | 133976.6667 | 64214.4167 | 138611 | 191125 | 52514 | 153788 | 155168
PRJ014 | Oct | 133976.6667 | 64214.4167 | 178902 | 276271 | 97369 | 227672 | 254878
PRJ014 | Nov | 133976.6667 | 64214.4167 | 69573 | 117241 | 47668 | 92058 | 95086
PRJ014 | Dec | 133976.6667 | 64214.4167 | 201429 | 198512 | -2917 | 173800 | 191166
PRJ015 | Jan | 65721.5 | 45432 | 95376 | 116442 | 21066 | 116271 | 108823
PRJ015 | Feb | 65721.5 | 45432 | 81941 | 95737 | 13796 | 86274 | 82886
PRJ015 | Mar | 65721.5 | 45432 | 134193 | 139289 | 5096 | 133573 | 115177
PRJ015 | Apr | 65721.5 | 45432 | 102688 | 126129 | 23441 | 104618 | 87633
PRJ015 | May | 65721.5 | 45432 | 75183 | 81588 | 6405 | 77862 | 54984
PRJ015 | Jun | 65721.5 | 45432 | 86186 | 112329 | 26143 | 98364 | 68294
PRJ015 | Jul | 65721.5 | 45432 | 128260 | 138835 | 10575 | 130155 | 125846
PRJ015 | Aug | 65721.5 | 45432 | 67053 | 103804 | 36751 | 85222 | 84077
PRJ015 | Sep | 65721.5 | 45432 | 105581 | 150945 | 45364 | 121001 | 99284
PRJ015 | Oct | 65721.5 | 45432 | 113310 | 141602 | 28292 | 121301 | 88323
PRJ015 | Nov | 65721.5 | 45432 | 64488 | 66666 | 2178 | 58586 | 52115
PRJ015 | Dec | 65721.5 | 45432 | 77307 | 119206 | 41899 | 102047 | 85677
PRJ016 | Jan | 237973 | 56641.1667 | 185937 | 302783 | 116846 | 219775 | 168626
PRJ016 | Feb | 237973 | 56641.1667 | 267944 | 266487 | -1457 | 267851 | 182296
PRJ016 | Mar | 237973 | 56641.1667 | 236287 | 229876 | -6411 | 199852 | 133009
PRJ016 | Apr | 237973 | 56641.1667 | 264071 | 328052 | 63981 | 316803 | 354993
PRJ016 | May | 237973 | 56641.1667 | 368879 | 381607 | 12728 | 348437 | 337267
PRJ016 | Jun | 237973 | 56641.1667 | 166922 | 246429 | 79507 | 197986 | 178121
PRJ016 | Jul | 237973 | 56641.1667 | 238509 | 278949 | 40440 | 252872 | 283972
PRJ016 | Aug | 237973 | 56641.1667 | 196434 | 269006 | 72572 | 260592 | 246248
PRJ016 | Sep | 237973 | 56641.1667 | 171181 | 186801 | 15620 | 180182 | 131076
PRJ016 | Oct | 237973 | 56641.1667 | 354167 | 369446 | 15279 | 314092 | 273210
PRJ016 | Nov | 237973 | 56641.1667 | 205768 | 227765 | 21997 | 228500 | 217881
PRJ016 | Dec | 237973 | 56641.1667 | 263442 | 295925 | 32483 | 254933 | 173445
PRJ017 | Jan | 137991.8333 | 103565.5 | 135135 | 210321 | 75186 | 161624 | 179369
PRJ017 | Feb | 137991.8333 | 103565.5 | 187808 | 215899 | 28091 | 180139 | 127320
PRJ017 | Mar | 137991.8333 | 103565.5 | 178923 | 185575 | 6652 | 165382 | 125472
PRJ017 | Apr | 137991.8333 | 103565.5 | 243472 | 238354 | -5118 | 206895 | 168293
PRJ017 | May | 137991.8333 | 103565.5 | 236246 | 320988 | 84742 | 262570 | 219104
PRJ017 | Jun | 137991.8333 | 103565.5 | 168469 | 220523 | 52054 | 210462 | 199999
PRJ017 | Jul | 137991.8333 | 103565.5 | 299029 | 310618 | 11589 | 288576 | 204096
PRJ017 | Aug | 137991.8333 | 103565.5 | 147579 | 199078 | 51499 | 180232 | 169354
PRJ017 | Sep | 137991.8333 | 103565.5 | 146355 | 224100 | 77745 | 201343 | 235653
PRJ017 | Oct | 137991.8333 | 103565.5 | 133286 | 172495 | 39209 | 151410 | 141319
PRJ017 | Nov | 137991.8333 | 103565.5 | 275542 | 345155 | 69613 | 294431 | 313257
PRJ017 | Dec | 137991.8333 | 103565.5 | 246072 | 285390 | 39318 | 279670 | 276724
PRJ018 | Jan | 74164.4167 | 73167.1667 | 87580 | 100155 | 12575 | 82380 | 65001
PRJ018 | Feb | 74164.4167 | 73167.1667 | 56321 | 88155 | 31834 | 93786 | 85575
PRJ018 | Mar | 74164.4167 | 73167.1667 | 114994 | 132557 | 17563 | 121992 | 80794
PRJ018 | Apr | 74164.4167 | 73167.1667 | 102674 | 114194 | 11520 | 87978 | 99682
PRJ018 | May | 74164.4167 | 73167.1667 | 96597 | 156884 | 60287 | 126760 | 97592
PRJ018 | Jun | 74164.4167 | 73167.1667 | 71031 | 108698 | 37667 | 110467 | 102849
PRJ018 | Jul | 74164.4167 | 73167.1667 | 210094 | 217848 | 7754 | 195956 | 205888
PRJ018 | Aug | 74164.4167 | 73167.1667 | 168117 | 195870 | 27753 | 153178 | 134716
PRJ018 | Sep | 74164.4167 | 73167.1667 | 78442 | 109283 | 30841 | 110456 | 118912
PRJ018 | Oct | 74164.4167 | 73167.1667 | 106626 | 160229 | 53603 | 127087 | 84962
PRJ018 | Nov | 74164.4167 | 73167.1667 | 99270 | 164054 | 64784 | 148053 | 96798
PRJ018 | Dec | 74164.4167 | 73167.1667 | 137963 | 199560 | 61597 | 151647 | 173854
PRJ019 | Jan | 32267.6667 | 9473.5833 | 43777 | 48952 | 5175 | 48806 | 48910
PRJ019 | Feb | 32267.6667 | 9473.5833 | 21357 | 31074 | 9717 | 24490 | 18936
PRJ019 | Mar | 32267.6667 | 9473.5833 | 53075 | 60010 | 6935 | 54279 | 46517
PRJ019 | Apr | 32267.6667 | 9473.5833 | 24401 | 27423 | 3022 | 26726 | 25700
PRJ019 | May | 32267.6667 | 9473.5833 | 58490 | 60461 | 1971 | 45844 | 36889
PRJ019 | Jun | 32267.6667 | 9473.5833 | 39976 | 40774 | 798 | 36318 | 32032
PRJ019 | Jul | 32267.6667 | 9473.5833 | 27549 | 45853 | 18304 | 37658 | 31421
PRJ019 | Aug | 32267.6667 | 9473.5833 | 30488 | 45178 | 14690 | 37391 | 36527
PRJ019 | Sep | 32267.6667 | 9473.5833 | 24753 | 35062 | 10309 | 31782 | 25711
PRJ019 | Oct | 32267.6667 | 9473.5833 | 37025 | 38689 | 1664 | 37824 | 27733
PRJ019 | Nov | 32267.6667 | 9473.5833 | 24789 | 26721 | 1932 | 22891 | 19765
PRJ019 | Dec | 32267.6667 | 9473.5833 | 25748 | 30504 | 4756 | 32308 | 21493
PRJ020 | Jan | 233578.0833 | 58209.4167 | 292638 | 395633 | 102995 | 333988 | 277831
PRJ020 | Feb | 233578.0833 | 58209.4167 | 269942 | 374503 | 104561 | 328806 | 273305
PRJ020 | Mar | 233578.0833 | 58209.4167 | 312831 | 316629 | 3798 | 287685 | 242315
PRJ020 | Apr | 233578.0833 | 58209.4167 | 215707 | 277658 | 61951 | 208690 | 148988
PRJ020 | May | 233578.0833 | 58209.4167 | 243027 | 213407 | -29620 | 205642 | 193165
PRJ020 | Jun | 233578.0833 | 58209.4167 | 180457 | 247934 | 67477 | 208294 | 207624
PRJ020 | Jul | 233578.0833 | 58209.4167 | 279374 | 397649 | 118275 | 311589 | 250720
PRJ020 | Aug | 233578.0833 | 58209.4167 | 324317 | 369396 | 45079 | 343494 | 222627
PRJ020 | Sep | 233578.0833 | 58209.4167 | 149426 | 191667 | 42241 | 168154 | 169013
PRJ020 | Oct | 233578.0833 | 58209.4167 | 242533 | 232984 | -9549 | 215722 | 231906
PRJ020 | Nov | 233578.0833 | 58209.4167 | 154904 | 274053 | 119149 | 236175 | 247262
PRJ020 | Dec | 233578.0833 | 58209.4167 | 214756 | 290891 | 76135 | 255386 | 298974
PRJ021 | Jan | 225012.25 | 102194.75 | 231329 | 316137 | 84808 | 236585 | 204234
PRJ021 | Feb | 225012.25 | 102194.75 | 276808 | 259448 | -17360 | 225505 | 189453
PRJ021 | Mar | 225012.25 | 102194.75 | 324109 | 288458 | -35651 | 296588 | 300225
PRJ021 | Apr | 225012.25 | 102194.75 | 310411 | 295470 | -14941 | 243902 | 222053
PRJ021 | May | 225012.25 | 102194.75 | 311937 | 475435 | 163498 | 419625 | 387064
PRJ021 | Jun | 225012.25 | 102194.75 | 316401 | 336233 | 19832 | 299087 | 280660
PRJ021 | Jul | 225012.25 | 102194.75 | 305193 | 376165 | 70972 | 335531 | 233911
PRJ021 | Aug | 225012.25 | 102194.75 | 334815 | 441233 | 106418 | 347705 | 420213
PRJ021 | Sep | 225012.25 | 102194.75 | 257203 | 428671 | 171468 | 365271 | 294607
PRJ021 | Oct | 225012.25 | 102194.75 | 163923 | 211577 | 47654 | 178789 | 135332
PRJ021 | Nov | 225012.25 | 102194.75 | 291438 | 356642 | 65204 | 326620 | 256963
PRJ021 | Dec | 225012.25 | 102194.75 | 430250 | 459128 | 28878 | 367306 | 384552
PRJ022 | Jan | 119485.5833 | 119203 | 272297 | 250778 | -21519 | 227524 | 226686
PRJ022 | Feb | 119485.5833 | 119203 | 205601 | 213626 | 8025 | 181350 | 139835
PRJ022 | Mar | 119485.5833 | 119203 | 133763 | 198712 | 64949 | 193729 | 183006
PRJ022 | Apr | 119485.5833 | 119203 | 139824 | 162725 | 22901 | 142388 | 151878
PRJ022 | May | 119485.5833 | 119203 | 292599 | 288735 | -3864 | 284664 | 288175
PRJ022 | Jun | 119485.5833 | 119203 | 138899 | 222333 | 83434 | 183200 | 204651
PRJ022 | Jul | 119485.5833 | 119203 | 208687 | 344782 | 136095 | 268300 | 286832
PRJ022 | Aug | 119485.5833 | 119203 | 160478 | 264155 | 103677 | 248281 | 210359
PRJ022 | Sep | 119485.5833 | 119203 | 275683 | 286616 | 10933 | 253379 | 249585
PRJ022 | Oct | 119485.5833 | 119203 | 203179 | 227469 | 24290 | 219057 | 160446
PRJ022 | Nov | 119485.5833 | 119203 | 232759 | 304777 | 72018 | 304235 | 239625
PRJ022 | Dec | 119485.5833 | 119203 | 113657 | 189011 | 75354 | 138110 | 106245
PRJ023 | Jan | 163049.0833 | 71877 | 250903 | 277371 | 26468 | 228495 | 185244
PRJ023 | Feb | 163049.0833 | 71877 | 188401 | 203223 | 14822 | 163574 | 110327
PRJ023 | Mar | 163049.0833 | 71877 | 271805 | 254260 | -17545 | 231079 | 270969
PRJ023 | Apr | 163049.0833 | 71877 | 301257 | 303335 | 2078 | 251936 | 263084
PRJ023 | May | 163049.0833 | 71877 | 194699 | 189503 | -5196 | 164672 | 133201
PRJ023 | Jun | 163049.0833 | 71877 | 169692 | 241553 | 71861 | 231656 | 173808
PRJ023 | Jul | 163049.0833 | 71877 | 279621 | 292357 | 12736 | 264877 | 228943
PRJ023 | Aug | 163049.0833 | 71877 | 112140 | 197903 | 85763 | 163591 | 125935
PRJ023 | Sep | 163049.0833 | 71877 | 179918 | 174763 | -5155 | 171941 | 157212
PRJ023 | Oct | 163049.0833 | 71877 | 201019 | 238878 | 37859 | 212272 | 197097
PRJ023 | Nov | 163049.0833 | 71877 | 141615 | 222786 | 81171 | 175785 | 201881
PRJ023 | Dec | 163049.0833 | 71877 | 141194 | 205706 | 64512 | 165104 | 166847
PRJ024 | Jan | 51775.6667 | 26010.5833 | 85692 | 106787 | 21095 | 84528 | 74136
PRJ024 | Feb | 51775.6667 | 26010.5833 | 76805 | 68662 | -8143 | 64775 | 68930
PRJ024 | Mar | 51775.6667 | 26010.5833 | 40259 | 66391 | 26132 | 63079 | 48947
PRJ024 | Apr | 51775.6667 | 26010.5833 | 77333 | 73865 | -3468 | 61765 | 48009
PRJ024 | May | 51775.6667 | 26010.5833 | 85557 | 73201 | -12356 | 74845 | 64361
PRJ024 | Jun | 51775.6667 | 26010.5833 | 45193 | 65903 | 20710 | 52143 | 56130
PRJ024 | Jul | 51775.6667 | 26010.5833 | 58040 | 62471 | 4431 | 56299 | 54680
PRJ024 | Aug | 51775.6667 | 26010.5833 | 61387 | 88976 | 27589 | 77157 | 58992
PRJ024 | Sep | 51775.6667 | 26010.5833 | 79254 | 99944 | 20690 | 101936 | 74526
PRJ024 | Oct | 51775.6667 | 26010.5833 | 63606 | 84372 | 20766 | 71906 | 64383
PRJ024 | Nov | 51775.6667 | 26010.5833 | 74294 | 67337 | -6957 | 69350 | 54441
PRJ024 | Dec | 51775.6667 | 26010.5833 | 85511 | 82178 | -3333 | 70786 | 78138
PRJ025 | Jan | 126661.4167 | 29682.1667 | 89094 | 139595 | 50501 | 100798 | 116392
PRJ025 | Feb | 126661.4167 | 29682.1667 | 152327 | 180513 | 28186 | 171150 | 114985
PRJ025 | Mar | 126661.4167 | 29682.1667 | 62576 | 92738 | 30162 | 85694 | 64820
PRJ025 | Apr | 126661.4167 | 29682.1667 | 146887 | 207407 | 60520 | 173873 | 163328
PRJ025 | May | 126661.4167 | 29682.1667 | 186095 | 197036 | 10941 | 168162 | 176947
PRJ025 | Jun | 126661.4167 | 29682.1667 | 156858 | 169642 | 12784 | 132535 | 101123
PRJ025 | Jul | 126661.4167 | 29682.1667 | 187737 | 186911 | -826 | 181222 | 176447
PRJ025 | Aug | 126661.4167 | 29682.1667 | 113783 | 113999 | 216 | 120643 | 95076
PRJ025 | Sep | 126661.4167 | 29682.1667 | 102654 | 110611 | 7957 | 106255 | 81220
PRJ025 | Oct | 126661.4167 | 29682.1667 | 84651 | 107498 | 22847 | 97680 | 85230
PRJ025 | Nov | 126661.4167 | 29682.1667 | 91595 | 107209 | 15614 | 93819 | 95205
PRJ025 | Dec | 126661.4167 | 29682.1667 | 61855 | 98718 | 36863 | 91912 | 62781
PRJ026 | Jan | 190546.9167 | 34749.1667 | 133158 | 167733 | 34575 | 132415 | 133547
PRJ026 | Feb | 190546.9167 | 34749.1667 | 166194 | 286005 | 119811 | 226014 | 253452
PRJ026 | Mar | 190546.9167 | 34749.1667 | 124251 | 151084 | 26833 | 132268 | 128197
PRJ026 | Apr | 190546.9167 | 34749.1667 | 139849 | 134764 | -5085 | 127601 | 99327
PRJ026 | May | 190546.9167 | 34749.1667 | 143283 | 134882 | -8401 | 124210 | 128233
PRJ026 | Jun | 190546.9167 | 34749.1667 | 175036 | 317339 | 142303 | 274955 | 264394
PRJ026 | Jul | 190546.9167 | 34749.1667 | 255093 | 249954 | -5139 | 239768 | 164091
PRJ026 | Aug | 190546.9167 | 34749.1667 | 120144 | 176445 | 56301 | 145791 | 135774
PRJ026 | Sep | 190546.9167 | 34749.1667 | 243652 | 232159 | -11493 | 235240 | 222103
PRJ026 | Oct | 190546.9167 | 34749.1667 | 94125 | 139194 | 45069 | 117160 | 78805
PRJ026 | Nov | 190546.9167 | 34749.1667 | 188810 | 230053 | 41243 | 230668 | 205382
PRJ026 | Dec | 190546.9167 | 34749.1667 | 287368 | 295332 | 7964 | 235251 | 209132
PRJ027 | Jan | 113429.6667 | 37862.25 | 144115 | 212388 | 68273 | 172375 | 128299
PRJ027 | Feb | 113429.6667 | 37862.25 | 159237 | 135602 | -23635 | 127231 | 121582
PRJ027 | Mar | 113429.6667 | 37862.25 | 87105 | 126670 | 39565 | 111738 | 109133
PRJ027 | Apr | 113429.6667 | 37862.25 | 118643 | 153839 | 35196 | 129038 | 132708
PRJ027 | May | 113429.6667 | 37862.25 | 127555 | 215534 | 87979 | 177625 | 137090
PRJ027 | Jun | 113429.6667 | 37862.25 | 130251 | 201385 | 71134 | 200691 | 170927
PRJ027 | Jul | 113429.6667 | 37862.25 | 111779 | 145616 | 33837 | 154295 | 149606
PRJ027 | Aug | 113429.6667 | 37862.25 | 93919 | 124799 | 30880 | 121278 | 122850
PRJ027 | Sep | 113429.6667 | 37862.25 | 176404 | 190920 | 14516 | 153160 | 184868
PRJ027 | Oct | 113429.6667 | 37862.25 | 204583 | 216623 | 12040 | 165640 | 157859
PRJ027 | Nov | 113429.6667 | 37862.25 | 142448 | 210238 | 67790 | 177481 | 170114
PRJ027 | Dec | 113429.6667 | 37862.25 | 154000 | 193211 | 39211 | 188624 | 183061
PRJ028 | Jan | 103806.1667 | 31107.1667 | 171045 | 160180 | -10865 | 144668 | 156427
PRJ028 | Feb | 103806.1667 | 31107.1667 | 123062 | 133398 | 10336 | 117897 | 121868
PRJ028 | Mar | 103806.1667 | 31107.1667 | 105758 | 129384 | 23626 | 116183 | 111625
PRJ028 | Apr | 103806.1667 | 31107.1667 | 112298 | 124070 | 11772 | 111359 | 81382
PRJ028 | May | 103806.1667 | 31107.1667 | 108246 | 147768 | 39522 | 139699 | 146595
PRJ028 | Jun | 103806.1667 | 31107.1667 | 157593 | 169870 | 12277 | 144238 | 117945
PRJ028 | Jul | 103806.1667 | 31107.1667 | 83491 | 115556 | 32065 | 93298 | 103197
PRJ028 | Aug | 103806.1667 | 31107.1667 | 105679 | 126664 | 20985 | 107196 | 94518
PRJ028 | Sep | 103806.1667 | 31107.1667 | 157308 | 185206 | 27898 | 176521 | 112810
PRJ028 | Oct | 103806.1667 | 31107.1667 | 149163 | 202632 | 53469 | 170427 | 150779
PRJ028 | Nov | 103806.1667 | 31107.1667 | 100248 | 134389 | 34141 | 115754 | 125184
PRJ028 | Dec | 103806.1667 | 31107.1667 | 116484 | 117392 | 908 | 116076 | 84404
PRJ029 | Jan | 105698.8333 | 60468.1667 | 190453 | 183909 | -6544 | 189348 | 193189
PRJ029 | Feb | 105698.8333 | 60468.1667 | 132993 | 166941 | 33948 | 137773 | 137830
PRJ029 | Mar | 105698.8333 | 60468.1667 | 141160 | 164224 | 23064 | 160099 | 164283
PRJ029 | Apr | 105698.8333 | 60468.1667 | 139442 | 195653 | 56211 | 187507 | 157016
PRJ029 | May | 105698.8333 | 60468.1667 | 160953 | 166188 | 5235 | 160050 | 121494
PRJ029 | Jun | 105698.8333 | 60468.1667 | 179296 | 176792 | -2504 | 158208 | 112053
PRJ029 | Jul | 105698.8333 | 60468.1667 | 177565 | 186642 | 9077 | 160084 | 168544
PRJ029 | Aug | 105698.8333 | 60468.1667 | 110762 | 156850 | 46088 | 141328 | 142749
PRJ029 | Sep | 105698.8333 | 60468.1667 | 141381 | 142505 | 1124 | 110214 | 131115
PRJ029 | Oct | 105698.8333 | 60468.1667 | 120513 | 144200 | 23687 | 117352 | 120827
PRJ029 | Nov | 105698.8333 | 60468.1667 | 129245 | 147641 | 18396 | 137082 | 88007
PRJ029 | Dec | 105698.8333 | 60468.1667 | 85493 | 153943 | 68450 | 129049 | 129299
PRJ030 | Jan | 57084.1667 | 35800 | 60221 | 96837 | 36616 | 80580 | 83780
PRJ030 | Feb | 57084.1667 | 35800 | 95207 | 116354 | 21147 | 88630 | 82970
PRJ030 | Mar | 57084.1667 | 35800 | 72958 | 109998 | 37040 | 98589 | 84807
PRJ030 | Apr | 57084.1667 | 35800 | 57418 | 63845 | 6427 | 54248 | 57589
PRJ030 | May | 57084.1667 | 35800 | 69827 | 86964 | 17137 | 74692 | 52125
PRJ030 | Jun | 57084.1667 | 35800 | 120968 | 112929 | -8039 | 103727 | 107690
PRJ030 | Jul | 57084.1667 | 35800 | 102221 | 110664 | 8443 | 102296 | 112799
PRJ030 | Aug | 57084.1667 | 35800 | 62826 | 73419 | 10593 | 66037 | 56815
PRJ030 | Sep | 57084.1667 | 35800 | 74940 | 89901 | 14961 | 62848 | 47871
PRJ030 | Oct | 57084.1667 | 35800 | 88444 | 94995 | 6551 | 86351 | 66125
PRJ030 | Nov | 57084.1667 | 35800 | 78607 | 77245 | -1362 | 71890 | 60974
PRJ030 | Dec | 57084.1667 | 35800 | 87526 | 100617 | 13091 | 82180 | 89679
PRJ031 | Jan | 37084.4167 | 36041.1667 | 68399 | 68345 | -54 | 62910 | 55157
PRJ031 | Feb | 37084.4167 | 36041.1667 | 77590 | 80614 | 3024 | 68134 | 58122
PRJ031 | Mar | 37084.4167 | 36041.1667 | 79877 | 90481 | 10604 | 88000 | 70413
PRJ031 | Apr | 37084.4167 | 36041.1667 | 70619 | 101853 | 31234 | 81304 | 76712
PRJ031 | May | 37084.4167 | 36041.1667 | 68977 | 77411 | 8434 | 60074 | 68154
PRJ031 | Jun | 37084.4167 | 36041.1667 | 52502 | 50810 | -1692 | 46571 | 39835
PRJ031 | Jul | 37084.4167 | 36041.1667 | 74801 | 78829 | 4028 | 68190 | 52592
PRJ031 | Aug | 37084.4167 | 36041.1667 | 44677 | 50515 | 5838 | 46880 | 51614
PRJ031 | Sep | 37084.4167 | 36041.1667 | 36397 | 60813 | 24416 | 53009 | 53551
PRJ031 | Oct | 37084.4167 | 36041.1667 | 45363 | 55267 | 9904 | 45186 | 52271
PRJ031 | Nov | 37084.4167 | 36041.1667 | 81587 | 77296 | -4291 | 80479 | 76721
PRJ031 | Dec | 37084.4167 | 36041.1667 | 63796 | 103506 | 39710 | 85386 | 84773
PRJ032 | Jan | 217629.4167 | 92592.25 | 286980 | 288485 | 1505 | 247328 | 170877
PRJ032 | Feb | 217629.4167 | 92592.25 | 224526 | 277887 | 53361 | 225102 | 216888
PRJ032 | Mar | 217629.4167 | 92592.25 | 232426 | 289795 | 57369 | 261429 | 222407
PRJ032 | Apr | 217629.4167 | 92592.25 | 176764 | 253727 | 76963 | 210403 | 222488
PRJ032 | May | 217629.4167 | 92592.25 | 221783 | 280282 | 58499 | 236991 | 252278
PRJ032 | Jun | 217629.4167 | 92592.25 | 152185 | 252192 | 100007 | 207762 | 186145
PRJ032 | Jul | 217629.4167 | 92592.25 | 212874 | 210317 | -2557 | 184047 | 174928
PRJ032 | Aug | 217629.4167 | 92592.25 | 223430 | 276439 | 53009 | 234272 | 211004
PRJ032 | Sep | 217629.4167 | 92592.25 | 285783 | 319030 | 33247 | 270917 | 295651
PRJ032 | Oct | 217629.4167 | 92592.25 | 241523 | 400139 | 158616 | 356877 | 285560
PRJ032 | Nov | 217629.4167 | 92592.25 | 303377 | 322829 | 19452 | 268828 | 219016
PRJ032 | Dec | 217629.4167 | 92592.25 | 422187 | 398843 | -23344 | 375626 | 346113
PRJ033 | Jan | 87187.5833 | 41581.25 | 140403 | 154148 | 13745 | 152025 | 125785
PRJ033 | Feb | 87187.5833 | 41581.25 | 109911 | 117410 | 7499 | 92207 | 71620
PRJ033 | Mar | 87187.5833 | 41581.25 | 128780 | 179322 | 50542 | 161788 | 137247
PRJ033 | Apr | 87187.5833 | 41581.25 | 106086 | 120832 | 14746 | 115914 | 87802
PRJ033 | May | 87187.5833 | 41581.25 | 114563 | 140226 | 25663 | 113487 | 117051
PRJ033 | Jun | 87187.5833 | 41581.25 | 113321 | 111882 | -1439 | 119997 | 100955
PRJ033 | Jul | 87187.5833 | 41581.25 | 109283 | 136532 | 27249 | 126757 | 88124
PRJ033 | Aug | 87187.5833 | 41581.25 | 98562 | 166212 | 67650 | 143732 | 113201
PRJ033 | Sep | 87187.5833 | 41581.25 | 87066 | 148999 | 61933 | 131889 | 129709
PRJ033 | Oct | 87187.5833 | 41581.25 | 80706 | 112341 | 31635 | 108619 | 90610
PRJ033 | Nov | 87187.5833 | 41581.25 | 115628 | 120346 | 4718 | 112346 | 118642
PRJ033 | Dec | 87187.5833 | 41581.25 | 106390 | 149121 | 42731 | 113093 | 82747
PRJ034 | Jan | 66257.5833 | 46824.75 | 82831 | 96234 | 13403 | 88690 | 77212
PRJ034 | Feb | 66257.5833 | 46824.75 | 90787 | 105432 | 14645 | 83172 | 90102
PRJ034 | Mar | 66257.5833 | 46824.75 | 118807 | 124735 | 5928 | 107879 | 94075
PRJ034 | Apr | 66257.5833 | 46824.75 | 99966 | 109356 | 9390 | 89919 | 80922
PRJ034 | May | 66257.5833 | 46824.75 | 106395 | 180595 | 74200 | 146758 | 102715
PRJ034 | Jun | 66257.5833 | 46824.75 | 59591 | 63376 | 3785 | 55043 | 61788
PRJ034 | Jul | 66257.5833 | 46824.75 | 74510 | 93515 | 19005 | 88330 | 77631
PRJ034 | Aug | 66257.5833 | 46824.75 | 79630 | 96707 | 17077 | 82919 | 69141
PRJ034 | Sep | 66257.5833 | 46824.75 | 86372 | 108013 | 21641 | 82329 | 77795
PRJ034 | Oct | 66257.5833 | 46824.75 | 85663 | 125141 | 39478 | 99893 | 96429
PRJ034 | Nov | 66257.5833 | 46824.75 | 81846 | 81004 | -842 | 81934 | 86018
PRJ034 | Dec | 66257.5833 | 46824.75 | 131686 | 145462 | 13776 | 154704 | 100509
PRJ035 | Jan | 204446.6667 | 89921.5833 | 335369 | 285482 | -49887 | 287722 | 285394
PRJ035 | Feb | 204446.6667 | 89921.5833 | 166563 | 236242 | 69679 | 192893 | 173748
PRJ035 | Mar | 204446.6667 | 89921.5833 | 250530 | 352422 | 101892 | 296629 | 221220
PRJ035 | Apr | 204446.6667 | 89921.5833 | 231389 | 256797 | 25408 | 216677 | 148267
PRJ035 | May | 204446.6667 | 89921.5833 | 162162 | 297368 | 135206 | 249220 | 220185
PRJ035 | Jun | 204446.6667 | 89921.5833 | 181852 | 237309 | 55457 | 182443 | 139250
PRJ035 | Jul | 204446.6667 | 89921.5833 | 171062 | 261449 | 90387 | 235255 | 235758
PRJ035 | Aug | 204446.6667 | 89921.5833 | 219104 | 210678 | -8426 | 205187 | 173282
PRJ035 | Sep | 204446.6667 | 89921.5833 | 299410 | 357503 | 58093 | 321762 | 377870
PRJ035 | Oct | 204446.6667 | 89921.5833 | 244909 | 243971 | -938 | 189263 | 173294
PRJ035 | Nov | 204446.6667 | 89921.5833 | 286763 | 292423 | 5660 | 275281 | 267495
PRJ035 | Dec | 204446.6667 | 89921.5833 | 148659 | 181384 | 32725 | 176528 | 167554
PRJ036 | Jan | 116750.8333 | 71461.25 | 174763 | 186840 | 12077 | 152061 | 173903
PRJ036 | Feb | 116750.8333 | 71461.25 | 133349 | 173013 | 39664 | 160514 | 141233
PRJ036 | Mar | 116750.8333 | 71461.25 | 151105 | 187345 | 36240 | 145784 | 159083
PRJ036 | Apr | 116750.8333 | 71461.25 | 160101 | 201794 | 41693 | 203169 | 165103
PRJ036 | May | 116750.8333 | 71461.25 | 230089 | 249128 | 19039 | 199597 | 174850
PRJ036 | Jun | 116750.8333 | 71461.25 | 163886 | 200345 | 36459 | 181241 | 113430
PRJ036 | Jul | 116750.8333 | 71461.25 | 92945 | 107839 | 14894 | 96749 | 76485
PRJ036 | Aug | 116750.8333 | 71461.25 | 110607 | 110079 | -528 | 100039 | 101394
PRJ036 | Sep | 116750.8333 | 71461.25 | 144671 | 244216 | 99545 | 181058 | 189075
PRJ036 | Oct | 116750.8333 | 71461.25 | 259650 | 269335 | 9685 | 225036 | 168055
PRJ036 | Nov | 116750.8333 | 71461.25 | 198151 | 243687 | 45536 | 184333 | 166124
PRJ036 | Dec | 116750.8333 | 71461.25 | 193925 | 239443 | 45518 | 207443 | 231895
PRJ037 | Jan | 53683.1667 | 46624.75 | 54317 | 98188 | 43871 | 73534 | 66921
PRJ037 | Feb | 53683.1667 | 46624.75 | 108479 | 113208 | 4729 | 107671 | 78805
PRJ037 | Mar | 53683.1667 | 46624.75 | 93644 | 114624 | 20980 | 95820 | 65160
PRJ037 | Apr | 53683.1667 | 46624.75 | 58537 | 81633 | 23096 | 79037 | 53230
PRJ037 | May | 53683.1667 | 46624.75 | 119358 | 123750 | 4392 | 120345 | 123140
PRJ037 | Jun | 53683.1667 | 46624.75 | 112380 | 107413 | -4967 | 93186 | 98480
PRJ037 | Jul | 53683.1667 | 46624.75 | 111974 | 115933 | 3959 | 127516 | 119326
PRJ037 | Aug | 53683.1667 | 46624.75 | 109400 | 101427 | -7973 | 95959 | 77910
PRJ037 | Sep | 53683.1667 | 46624.75 | 83120 | 133136 | 50016 | 127794 | 81426
PRJ037 | Oct | 53683.1667 | 46624.75 | 102152 | 104392 | 2240 | 89323 | 83331
PRJ037 | Nov | 53683.1667 | 46624.75 | 97331 | 98206 | 875 | 80954 | 58864
PRJ037 | Dec | 53683.1667 | 46624.75 | 79331 | 112284 | 32953 | 111772 | 99129
PRJ038 | Jan | 85517.8333 | 65967.8333 | 105944 | 118928 | 12984 | 110389 | 113665
PRJ038 | Feb | 85517.8333 | 65967.8333 | 111247 | 164394 | 53147 | 172226 | 110996
PRJ038 | Mar | 85517.8333 | 65967.8333 | 129865 | 141123 | 11258 | 130138 | 132097
PRJ038 | Apr | 85517.8333 | 65967.8333 | 134606 | 115197 | -19409 | 104947 | 109155
PRJ038 | May | 85517.8333 | 65967.8333 | 110005 | 189903 | 79898 | 145891 | 118128
PRJ038 | Jun | 85517.8333 | 65967.8333 | 99973 | 101698 | 1725 | 83655 | 83883
PRJ038 | Jul | 85517.8333 | 65967.8333 | 129571 | 167931 | 38360 | 128890 | 140750
PRJ038 | Aug | 85517.8333 | 65967.8333 | 180823 | 177260 | -3563 | 143328 | 164125
PRJ038 | Sep | 85517.8333 | 65967.8333 | 136499 | 147232 | 10733 | 127736 | 112237
PRJ038 | Oct | 85517.8333 | 65967.8333 | 75377 | 112825 | 37448 | 105572 | 92320
PRJ038 | Nov | 85517.8333 | 65967.8333 | 108140 | 161246 | 53106 | 169000 | 147297
PRJ038 | Dec | 85517.8333 | 65967.8333 | 120853 | 129178 | 8325 | 119764 | 91076
PRJ039 | Jan | 164889 | 95544.75 | 260554 | 355264 | 94710 | 307758 | 282748
PRJ039 | Feb | 164889 | 95544.75 | 194142 | 226020 | 31878 | 222552 | 190237
PRJ039 | Mar | 164889 | 95544.75 | 130567 | 174752 | 44185 | 142164 | 140258
PRJ039 | Apr | 164889 | 95544.75 | 134958 | 174733 | 39775 | 170345 | 120002
PRJ039 | May | 164889 | 95544.75 | 228436 | 250747 | 22311 | 250549 | 226826
PRJ039 | Jun | 164889 | 95544.75 | 193976 | 208161 | 14185 | 193084 | 153455
PRJ039 | Jul | 164889 | 95544.75 | 138806 | 236990 | 98184 | 191387 | 172820
PRJ039 | Aug | 164889 | 95544.75 | 256813 | 238880 | -17933 | 248651 | 254384
PRJ039 | Sep | 164889 | 95544.75 | 197378 | 217639 | 20261 | 229352 | 208161
PRJ039 | Oct | 164889 | 95544.75 | 181203 | 277025 | 95822 | 224150 | 236186
PRJ039 | Nov | 164889 | 95544.75 | 187343 | 216077 | 28734 | 169212 | 133084
PRJ039 | Dec | 164889 | 95544.75 | 265660 | 237955 | -27705 | 250495 | 198753
PRJ040 | Jan | 104595.75 | 36505.8333 | 111391 | 122774 | 11383 | 115476 | 79012
PRJ040 | Feb | 104595.75 | 36505.8333 | 68731 | 101938 | 33207 | 105889 | 85494
PRJ040 | Mar | 104595.75 | 36505.8333 | 105364 | 106142 | 778 | 96749 | 86375
PRJ040 | Apr | 104595.75 | 36505.8333 | 152689 | 156725 | 4036 | 115008 | 132667
PRJ040 | May | 104595.75 | 36505.8333 | 141596 | 175336 | 33740 | 135280 | 140998
PRJ040 | Jun | 104595.75 | 36505.8333 | 119554 | 163580 | 44026 | 153169 | 130992
PRJ040 | Jul | 104595.75 | 36505.8333 | 64517 | 122606 | 58089 | 86518 | 84403
PRJ040 | Aug | 104595.75 | 36505.8333 | 131713 | 155187 | 23474 | 146024 | 141293
PRJ040 | Sep | 104595.75 | 36505.8333 | 111360 | 114382 | 3022 | 119860 | 124118
PRJ040 | Oct | 104595.75 | 36505.8333 | 87975 | 87867 | -108 | 85322 | 68750
PRJ040 | Nov | 104595.75 | 36505.8333 | 170809 | 158960 | -11849 | 156305 | 159422
PRJ040 | Dec | 104595.75 | 36505.8333 | 175890 | 175479 | -411 | 157845 | 150862

## Resources
Resource | Skill | Role | Project ID | Project | Month | Allocation % | Capacity %
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-04-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-05-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-06-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-07-01 | 40 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-08-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-09-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-10-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-11-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2025-12-01 | 40 | 100
Resource 01 | BA | Analyst | PRJ022 | DevOps Tools | 2026-01-01 | 0 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-02-01 | 90 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-03-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-04-01 | 85 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-05-01 | 90 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-06-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-07-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-08-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-09-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-10-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-11-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2025-12-01 | 85 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-01-01 | 50 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-02-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-03-01 | 75 | 100
Resource 01 | BA | Analyst | PRJ040 | Zero-Trust Net | 2026-04-01 | 65 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-05-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-06-01 | 40 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-07-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-08-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-09-01 | 25 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-10-01 | 15 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-11-01 | 35 | 100
Resource 01 | BA | Analyst | PRJ036 | HR Self-Service | 2025-12-01 | 0 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-02-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-03-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-04-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-05-01 | 60 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-06-01 | 65 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-07-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-08-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-09-01 | 25 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-10-01 | 25 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-11-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2025-12-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2026-01-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2026-02-01 | 50 | 100
Resource 02 | UX | Architect | PRJ014 | Identity Mgmt | 2026-03-01 | 60 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2025-11-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2025-12-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-01-01 | 35 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-02-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-03-01 | 35 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-04-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-05-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-06-01 | 35 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-07-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-08-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-09-01 | 40 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-10-01 | 0 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-11-01 | 15 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2026-12-01 | 25 | 100
Resource 02 | UX | Architect | PRJ034 | Treasury Sys | 2027-01-01 | 0 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-03-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-04-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-05-01 | 75 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-06-01 | 75 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-07-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-08-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-09-01 | 75 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-10-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-11-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2025-12-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-01-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-02-01 | 90 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-03-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-04-01 | 100 | 100
Resource 02 | UX | Architect | PRJ006 | Cyber Security Program | 2026-05-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-05-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-06-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-07-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-08-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-09-01 | 65 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-10-01 | 65 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-11-01 | 25 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2025-12-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-01-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-02-01 | 25 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-03-01 | 25 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-04-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-05-01 | 60 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-06-01 | 65 | 100
Resource 03 | DevOps | Analyst | PRJ035 | Payroll Cloud | 2026-07-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-04-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-05-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-06-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-07-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-08-01 | 85 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-09-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-10-01 | 90 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-11-01 | 85 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2025-12-01 | 85 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2026-01-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ027 | Cyber Program | 2026-02-01 | 75 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-04-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-05-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-06-01 | 50 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-07-01 | 40 | 100
Resource 03 | DevOps | Analyst | PRJ020 | Process Automation | 2025-08-01 | 50 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-02-01 | 75 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-03-01 | 75 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-04-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-05-01 | 85 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-06-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-07-01 | 90 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-08-01 | 85 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-09-01 | 75 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-10-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-11-01 | 65 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2025-12-01 | 90 | 100
Resource 04 | Data | Tester | PRJ010 | Workforce Enablement | 2026-01-01 | 90 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-05-01 | 25 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-06-01 | 35 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-07-01 | 15 | 100
Resource 05 | Dev | Developer | PRJ008 | Mobile App | 2025-08-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-02-01 | 40 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-03-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-04-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-05-01 | 15 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-06-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-07-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-08-01 | 35 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-09-01 | 15 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-10-01 | 35 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-11-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2025-12-01 | 0 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2026-01-01 | 0 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2026-02-01 | 25 | 100
Resource 06 | DevOps | Tester | PRJ014 | Identity Mgmt | 2026-03-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-02-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-03-01 | 35 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-04-01 | 35 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-05-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-06-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-07-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-08-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-09-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-10-01 | 25 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-11-01 | 35 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2025-12-01 | 40 | 100
Resource 07 | Dev | Analyst | PRJ010 | Workforce Enablement | 2026-01-01 | 15 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-03-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-04-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-05-01 | 75 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-06-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-07-01 | 100 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-08-01 | 75 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-09-01 | 90 | 100
Resource 07 | Dev | Analyst | PRJ037 | SAP S/4HANA | 2025-10-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-03-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-04-01 | 90 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-05-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-06-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-07-01 | 75 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-08-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-09-01 | 75 | 100
Resource 08 | Architect | Project Manager | PRJ002 | Cloud Migration | 2025-10-01 | 100 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2025-12-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-01-01 | 40 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-02-01 | 25 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-03-01 | 25 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-04-01 | 60 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-05-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-06-01 | 65 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-07-01 | 65 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-08-01 | 25 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-09-01 | 60 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-10-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-11-01 | 40 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2026-12-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2027-01-01 | 50 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2027-02-01 | 60 | 100
Resource 08 | Architect | Project Manager | PRJ013 | API Gateway | 2027-03-01 | 60 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2025-12-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-02-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-03-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-04-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-05-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-06-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-07-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-08-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-09-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-11-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2026-12-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ024 | Process Mining | 2027-01-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-02-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-03-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-04-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-05-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-06-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-07-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-08-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-09-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-10-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-11-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-12-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-01-01 | 100 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-02-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-03-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-02-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-03-01 | 85 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-04-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-05-01 | 50 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-06-01 | 85 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-07-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-08-01 | 50 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-09-01 | 50 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-10-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-11-01 | 90 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2025-12-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-01-01 | 75 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-02-01 | 65 | 100
Resource 09 | Architect | Project Manager | PRJ014 | Identity Mgmt | 2026-03-01 | 85 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2025-12-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-01-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-02-01 | 60 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-03-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-04-01 | 25 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-05-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-06-01 | 60 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-07-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-08-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-09-01 | 60 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-10-01 | 65 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-11-01 | 50 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2026-12-01 | 40 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2027-01-01 | 25 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2027-02-01 | 25 | 100
Resource 10 | UX | Architect | PRJ013 | API Gateway | 2027-03-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-08-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-09-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-10-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-11-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2025-12-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-01-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-02-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-03-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-04-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-05-01 | 0 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-06-01 | 0 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-07-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-08-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-09-01 | 0 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-10-01 | 35 | 100
Resource 11 | DevOps | Tester | PRJ031 | Quality Mgmt | 2026-11-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2025-12-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-02-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-03-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-04-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-05-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-06-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-07-01 | 75 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-08-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-09-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-11-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2026-12-01 | 75 | 100
Resource 11 | DevOps | Tester | PRJ024 | Process Mining | 2027-01-01 | 100 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2025-11-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2025-12-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-01-01 | 25 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-02-01 | 40 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-03-01 | 15 | 100
Resource 11 | DevOps | Tester | PRJ011 | IoT Initiative | 2026-04-01 | 25 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2025-12-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-02-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-03-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-04-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-05-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-06-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-07-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-08-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-09-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-11-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2026-12-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ024 | Process Mining | 2027-01-01 | 100 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2025-11-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2025-12-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-01-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-02-01 | 75 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-03-01 | 90 | 100
Resource 12 | Dev | Project Manager | PRJ011 | IoT Initiative | 2026-04-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-09-01 | 65 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-10-01 | 50 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-11-01 | 65 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2025-12-01 | 85 | 100
Resource 13 | Data | Project Manager | PRJ038 | Salesforce CRM | 2026-01-01 | 75 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2025-12-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-01-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-02-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-03-01 | 75 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-04-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-05-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-06-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-07-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-08-01 | 90 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-09-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-10-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-11-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2026-12-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ024 | Process Mining | 2027-01-01 | 100 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-05-01 | 25 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-06-01 | 25 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-07-01 | 0 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-08-01 | 0 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-09-01 | 15 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-10-01 | 0 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-11-01 | 25 | 100
Resource 13 | Data | Project Manager | PRJ036 | HR Self-Service | 2025-12-01 | 25 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2025-11-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2025-12-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-01-01 | 75 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-02-01 | 50 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-03-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-04-01 | 50 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-05-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-06-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-07-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-08-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-09-01 | 90 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-10-01 | 65 | 100
Resource 14 | DevOps | Tester | PRJ029 | Analytics Platform 2 | 2026-11-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-03-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-04-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-05-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-06-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-07-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-08-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-09-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-10-01 | 90 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-11-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2025-12-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-01-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-02-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-03-01 | 100 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-04-01 | 75 | 100
Resource 15 | Dev | Developer | PRJ006 | Cyber Security Program | 2026-05-01 | 100 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-07-01 | 90 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-08-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-09-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-10-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-11-01 | 85 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2025-12-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-01-01 | 85 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-02-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-03-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-04-01 | 90 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-05-01 | 75 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-06-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-07-01 | 50 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-08-01 | 65 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-09-01 | 90 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-10-01 | 75 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-11-01 | 85 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2026-12-01 | 75 | 100
Resource 16 | BA | Tester | PRJ005 | Network Refresh | 2027-01-01 | 75 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-02-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-03-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-04-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-05-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-06-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-07-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-08-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-09-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-10-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-11-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2025-12-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-01-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-02-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-03-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ040 | Zero-Trust Net | 2026-04-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-05-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-06-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-07-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-08-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-09-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-10-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-11-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2025-12-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-01-01 | 65 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-02-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-03-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-04-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-05-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-06-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-07-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-08-01 | 60 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-09-01 | 40 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-10-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-11-01 | 25 | 100
Resource 17 | Dev | Architect | PRJ007 | CRM Upgrade | 2026-12-01 | 50 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-05-01 | 75 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-06-01 | 100 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-07-01 | 90 | 100
Resource 17 | Dev | Architect | PRJ008 | Mobile App | 2025-08-01 | 100 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-04-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-05-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-06-01 | 0 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-07-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-08-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-09-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-10-01 | 35 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-11-01 | 40 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2025-12-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-01-01 | 40 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-02-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-03-01 | 15 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-04-01 | 35 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-05-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-06-01 | 25 | 100
Resource 18 | Data | Tester | PRJ003 | Data Platform | 2026-07-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2025-12-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-01-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-02-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-03-01 | 15 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-04-01 | 0 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-05-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-06-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-07-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-08-01 | 0 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-09-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-10-01 | 25 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-11-01 | 35 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2026-12-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2027-01-01 | 40 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2027-02-01 | 0 | 100
Resource 18 | Data | Tester | PRJ013 | API Gateway | 2027-03-01 | 0 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-02-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-03-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-04-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-05-01 | 75 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-06-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-07-01 | 90 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-08-01 | 75 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-09-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-10-01 | 90 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-11-01 | 100 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2025-12-01 | 90 | 100
Resource 18 | Data | Tester | PRJ010 | Workforce Enablement | 2026-01-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-01-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-02-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-03-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-04-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-05-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-06-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-07-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-08-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-09-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-10-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-11-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2025-12-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-01-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-02-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-03-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-04-01 | 90 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-05-01 | 100 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-06-01 | 75 | 100
Resource 19 | Security | Project Manager | PRJ028 | Mobile App 2 | 2026-07-01 | 75 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-06-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-07-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-08-01 | 65 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-09-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-10-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-11-01 | 50 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2025-12-01 | 65 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-01-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-02-01 | 40 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-03-01 | 50 | 100
Resource 20 | DevOps | Analyst | PRJ015 | Service Desk | 2026-04-01 | 60 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-01-01 | 50 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-02-01 | 60 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-03-01 | 60 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-04-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-05-01 | 25 | 100
Resource 20 | DevOps | Analyst | PRJ021 | Data Warehouse | 2025-06-01 | 65 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2025-12-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-01-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-02-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-03-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-04-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-05-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-06-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-07-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-08-01 | 85 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-09-01 | 50 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-10-01 | 50 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-11-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2026-12-01 | 50 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2027-01-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2027-02-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ013 | API Gateway | 2027-03-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2025-12-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-01-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-02-01 | 75 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-03-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-04-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-05-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-06-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-07-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-08-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-09-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-10-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-11-01 | 90 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2026-12-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2027-01-01 | 100 | 100
Resource 21 | Architect | Analyst | PRJ025 | Customer Insights | 2027-02-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2025-12-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-01-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-02-01 | 90 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-03-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-04-01 | 75 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-05-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-06-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-07-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-08-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-09-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-10-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-11-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2026-12-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-01-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-02-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-03-01 | 75 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-04-01 | 75 | 100
Resource 22 | UX | Project Manager | PRJ032 | Compliance Hub | 2027-05-01 | 100 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-04-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-05-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-06-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-07-01 | 60 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-08-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-09-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-10-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-11-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2025-12-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-01-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-02-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-03-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-04-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-05-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-06-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ003 | Data Platform | 2026-07-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2025-12-01 | 40 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-01-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-02-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-03-01 | 60 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-04-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-05-01 | 65 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-06-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-07-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-08-01 | 25 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-09-01 | 50 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-10-01 | 40 | 100
Resource 22 | UX | Project Manager | PRJ016 | Infrastructure Upg | 2026-11-01 | 25 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-05-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-06-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-07-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-08-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-09-01 | 75 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-10-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-11-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2025-12-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-01-01 | 75 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-02-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-03-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-04-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-05-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-06-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-07-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-08-01 | 75 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-09-01 | 100 | 100
Resource 23 | Architect | Tester | PRJ030 | Service Desk 2 | 2026-10-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2025-11-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2025-12-01 | 85 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-01-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-02-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-03-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-04-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-05-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-06-01 | 90 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-07-01 | 50 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-08-01 | 85 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-09-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-10-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-11-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2026-12-01 | 50 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-01-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-02-01 | 85 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-03-01 | 75 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-04-01 | 65 | 100
Resource 24 | QA | Tester | PRJ033 | Risk Platform | 2027-05-01 | 85 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-03-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-04-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-05-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-06-01 | 0 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-07-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-08-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-09-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-10-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-11-01 | 15 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2025-12-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-01-01 | 0 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-02-01 | 40 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-03-01 | 25 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-04-01 | 35 | 100
Resource 24 | QA | Tester | PRJ006 | Cyber Security Program | 2026-05-01 | 25 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2025-12-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-01-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-02-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-03-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-04-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-05-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-06-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-07-01 | 90 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-08-01 | 75 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-09-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-10-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-11-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2026-12-01 | 90 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2027-01-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2027-02-01 | 100 | 100
Resource 25 | Security | Architect | PRJ013 | API Gateway | 2027-03-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-05-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-06-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-07-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-08-01 | 75 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-09-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-10-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-11-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2025-12-01 | 50 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-01-01 | 85 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-02-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-03-01 | 75 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-04-01 | 75 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-05-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-06-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-07-01 | 65 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-08-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-09-01 | 90 | 100
Resource 25 | Security | Architect | PRJ030 | Service Desk 2 | 2026-10-01 | 75 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-07-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-08-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-09-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-10-01 | 65 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-11-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2025-12-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-01-01 | 65 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-02-01 | 60 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-03-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-04-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-05-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-06-01 | 25 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-07-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-08-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-09-01 | 25 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-10-01 | 40 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-11-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2026-12-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ005 | Network Refresh | 2027-01-01 | 50 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-05-01 | 100 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-06-01 | 100 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-07-01 | 75 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-08-01 | 90 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-09-01 | 90 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-10-01 | 100 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-11-01 | 90 | 100
Resource 26 | Security | Analyst | PRJ036 | HR Self-Service | 2025-12-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-05-01 | 65 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-06-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-07-01 | 65 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-08-01 | 50 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-09-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-10-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-11-01 | 25 | 100
Resource 27 | DevOps | Tester | PRJ036 | HR Self-Service | 2025-12-01 | 50 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2025-11-01 | 50 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2025-12-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2026-01-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2026-02-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ039 | M365 Rollout | 2026-03-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-03-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-04-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-05-01 | 90 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-06-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-07-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-08-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-09-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-10-01 | 75 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-11-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2025-12-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-01-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-02-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-03-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-04-01 | 100 | 100
Resource 27 | DevOps | Tester | PRJ006 | Cyber Security Program | 2026-05-01 | 75 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-01-01 | 85 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-02-01 | 90 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-03-01 | 75 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-04-01 | 90 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-05-01 | 90 | 100
Resource 28 | QA | Architect | PRJ021 | Data Warehouse | 2025-06-01 | 65 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-05-01 | 40 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-06-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-07-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-08-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-09-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-10-01 | 60 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-11-01 | 25 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2025-12-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-01-01 | 60 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-02-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-03-01 | 65 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-04-01 | 25 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-05-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-06-01 | 60 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-07-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-08-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-09-01 | 65 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-10-01 | 40 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-11-01 | 50 | 100
Resource 29 | Security | Developer | PRJ007 | CRM Upgrade | 2026-12-01 | 40 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2025-12-01 | 50 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-01-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-02-01 | 85 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-03-01 | 50 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-04-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-05-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-06-01 | 50 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-07-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-08-01 | 90 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-09-01 | 65 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-10-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-11-01 | 85 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-12-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2027-01-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2025-12-01 | 35 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-01-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-02-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-03-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-04-01 | 0 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-05-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-06-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-07-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-08-01 | 0 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-09-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-10-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-11-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2026-12-01 | 15 | 100
Resource 30 | Data | Analyst | PRJ024 | Process Mining | 2027-01-01 | 25 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-01-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-02-01 | 100 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-03-01 | 75 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-04-01 | 100 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-05-01 | 100 | 100
Resource 30 | Data | Analyst | PRJ021 | Data Warehouse | 2025-06-01 | 100 | 100

## Dependencies
From Project | To Project | Dependency Type | Status | Impact
PRJ027 | PRJ022 | Shared Resource | Healthy | Low
PRJ017 | PRJ033 | Finish-Start | At Risk | Medium
PRJ039 | PRJ036 | Blocks | At Risk | High
PRJ002 | PRJ004 | Start-Start | Blocked | Medium
PRJ009 | PRJ001 | Shared Resource | Healthy | High
PRJ020 | PRJ021 | Finish-Start | Healthy | Low
PRJ016 | PRJ034 | Start-Start | Blocked | High
PRJ027 | PRJ021 | Shared Resource | At Risk | High
PRJ009 | PRJ017 | Start-Start | Blocked | High
PRJ021 | PRJ019 | Start-Start | Healthy | Medium
PRJ024 | PRJ012 | Shared Resource | At Risk | High
PRJ015 | PRJ002 | Finish-Start | Blocked | High
PRJ040 | PRJ015 | Finish-Start | At Risk | Low
PRJ017 | PRJ011 | Finish-Start | At Risk | High
PRJ028 | PRJ039 | Blocks | Healthy | Low
PRJ024 | PRJ011 | Finish-Start | Healthy | High
PRJ034 | PRJ028 | Shared Resource | Blocked | Medium
PRJ008 | PRJ015 | Start-Start | Healthy | Medium
PRJ019 | PRJ032 | Shared Resource | Healthy | Medium
PRJ014 | PRJ039 | Start-Start | At Risk | High
PRJ013 | PRJ027 | Start-Start | At Risk | Low
PRJ002 | PRJ019 | Blocks | Healthy | High
PRJ029 | PRJ016 | Blocks | Blocked | High
PRJ030 | PRJ006 | Finish-Start | At Risk | Low
PRJ021 | PRJ026 | Start-Start | Blocked | Medium
PRJ028 | PRJ039 | Blocks | Healthy | Low
PRJ036 | PRJ004 | Finish-Start | At Risk | Low
PRJ031 | PRJ023 | Finish-Start | Healthy | Medium
PRJ033 | PRJ040 | Shared Resource | At Risk | Medium
PRJ024 | PRJ009 | Finish-Start | Blocked | Low
PRJ017 | PRJ011 | Shared Resource | At Risk | Medium
PRJ009 | PRJ006 | Blocks | Blocked | High
PRJ028 | PRJ010 | Blocks | Healthy | Medium
PRJ003 | PRJ009 | Shared Resource | At Risk | High
PRJ024 | PRJ028 | Blocks | At Risk | High
PRJ017 | PRJ034 | Blocks | At Risk | Low
PRJ021 | PRJ032 | Start-Start | Blocked | High
PRJ029 | PRJ004 | Start-Start | Healthy | Low
PRJ015 | PRJ012 | Finish-Start | At Risk | Medium
PRJ011 | PRJ030 | Shared Resource | Healthy | Medium

## Pipeline
Idea ID | Name | Submitter | Strategic Fit (1-5) | Value (1-5) | Risk (1-5) | Effort (1-5) | Priority Score | Decision | Est. Budget ($K)
IDEA008 | Quantum Pilot | Priya Patel | 4 | 4 | 3 | 5 | 32 | New | 724
IDEA004 | Edge Analytics | Alex Brown | 5 | 2 | 5 | 1 | 28 | Parked | 419
IDEA009 | SaaS Rationalisation | Priya Patel | 1 | 5 | 4 | 3 | 25 | Parked | 314
IDEA007 | Citizen Dev Studio | John Smith | 1 | 3 | 2 | 1 | 21 | Rejected | 1751
IDEA005 | Green IT | Priya Patel | 4 | 1 | 2 | 4 | 14 | New | 1867
IDEA001 | Process Automation v2 | Sarah Lee | 1 | 4 | 3 | 5 | 14 | Rejected | 1059
IDEA006 | ESG Data Hub | Sarah Lee | 3 | 1 | 3 | 1 | 14 | Approved | 1259
IDEA003 | ML Ops Platform | Carlos Diaz | 3 | 2 | 2 | 5 | 13 | Approved | 1203
IDEA002 | Customer 360 | John Smith | 1 | 2 | 1 | 3 | 10 | Under Review | 1828
IDEA010 | Zero Trust v2 | Carlos Diaz | 2 | 1 | 3 | 3 | 2 | New | 1573

## CostBenefit
Project ID | Project Name | Program | Year Offset | Year | CAPEX | OPEX | Total Cost | Benefit Recurring | Benefit One-Off | Total Benefit | Net Benefit | Benefit Type | Benefit Category | Confidence %
PRJ001 | Customer Portal | Digital Transformation | 0 | 2025 | 1319588 | 1274177 | 2593765 | 0 | 0 | 0 | -2593765 | Recurring | Compliance | 70
PRJ001 | Customer Portal | Digital Transformation | 1 | 2026 | 1319588 | 1274177 | 2593765 | 738473 | 0 | 738473 | -1855292 | Recurring | Compliance | 70
PRJ001 | Customer Portal | Digital Transformation | 2 | 2027 | 1319588 | 1274177 | 2593765 | 807665 | 0 | 807665 | -1786100 | Recurring | Compliance | 70
PRJ001 | Customer Portal | Digital Transformation | 3 | 2028 | 1319588 | 1274177 | 2593765 | 859774 | 0 | 859774 | -1733991 | Recurring | Compliance | 80
PRJ001 | Customer Portal | Digital Transformation | 4 | 2029 | 1319588 | 1274177 | 2593765 | 833860 | 0 | 833860 | -1759905 | Recurring | Compliance | 60
PRJ002 | Cloud Migration | Digital Transformation | 0 | 2025 | 1106272 | 745643 | 1851915 | 0 | 0 | 0 | -1851915 | Recurring | Compliance | 90
PRJ002 | Cloud Migration | Digital Transformation | 1 | 2026 | 1106272 | 745643 | 1851915 | 653868 | 0 | 653868 | -1198047 | Recurring | Compliance | 70
PRJ002 | Cloud Migration | Digital Transformation | 2 | 2027 | 1106272 | 745643 | 1851915 | 563363 | 0 | 563363 | -1288552 | Recurring | Compliance | 80
PRJ002 | Cloud Migration | Digital Transformation | 3 | 2028 | 1106272 | 745643 | 1851915 | 731003 | 0 | 731003 | -1120912 | Recurring | Compliance | 70
PRJ002 | Cloud Migration | Digital Transformation | 4 | 2029 | 1106272 | 745643 | 1851915 | 730897 | 0 | 730897 | -1121018 | Recurring | Compliance | 60
PRJ003 | Data Platform | Cyber Security | 0 | 2025 | 2463632 | 1431519 | 3895151 | 0 | 0 | 0 | -3895151 | Recurring | Risk Avoidance | 70
PRJ003 | Data Platform | Cyber Security | 1 | 2026 | 2463632 | 1431519 | 3895151 | 2114749 | 0 | 2114749 | -1780402 | Recurring | Risk Avoidance | 90
PRJ003 | Data Platform | Cyber Security | 2 | 2027 | 2463632 | 1431519 | 3895151 | 1952878 | 0 | 1952878 | -1942273 | Recurring | Risk Avoidance | 60
PRJ003 | Data Platform | Cyber Security | 3 | 2028 | 2463632 | 1431519 | 3895151 | 2269327 | 0 | 2269327 | -1625824 | Recurring | Risk Avoidance | 90
PRJ003 | Data Platform | Cyber Security | 4 | 2029 | 2463632 | 1431519 | 3895151 | 2119194 | 0 | 2119194 | -1775957 | Recurring | Risk Avoidance | 80
PRJ004 | AI Assistant | Data & AI | 0 | 2025 | 885049 | 658657 | 1543706 | 0 | 0 | 0 | -1543706 | One-Off | Cost Savings | 70
PRJ004 | AI Assistant | Data & AI | 1 | 2026 | 885049 | 658657 | 1543706 | 0 | 0 | 0 | -1543706 | One-Off | Cost Savings | 90
PRJ004 | AI Assistant | Data & AI | 2 | 2027 | 885049 | 658657 | 1543706 | 0 | 509515 | 509515 | -1034191 | One-Off | Cost Savings | 90
PRJ004 | AI Assistant | Data & AI | 3 | 2028 | 885049 | 658657 | 1543706 | 0 | 0 | 0 | -1543706 | One-Off | Cost Savings | 80
PRJ004 | AI Assistant | Data & AI | 4 | 2029 | 885049 | 658657 | 1543706 | 0 | 0 | 0 | -1543706 | One-Off | Cost Savings | 70
PRJ005 | Network Refresh | Cyber Security | 0 | 2025 | 870832 | 793711 | 1664543 | 0 | 0 | 0 | -1664543 | Recurring | Revenue Uplift | 60
PRJ005 | Network Refresh | Cyber Security | 1 | 2026 | 870832 | 793711 | 1664543 | 1022279 | 0 | 1022279 | -642264 | Recurring | Revenue Uplift | 60
PRJ005 | Network Refresh | Cyber Security | 2 | 2027 | 870832 | 793711 | 1664543 | 1149000 | 0 | 1149000 | -515543 | Recurring | Revenue Uplift | 90
PRJ005 | Network Refresh | Cyber Security | 3 | 2028 | 870832 | 793711 | 1664543 | 1116960 | 0 | 1116960 | -547583 | Recurring | Revenue Uplift | 90
PRJ005 | Network Refresh | Cyber Security | 4 | 2029 | 870832 | 793711 | 1664543 | 911375 | 0 | 911375 | -753168 | Recurring | Revenue Uplift | 70
PRJ006 | Cyber Security Program | Customer Experience | 0 | 2025 | 956077 | 701585 | 1657662 | 0 | 0 | 0 | -1657662 | Recurring | Cost Savings | 70
PRJ006 | Cyber Security Program | Customer Experience | 1 | 2026 | 956077 | 701585 | 1657662 | 425057 | 0 | 425057 | -1232605 | Recurring | Cost Savings | 70
PRJ006 | Cyber Security Program | Customer Experience | 2 | 2027 | 956077 | 701585 | 1657662 | 347705 | 0 | 347705 | -1309957 | Recurring | Cost Savings | 90
PRJ006 | Cyber Security Program | Customer Experience | 3 | 2028 | 956077 | 701585 | 1657662 | 348394 | 0 | 348394 | -1309268 | Recurring | Cost Savings | 90
PRJ006 | Cyber Security Program | Customer Experience | 4 | 2029 | 956077 | 701585 | 1657662 | 462890 | 0 | 462890 | -1194772 | Recurring | Cost Savings | 70
PRJ007 | CRM Upgrade | Digital Transformation | 0 | 2025 | 2708481 | 842194 | 3550675 | 0 | 0 | 0 | -3550675 | Recurring | Productivity | 60
PRJ007 | CRM Upgrade | Digital Transformation | 1 | 2026 | 2708481 | 842194 | 3550675 | 2399019 | 0 | 2399019 | -1151656 | Recurring | Productivity | 90
PRJ007 | CRM Upgrade | Digital Transformation | 2 | 2027 | 2708481 | 842194 | 3550675 | 2056671 | 0 | 2056671 | -1494004 | Recurring | Productivity | 80
PRJ007 | CRM Upgrade | Digital Transformation | 3 | 2028 | 2708481 | 842194 | 3550675 | 2023700 | 0 | 2023700 | -1526975 | Recurring | Productivity | 90
PRJ007 | CRM Upgrade | Digital Transformation | 4 | 2029 | 2708481 | 842194 | 3550675 | 1625671 | 0 | 1625671 | -1925004 | Recurring | Productivity | 80
PRJ008 | Mobile App | Data & AI | 0 | 2025 | 2612949 | 1069176 | 3682125 | 0 | 0 | 0 | -3682125 | One-Off | Cost Savings | 80
PRJ008 | Mobile App | Data & AI | 1 | 2026 | 2612949 | 1069176 | 3682125 | 0 | 0 | 0 | -3682125 | One-Off | Cost Savings | 70
PRJ008 | Mobile App | Data & AI | 2 | 2027 | 2612949 | 1069176 | 3682125 | 0 | 3219136 | 3219136 | -462989 | One-Off | Cost Savings | 70
PRJ008 | Mobile App | Data & AI | 3 | 2028 | 2612949 | 1069176 | 3682125 | 0 | 0 | 0 | -3682125 | One-Off | Cost Savings | 80
PRJ008 | Mobile App | Data & AI | 4 | 2029 | 2612949 | 1069176 | 3682125 | 0 | 0 | 0 | -3682125 | One-Off | Cost Savings | 90
PRJ009 | ERP Modernisation | Customer Experience | 0 | 2026 | 913044 | 220677 | 1133721 | 0 | 0 | 0 | -1133721 | Recurring | Productivity | 80
PRJ009 | ERP Modernisation | Customer Experience | 1 | 2027 | 913044 | 220677 | 1133721 | 445276 | 0 | 445276 | -688445 | Recurring | Productivity | 70
PRJ009 | ERP Modernisation | Customer Experience | 2 | 2028 | 913044 | 220677 | 1133721 | 417495 | 0 | 417495 | -716226 | Recurring | Productivity | 70
PRJ009 | ERP Modernisation | Customer Experience | 3 | 2029 | 913044 | 220677 | 1133721 | 390121 | 0 | 390121 | -743600 | Recurring | Productivity | 90
PRJ009 | ERP Modernisation | Customer Experience | 4 | 2030 | 913044 | 220677 | 1133721 | 349818 | 0 | 349818 | -783903 | Recurring | Productivity | 60
PRJ010 | Workforce Enablement | Data & AI | 0 | 2025 | 1203486 | 1191430 | 2394916 | 0 | 0 | 0 | -2394916 | Recurring | Productivity | 60
PRJ010 | Workforce Enablement | Data & AI | 1 | 2026 | 1203486 | 1191430 | 2394916 | 665293 | 0 | 665293 | -1729623 | Recurring | Productivity | 70
PRJ010 | Workforce Enablement | Data & AI | 2 | 2027 | 1203486 | 1191430 | 2394916 | 710566 | 0 | 710566 | -1684350 | Recurring | Productivity | 80
PRJ010 | Workforce Enablement | Data & AI | 3 | 2028 | 1203486 | 1191430 | 2394916 | 871784 | 0 | 871784 | -1523132 | Recurring | Productivity | 80
PRJ010 | Workforce Enablement | Data & AI | 4 | 2029 | 1203486 | 1191430 | 2394916 | 904389 | 0 | 904389 | -1490527 | Recurring | Productivity | 60
PRJ011 | IoT Initiative | Cloud Migration | 0 | 2025 | 341847 | 126024 | 467871 | 0 | 0 | 0 | -467871 | One-Off | Cost Savings | 60
PRJ011 | IoT Initiative | Cloud Migration | 1 | 2026 | 341847 | 126024 | 467871 | 0 | 0 | 0 | -467871 | One-Off | Cost Savings | 60
PRJ011 | IoT Initiative | Cloud Migration | 2 | 2027 | 341847 | 126024 | 467871 | 0 | 277100 | 277100 | -190771 | One-Off | Cost Savings | 60
PRJ011 | IoT Initiative | Cloud Migration | 3 | 2028 | 341847 | 126024 | 467871 | 0 | 0 | 0 | -467871 | One-Off | Cost Savings | 70
PRJ011 | IoT Initiative | Cloud Migration | 4 | 2029 | 341847 | 126024 | 467871 | 0 | 0 | 0 | -467871 | One-Off | Cost Savings | 90
PRJ012 | Analytics Platform | Cyber Security | 0 | 2025 | 1534958 | 369291 | 1904249 | 0 | 0 | 0 | -1904249 | One-Off | Cost Savings | 70
PRJ012 | Analytics Platform | Cyber Security | 1 | 2026 | 1534958 | 369291 | 1904249 | 0 | 1433938 | 1433938 | -470311 | One-Off | Cost Savings | 70
PRJ012 | Analytics Platform | Cyber Security | 2 | 2027 | 1534958 | 369291 | 1904249 | 0 | 0 | 0 | -1904249 | One-Off | Cost Savings | 80
PRJ012 | Analytics Platform | Cyber Security | 3 | 2028 | 1534958 | 369291 | 1904249 | 0 | 0 | 0 | -1904249 | One-Off | Cost Savings | 80
PRJ012 | Analytics Platform | Cyber Security | 4 | 2029 | 1534958 | 369291 | 1904249 | 0 | 0 | 0 | -1904249 | One-Off | Cost Savings | 70
PRJ013 | API Gateway | Cloud Migration | 0 | 2025 | 2337318 | 1605386 | 3942704 | 0 | 0 | 0 | -3942704 | Recurring | Compliance | 90
PRJ013 | API Gateway | Cloud Migration | 1 | 2026 | 2337318 | 1605386 | 3942704 | 1047962 | 0 | 1047962 | -2894742 | Recurring | Compliance | 80
PRJ013 | API Gateway | Cloud Migration | 2 | 2027 | 2337318 | 1605386 | 3942704 | 1153749 | 0 | 1153749 | -2788955 | Recurring | Compliance | 60
PRJ013 | API Gateway | Cloud Migration | 3 | 2028 | 2337318 | 1605386 | 3942704 | 1241960 | 0 | 1241960 | -2700744 | Recurring | Compliance | 70
PRJ013 | API Gateway | Cloud Migration | 4 | 2029 | 2337318 | 1605386 | 3942704 | 848436 | 0 | 848436 | -3094268 | Recurring | Compliance | 70
PRJ014 | Identity Mgmt | Digital Transformation | 0 | 2025 | 1607720 | 770573 | 2378293 | 0 | 0 | 0 | -2378293 | One-Off | Cost Savings | 80
PRJ014 | Identity Mgmt | Digital Transformation | 1 | 2026 | 1607720 | 770573 | 2378293 | 0 | 0 | 0 | -2378293 | One-Off | Cost Savings | 80
PRJ014 | Identity Mgmt | Digital Transformation | 2 | 2027 | 1607720 | 770573 | 2378293 | 0 | 3086630 | 3086630 | 708337 | One-Off | Cost Savings | 70
PRJ014 | Identity Mgmt | Digital Transformation | 3 | 2028 | 1607720 | 770573 | 2378293 | 0 | 0 | 0 | -2378293 | One-Off | Cost Savings | 70
PRJ014 | Identity Mgmt | Digital Transformation | 4 | 2029 | 1607720 | 770573 | 2378293 | 0 | 0 | 0 | -2378293 | One-Off | Cost Savings | 90
PRJ015 | Service Desk | Data & AI | 0 | 2025 | 788658 | 545184 | 1333842 | 0 | 0 | 0 | -1333842 | One-Off | Productivity | 80
PRJ015 | Service Desk | Data & AI | 1 | 2026 | 788658 | 545184 | 1333842 | 0 | 0 | 0 | -1333842 | One-Off | Productivity | 90
PRJ015 | Service Desk | Data & AI | 2 | 2027 | 788658 | 545184 | 1333842 | 0 | 1172866 | 1172866 | -160976 | One-Off | Productivity | 80
PRJ015 | Service Desk | Data & AI | 3 | 2028 | 788658 | 545184 | 1333842 | 0 | 0 | 0 | -1333842 | One-Off | Productivity | 80
PRJ015 | Service Desk | Data & AI | 4 | 2029 | 788658 | 545184 | 1333842 | 0 | 0 | 0 | -1333842 | One-Off | Productivity | 70
PRJ016 | Infrastructure Upg | Digital Transformation | 0 | 2025 | 2855676 | 679694 | 3535370 | 0 | 0 | 0 | -3535370 | Recurring | Cost Savings | 80
PRJ016 | Infrastructure Upg | Digital Transformation | 1 | 2026 | 2855676 | 679694 | 3535370 | 1253380 | 0 | 1253380 | -2281990 | Recurring | Cost Savings | 60
PRJ016 | Infrastructure Upg | Digital Transformation | 2 | 2027 | 2855676 | 679694 | 3535370 | 1489190 | 0 | 1489190 | -2046180 | Recurring | Cost Savings | 60
PRJ016 | Infrastructure Upg | Digital Transformation | 3 | 2028 | 2855676 | 679694 | 3535370 | 1261877 | 0 | 1261877 | -2273493 | Recurring | Cost Savings | 80
PRJ016 | Infrastructure Upg | Digital Transformation | 4 | 2029 | 2855676 | 679694 | 3535370 | 1389107 | 0 | 1389107 | -2146263 | Recurring | Cost Savings | 70
PRJ017 | App Modernisation | Digital Transformation | 0 | 2025 | 1655902 | 1242786 | 2898688 | 0 | 0 | 0 | -2898688 | One-Off | Compliance | 80
PRJ017 | App Modernisation | Digital Transformation | 1 | 2026 | 1655902 | 1242786 | 2898688 | 0 | 3587974 | 3587974 | 689286 | One-Off | Compliance | 70
PRJ017 | App Modernisation | Digital Transformation | 2 | 2027 | 1655902 | 1242786 | 2898688 | 0 | 0 | 0 | -2898688 | One-Off | Compliance | 70
PRJ017 | App Modernisation | Digital Transformation | 3 | 2028 | 1655902 | 1242786 | 2898688 | 0 | 0 | 0 | -2898688 | One-Off | Compliance | 70
PRJ017 | App Modernisation | Digital Transformation | 4 | 2029 | 1655902 | 1242786 | 2898688 | 0 | 0 | 0 | -2898688 | One-Off | Compliance | 60
PRJ018 | RPA Program | Cyber Security | 0 | 2025 | 889973 | 878006 | 1767979 | 0 | 0 | 0 | -1767979 | Recurring | Risk Avoidance | 70
PRJ018 | RPA Program | Cyber Security | 1 | 2026 | 889973 | 878006 | 1767979 | 319985 | 0 | 319985 | -1447994 | Recurring | Risk Avoidance | 90
PRJ018 | RPA Program | Cyber Security | 2 | 2027 | 889973 | 878006 | 1767979 | 323427 | 0 | 323427 | -1444552 | Recurring | Risk Avoidance | 80
PRJ018 | RPA Program | Cyber Security | 3 | 2028 | 889973 | 878006 | 1767979 | 404693 | 0 | 404693 | -1363286 | Recurring | Risk Avoidance | 90
PRJ018 | RPA Program | Cyber Security | 4 | 2029 | 889973 | 878006 | 1767979 | 292102 | 0 | 292102 | -1475877 | Recurring | Risk Avoidance | 70
PRJ019 | Vendor Mgmt | Digital Transformation | 0 | 2025 | 387212 | 113683 | 500895 | 0 | 0 | 0 | -500895 | Recurring | Risk Avoidance | 90
PRJ019 | Vendor Mgmt | Digital Transformation | 1 | 2026 | 387212 | 113683 | 500895 | 296269 | 0 | 296269 | -204626 | Recurring | Risk Avoidance | 80
PRJ019 | Vendor Mgmt | Digital Transformation | 2 | 2027 | 387212 | 113683 | 500895 | 287036 | 0 | 287036 | -213859 | Recurring | Risk Avoidance | 60
PRJ019 | Vendor Mgmt | Digital Transformation | 3 | 2028 | 387212 | 113683 | 500895 | 205318 | 0 | 205318 | -295577 | Recurring | Risk Avoidance | 70
PRJ019 | Vendor Mgmt | Digital Transformation | 4 | 2029 | 387212 | 113683 | 500895 | 238948 | 0 | 238948 | -261947 | Recurring | Risk Avoidance | 80
PRJ020 | Process Automation | Cloud Migration | 0 | 2025 | 2802937 | 698513 | 3501450 | 0 | 0 | 0 | -3501450 | Recurring | Cost Savings | 80
PRJ020 | Process Automation | Cloud Migration | 1 | 2026 | 2802937 | 698513 | 3501450 | 872874 | 0 | 872874 | -2628576 | Recurring | Cost Savings | 90
PRJ020 | Process Automation | Cloud Migration | 2 | 2027 | 2802937 | 698513 | 3501450 | 640172 | 0 | 640172 | -2861278 | Recurring | Cost Savings | 60
PRJ020 | Process Automation | Cloud Migration | 3 | 2028 | 2802937 | 698513 | 3501450 | 794427 | 0 | 794427 | -2707023 | Recurring | Cost Savings | 80
PRJ020 | Process Automation | Cloud Migration | 4 | 2029 | 2802937 | 698513 | 3501450 | 842193 | 0 | 842193 | -2659257 | Recurring | Cost Savings | 70
PRJ021 | Data Warehouse | Cloud Migration | 0 | 2025 | 2700147 | 1226337 | 3926484 | 0 | 0 | 0 | -3926484 | Recurring | Compliance | 80
PRJ021 | Data Warehouse | Cloud Migration | 1 | 2026 | 2700147 | 1226337 | 3926484 | 2187373 | 0 | 2187373 | -1739111 | Recurring | Compliance | 90
PRJ021 | Data Warehouse | Cloud Migration | 2 | 2027 | 2700147 | 1226337 | 3926484 | 2118510 | 0 | 2118510 | -1807974 | Recurring | Compliance | 90
PRJ021 | Data Warehouse | Cloud Migration | 3 | 2028 | 2700147 | 1226337 | 3926484 | 2389439 | 0 | 2389439 | -1537045 | Recurring | Compliance | 60
PRJ021 | Data Warehouse | Cloud Migration | 4 | 2029 | 2700147 | 1226337 | 3926484 | 2257247 | 0 | 2257247 | -1669237 | Recurring | Compliance | 60
PRJ022 | DevOps Tools | Cloud Migration | 0 | 2025 | 1433827 | 1430436 | 2864263 | 0 | 0 | 0 | -2864263 | One-Off | Compliance | 70
PRJ022 | DevOps Tools | Cloud Migration | 1 | 2026 | 1433827 | 1430436 | 2864263 | 0 | 2729899 | 2729899 | -134364 | One-Off | Compliance | 70
PRJ022 | DevOps Tools | Cloud Migration | 2 | 2027 | 1433827 | 1430436 | 2864263 | 0 | 0 | 0 | -2864263 | One-Off | Compliance | 70
PRJ022 | DevOps Tools | Cloud Migration | 3 | 2028 | 1433827 | 1430436 | 2864263 | 0 | 0 | 0 | -2864263 | One-Off | Compliance | 90
PRJ022 | DevOps Tools | Cloud Migration | 4 | 2029 | 1433827 | 1430436 | 2864263 | 0 | 0 | 0 | -2864263 | One-Off | Compliance | 80
PRJ023 | Workforce Portal | Customer Experience | 0 | 2025 | 1956589 | 862524 | 2819113 | 0 | 0 | 0 | -2819113 | Recurring | Compliance | 70
PRJ023 | Workforce Portal | Customer Experience | 1 | 2026 | 1956589 | 862524 | 2819113 | 1518227 | 0 | 1518227 | -1300886 | Recurring | Compliance | 80
PRJ023 | Workforce Portal | Customer Experience | 2 | 2027 | 1956589 | 862524 | 2819113 | 1665240 | 0 | 1665240 | -1153873 | Recurring | Compliance | 80
PRJ023 | Workforce Portal | Customer Experience | 3 | 2028 | 1956589 | 862524 | 2819113 | 1369014 | 0 | 1369014 | -1450099 | Recurring | Compliance | 80
PRJ023 | Workforce Portal | Customer Experience | 4 | 2029 | 1956589 | 862524 | 2819113 | 1348892 | 0 | 1348892 | -1470221 | Recurring | Compliance | 80
PRJ024 | Process Mining | Cyber Security | 0 | 2025 | 621308 | 312127 | 933435 | 0 | 0 | 0 | -933435 | Recurring | Cost Savings | 90
PRJ024 | Process Mining | Cyber Security | 1 | 2026 | 621308 | 312127 | 933435 | 328407 | 0 | 328407 | -605028 | Recurring | Cost Savings | 60
PRJ024 | Process Mining | Cyber Security | 2 | 2027 | 621308 | 312127 | 933435 | 289938 | 0 | 289938 | -643497 | Recurring | Cost Savings | 70
PRJ024 | Process Mining | Cyber Security | 3 | 2028 | 621308 | 312127 | 933435 | 266274 | 0 | 266274 | -667161 | Recurring | Cost Savings | 60
PRJ024 | Process Mining | Cyber Security | 4 | 2029 | 621308 | 312127 | 933435 | 285039 | 0 | 285039 | -648396 | Recurring | Cost Savings | 60
PRJ025 | Customer Insights | Cyber Security | 0 | 2025 | 1519937 | 356186 | 1876123 | 0 | 0 | 0 | -1876123 | Recurring | Cost Savings | 60
PRJ025 | Customer Insights | Cyber Security | 1 | 2026 | 1519937 | 356186 | 1876123 | 557802 | 0 | 557802 | -1318321 | Recurring | Cost Savings | 80
PRJ025 | Customer Insights | Cyber Security | 2 | 2027 | 1519937 | 356186 | 1876123 | 570031 | 0 | 570031 | -1306092 | Recurring | Cost Savings | 70
PRJ025 | Customer Insights | Cyber Security | 3 | 2028 | 1519937 | 356186 | 1876123 | 508780 | 0 | 508780 | -1367343 | Recurring | Cost Savings | 70
PRJ025 | Customer Insights | Cyber Security | 4 | 2029 | 1519937 | 356186 | 1876123 | 485411 | 0 | 485411 | -1390712 | Recurring | Cost Savings | 90
PRJ026 | ERP Modernisation 2 | Cyber Security | 0 | 2025 | 2286563 | 416990 | 2703553 | 0 | 0 | 0 | -2703553 | Recurring | Cost Savings | 70
PRJ026 | ERP Modernisation 2 | Cyber Security | 1 | 2026 | 2286563 | 416990 | 2703553 | 1692598 | 0 | 1692598 | -1010955 | Recurring | Cost Savings | 80
PRJ026 | ERP Modernisation 2 | Cyber Security | 2 | 2027 | 2286563 | 416990 | 2703553 | 1603427 | 0 | 1603427 | -1100126 | Recurring | Cost Savings | 70
PRJ026 | ERP Modernisation 2 | Cyber Security | 3 | 2028 | 2286563 | 416990 | 2703553 | 1394812 | 0 | 1394812 | -1308741 | Recurring | Cost Savings | 60
PRJ026 | ERP Modernisation 2 | Cyber Security | 4 | 2029 | 2286563 | 416990 | 2703553 | 1447654 | 0 | 1447654 | -1255899 | Recurring | Cost Savings | 70
PRJ027 | Cyber Program | Cyber Security | 0 | 2025 | 1361156 | 454347 | 1815503 | 0 | 0 | 0 | -1815503 | One-Off | Compliance | 80
PRJ027 | Cyber Program | Cyber Security | 1 | 2026 | 1361156 | 454347 | 1815503 | 0 | 2283746 | 2283746 | 468243 | One-Off | Compliance | 90
PRJ027 | Cyber Program | Cyber Security | 2 | 2027 | 1361156 | 454347 | 1815503 | 0 | 0 | 0 | -1815503 | One-Off | Compliance | 80
PRJ027 | Cyber Program | Cyber Security | 3 | 2028 | 1361156 | 454347 | 1815503 | 0 | 0 | 0 | -1815503 | One-Off | Compliance | 80
PRJ027 | Cyber Program | Cyber Security | 4 | 2029 | 1361156 | 454347 | 1815503 | 0 | 0 | 0 | -1815503 | One-Off | Compliance | 60
PRJ028 | Mobile App 2 | Data & AI | 0 | 2025 | 1245674 | 373286 | 1618960 | 0 | 0 | 0 | -1618960 | One-Off | Risk Avoidance | 90
PRJ028 | Mobile App 2 | Data & AI | 1 | 2026 | 1245674 | 373286 | 1618960 | 0 | 573194 | 573194 | -1045766 | One-Off | Risk Avoidance | 60
PRJ028 | Mobile App 2 | Data & AI | 2 | 2027 | 1245674 | 373286 | 1618960 | 0 | 0 | 0 | -1618960 | One-Off | Risk Avoidance | 90
PRJ028 | Mobile App 2 | Data & AI | 3 | 2028 | 1245674 | 373286 | 1618960 | 0 | 0 | 0 | -1618960 | One-Off | Risk Avoidance | 90
PRJ028 | Mobile App 2 | Data & AI | 4 | 2029 | 1245674 | 373286 | 1618960 | 0 | 0 | 0 | -1618960 | One-Off | Risk Avoidance | 70
PRJ029 | Analytics Platform 2 | Customer Experience | 0 | 2025 | 1268386 | 725618 | 1994004 | 0 | 0 | 0 | -1994004 | One-Off | Cost Savings | 70
PRJ029 | Analytics Platform 2 | Customer Experience | 1 | 2026 | 1268386 | 725618 | 1994004 | 0 | 1457637 | 1457637 | -536367 | One-Off | Cost Savings | 80
PRJ029 | Analytics Platform 2 | Customer Experience | 2 | 2027 | 1268386 | 725618 | 1994004 | 0 | 0 | 0 | -1994004 | One-Off | Cost Savings | 80
PRJ029 | Analytics Platform 2 | Customer Experience | 3 | 2028 | 1268386 | 725618 | 1994004 | 0 | 0 | 0 | -1994004 | One-Off | Cost Savings | 90
PRJ029 | Analytics Platform 2 | Customer Experience | 4 | 2029 | 1268386 | 725618 | 1994004 | 0 | 0 | 0 | -1994004 | One-Off | Cost Savings | 90
PRJ030 | Service Desk 2 | Digital Transformation | 0 | 2025 | 685010 | 429600 | 1114610 | 0 | 0 | 0 | -1114610 | One-Off | Compliance | 80
PRJ030 | Service Desk 2 | Digital Transformation | 1 | 2026 | 685010 | 429600 | 1114610 | 0 | 0 | 0 | -1114610 | One-Off | Compliance | 70
PRJ030 | Service Desk 2 | Digital Transformation | 2 | 2027 | 685010 | 429600 | 1114610 | 0 | 603368 | 603368 | -511242 | One-Off | Compliance | 70
PRJ030 | Service Desk 2 | Digital Transformation | 3 | 2028 | 685010 | 429600 | 1114610 | 0 | 0 | 0 | -1114610 | One-Off | Compliance | 60
PRJ030 | Service Desk 2 | Digital Transformation | 4 | 2029 | 685010 | 429600 | 1114610 | 0 | 0 | 0 | -1114610 | One-Off | Compliance | 70
PRJ031 | Quality Mgmt | Customer Experience | 0 | 2025 | 445013 | 432494 | 877507 | 0 | 0 | 0 | -877507 | One-Off | Productivity | 90
PRJ031 | Quality Mgmt | Customer Experience | 1 | 2026 | 445013 | 432494 | 877507 | 0 | 0 | 0 | -877507 | One-Off | Productivity | 60
PRJ031 | Quality Mgmt | Customer Experience | 2 | 2027 | 445013 | 432494 | 877507 | 0 | 1005938 | 1005938 | 128431 | One-Off | Productivity | 90
PRJ031 | Quality Mgmt | Customer Experience | 3 | 2028 | 445013 | 432494 | 877507 | 0 | 0 | 0 | -877507 | One-Off | Productivity | 90
PRJ031 | Quality Mgmt | Customer Experience | 4 | 2029 | 445013 | 432494 | 877507 | 0 | 0 | 0 | -877507 | One-Off | Productivity | 60
PRJ032 | Compliance Hub | Cloud Migration | 0 | 2025 | 2611553 | 1111107 | 3722660 | 0 | 0 | 0 | -3722660 | One-Off | Revenue Uplift | 90
PRJ032 | Compliance Hub | Cloud Migration | 1 | 2026 | 2611553 | 1111107 | 3722660 | 0 | 0 | 0 | -3722660 | One-Off | Revenue Uplift | 60
PRJ032 | Compliance Hub | Cloud Migration | 2 | 2027 | 2611553 | 1111107 | 3722660 | 0 | 4965523 | 4965523 | 1242863 | One-Off | Revenue Uplift | 60
PRJ032 | Compliance Hub | Cloud Migration | 3 | 2028 | 2611553 | 1111107 | 3722660 | 0 | 0 | 0 | -3722660 | One-Off | Revenue Uplift | 80
PRJ032 | Compliance Hub | Cloud Migration | 4 | 2029 | 2611553 | 1111107 | 3722660 | 0 | 0 | 0 | -3722660 | One-Off | Revenue Uplift | 60
PRJ033 | Risk Platform | Cyber Security | 0 | 2025 | 1046251 | 498975 | 1545226 | 0 | 0 | 0 | -1545226 | Recurring | Risk Avoidance | 70
PRJ033 | Risk Platform | Cyber Security | 1 | 2026 | 1046251 | 498975 | 1545226 | 234403 | 0 | 234403 | -1310823 | Recurring | Risk Avoidance | 60
PRJ033 | Risk Platform | Cyber Security | 2 | 2027 | 1046251 | 498975 | 1545226 | 223983 | 0 | 223983 | -1321243 | Recurring | Risk Avoidance | 60
PRJ033 | Risk Platform | Cyber Security | 3 | 2028 | 1046251 | 498975 | 1545226 | 276791 | 0 | 276791 | -1268435 | Recurring | Risk Avoidance | 90
PRJ033 | Risk Platform | Cyber Security | 4 | 2029 | 1046251 | 498975 | 1545226 | 206353 | 0 | 206353 | -1338873 | Recurring | Risk Avoidance | 60
PRJ034 | Treasury Sys | Data & AI | 0 | 2025 | 795091 | 561897 | 1356988 | 0 | 0 | 0 | -1356988 | Recurring | Productivity | 90
PRJ034 | Treasury Sys | Data & AI | 1 | 2026 | 795091 | 561897 | 1356988 | 655615 | 0 | 655615 | -701373 | Recurring | Productivity | 60
PRJ034 | Treasury Sys | Data & AI | 2 | 2027 | 795091 | 561897 | 1356988 | 618701 | 0 | 618701 | -738287 | Recurring | Productivity | 90
PRJ034 | Treasury Sys | Data & AI | 3 | 2028 | 795091 | 561897 | 1356988 | 650026 | 0 | 650026 | -706962 | Recurring | Productivity | 60
PRJ034 | Treasury Sys | Data & AI | 4 | 2029 | 795091 | 561897 | 1356988 | 654609 | 0 | 654609 | -702379 | Recurring | Productivity | 60
PRJ035 | Payroll Cloud | Data & AI | 0 | 2025 | 2453360 | 1079059 | 3532419 | 0 | 0 | 0 | -3532419 | Recurring | Cost Savings | 60
PRJ035 | Payroll Cloud | Data & AI | 1 | 2026 | 2453360 | 1079059 | 3532419 | 1237968 | 0 | 1237968 | -2294451 | Recurring | Cost Savings | 70
PRJ035 | Payroll Cloud | Data & AI | 2 | 2027 | 2453360 | 1079059 | 3532419 | 1113471 | 0 | 1113471 | -2418948 | Recurring | Cost Savings | 80
PRJ035 | Payroll Cloud | Data & AI | 3 | 2028 | 2453360 | 1079059 | 3532419 | 1084946 | 0 | 1084946 | -2447473 | Recurring | Cost Savings | 70
PRJ035 | Payroll Cloud | Data & AI | 4 | 2029 | 2453360 | 1079059 | 3532419 | 944283 | 0 | 944283 | -2588136 | Recurring | Cost Savings | 90
PRJ036 | HR Self-Service | Digital Transformation | 0 | 2025 | 1401010 | 857535 | 2258545 | 0 | 0 | 0 | -2258545 | One-Off | Productivity | 80
PRJ036 | HR Self-Service | Digital Transformation | 1 | 2026 | 1401010 | 857535 | 2258545 | 0 | 3306307 | 3306307 | 1047762 | One-Off | Productivity | 70
PRJ036 | HR Self-Service | Digital Transformation | 2 | 2027 | 1401010 | 857535 | 2258545 | 0 | 0 | 0 | -2258545 | One-Off | Productivity | 60
PRJ036 | HR Self-Service | Digital Transformation | 3 | 2028 | 1401010 | 857535 | 2258545 | 0 | 0 | 0 | -2258545 | One-Off | Productivity | 70
PRJ036 | HR Self-Service | Digital Transformation | 4 | 2029 | 1401010 | 857535 | 2258545 | 0 | 0 | 0 | -2258545 | One-Off | Productivity | 60
PRJ037 | SAP S/4HANA | Cloud Migration | 0 | 2025 | 644198 | 559497 | 1203695 | 0 | 0 | 0 | -1203695 | Recurring | Revenue Uplift | 80
PRJ037 | SAP S/4HANA | Cloud Migration | 1 | 2026 | 644198 | 559497 | 1203695 | 559351 | 0 | 559351 | -644344 | Recurring | Revenue Uplift | 80
PRJ037 | SAP S/4HANA | Cloud Migration | 2 | 2027 | 644198 | 559497 | 1203695 | 587763 | 0 | 587763 | -615932 | Recurring | Revenue Uplift | 60
PRJ037 | SAP S/4HANA | Cloud Migration | 3 | 2028 | 644198 | 559497 | 1203695 | 631939 | 0 | 631939 | -571756 | Recurring | Revenue Uplift | 70
PRJ037 | SAP S/4HANA | Cloud Migration | 4 | 2029 | 644198 | 559497 | 1203695 | 594096 | 0 | 594096 | -609599 | Recurring | Revenue Uplift | 80
PRJ038 | Salesforce CRM | Cyber Security | 0 | 2025 | 1026214 | 791614 | 1817828 | 0 | 0 | 0 | -1817828 | One-Off | Risk Avoidance | 60
PRJ038 | Salesforce CRM | Cyber Security | 1 | 2026 | 1026214 | 791614 | 1817828 | 0 | 722882 | 722882 | -1094946 | One-Off | Risk Avoidance | 90
PRJ038 | Salesforce CRM | Cyber Security | 2 | 2027 | 1026214 | 791614 | 1817828 | 0 | 0 | 0 | -1817828 | One-Off | Risk Avoidance | 80
PRJ038 | Salesforce CRM | Cyber Security | 3 | 2028 | 1026214 | 791614 | 1817828 | 0 | 0 | 0 | -1817828 | One-Off | Risk Avoidance | 70
PRJ038 | Salesforce CRM | Cyber Security | 4 | 2029 | 1026214 | 791614 | 1817828 | 0 | 0 | 0 | -1817828 | One-Off | Risk Avoidance | 80
PRJ039 | M365 Rollout | Cyber Security | 0 | 2025 | 1978668 | 1146537 | 3125205 | 0 | 0 | 0 | -3125205 | One-Off | Revenue Uplift | 70
PRJ039 | M365 Rollout | Cyber Security | 1 | 2026 | 1978668 | 1146537 | 3125205 | 0 | 2030910 | 2030910 | -1094295 | One-Off | Revenue Uplift | 70
PRJ039 | M365 Rollout | Cyber Security | 2 | 2027 | 1978668 | 1146537 | 3125205 | 0 | 0 | 0 | -3125205 | One-Off | Revenue Uplift | 60
PRJ039 | M365 Rollout | Cyber Security | 3 | 2028 | 1978668 | 1146537 | 3125205 | 0 | 0 | 0 | -3125205 | One-Off | Revenue Uplift | 90
PRJ039 | M365 Rollout | Cyber Security | 4 | 2029 | 1978668 | 1146537 | 3125205 | 0 | 0 | 0 | -3125205 | One-Off | Revenue Uplift | 70
PRJ040 | Zero-Trust Net | Customer Experience | 0 | 2025 | 1255149 | 438070 | 1693219 | 0 | 0 | 0 | -1693219 | One-Off | Compliance | 70
PRJ040 | Zero-Trust Net | Customer Experience | 1 | 2026 | 1255149 | 438070 | 1693219 | 0 | 1873752 | 1873752 | 180533 | One-Off | Compliance | 80
PRJ040 | Zero-Trust Net | Customer Experience | 2 | 2027 | 1255149 | 438070 | 1693219 | 0 | 0 | 0 | -1693219 | One-Off | Compliance | 70
PRJ040 | Zero-Trust Net | Customer Experience | 3 | 2028 | 1255149 | 438070 | 1693219 | 0 | 0 | 0 | -1693219 | One-Off | Compliance | 70
PRJ040 | Zero-Trust Net | Customer Experience | 4 | 2029 | 1255149 | 438070 | 1693219 | 0 | 0 | 0 | -1693219 | One-Off | Compliance | 70

## Benefits
Benefit ID | Project ID | Project Name | Description | Category | Target Value | Realised Value | Benefits Remaining | Realisation % | Owner | Start Date | End Date | Status
BEN001 | PRJ001 | Customer Portal | Process cycle-time reduction | Cost Reduction | 569626 | 250989 | 318637 | 0.44062 | Carlos Diaz | 2025-02-14 | 2026-03-13 | At Risk
BEN002 | PRJ001 | Customer Portal | Risk loss avoidance | Compliance | 497551 | 28353 | 469198 | 0.056985 | Alex Brown | 2025-02-14 | 2026-03-13 | At Risk
BEN003 | PRJ002 | Cloud Migration | Regulatory compliance achievement | Customer Experience | 1527159 | 400095 | 1127064 | 0.26199 | Jane Doe | 2025-03-21 | 2025-10-07 | Realised
BEN004 | PRJ002 | Cloud Migration | Risk loss avoidance | Customer Experience | 1098404 | 371599 | 726805 | 0.33831 | Mike Johnson | 2025-03-21 | 2025-10-07 | Planned
BEN005 | PRJ002 | Cloud Migration | Risk loss avoidance | Cost Reduction | 493679 | 309250 | 184429 | 0.62642 | Sarah Lee | 2025-03-21 | 2025-10-07 | At Risk
BEN006 | PRJ003 | Data Platform | Process cycle-time reduction | Productivity Improvement | 1185604 | 776392 | 409212 | 0.65485 | Alex Brown | 2025-04-09 | 2026-07-03 | Planned
BEN007 | PRJ003 | Data Platform | Revenue growth from new channel | Risk Reduction | 660591 | 239910 | 420681 | 0.36317 | John Smith | 2025-04-09 | 2026-07-03 | Realised
BEN008 | PRJ004 | AI Assistant | Process cycle-time reduction | Customer Experience | 957187 | 289792 | 667395 | 0.30275 | Mike Johnson | 2025-10-01 | 2027-01-07 | Planned
BEN009 | PRJ004 | AI Assistant | Customer NPS uplift | Revenue Increase | 441175 | 72200 | 368975 | 0.16365 | Mike Johnson | 2025-10-01 | 2027-01-07 | Planned
BEN010 | PRJ005 | Network Refresh | Headcount cost avoidance | Productivity Improvement | 1860551 | 128167 | 1732384 | 0.068887 | John Smith | 2025-07-22 | 2027-01-15 | Realised
BEN011 | PRJ005 | Network Refresh | Process cycle-time reduction | Compliance | 473628 | 109157 | 364471 | 0.23047 | Carlos Diaz | 2025-07-22 | 2027-01-15 | In Progress
BEN012 | PRJ006 | Cyber Security Program | Customer NPS uplift | Compliance | 1247665 | 120407 | 1127258 | 0.096506 | Alex Brown | 2025-03-20 | 2026-05-05 | Realised
BEN013 | PRJ006 | Cyber Security Program | Risk loss avoidance | Customer Experience | 635506 | 154201 | 481305 | 0.24264 | Carlos Diaz | 2025-03-20 | 2026-05-05 | Planned
BEN014 | PRJ006 | Cyber Security Program | Revenue growth from new channel | Customer Experience | 996808 | 357707 | 639101 | 0.35885 | Jane Doe | 2025-03-20 | 2026-05-05 | At Risk
BEN015 | PRJ007 | CRM Upgrade | Risk loss avoidance | Compliance | 1080068 | 594234 | 485834 | 0.55018 | Carlos Diaz | 2025-05-15 | 2026-12-23 | Planned
BEN016 | PRJ008 | Mobile App | Customer NPS uplift | Customer Experience | 1707023 | 512372 | 1194651 | 0.30016 | Jane Doe | 2025-05-03 | 2025-08-30 | Planned
BEN017 | PRJ008 | Mobile App | Revenue growth from new channel | Productivity Improvement | 811930 | 328228 | 483702 | 0.40426 | Priya Patel | 2025-05-03 | 2025-08-30 | Realised
BEN018 | PRJ009 | ERP Modernisation | Risk loss avoidance | Compliance | 528432 | 157475 | 370957 | 0.298 | Alex Brown | 2026-01-01 | 2026-09-07 | Planned
BEN019 | PRJ009 | ERP Modernisation | Revenue growth from new channel | Cost Reduction | 1178397 | 26568 | 1151829 | 0.022546 | Mike Johnson | 2026-01-01 | 2026-09-07 | At Risk
BEN020 | PRJ010 | Workforce Enablement | Regulatory compliance achievement | Customer Experience | 487989 | 133438 | 354551 | 0.27344 | Jane Doe | 2025-02-06 | 2026-01-25 | Realised
BEN021 | PRJ010 | Workforce Enablement | Process cycle-time reduction | Revenue Increase | 1182079 | 373625 | 808454 | 0.31607 | Jane Doe | 2025-02-06 | 2026-01-25 | In Progress
BEN022 | PRJ011 | IoT Initiative | Headcount cost avoidance | Cost Reduction | 1670302 | 705460 | 964842 | 0.42235 | Jane Doe | 2025-11-27 | 2026-04-16 | Realised
BEN023 | PRJ012 | Analytics Platform | Headcount cost avoidance | Customer Experience | 542775 | 250599 | 292176 | 0.4617 | John Smith | 2025-10-04 | 2027-03-06 | Planned
BEN024 | PRJ013 | API Gateway | Risk loss avoidance | Cost Reduction | 720867 | 459098 | 261769 | 0.63687 | John Smith | 2025-12-05 | 2027-03-07 | At Risk
BEN025 | PRJ014 | Identity Mgmt | Revenue growth from new channel | Cost Reduction | 1511971 | 411702 | 1100269 | 0.27229 | Carlos Diaz | 2025-02-05 | 2026-03-06 | At Risk
BEN026 | PRJ014 | Identity Mgmt | Revenue growth from new channel | Risk Reduction | 1654003 | 769698 | 884305 | 0.46535 | Alex Brown | 2025-02-05 | 2026-03-06 | In Progress
BEN027 | PRJ015 | Service Desk | Revenue growth from new channel | Revenue Increase | 1461867 | 469653 | 992214 | 0.32127 | Jane Doe | 2025-06-03 | 2026-04-23 | At Risk
BEN028 | PRJ015 | Service Desk | Process cycle-time reduction | Risk Reduction | 1249212 | 215849 | 1033363 | 0.17279 | Sarah Lee | 2025-06-03 | 2026-04-23 | Planned
BEN029 | PRJ015 | Service Desk | Risk loss avoidance | Productivity Improvement | 1500852 | 302479 | 1198373 | 0.20154 | Priya Patel | 2025-06-03 | 2026-04-23 | In Progress
BEN030 | PRJ016 | Infrastructure Upg | Customer NPS uplift | Customer Experience | 573356 | 361200 | 212156 | 0.62998 | Sarah Lee | 2025-12-01 | 2026-11-26 | In Progress
BEN031 | PRJ016 | Infrastructure Upg | Customer NPS uplift | Revenue Increase | 1427192 | 95442 | 1331750 | 0.066874 | Jane Doe | 2025-12-01 | 2026-11-26 | Realised
BEN032 | PRJ017 | App Modernisation | Customer NPS uplift | Cost Reduction | 1840963 | 899551 | 941412 | 0.48863 | Sarah Lee | 2025-02-17 | 2026-04-07 | Planned
BEN033 | PRJ017 | App Modernisation | Headcount cost avoidance | Risk Reduction | 1991101 | 106670 | 1884431 | 0.053573 | Carlos Diaz | 2025-02-17 | 2026-04-07 | At Risk
BEN034 | PRJ017 | App Modernisation | Headcount cost avoidance | Customer Experience | 413194 | 59979 | 353215 | 0.14516 | John Smith | 2025-02-17 | 2026-04-07 | At Risk
BEN035 | PRJ018 | RPA Program | Revenue growth from new channel | Customer Experience | 752950 | 210479 | 542471 | 0.27954 | John Smith | 2025-10-26 | 2026-11-02 | Planned
BEN036 | PRJ018 | RPA Program | Customer NPS uplift | Compliance | 1447289 | 138269 | 1309020 | 0.095537 | Sarah Lee | 2025-10-26 | 2026-11-02 | Planned
BEN037 | PRJ019 | Vendor Mgmt | Risk loss avoidance | Cost Reduction | 1142014 | 193692 | 948322 | 0.16961 | Sarah Lee | 2025-03-25 | 2026-11-04 | In Progress
BEN038 | PRJ020 | Process Automation | Headcount cost avoidance | Risk Reduction | 1253278 | 155489 | 1097789 | 0.12407 | Priya Patel | 2025-04-25 | 2025-08-05 | Planned
BEN039 | PRJ021 | Data Warehouse | Revenue growth from new channel | Customer Experience | 1550819 | 735349 | 815470 | 0.47417 | Mike Johnson | 2025-01-20 | 2025-06-14 | Planned
BEN040 | PRJ021 | Data Warehouse | Risk loss avoidance | Compliance | 1796107 | 669246 | 1126861 | 0.37261 | John Smith | 2025-01-20 | 2025-06-14 | Planned
BEN041 | PRJ021 | Data Warehouse | Headcount cost avoidance | Risk Reduction | 842175 | 181764 | 660411 | 0.21583 | John Smith | 2025-01-20 | 2025-06-14 | In Progress
BEN042 | PRJ022 | DevOps Tools | Headcount cost avoidance | Revenue Increase | 811825 | 135557 | 676268 | 0.16698 | Sarah Lee | 2025-04-11 | 2026-01-12 | Realised
BEN043 | PRJ023 | Workforce Portal | Headcount cost avoidance | Compliance | 1391923 | 61551 | 1330372 | 0.04422 | Jane Doe | 2025-11-12 | 2026-11-28 | At Risk
BEN044 | PRJ024 | Process Mining | Regulatory compliance achievement | Compliance | 304599 | 69753 | 234846 | 0.229 | Jane Doe | 2025-12-06 | 2027-01-24 | At Risk
BEN045 | PRJ024 | Process Mining | Revenue growth from new channel | Revenue Increase | 1883954 | 159312 | 1724642 | 0.084563 | Mike Johnson | 2025-12-06 | 2027-01-24 | Planned
BEN046 | PRJ024 | Process Mining | Risk loss avoidance | Cost Reduction | 864065 | 191276 | 672789 | 0.22137 | Sarah Lee | 2025-12-06 | 2027-01-24 | Realised
BEN047 | PRJ025 | Customer Insights | Revenue growth from new channel | Customer Experience | 1285428 | 39536 | 1245892 | 0.030757 | Mike Johnson | 2025-12-02 | 2027-02-17 | Planned
BEN048 | PRJ025 | Customer Insights | Regulatory compliance achievement | Cost Reduction | 1453809 | 805238 | 648571 | 0.55388 | Mike Johnson | 2025-12-02 | 2027-02-17 | Realised
BEN049 | PRJ025 | Customer Insights | Customer NPS uplift | Compliance | 1964690 | 957631 | 1007059 | 0.48742 | Jane Doe | 2025-12-02 | 2027-02-17 | Realised
BEN050 | PRJ026 | ERP Modernisation 2 | Regulatory compliance achievement | Risk Reduction | 1016048 | 238338 | 777710 | 0.23457 | Sarah Lee | 2025-09-16 | 2026-07-21 | In Progress
BEN051 | PRJ026 | ERP Modernisation 2 | Headcount cost avoidance | Cost Reduction | 1056498 | 521107 | 535391 | 0.49324 | John Smith | 2025-09-16 | 2026-07-21 | Realised
BEN052 | PRJ026 | ERP Modernisation 2 | Revenue growth from new channel | Risk Reduction | 549153 | 164718 | 384435 | 0.29995 | John Smith | 2025-09-16 | 2026-07-21 | Realised
BEN053 | PRJ027 | Cyber Program | Revenue growth from new channel | Compliance | 663568 | 70451 | 593117 | 0.10617 | John Smith | 2025-04-29 | 2026-02-09 | At Risk
BEN054 | PRJ027 | Cyber Program | Process cycle-time reduction | Productivity Improvement | 1504586 | 346180 | 1158406 | 0.23008 | Priya Patel | 2025-04-29 | 2026-02-09 | At Risk
BEN055 | PRJ028 | Mobile App 2 | Revenue growth from new channel | Compliance | 1644150 | 863813 | 780337 | 0.52539 | Mike Johnson | 2025-01-04 | 2026-07-30 | In Progress
BEN056 | PRJ028 | Mobile App 2 | Customer NPS uplift | Cost Reduction | 1124692 | 713777 | 410915 | 0.63464 | Carlos Diaz | 2025-01-04 | 2026-07-30 | In Progress
BEN057 | PRJ028 | Mobile App 2 | Process cycle-time reduction | Cost Reduction | 1255320 | 335221 | 920099 | 0.26704 | Sarah Lee | 2025-01-04 | 2026-07-30 | Planned
BEN058 | PRJ029 | Analytics Platform 2 | Customer NPS uplift | Cost Reduction | 232971 | 31387 | 201584 | 0.13472 | Jane Doe | 2025-11-15 | 2026-11-13 | In Progress
BEN059 | PRJ029 | Analytics Platform 2 | Revenue growth from new channel | Cost Reduction | 1225998 | 713353 | 512645 | 0.58185 | Alex Brown | 2025-11-15 | 2026-11-13 | At Risk
BEN060 | PRJ030 | Service Desk 2 | Risk loss avoidance | Cost Reduction | 411902 | 56956 | 354946 | 0.13828 | Alex Brown | 2025-05-10 | 2026-10-09 | Realised
BEN061 | PRJ030 | Service Desk 2 | Revenue growth from new channel | Productivity Improvement | 1195201 | 809639 | 385562 | 0.67741 | Carlos Diaz | 2025-05-10 | 2026-10-09 | Realised
BEN062 | PRJ031 | Quality Mgmt | Risk loss avoidance | Risk Reduction | 817663 | 269419 | 548244 | 0.3295 | Alex Brown | 2025-08-27 | 2026-11-18 | At Risk
BEN063 | PRJ031 | Quality Mgmt | Headcount cost avoidance | Productivity Improvement | 137641 | 36749 | 100892 | 0.26699 | Alex Brown | 2025-08-27 | 2026-11-18 | In Progress
BEN064 | PRJ032 | Compliance Hub | Process cycle-time reduction | Customer Experience | 822855 | 176168 | 646687 | 0.21409 | Alex Brown | 2025-12-20 | 2027-05-19 | Planned
BEN065 | PRJ032 | Compliance Hub | Revenue growth from new channel | Cost Reduction | 733145 | 366869 | 366276 | 0.5004 | Jane Doe | 2025-12-20 | 2027-05-19 | Realised
BEN066 | PRJ033 | Risk Platform | Risk loss avoidance | Compliance | 868655 | 252843 | 615812 | 0.29107 | Mike Johnson | 2025-11-22 | 2027-05-22 | Realised
BEN067 | PRJ033 | Risk Platform | Risk loss avoidance | Revenue Increase | 1317993 | 542771 | 775222 | 0.41182 | John Smith | 2025-11-22 | 2027-05-22 | In Progress
BEN068 | PRJ034 | Treasury Sys | Customer NPS uplift | Productivity Improvement | 1549607 | 1038187 | 511420 | 0.66997 | Alex Brown | 2025-11-09 | 2027-01-15 | Realised
BEN069 | PRJ035 | Payroll Cloud | Risk loss avoidance | Compliance | 209639 | 56547 | 153092 | 0.26974 | Jane Doe | 2025-05-04 | 2026-07-21 | Planned
BEN070 | PRJ035 | Payroll Cloud | Customer NPS uplift | Compliance | 1850790 | 468231 | 1382559 | 0.25299 | John Smith | 2025-05-04 | 2026-07-21 | In Progress
BEN071 | PRJ035 | Payroll Cloud | Customer NPS uplift | Cost Reduction | 596528 | 190191 | 406337 | 0.31883 | Mike Johnson | 2025-05-04 | 2026-07-21 | In Progress
BEN072 | PRJ036 | HR Self-Service | Customer NPS uplift | Customer Experience | 321788 | 20792 | 300996 | 0.064614 | Sarah Lee | 2025-05-09 | 2025-12-03 | Planned
BEN073 | PRJ037 | SAP S/4HANA | Revenue growth from new channel | Customer Experience | 1828903 | 1121491 | 707412 | 0.6132 | Mike Johnson | 2025-03-06 | 2025-10-22 | At Risk
BEN074 | PRJ037 | SAP S/4HANA | Customer NPS uplift | Revenue Increase | 1213552 | 623466 | 590086 | 0.51375 | John Smith | 2025-03-06 | 2025-10-22 | Realised
BEN075 | PRJ037 | SAP S/4HANA | Revenue growth from new channel | Compliance | 1647033 | 310161 | 1336872 | 0.18831 | Sarah Lee | 2025-03-06 | 2025-10-22 | Planned
BEN076 | PRJ038 | Salesforce CRM | Headcount cost avoidance | Compliance | 1651140 | 1825 | 1649315 | 0.0011053 | Sarah Lee | 2025-09-09 | 2026-01-14 | Realised
BEN077 | PRJ039 | M365 Rollout | Revenue growth from new channel | Compliance | 918804 | 113455 | 805349 | 0.12348 | Jane Doe | 2025-11-14 | 2026-03-14 | In Progress
BEN078 | PRJ039 | M365 Rollout | Regulatory compliance achievement | Cost Reduction | 1054966 | 81408 | 973558 | 0.077166 | Jane Doe | 2025-11-14 | 2026-03-14 | In Progress
BEN079 | PRJ039 | M365 Rollout | Risk loss avoidance | Customer Experience | 1637439 | 219940 | 1417499 | 0.13432 | Priya Patel | 2025-11-14 | 2026-03-14 | In Progress
BEN080 | PRJ040 | Zero-Trust Net | Process cycle-time reduction | Revenue Increase | 656939 | 173701 | 483238 | 0.26441 | Mike Johnson | 2025-02-06 | 2026-04-23 | In Progress
Formulas:
Start Date = IFERROR(VLOOKUP([Project ID],Projects!$A:$AK,16,FALSE()),"")
End Date = IFERROR(VLOOKUP([Project ID],Projects!$A:$AK,17,FALSE()),"")

## Decisions
Decision ID | Type | Project ID | Program | Description | Required By | Owner | Due Date | Priority | Status | Outcome | Approval Date
DEC001 | General |  |  | Approve full project funding | CIO | Mike Johnson | 2026-05-04 |  | Closed
DEC002 | Project | PRJ007 | Digital Transformation | Approve architecture pattern | CIO | Sarah Lee | 2026-07-23 | P2 - High | Closed
DEC003 | SteerCo | PRJ032 | Cloud Migration | Defer benefits realisation date | COO | Alex Brown | 2026-07-15 | P1 - Critical | Approved
DEC004 | Architecture | PRJ021 | Cloud Migration | Cut scope of MVP | CMO | Sarah Lee | 2026-04-06 | P4 - Low | Open
DEC005 | Architecture | PRJ007 | Digital Transformation | Re-baseline schedule | CMO | Priya Patel | 2026-04-03 | P2 - High | Open
DEC006 | Program | PRJ034 | Data & AI | Accept residual risk | CFO | Mike Johnson | 2026-06-05 | P3 - Medium | Closed
DEC007 | General | PRJ033 | Cyber Security | Accept residual risk | CFO | John Smith | 2026-06-26 | P4 - Low | Approved
DEC008 | Architecture | PRJ003 | Cyber Security | Accept residual risk | CMO | Jane Doe | 2026-01-06 | P4 - Low | Rejected
DEC009 | Program | PRJ023 | Customer Experience | Re-baseline schedule | CIO | Priya Patel | 2026-04-14 | P3 - Medium | Approved
DEC010 | Funding | PRJ010 | Data & AI | Choose vendor for cloud migration | CMO | Carlos Diaz | 2026-06-06 | P4 - Low | Approved
DEC011 | General | PRJ011 | Cloud Migration | Approve full project funding | CMO | Priya Patel | 2026-08-03 | P4 - Low | In Review
DEC012 | Funding | PRJ011 | Cloud Migration | Approve full project funding | CMO | Priya Patel | 2026-03-05 | P4 - Low | In Review
DEC013 | Risk | PRJ018 | Cyber Security | Accept residual risk | COO | Priya Patel | 2026-03-26 | P1 - Critical | Open
DEC014 | Portfolio | PRJ035 | Data & AI | Approve full project funding | COO | Carlos Diaz | 2026-06-21 | P2 - High | Closed
DEC015 | Program |  |  | Re-baseline schedule | CMO | Priya Patel | 2026-07-17 |  | Closed
DEC016 | Risk | PRJ015 | Data & AI | Cut scope of MVP | CIO | Mike Johnson | 2026-08-09 | P2 - High | Open
DEC017 | Architecture | PRJ038 | Cyber Security | Accept residual risk | CIO | Alex Brown | 2026-01-24 | P4 - Low | In Review
DEC018 | Architecture | PRJ025 | Cyber Security | Cut scope of MVP | CIO | Alex Brown | 2026-08-08 | P2 - High | In Review
DEC019 | Risk | PRJ028 | Data & AI | Defer benefits realisation date | COO | Carlos Diaz | 2026-08-06 | P2 - High | In Review
DEC020 | Funding | PRJ007 | Digital Transformation | Approve full project funding | CTO | Carlos Diaz | 2026-05-15 | P2 - High | Approved
DEC021 | SteerCo | PRJ015 | Data & AI | Accept residual risk | CMO | Jane Doe | 2026-02-08 | P2 - High | Approved
DEC022 | Project | PRJ039 | Cyber Security | Cut scope of MVP | CTO | Priya Patel | 2026-02-08 | P2 - High | Approved
DEC023 | General |  |  | Re-baseline schedule | COO | Priya Patel | 2026-08-07 |  | Open
DEC024 | Architecture | PRJ010 | Data & AI | Defer benefits realisation date | CFO | Priya Patel | 2026-07-28 | P4 - Low | Open
DEC025 | Portfolio | PRJ032 | Cloud Migration | Cut scope of MVP | CFO | John Smith | 2026-08-11 | P1 - Critical | Rejected
DEC026 | Risk |  |  | Cut scope of MVP | CMO | Sarah Lee | 2026-03-29 |  | Closed
DEC027 | SteerCo | PRJ019 | Digital Transformation | Accept residual risk | CTO | Sarah Lee | 2026-07-07 | P2 - High | In Review
DEC028 | Project | PRJ020 | Cloud Migration | Accept residual risk | CFO | Alex Brown | 2026-03-25 | P3 - Medium | Rejected
DEC029 | General | PRJ019 | Digital Transformation | Choose vendor for cloud migration | CFO | Carlos Diaz | 2026-06-29 | P2 - High | In Review
DEC030 | Project | PRJ024 | Cyber Security | Accept residual risk | CFO | Sarah Lee | 2026-07-09 | P1 - Critical | In Review
DEC031 | Program | PRJ023 | Customer Experience | Choose vendor for cloud migration | CIO | John Smith | 2026-01-16 | P3 - Medium | Approved
DEC032 | Risk | PRJ010 | Data & AI | Choose vendor for cloud migration | CIO | John Smith | 2026-06-02 | P4 - Low | Rejected
DEC033 | SteerCo | PRJ039 | Cyber Security | Accept residual risk | CMO | Carlos Diaz | 2026-05-07 | P2 - High | Open
DEC034 | General |  |  | Cut scope of MVP | CMO | Mike Johnson | 2026-07-20 |  | Open
DEC035 | Program | PRJ008 | Data & AI | Accept residual risk | CTO | Jane Doe | 2026-01-31 | P2 - High | Closed
DEC036 | General | PRJ018 | Cyber Security | Defer benefits realisation date | CTO | Jane Doe | 2026-05-28 | P1 - Critical | Rejected
DEC037 | Risk | PRJ020 | Cloud Migration | Approve full project funding | COO | John Smith | 2026-06-16 | P3 - Medium | Closed
DEC038 | Risk | PRJ002 | Digital Transformation | Approve architecture pattern | CTO | Carlos Diaz | 2026-02-18 | P3 - Medium | Rejected
DEC039 | Program | PRJ014 | Digital Transformation | Choose vendor for cloud migration | CTO | Priya Patel | 2026-01-18 | P1 - Critical | Open
DEC040 | General | PRJ021 | Cloud Migration | Approve full project funding | CFO | Alex Brown | 2026-05-24 | P4 - Low | In Review

## Actions
Action ID | Project ID | Description | Owner | Due Date | Priority | Status | Comments
ACT001 | PRJ017 | Close out stage gate evidence | Carlos Diaz | 2026-01-07 | High | Complete
ACT002 | PRJ033 | Publish SteerCo pack | Mike Johnson | 2026-01-06 | Low | Overdue
ACT003 | PRJ001 | Update risk register | Mike Johnson | 2026-01-28 | High | Overdue
ACT004 | PRJ035 | Resolve blocker on environment | Jane Doe | 2026-04-27 | Low | Overdue
ACT005 | PRJ021 | Schedule architecture review | Mike Johnson | 2026-04-20 | Low | Complete
ACT006 | PRJ014 | Submit funding paper | John Smith | 2026-05-02 | Low | Complete
ACT007 | PRJ016 | Confirm vendor SOW | Jane Doe | 2026-07-13 | High | Overdue
ACT008 | PRJ009 | Schedule architecture review | Alex Brown | 2026-03-02 | High | Overdue
ACT009 | PRJ018 | Update risk register | Priya Patel | 2026-05-16 | Low | Overdue
ACT010 | PRJ036 | Publish SteerCo pack | Mike Johnson | 2026-04-03 | Medium | Overdue
ACT011 | PRJ026 | Resolve blocker on environment | John Smith | 2026-05-31 | Medium | Overdue
ACT012 | PRJ010 | Schedule architecture review | Jane Doe | 2026-06-07 | High | Overdue
ACT013 | PRJ018 | Submit funding paper | Priya Patel | 2026-05-26 | Low | Complete
ACT014 | PRJ024 | Schedule architecture review | Priya Patel | 2026-02-03 | Low | Complete
ACT015 | PRJ039 | Update risk register | Sarah Lee | 2026-07-14 | High | Complete
ACT016 | PRJ025 | Confirm vendor SOW | Alex Brown | 2026-03-06 | High | Overdue
ACT017 | PRJ008 | Schedule architecture review | John Smith | 2026-01-04 | Low | Overdue
ACT018 | PRJ005 | Publish SteerCo pack | Priya Patel | 2026-05-05 | High | Overdue
ACT019 | PRJ018 | Update risk register | Carlos Diaz | 2026-03-18 | High | Overdue
ACT020 | PRJ007 | Resolve blocker on environment | Jane Doe | 2026-02-24 | Medium | Overdue
ACT021 | PRJ012 | Schedule architecture review | Priya Patel | 2026-01-11 | Medium | Overdue
ACT022 | PRJ007 | Schedule architecture review | Mike Johnson | 2026-05-15 | Low | Overdue
ACT023 | PRJ036 | Publish SteerCo pack | Alex Brown | 2026-05-11 | High | Overdue
ACT024 | PRJ021 | Close out stage gate evidence | Sarah Lee | 2025-12-28 | High | Overdue
ACT025 | PRJ035 | Schedule architecture review | Alex Brown | 2026-03-14 | Medium | Complete
ACT026 | PRJ009 | Publish SteerCo pack | John Smith | 2026-04-17 | Low | Complete
ACT027 | PRJ010 | Submit funding paper | Jane Doe | 2026-04-26 | High | Complete
ACT028 | PRJ018 | Confirm vendor SOW | Priya Patel | 2026-03-22 | Low | Complete
ACT029 | PRJ016 | Submit funding paper | Alex Brown | 2026-03-20 | Medium | Complete
ACT030 | PRJ012 | Resolve blocker on environment | Mike Johnson | 2026-06-14 | Medium | Overdue
ACT031 | PRJ018 | Resolve blocker on environment | Alex Brown | 2026-04-23 | Low | Overdue
ACT032 | PRJ020 | Submit funding paper | Carlos Diaz | 2026-07-12 | High | Overdue
ACT033 | PRJ021 | Close out stage gate evidence | John Smith | 2026-03-04 | Low | Overdue
ACT034 | PRJ016 | Confirm vendor SOW | Jane Doe | 2026-01-05 | Low | Overdue
ACT035 | PRJ019 | Schedule architecture review | Sarah Lee | 2025-12-30 | High | Overdue
ACT036 | PRJ033 | Submit funding paper | Jane Doe | 2026-04-03 | Medium | Complete
ACT037 | PRJ035 | Submit funding paper | John Smith | 2026-04-22 | Medium | Complete
ACT038 | PRJ013 | Close out stage gate evidence | Priya Patel | 2025-12-19 | High | Complete
ACT039 | PRJ035 | Submit funding paper | Mike Johnson | 2026-06-16 | High | Overdue
ACT040 | PRJ034 | Submit funding paper | Alex Brown | 2026-06-23 | High | Complete
ACT041 | PRJ011 | Submit funding paper | Carlos Diaz | 2026-05-20 | Low | Overdue
ACT042 | PRJ005 | Publish SteerCo pack | Carlos Diaz | 2026-02-11 | High | Overdue
ACT043 | PRJ004 | Resolve blocker on environment | Sarah Lee | 2026-04-26 | Medium | Overdue
ACT044 | PRJ008 | Publish SteerCo pack | Priya Patel | 2026-01-28 | High | Overdue
ACT045 | PRJ019 | Publish SteerCo pack | Sarah Lee | 2026-05-03 | Medium | Overdue
ACT046 | PRJ001 | Submit funding paper | Priya Patel | 2026-02-21 | Low | Overdue
ACT047 | PRJ020 | Submit funding paper | Alex Brown | 2026-03-26 | High | Overdue
ACT048 | PRJ032 | Confirm vendor SOW | Mike Johnson | 2026-04-13 | High | Complete
ACT049 | PRJ022 | Publish SteerCo pack | Mike Johnson | 2026-05-22 | High | Overdue
ACT050 | PRJ012 | Resolve blocker on environment | Mike Johnson | 2025-12-17 | High | Overdue
ACT051 | PRJ032 | Update risk register | John Smith | 2026-01-10 | Low | Overdue
ACT052 | PRJ027 | Confirm vendor SOW | Sarah Lee | 2026-04-26 | High | Overdue
ACT053 | PRJ017 | Update risk register | Sarah Lee | 2026-01-24 | Medium | Complete
ACT054 | PRJ024 | Resolve blocker on environment | Jane Doe | 2026-03-21 | Low | Overdue
ACT055 | PRJ007 | Resolve blocker on environment | Priya Patel | 2026-07-11 | Medium | Overdue
ACT056 | PRJ023 | Submit funding paper | Sarah Lee | 2026-01-26 | High | Overdue
ACT057 | PRJ013 | Confirm vendor SOW | Jane Doe | 2026-03-17 | Medium | Complete
ACT058 | PRJ026 | Resolve blocker on environment | Priya Patel | 2025-12-26 | Medium | Overdue
ACT059 | PRJ013 | Resolve blocker on environment | Priya Patel | 2025-12-24 | Medium | Overdue
ACT060 | PRJ032 | Schedule architecture review | Sarah Lee | 2026-01-15 | Low | Overdue

## Milestones
Project ID | Milestone | Planned Date | Forecast Date | Actual Date | Status | Owner | Source | _Key
PRJ001 | Discovery | 2025-02-14 | 2025-03-01 | 2025-03-01 | Complete | CTO | StageGate | PRJ001¦Discovery
PRJ001 | Business Case / Seed Funding | 2025-04-15 | 0 | 0 | In Progress | CTO | StageGate | PRJ001¦Business Case / Seed Funding
PRJ001 | Design | 2025-06-14 | 0 | 0 | Not Started | CTO | StageGate | PRJ001¦Design
PRJ001 | Business Case / Full Funding | 2025-08-13 | 0 | 0 | Not Started | CTO | StageGate | PRJ001¦Business Case / Full Funding
PRJ001 | Build | 2025-10-12 | 0 | 0 | Not Started | CTO | StageGate | PRJ001¦Build
PRJ001 | Testing | 2025-12-11 | 0 | 0 | Not Started | CTO | StageGate | PRJ001¦Testing
PRJ001 | Deployment | 2026-02-09 | 0 | 0 | Not Started | CTO | StageGate | PRJ001¦Deployment
PRJ001 | Handover | 2026-04-10 | 0 | 0 | Not Started | CTO | StageGate | PRJ001¦Handover
PRJ002 | Discovery | 2025-03-21 | 2025-03-29 | 2025-03-29 | Complete | COO | StageGate | PRJ002¦Discovery
PRJ002 | Business Case / Seed Funding | 2025-05-20 | 2025-05-07 | 2025-05-07 | Complete | COO | StageGate | PRJ002¦Business Case / Seed Funding
PRJ002 | Design | 2025-07-19 | 2025-07-05 | 2025-07-05 | Complete | COO | StageGate | PRJ002¦Design
PRJ002 | Business Case / Full Funding | 2025-09-17 | 0 | 0 | In Progress | COO | StageGate | PRJ002¦Business Case / Full Funding
PRJ002 | Build | 2025-11-16 | 0 | 0 | Not Started | COO | StageGate | PRJ002¦Build
PRJ002 | Testing | 2026-01-15 | 0 | 0 | Not Started | COO | StageGate | PRJ002¦Testing
PRJ002 | Deployment | 2026-03-16 | 0 | 0 | Not Started | COO | StageGate | PRJ002¦Deployment
PRJ002 | Handover | 2026-05-15 | 0 | 0 | Not Started | COO | StageGate | PRJ002¦Handover
PRJ003 | Discovery | 2025-04-09 | 2025-04-23 | 2025-04-23 | Complete | CFO | StageGate | PRJ003¦Discovery
PRJ003 | Business Case / Seed Funding | 2025-06-08 | 2025-06-03 | 2025-06-03 | Complete | CFO | StageGate | PRJ003¦Business Case / Seed Funding
PRJ003 | Design | 2025-08-07 | 2025-08-03 | 2025-08-03 | Complete | CFO | StageGate | PRJ003¦Design
PRJ003 | Business Case / Full Funding | 2025-10-06 | 2025-09-25 | 2025-09-25 | Complete | CFO | StageGate | PRJ003¦Business Case / Full Funding
PRJ003 | Build | 2025-12-05 | 2025-12-16 | 2025-12-16 | Complete | CFO | StageGate | PRJ003¦Build
PRJ003 | Testing | 2026-02-03 | 2026-01-23 | 2026-01-23 | Complete | CFO | StageGate | PRJ003¦Testing
PRJ003 | Deployment | 2026-04-04 | 2026-04-02 | 2026-04-02 | Complete | CFO | StageGate | PRJ003¦Deployment
PRJ003 | Handover | 2026-06-03 | 0 | 0 | In Progress | CFO | StageGate | PRJ003¦Handover
PRJ004 | Discovery | 2025-10-01 | 0 | 0 | In Progress | CTO | StageGate | PRJ004¦Discovery
PRJ004 | Business Case / Seed Funding | 2025-11-30 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Business Case / Seed Funding
PRJ004 | Design | 2026-01-29 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Design
PRJ004 | Business Case / Full Funding | 2026-03-30 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Business Case / Full Funding
PRJ004 | Build | 2026-05-29 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Build
PRJ004 | Testing | 2026-07-28 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Testing
PRJ004 | Deployment | 2026-09-26 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Deployment
PRJ004 | Handover | 2026-11-25 | 0 | 0 | Not Started | CTO | StageGate | PRJ004¦Handover
PRJ005 | Discovery | 2025-07-22 | 2025-07-24 | 2025-07-24 | Complete | CFO | StageGate | PRJ005¦Discovery
PRJ005 | Business Case / Seed Funding | 2025-09-20 | 2025-09-28 | 2025-09-28 | Complete | CFO | StageGate | PRJ005¦Business Case / Seed Funding
PRJ005 | Design | 2025-11-19 | 2025-12-10 | 2025-12-10 | Complete | CFO | StageGate | PRJ005¦Design
PRJ005 | Business Case / Full Funding | 2026-01-18 | 2026-01-22 | 2026-01-22 | Complete | CFO | StageGate | PRJ005¦Business Case / Full Funding
PRJ005 | Build | 2026-03-19 | 2026-03-09 | 2026-03-09 | Complete | CFO | StageGate | PRJ005¦Build
PRJ005 | Testing | 2026-05-18 | 0 | 0 | In Progress | CFO | StageGate | PRJ005¦Testing
PRJ005 | Deployment | 2026-07-17 | 0 | 0 | Not Started | CFO | StageGate | PRJ005¦Deployment
PRJ005 | Handover | 2026-09-15 | 0 | 0 | Not Started | CFO | StageGate | PRJ005¦Handover
PRJ006 | Discovery | 2025-03-20 | 2025-04-15 | 2025-04-15 | Complete | CMO | StageGate | PRJ006¦Discovery
PRJ006 | Business Case / Seed Funding | 2025-05-19 | 2025-06-06 | 2025-06-06 | Complete | CMO | StageGate | PRJ006¦Business Case / Seed Funding
PRJ006 | Design | 2025-07-18 | 2025-07-16 | 2025-07-16 | Complete | CMO | StageGate | PRJ006¦Design
PRJ006 | Business Case / Full Funding | 2025-09-16 | 2025-09-03 | 2025-09-03 | Complete | CMO | StageGate | PRJ006¦Business Case / Full Funding
PRJ006 | Build | 2025-11-15 | 2025-12-04 | 2025-12-04 | Complete | CMO | StageGate | PRJ006¦Build
PRJ006 | Testing | 2026-01-14 | 2026-01-19 | 2026-01-19 | Complete | CMO | StageGate | PRJ006¦Testing
PRJ006 | Deployment | 2026-03-15 | 0 | 0 | In Progress | CMO | StageGate | PRJ006¦Deployment
PRJ006 | Handover | 2026-05-14 | 0 | 0 | Not Started | CMO | StageGate | PRJ006¦Handover
PRJ007 | Discovery | 2025-05-15 | 2025-06-05 | 2025-06-05 | Complete | CTO | StageGate | PRJ007¦Discovery
PRJ007 | Business Case / Seed Funding | 2025-07-14 | 2025-07-23 | 2025-07-23 | Complete | CTO | StageGate | PRJ007¦Business Case / Seed Funding
PRJ007 | Design | 2025-09-12 | 2025-09-29 | 2025-09-29 | Complete | CTO | StageGate | PRJ007¦Design
PRJ007 | Business Case / Full Funding | 2025-11-11 | 0 | 0 | In Progress | CTO | StageGate | PRJ007¦Business Case / Full Funding
PRJ007 | Build | 2026-01-10 | 0 | 0 | Not Started | CTO | StageGate | PRJ007¦Build
PRJ007 | Testing | 2026-03-11 | 0 | 0 | Not Started | CTO | StageGate | PRJ007¦Testing
PRJ007 | Deployment | 2026-05-10 | 0 | 0 | Not Started | CTO | StageGate | PRJ007¦Deployment
PRJ007 | Handover | 2026-07-09 | 0 | 0 | Not Started | CTO | StageGate | PRJ007¦Handover
PRJ008 | Discovery | 2025-05-03 | 2025-05-19 | 2025-05-19 | Complete | CTO | StageGate | PRJ008¦Discovery
PRJ008 | Business Case / Seed Funding | 2025-07-02 | 2025-07-22 | 2025-07-22 | Complete | CTO | StageGate | PRJ008¦Business Case / Seed Funding
PRJ008 | Design | 2025-08-31 | 2025-08-27 | 2025-08-27 | Complete | CTO | StageGate | PRJ008¦Design
PRJ008 | Business Case / Full Funding | 2025-10-30 | 2025-11-23 | 2025-11-23 | Complete | CTO | StageGate | PRJ008¦Business Case / Full Funding
PRJ008 | Build | 2025-12-29 | 2026-01-28 | 2026-01-28 | Complete | CTO | StageGate | PRJ008¦Build
PRJ008 | Testing | 2026-02-27 | 2026-03-01 | 2026-03-01 | Complete | CTO | StageGate | PRJ008¦Testing
PRJ008 | Deployment | 2026-04-28 | 2026-05-28 | 2026-05-28 | Complete | CTO | StageGate | PRJ008¦Deployment
PRJ008 | Handover | 2026-06-27 | 0 | 0 | In Progress | CTO | StageGate | PRJ008¦Handover
PRJ009 | Discovery | 2026-01-01 | 0 | 0 | In Progress | CFO | StageGate | PRJ009¦Discovery
PRJ009 | Business Case / Seed Funding | 2026-03-02 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Business Case / Seed Funding
PRJ009 | Design | 2026-05-01 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Design
PRJ009 | Business Case / Full Funding | 2026-06-30 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Business Case / Full Funding
PRJ009 | Build | 2026-08-29 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Build
PRJ009 | Testing | 2026-10-28 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Testing
PRJ009 | Deployment | 2026-12-27 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Deployment
PRJ009 | Handover | 2027-02-25 | 0 | 0 | Not Started | CFO | StageGate | PRJ009¦Handover
PRJ010 | Discovery | 2025-02-06 | 2025-02-15 | 2025-02-15 | Complete | CFO | StageGate | PRJ010¦Discovery
PRJ010 | Business Case / Seed Funding | 2025-04-07 | 2025-04-18 | 2025-04-18 | Complete | CFO | StageGate | PRJ010¦Business Case / Seed Funding
PRJ010 | Design | 2025-06-06 | 2025-06-26 | 2025-06-26 | Complete | CFO | StageGate | PRJ010¦Design
PRJ010 | Business Case / Full Funding | 2025-08-05 | 2025-09-02 | 2025-09-02 | Complete | CFO | StageGate | PRJ010¦Business Case / Full Funding
PRJ010 | Build | 2025-10-04 | 2025-09-27 | 2025-09-27 | Complete | CFO | StageGate | PRJ010¦Build
PRJ010 | Testing | 2025-12-03 | 0 | 0 | In Progress | CFO | StageGate | PRJ010¦Testing
PRJ010 | Deployment | 2026-02-01 | 0 | 0 | Not Started | CFO | StageGate | PRJ010¦Deployment
PRJ010 | Handover | 2026-04-02 | 0 | 0 | Not Started | CFO | StageGate | PRJ010¦Handover
PRJ011 | Discovery | 2025-11-27 | 2025-12-12 | 2025-12-12 | Complete | CFO | StageGate | PRJ011¦Discovery
PRJ011 | Business Case / Seed Funding | 2026-01-26 | 2026-01-27 | 2026-01-27 | Complete | CFO | StageGate | PRJ011¦Business Case / Seed Funding
PRJ011 | Design | 2026-03-27 | 2026-04-19 | 2026-04-19 | Complete | CFO | StageGate | PRJ011¦Design
PRJ011 | Business Case / Full Funding | 2026-05-26 | 2026-05-17 | 2026-05-17 | Complete | CFO | StageGate | PRJ011¦Business Case / Full Funding
PRJ011 | Build | 2026-07-25 | 0 | 0 | In Progress | CFO | StageGate | PRJ011¦Build
PRJ011 | Testing | 2026-09-23 | 0 | 0 | Not Started | CFO | StageGate | PRJ011¦Testing
PRJ011 | Deployment | 2026-11-22 | 0 | 0 | Not Started | CFO | StageGate | PRJ011¦Deployment
PRJ011 | Handover | 2027-01-21 | 0 | 0 | Not Started | CFO | StageGate | PRJ011¦Handover
PRJ012 | Discovery | 2025-10-04 | 2025-10-08 | 2025-10-08 | Complete | CMO | StageGate | PRJ012¦Discovery
PRJ012 | Business Case / Seed Funding | 2025-12-03 | 2025-12-18 | 2025-12-18 | Complete | CMO | StageGate | PRJ012¦Business Case / Seed Funding
PRJ012 | Design | 2026-02-01 | 0 | 0 | In Progress | CMO | StageGate | PRJ012¦Design
PRJ012 | Business Case / Full Funding | 2026-04-02 | 0 | 0 | Not Started | CMO | StageGate | PRJ012¦Business Case / Full Funding
PRJ012 | Build | 2026-06-01 | 0 | 0 | Not Started | CMO | StageGate | PRJ012¦Build
PRJ012 | Testing | 2026-07-31 | 0 | 0 | Not Started | CMO | StageGate | PRJ012¦Testing
PRJ012 | Deployment | 2026-09-29 | 0 | 0 | Not Started | CMO | StageGate | PRJ012¦Deployment
PRJ012 | Handover | 2026-11-28 | 0 | 0 | Not Started | CMO | StageGate | PRJ012¦Handover
PRJ013 | Discovery | 2025-12-05 | 2025-12-27 | 2025-12-27 | Complete | CTO | StageGate | PRJ013¦Discovery
PRJ013 | Business Case / Seed Funding | 2026-02-03 | 2026-02-17 | 2026-02-17 | Complete | CTO | StageGate | PRJ013¦Business Case / Seed Funding
PRJ013 | Design | 2026-04-04 | 2026-04-07 | 2026-04-07 | Complete | CTO | StageGate | PRJ013¦Design
PRJ013 | Business Case / Full Funding | 2026-06-03 | 0 | 0 | In Progress | CTO | StageGate | PRJ013¦Business Case / Full Funding
PRJ013 | Build | 2026-08-02 | 0 | 0 | Not Started | CTO | StageGate | PRJ013¦Build
PRJ013 | Testing | 2026-10-01 | 0 | 0 | Not Started | CTO | StageGate | PRJ013¦Testing
PRJ013 | Deployment | 2026-11-30 | 0 | 0 | Not Started | CTO | StageGate | PRJ013¦Deployment
PRJ013 | Handover | 2027-01-29 | 0 | 0 | Not Started | CTO | StageGate | PRJ013¦Handover
PRJ014 | Discovery | 2025-02-05 | 2025-02-28 | 2025-02-28 | Complete | CTO | StageGate | PRJ014¦Discovery
PRJ014 | Business Case / Seed Funding | 2025-04-06 | 2025-04-25 | 2025-04-25 | Complete | CTO | StageGate | PRJ014¦Business Case / Seed Funding
PRJ014 | Design | 2025-06-05 | 2025-06-13 | 2025-06-13 | Complete | CTO | StageGate | PRJ014¦Design
PRJ014 | Business Case / Full Funding | 2025-08-04 | 2025-08-04 | 2025-08-04 | Complete | CTO | StageGate | PRJ014¦Business Case / Full Funding
PRJ014 | Build | 2025-10-03 | 2025-10-29 | 2025-10-29 | Complete | CTO | StageGate | PRJ014¦Build
PRJ014 | Testing | 2025-12-02 | 2025-12-08 | 2025-12-08 | Complete | CTO | StageGate | PRJ014¦Testing
PRJ014 | Deployment | 2026-01-31 | 2026-01-16 | 2026-01-16 | Complete | CTO | StageGate | PRJ014¦Deployment
PRJ014 | Handover | 2026-04-01 | 0 | 0 | In Progress | CTO | StageGate | PRJ014¦Handover
PRJ015 | Discovery | 2025-06-03 | 2025-06-17 | 2025-06-17 | Complete | CIO | StageGate | PRJ015¦Discovery
PRJ015 | Business Case / Seed Funding | 2025-08-02 | 2025-07-19 | 2025-07-19 | Complete | CIO | StageGate | PRJ015¦Business Case / Seed Funding
PRJ015 | Design | 2025-10-01 | 2025-10-04 | 2025-10-04 | Complete | CIO | StageGate | PRJ015¦Design
PRJ015 | Business Case / Full Funding | 2025-11-30 | 2025-11-22 | 2025-11-22 | Complete | CIO | StageGate | PRJ015¦Business Case / Full Funding
PRJ015 | Build | 2026-01-29 | 2026-02-02 | 2026-02-02 | Complete | CIO | StageGate | PRJ015¦Build
PRJ015 | Testing | 2026-03-30 | 2026-03-28 | 2026-03-28 | Complete | CIO | StageGate | PRJ015¦Testing
PRJ015 | Deployment | 2026-05-29 | 0 | 0 | In Progress | CIO | StageGate | PRJ015¦Deployment
PRJ015 | Handover | 2026-07-28 | 0 | 0 | Not Started | CIO | StageGate | PRJ015¦Handover
PRJ016 | Discovery | 2025-12-01 | 2025-11-20 | 2025-11-20 | Complete | CIO | StageGate | PRJ016¦Discovery
PRJ016 | Business Case / Seed Funding | 2026-01-30 | 2026-03-01 | 2026-03-01 | Complete | CIO | StageGate | PRJ016¦Business Case / Seed Funding
PRJ016 | Design | 2026-03-31 | 2026-04-06 | 2026-04-06 | Complete | CIO | StageGate | PRJ016¦Design
PRJ016 | Business Case / Full Funding | 2026-05-30 | 2026-05-30 | 2026-05-30 | Complete | CIO | StageGate | PRJ016¦Business Case / Full Funding
PRJ016 | Build | 2026-07-29 | 2026-08-04 | 2026-08-04 | Complete | CIO | StageGate | PRJ016¦Build
PRJ016 | Testing | 2026-09-27 | 0 | 0 | In Progress | CIO | StageGate | PRJ016¦Testing
PRJ016 | Deployment | 2026-11-26 | 0 | 0 | Not Started | CIO | StageGate | PRJ016¦Deployment
PRJ016 | Handover | 2027-01-25 | 0 | 0 | Not Started | CIO | StageGate | PRJ016¦Handover
PRJ017 | Discovery | 2025-02-17 | 2025-03-02 | 2025-03-02 | Complete | CFO | StageGate | PRJ017¦Discovery
PRJ017 | Business Case / Seed Funding | 2025-04-18 | 2025-04-03 | 2025-04-03 | Complete | CFO | StageGate | PRJ017¦Business Case / Seed Funding
PRJ017 | Design | 2025-06-17 | 2025-06-19 | 2025-06-19 | Complete | CFO | StageGate | PRJ017¦Design
PRJ017 | Business Case / Full Funding | 2025-08-16 | 0 | 0 | In Progress | CFO | StageGate | PRJ017¦Business Case / Full Funding
PRJ017 | Build | 2025-10-15 | 0 | 0 | Not Started | CFO | StageGate | PRJ017¦Build
PRJ017 | Testing | 2025-12-14 | 0 | 0 | Not Started | CFO | StageGate | PRJ017¦Testing
PRJ017 | Deployment | 2026-02-12 | 0 | 0 | Not Started | CFO | StageGate | PRJ017¦Deployment
PRJ017 | Handover | 2026-04-13 | 0 | 0 | Not Started | CFO | StageGate | PRJ017¦Handover
PRJ018 | Discovery | 2025-10-26 | 2025-11-19 | 2025-11-19 | Complete | COO | StageGate | PRJ018¦Discovery
PRJ018 | Business Case / Seed Funding | 2025-12-25 | 2026-01-01 | 2026-01-01 | Complete | COO | StageGate | PRJ018¦Business Case / Seed Funding
PRJ018 | Design | 2026-02-23 | 2026-03-19 | 2026-03-19 | Complete | COO | StageGate | PRJ018¦Design
PRJ018 | Business Case / Full Funding | 2026-04-24 | 2026-05-18 | 2026-05-18 | Complete | COO | StageGate | PRJ018¦Business Case / Full Funding
PRJ018 | Build | 2026-06-23 | 2026-06-28 | 2026-06-28 | Complete | COO | StageGate | PRJ018¦Build
PRJ018 | Testing | 2026-08-22 | 2026-08-26 | 2026-08-26 | Complete | COO | StageGate | PRJ018¦Testing
PRJ018 | Deployment | 2026-10-21 | 0 | 0 | In Progress | COO | StageGate | PRJ018¦Deployment
PRJ018 | Handover | 2026-12-20 | 0 | 0 | Not Started | COO | StageGate | PRJ018¦Handover
PRJ019 | Discovery | 2025-03-25 | 2025-04-06 | 2025-04-06 | Complete | COO | StageGate | PRJ019¦Discovery
PRJ019 | Business Case / Seed Funding | 2025-05-24 | 2025-06-18 | 2025-06-18 | Complete | COO | StageGate | PRJ019¦Business Case / Seed Funding
PRJ019 | Design | 2025-07-23 | 2025-08-08 | 2025-08-08 | Complete | COO | StageGate | PRJ019¦Design
PRJ019 | Business Case / Full Funding | 2025-09-21 | 2025-09-17 | 2025-09-17 | Complete | COO | StageGate | PRJ019¦Business Case / Full Funding
PRJ019 | Build | 2025-11-20 | 2025-12-14 | 2025-12-14 | Complete | COO | StageGate | PRJ019¦Build
PRJ019 | Testing | 2026-01-19 | 2026-01-04 | 2026-01-04 | Complete | COO | StageGate | PRJ019¦Testing
PRJ019 | Deployment | 2026-03-20 | 0 | 0 | In Progress | COO | StageGate | PRJ019¦Deployment
PRJ019 | Handover | 2026-05-19 | 0 | 0 | Not Started | COO | StageGate | PRJ019¦Handover
PRJ020 | Discovery | 2025-04-25 | 2025-05-25 | 2025-05-25 | Complete | CIO | StageGate | PRJ020¦Discovery
PRJ020 | Business Case / Seed Funding | 2025-06-24 | 2025-06-19 | 2025-06-19 | Complete | CIO | StageGate | PRJ020¦Business Case / Seed Funding
PRJ020 | Design | 2025-08-23 | 2025-08-22 | 2025-08-22 | Complete | CIO | StageGate | PRJ020¦Design
PRJ020 | Business Case / Full Funding | 2025-10-22 | 2025-10-24 | 2025-10-24 | Complete | CIO | StageGate | PRJ020¦Business Case / Full Funding
PRJ020 | Build | 2025-12-21 | 2025-12-16 | 2025-12-16 | Complete | CIO | StageGate | PRJ020¦Build
PRJ020 | Testing | 2026-02-19 | 2026-03-11 | 2026-03-11 | Complete | CIO | StageGate | PRJ020¦Testing
PRJ020 | Deployment | 2026-04-20 | 0 | 0 | In Progress | CIO | StageGate | PRJ020¦Deployment
PRJ020 | Handover | 2026-06-19 | 0 | 0 | Not Started | CIO | StageGate | PRJ020¦Handover
PRJ021 | Discovery | 2025-01-20 | 2025-01-11 | 2025-01-11 | Complete | CTO | StageGate | PRJ021¦Discovery
PRJ021 | Business Case / Seed Funding | 2025-03-21 | 2025-03-08 | 2025-03-08 | Complete | CTO | StageGate | PRJ021¦Business Case / Seed Funding
PRJ021 | Design | 2025-05-20 | 2025-05-27 | 2025-05-27 | Complete | CTO | StageGate | PRJ021¦Design
PRJ021 | Business Case / Full Funding | 2025-07-19 | 2025-07-11 | 2025-07-11 | Complete | CTO | StageGate | PRJ021¦Business Case / Full Funding
PRJ021 | Build | 2025-09-17 | 2025-10-09 | 2025-10-09 | Complete | CTO | StageGate | PRJ021¦Build
PRJ021 | Testing | 2025-11-16 | 2025-11-11 | 2025-11-11 | Complete | CTO | StageGate | PRJ021¦Testing
PRJ021 | Deployment | 2026-01-15 | 0 | 0 | In Progress | CTO | StageGate | PRJ021¦Deployment
PRJ021 | Handover | 2026-03-16 | 0 | 0 | Not Started | CTO | StageGate | PRJ021¦Handover
PRJ022 | Discovery | 2025-04-11 | 2025-05-11 | 2025-05-11 | Complete | CIO | StageGate | PRJ022¦Discovery
PRJ022 | Business Case / Seed Funding | 2025-06-10 | 2025-07-01 | 2025-07-01 | Complete | CIO | StageGate | PRJ022¦Business Case / Seed Funding
PRJ022 | Design | 2025-08-09 | 2025-08-02 | 2025-08-02 | Complete | CIO | StageGate | PRJ022¦Design
PRJ022 | Business Case / Full Funding | 2025-10-08 | 2025-10-10 | 2025-10-10 | Complete | CIO | StageGate | PRJ022¦Business Case / Full Funding
PRJ022 | Build | 2025-12-07 | 2025-12-07 | 2025-12-07 | Complete | CIO | StageGate | PRJ022¦Build
PRJ022 | Testing | 2026-02-05 | 0 | 0 | In Progress | CIO | StageGate | PRJ022¦Testing
PRJ022 | Deployment | 2026-04-06 | 0 | 0 | Not Started | CIO | StageGate | PRJ022¦Deployment
PRJ022 | Handover | 2026-06-05 | 0 | 0 | Not Started | CIO | StageGate | PRJ022¦Handover
PRJ023 | Discovery | 2025-11-12 | 2025-11-25 | 2025-11-25 | Complete | COO | StageGate | PRJ023¦Discovery
PRJ023 | Business Case / Seed Funding | 2026-01-11 | 2026-01-21 | 2026-01-21 | Complete | COO | StageGate | PRJ023¦Business Case / Seed Funding
PRJ023 | Design | 2026-03-12 | 2026-03-26 | 2026-03-26 | Complete | COO | StageGate | PRJ023¦Design
PRJ023 | Business Case / Full Funding | 2026-05-11 | 2026-06-02 | 2026-06-02 | Complete | COO | StageGate | PRJ023¦Business Case / Full Funding
PRJ023 | Build | 2026-07-10 | 2026-07-24 | 2026-07-24 | Complete | COO | StageGate | PRJ023¦Build
PRJ023 | Testing | 2026-09-08 | 2026-09-27 | 2026-09-27 | Complete | COO | StageGate | PRJ023¦Testing
PRJ023 | Deployment | 2026-11-07 | 0 | 0 | In Progress | COO | StageGate | PRJ023¦Deployment
PRJ023 | Handover | 2027-01-06 | 0 | 0 | Not Started | COO | StageGate | PRJ023¦Handover
PRJ024 | Discovery | 2025-12-06 | 2025-12-26 | 2025-12-26 | Complete | CFO | StageGate | PRJ024¦Discovery
PRJ024 | Business Case / Seed Funding | 2026-02-04 | 2026-02-10 | 2026-02-10 | Complete | CFO | StageGate | PRJ024¦Business Case / Seed Funding
PRJ024 | Design | 2026-04-05 | 2026-03-27 | 2026-03-27 | Complete | CFO | StageGate | PRJ024¦Design
PRJ024 | Business Case / Full Funding | 2026-06-04 | 2026-05-27 | 2026-05-27 | Complete | CFO | StageGate | PRJ024¦Business Case / Full Funding
PRJ024 | Build | 2026-08-03 | 2026-08-17 | 2026-08-17 | Complete | CFO | StageGate | PRJ024¦Build
PRJ024 | Testing | 2026-10-02 | 0 | 0 | In Progress | CFO | StageGate | PRJ024¦Testing
PRJ024 | Deployment | 2026-12-01 | 0 | 0 | Not Started | CFO | StageGate | PRJ024¦Deployment
PRJ024 | Handover | 2027-01-30 | 0 | 0 | Not Started | CFO | StageGate | PRJ024¦Handover
PRJ025 | Discovery | 2025-12-02 | 2025-11-22 | 2025-11-22 | Complete | CTO | StageGate | PRJ025¦Discovery
PRJ025 | Business Case / Seed Funding | 2026-01-31 | 2026-01-19 | 2026-01-19 | Complete | CTO | StageGate | PRJ025¦Business Case / Seed Funding
PRJ025 | Design | 2026-04-01 | 2026-04-30 | 2026-04-30 | Complete | CTO | StageGate | PRJ025¦Design
PRJ025 | Business Case / Full Funding | 2026-05-31 | 2026-06-26 | 2026-06-26 | Complete | CTO | StageGate | PRJ025¦Business Case / Full Funding
PRJ025 | Build | 2026-07-30 | 0 | 0 | In Progress | CTO | StageGate | PRJ025¦Build
PRJ025 | Testing | 2026-09-28 | 0 | 0 | Not Started | CTO | StageGate | PRJ025¦Testing
PRJ025 | Deployment | 2026-11-27 | 0 | 0 | Not Started | CTO | StageGate | PRJ025¦Deployment
PRJ025 | Handover | 2027-01-26 | 0 | 0 | Not Started | CTO | StageGate | PRJ025¦Handover
PRJ026 | Discovery | 2025-09-16 | 2025-09-08 | 2025-09-08 | Complete | COO | StageGate | PRJ026¦Discovery
PRJ026 | Business Case / Seed Funding | 2025-11-15 | 2025-11-30 | 2025-11-30 | Complete | COO | StageGate | PRJ026¦Business Case / Seed Funding
PRJ026 | Design | 2026-01-14 | 2026-01-23 | 2026-01-23 | Complete | COO | StageGate | PRJ026¦Design
PRJ026 | Business Case / Full Funding | 2026-03-15 | 2026-03-06 | 2026-03-06 | Complete | COO | StageGate | PRJ026¦Business Case / Full Funding
PRJ026 | Build | 2026-05-14 | 2026-05-18 | 2026-05-18 | Complete | COO | StageGate | PRJ026¦Build
PRJ026 | Testing | 2026-07-13 | 0 | 0 | In Progress | COO | StageGate | PRJ026¦Testing
PRJ026 | Deployment | 2026-09-11 | 0 | 0 | Not Started | COO | StageGate | PRJ026¦Deployment
PRJ026 | Handover | 2026-11-10 | 0 | 0 | Not Started | COO | StageGate | PRJ026¦Handover
PRJ027 | Discovery | 2025-04-29 | 2025-05-06 | 2025-05-06 | Complete | CMO | StageGate | PRJ027¦Discovery
PRJ027 | Business Case / Seed Funding | 2025-06-28 | 2025-07-09 | 2025-07-09 | Complete | CMO | StageGate | PRJ027¦Business Case / Seed Funding
PRJ027 | Design | 2025-08-27 | 2025-08-17 | 2025-08-17 | Complete | CMO | StageGate | PRJ027¦Design
PRJ027 | Business Case / Full Funding | 2025-10-26 | 2025-10-18 | 2025-10-18 | Complete | CMO | StageGate | PRJ027¦Business Case / Full Funding
PRJ027 | Build | 2025-12-25 | 2026-01-06 | 2026-01-06 | Complete | CMO | StageGate | PRJ027¦Build
PRJ027 | Testing | 2026-02-23 | 2026-02-23 | 2026-02-23 | Complete | CMO | StageGate | PRJ027¦Testing
PRJ027 | Deployment | 2026-04-24 | 2026-04-24 | 2026-04-24 | Complete | CMO | StageGate | PRJ027¦Deployment
PRJ027 | Handover | 2026-06-23 | 0 | 0 | In Progress | CMO | StageGate | PRJ027¦Handover
PRJ028 | Discovery | 2025-01-04 | 2025-01-14 | 2025-01-14 | Complete | CTO | StageGate | PRJ028¦Discovery
PRJ028 | Business Case / Seed Funding | 2025-03-05 | 2025-03-05 | 2025-03-05 | Complete | CTO | StageGate | PRJ028¦Business Case / Seed Funding
PRJ028 | Design | 2025-05-04 | 2025-04-26 | 2025-04-26 | Complete | CTO | StageGate | PRJ028¦Design
PRJ028 | Business Case / Full Funding | 2025-07-03 | 0 | 0 | In Progress | CTO | StageGate | PRJ028¦Business Case / Full Funding
PRJ028 | Build | 2025-09-01 | 0 | 0 | Not Started | CTO | StageGate | PRJ028¦Build
PRJ028 | Testing | 2025-10-31 | 0 | 0 | Not Started | CTO | StageGate | PRJ028¦Testing
PRJ028 | Deployment | 2025-12-30 | 0 | 0 | Not Started | CTO | StageGate | PRJ028¦Deployment
PRJ028 | Handover | 2026-02-28 | 0 | 0 | Not Started | CTO | StageGate | PRJ028¦Handover
PRJ029 | Discovery | 2025-11-15 | 0 | 0 | In Progress | CIO | StageGate | PRJ029¦Discovery
PRJ029 | Business Case / Seed Funding | 2026-01-14 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Business Case / Seed Funding
PRJ029 | Design | 2026-03-15 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Design
PRJ029 | Business Case / Full Funding | 2026-05-14 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Business Case / Full Funding
PRJ029 | Build | 2026-07-13 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Build
PRJ029 | Testing | 2026-09-11 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Testing
PRJ029 | Deployment | 2026-11-10 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Deployment
PRJ029 | Handover | 2027-01-09 | 0 | 0 | Not Started | CIO | StageGate | PRJ029¦Handover
PRJ030 | Discovery | 2025-05-10 | 2025-04-30 | 2025-04-30 | Complete | COO | StageGate | PRJ030¦Discovery
PRJ030 | Business Case / Seed Funding | 2025-07-09 | 2025-07-28 | 2025-07-28 | Complete | COO | StageGate | PRJ030¦Business Case / Seed Funding
PRJ030 | Design | 2025-09-07 | 2025-09-29 | 2025-09-29 | Complete | COO | StageGate | PRJ030¦Design
PRJ030 | Business Case / Full Funding | 2025-11-06 | 2025-12-05 | 2025-12-05 | Complete | COO | StageGate | PRJ030¦Business Case / Full Funding
PRJ030 | Build | 2026-01-05 | 0 | 0 | In Progress | COO | StageGate | PRJ030¦Build
PRJ030 | Testing | 2026-03-06 | 0 | 0 | Not Started | COO | StageGate | PRJ030¦Testing
PRJ030 | Deployment | 2026-05-05 | 0 | 0 | Not Started | COO | StageGate | PRJ030¦Deployment
PRJ030 | Handover | 2026-07-04 | 0 | 0 | Not Started | COO | StageGate | PRJ030¦Handover
PRJ031 | Discovery | 2025-08-27 | 2025-08-12 | 2025-08-12 | Complete | CIO | StageGate | PRJ031¦Discovery
PRJ031 | Business Case / Seed Funding | 2025-10-26 | 0 | 0 | In Progress | CIO | StageGate | PRJ031¦Business Case / Seed Funding
PRJ031 | Design | 2025-12-25 | 0 | 0 | Not Started | CIO | StageGate | PRJ031¦Design
PRJ031 | Business Case / Full Funding | 2026-02-23 | 0 | 0 | Not Started | CIO | StageGate | PRJ031¦Business Case / Full Funding
PRJ031 | Build | 2026-04-24 | 0 | 0 | Not Started | CIO | StageGate | PRJ031¦Build
PRJ031 | Testing | 2026-06-23 | 0 | 0 | Not Started | CIO | StageGate | PRJ031¦Testing
PRJ031 | Deployment | 2026-08-22 | 0 | 0 | Not Started | CIO | StageGate | PRJ031¦Deployment
PRJ031 | Handover | 2026-10-21 | 0 | 0 | Not Started | CIO | StageGate | PRJ031¦Handover
PRJ032 | Discovery | 2025-12-20 | 2026-01-19 | 2026-01-19 | Complete | CIO | StageGate | PRJ032¦Discovery
PRJ032 | Business Case / Seed Funding | 2026-02-18 | 2026-03-04 | 2026-03-04 | Complete | CIO | StageGate | PRJ032¦Business Case / Seed Funding
PRJ032 | Design | 2026-04-19 | 2026-05-05 | 2026-05-05 | Complete | CIO | StageGate | PRJ032¦Design
PRJ032 | Business Case / Full Funding | 2026-06-18 | 2026-06-13 | 2026-06-13 | Complete | CIO | StageGate | PRJ032¦Business Case / Full Funding
PRJ032 | Build | 2026-08-17 | 0 | 0 | In Progress | CIO | StageGate | PRJ032¦Build
PRJ032 | Testing | 2026-10-16 | 0 | 0 | Not Started | CIO | StageGate | PRJ032¦Testing
PRJ032 | Deployment | 2026-12-15 | 0 | 0 | Not Started | CIO | StageGate | PRJ032¦Deployment
PRJ032 | Handover | 2027-02-13 | 0 | 0 | Not Started | CIO | StageGate | PRJ032¦Handover
PRJ033 | Discovery | 2025-11-22 | 2025-11-30 | 2025-11-30 | Complete | CTO | StageGate | PRJ033¦Discovery
PRJ033 | Business Case / Seed Funding | 2026-01-21 | 2026-01-17 | 2026-01-17 | Complete | CTO | StageGate | PRJ033¦Business Case / Seed Funding
PRJ033 | Design | 2026-03-22 | 2026-03-21 | 2026-03-21 | Complete | CTO | StageGate | PRJ033¦Design
PRJ033 | Business Case / Full Funding | 2026-05-21 | 2026-06-01 | 2026-06-01 | Complete | CTO | StageGate | PRJ033¦Business Case / Full Funding
PRJ033 | Build | 2026-07-20 | 2026-07-09 | 2026-07-09 | Complete | CTO | StageGate | PRJ033¦Build
PRJ033 | Testing | 2026-09-18 | 2026-10-05 | 2026-10-05 | Complete | CTO | StageGate | PRJ033¦Testing
PRJ033 | Deployment | 2026-11-17 | 2026-11-16 | 2026-11-16 | Complete | CTO | StageGate | PRJ033¦Deployment
PRJ033 | Handover | 2027-01-16 | 0 | 0 | In Progress | CTO | StageGate | PRJ033¦Handover
PRJ034 | Discovery | 2025-11-09 | 2025-11-14 | 2025-11-14 | Complete | CMO | StageGate | PRJ034¦Discovery
PRJ034 | Business Case / Seed Funding | 2026-01-08 | 2025-12-24 | 2025-12-24 | Complete | CMO | StageGate | PRJ034¦Business Case / Seed Funding
PRJ034 | Design | 2026-03-09 | 2026-03-12 | 2026-03-12 | Complete | CMO | StageGate | PRJ034¦Design
PRJ034 | Business Case / Full Funding | 2026-05-08 | 2026-05-22 | 2026-05-22 | Complete | CMO | StageGate | PRJ034¦Business Case / Full Funding
PRJ034 | Build | 2026-07-07 | 0 | 0 | In Progress | CMO | StageGate | PRJ034¦Build
PRJ034 | Testing | 2026-09-05 | 0 | 0 | Not Started | CMO | StageGate | PRJ034¦Testing
PRJ034 | Deployment | 2026-11-04 | 0 | 0 | Not Started | CMO | StageGate | PRJ034¦Deployment
PRJ034 | Handover | 2027-01-03 | 0 | 0 | Not Started | CMO | StageGate | PRJ034¦Handover
PRJ035 | Discovery | 2025-05-04 | 2025-04-19 | 2025-04-19 | Complete | COO | StageGate | PRJ035¦Discovery
PRJ035 | Business Case / Seed Funding | 2025-07-03 | 2025-06-24 | 2025-06-24 | Complete | COO | StageGate | PRJ035¦Business Case / Seed Funding
PRJ035 | Design | 2025-09-01 | 2025-09-12 | 2025-09-12 | Complete | COO | StageGate | PRJ035¦Design
PRJ035 | Business Case / Full Funding | 2025-10-31 | 2025-10-25 | 2025-10-25 | Complete | COO | StageGate | PRJ035¦Business Case / Full Funding
PRJ035 | Build | 2025-12-30 | 2025-12-17 | 2025-12-17 | Complete | COO | StageGate | PRJ035¦Build
PRJ035 | Testing | 2026-02-28 | 0 | 0 | In Progress | COO | StageGate | PRJ035¦Testing
PRJ035 | Deployment | 2026-04-29 | 0 | 0 | Not Started | COO | StageGate | PRJ035¦Deployment
PRJ035 | Handover | 2026-06-28 | 0 | 0 | Not Started | COO | StageGate | PRJ035¦Handover
PRJ036 | Discovery | 2025-05-09 | 2025-04-28 | 2025-04-28 | Complete | CFO | StageGate | PRJ036¦Discovery
PRJ036 | Business Case / Seed Funding | 2025-07-08 | 2025-08-04 | 2025-08-04 | Complete | CFO | StageGate | PRJ036¦Business Case / Seed Funding
PRJ036 | Design | 2025-09-06 | 2025-09-09 | 2025-09-09 | Complete | CFO | StageGate | PRJ036¦Design
PRJ036 | Business Case / Full Funding | 2025-11-05 | 2025-11-15 | 2025-11-15 | Complete | CFO | StageGate | PRJ036¦Business Case / Full Funding
PRJ036 | Build | 2026-01-04 | 2026-01-17 | 2026-01-17 | Complete | CFO | StageGate | PRJ036¦Build
PRJ036 | Testing | 2026-03-05 | 2026-02-22 | 2026-02-22 | Complete | CFO | StageGate | PRJ036¦Testing
PRJ036 | Deployment | 2026-05-04 | 0 | 0 | In Progress | CFO | StageGate | PRJ036¦Deployment
PRJ036 | Handover | 2026-07-03 | 0 | 0 | Not Started | CFO | StageGate | PRJ036¦Handover
PRJ037 | Discovery | 2025-03-06 | 2025-03-11 | 2025-03-11 | Complete | CMO | StageGate | PRJ037¦Discovery
PRJ037 | Business Case / Seed Funding | 2025-05-05 | 2025-05-24 | 2025-05-24 | Complete | CMO | StageGate | PRJ037¦Business Case / Seed Funding
PRJ037 | Design | 2025-07-04 | 2025-07-17 | 2025-07-17 | Complete | CMO | StageGate | PRJ037¦Design
PRJ037 | Business Case / Full Funding | 2025-09-02 | 2025-09-03 | 2025-09-03 | Complete | CMO | StageGate | PRJ037¦Business Case / Full Funding
PRJ037 | Build | 2025-11-01 | 2025-10-27 | 2025-10-27 | Complete | CMO | StageGate | PRJ037¦Build
PRJ037 | Testing | 2025-12-31 | 2025-12-29 | 2025-12-29 | Complete | CMO | StageGate | PRJ037¦Testing
PRJ037 | Deployment | 2026-03-01 | 2026-02-19 | 2026-02-19 | Complete | CMO | StageGate | PRJ037¦Deployment
PRJ037 | Handover | 2026-04-30 | 0 | 0 | In Progress | CMO | StageGate | PRJ037¦Handover
PRJ038 | Discovery | 2025-09-09 | 2025-08-26 | 2025-08-26 | Complete | CIO | StageGate | PRJ038¦Discovery
PRJ038 | Business Case / Seed Funding | 2025-11-08 | 2025-11-28 | 2025-11-28 | Complete | CIO | StageGate | PRJ038¦Business Case / Seed Funding
PRJ038 | Design | 2026-01-07 | 0 | 0 | In Progress | CIO | StageGate | PRJ038¦Design
PRJ038 | Business Case / Full Funding | 2026-03-08 | 0 | 0 | Not Started | CIO | StageGate | PRJ038¦Business Case / Full Funding
PRJ038 | Build | 2026-05-07 | 0 | 0 | Not Started | CIO | StageGate | PRJ038¦Build
PRJ038 | Testing | 2026-07-06 | 0 | 0 | Not Started | CIO | StageGate | PRJ038¦Testing
PRJ038 | Deployment | 2026-09-04 | 0 | 0 | Not Started | CIO | StageGate | PRJ038¦Deployment
PRJ038 | Handover | 2026-11-03 | 0 | 0 | Not Started | CIO | StageGate | PRJ038¦Handover
PRJ039 | Discovery | 2025-11-14 | 2025-10-31 | 2025-10-31 | Complete | CIO | StageGate | PRJ039¦Discovery
PRJ039 | Business Case / Seed Funding | 2026-01-13 | 0 | 0 | In Progress | CIO | StageGate | PRJ039¦Business Case / Seed Funding
PRJ039 | Design | 2026-03-14 | 0 | 0 | Not Started | CIO | StageGate | PRJ039¦Design
PRJ039 | Business Case / Full Funding | 2026-05-13 | 0 | 0 | Not Started | CIO | StageGate | PRJ039¦Business Case / Full Funding
PRJ039 | Build | 2026-07-12 | 0 | 0 | Not Started | CIO | StageGate | PRJ039¦Build
PRJ039 | Testing | 2026-09-10 | 0 | 0 | Not Started | CIO | StageGate | PRJ039¦Testing
PRJ039 | Deployment | 2026-11-09 | 0 | 0 | Not Started | CIO | StageGate | PRJ039¦Deployment
PRJ039 | Handover | 2027-01-08 | 0 | 0 | Not Started | CIO | StageGate | PRJ039¦Handover
PRJ040 | Discovery | 2025-02-06 | 2025-02-02 | 2025-02-02 | Complete | CIO | StageGate | PRJ040¦Discovery
PRJ040 | Business Case / Seed Funding | 2025-04-07 | 2025-04-03 | 2025-04-03 | Complete | CIO | StageGate | PRJ040¦Business Case / Seed Funding
PRJ040 | Design | 2025-06-06 | 2025-06-19 | 2025-06-19 | Complete | CIO | StageGate | PRJ040¦Design
PRJ040 | Business Case / Full Funding | 2025-08-05 | 2025-08-29 | 2025-08-29 | Complete | CIO | StageGate | PRJ040¦Business Case / Full Funding
PRJ040 | Build | 2025-10-04 | 2025-10-20 | 2025-10-20 | Complete | CIO | StageGate | PRJ040¦Build
PRJ040 | Testing | 2025-12-03 | 2025-11-21 | 2025-11-21 | Complete | CIO | StageGate | PRJ040¦Testing
PRJ040 | Deployment | 2026-02-01 | 0 | 0 | In Progress | CIO | StageGate | PRJ040¦Deployment
PRJ040 | Handover | 2026-04-02 | 0 | 0 | Not Started | CIO | StageGate | PRJ040¦Handover

## PortfolioMovements
Movement ID | Project ID | Project Name | From Category | To Category | Moved By | Moved On | Reason
MV001 | PRJ009 | ERP Modernisation | CAPEX | IT Strategic | sponsor | 2026-01-06 | Promoted from unfunded to IT strategic
MV002 | PRJ009 | ERP Modernisation | Business Strategic | IT Strategic | admin | 2025-08-06 | Reclassified following strategy review
MV003 | PRJ023 | Workforce Portal | Business Strategic | Unfunded | admin | 2025-07-18 | De-funded; moved to unfunded backlog
MV004 | PRJ028 | Mobile App 2 | Business Strategic | CAPEX | governance | 2025-09-17 | De-funded; moved to unfunded backlog
MV005 | PRJ032 | Compliance Hub | Business Strategic | CAPEX | admin | 2025-12-10 | Reclassified following strategy review
MV006 | PRJ033 | Risk Platform | IT Strategic | Business Strategic | governance | 2026-01-17 | Funding approved — move to CAPEX
MV007 | PRJ017 | App Modernisation | IT Strategic | Unfunded | governance | 2025-08-24 | Promoted from unfunded to IT strategic
MV008 | PRJ007 | CRM Upgrade | IT Strategic | Business Strategic | sponsor | 2025-12-13 | Reclassified following strategy review
MV009 | PRJ015 | Service Desk | Business Strategic | IT Strategic | governance | 2025-07-14 | De-funded; moved to unfunded backlog
MV010 | PRJ013 | API Gateway | IT Strategic | CAPEX | admin | 2025-12-09 | Reclassified following strategy review

## Prioritisation
Project ID | Project Name | Strategic Alignment (1-5) | Benefit Value (1-5) | Risk Reduction (1-5) | Compliance (1-5) | Complexity (1-5) | Score
PRJ027 | Cyber Program | 4 | 5 | 5 | 3 | 3 | 72
PRJ011 | IoT Initiative | 3 | 5 | 5 | 5 | 3 | 72
PRJ037 | SAP S/4HANA | 4 | 3 | 5 | 5 | 2 | 70
PRJ034 | Treasury Sys | 4 | 5 | 3 | 3 | 1 | 68
PRJ024 | Process Mining | 4 | 5 | 4 | 4 | 5 | 67
PRJ039 | M365 Rollout | 5 | 4 | 2 | 4 | 2 | 66
PRJ003 | Data Platform | 4 | 1 | 5 | 4 | 1 | 59
PRJ016 | Infrastructure Upg | 3 | 4 | 2 | 5 | 2 | 57
PRJ040 | Zero-Trust Net | 4 | 3 | 2 | 4 | 1 | 57
PRJ036 | HR Self-Service | 3 | 1 | 5 | 5 | 1 | 56
PRJ018 | RPA Program | 3 | 5 | 3 | 3 | 4 | 56
PRJ020 | Process Automation | 5 | 5 | 1 | 2 | 5 | 55
PRJ005 | Network Refresh | 3 | 4 | 2 | 3 | 1 | 53
PRJ026 | ERP Modernisation 2 | 5 | 2 | 5 | 1 | 5 | 53
PRJ028 | Mobile App 2 | 2 | 3 | 3 | 5 | 1 | 52
PRJ038 | Salesforce CRM | 4 | 2 | 3 | 3 | 2 | 51
PRJ033 | Risk Platform | 3 | 1 | 5 | 3 | 2 | 48
PRJ009 | ERP Modernisation | 3 | 3 | 3 | 1 | 1 | 46
PRJ023 | Workforce Portal | 5 | 1 | 2 | 4 | 5 | 45
PRJ010 | Workforce Enablement | 1 | 5 | 2 | 3 | 3 | 42
PRJ012 | Analytics Platform | 2 | 3 | 2 | 5 | 4 | 42
PRJ007 | CRM Upgrade | 2 | 3 | 4 | 3 | 5 | 42
PRJ015 | Service Desk | 1 | 1 | 5 | 5 | 3 | 40
PRJ004 | AI Assistant | 3 | 1 | 3 | 3 | 3 | 38
PRJ029 | Analytics Platform 2 | 2 | 2 | 1 | 5 | 2 | 37
PRJ014 | Identity Mgmt | 1 | 5 | 2 | 2 | 4 | 37
PRJ002 | Cloud Migration | 3 | 2 | 2 | 3 | 4 | 37
PRJ030 | Service Desk 2 | 3 | 1 | 2 | 3 | 2 | 36
PRJ008 | Mobile App | 1 | 4 | 2 | 3 | 4 | 35
PRJ025 | Customer Insights | 3 | 2 | 2 | 1 | 2 | 35
PRJ022 | DevOps Tools | 1 | 2 | 4 | 4 | 5 | 34
PRJ035 | Payroll Cloud | 1 | 3 | 2 | 3 | 2 | 34
PRJ019 | Vendor Mgmt | 1 | 4 | 1 | 4 | 4 | 34
PRJ021 | Data Warehouse | 3 | 2 | 3 | 1 | 5 | 33
PRJ032 | Compliance Hub | 1 | 1 | 3 | 5 | 3 | 32
PRJ013 | API Gateway | 1 | 1 | 2 | 5 | 1 | 32
PRJ001 | Customer Portal | 1 | 1 | 4 | 4 | 5 | 29
PRJ031 | Quality Mgmt | 3 | 1 | 2 | 2 | 5 | 27
PRJ017 | App Modernisation | 1 | 2 | 2 | 4 | 5 | 26
PRJ006 | Cyber Security Program | 2 | 1 | 1 | 1 | 3 | 18

## Config
Category | Value | Display Order | Active
Status | Active | 1 | TRUE
Status | Active | 2 | TRUE
Status | Active | 3 | TRUE
Status | Completed | 4 | TRUE
Status | Pipeline | 5 | TRUE
Status | On Hold | 6 | TRUE
Status | Cancelled | 7 | TRUE
RAG | Green | 1 | TRUE
RAG | Amber | 2 | TRUE
RAG | Red | 3 | TRUE
Priority | P1 - Critical | 1 | TRUE
Priority | P2 - High | 2 | TRUE
Priority | P3 - Medium | 3 | TRUE
Priority | P4 - Low | 4 | TRUE
Investment Type | Run | 1 | TRUE
Investment Type | Grow | 2 | TRUE
Investment Type | Transform | 3 | TRUE
Delivery Method | Waterfall | 1 | TRUE
Delivery Method | Agile | 2 | TRUE
Delivery Method | Hybrid | 3 | TRUE
Funding Type | CAPEX | 1 | TRUE
Funding Type | OPEX | 2 | TRUE
Funding Type | Mixed | 3 | TRUE
Funding Type | Unfunded | 4 | TRUE
Portfolio Category | Business Strategic | 1 | TRUE
Portfolio Category | IT Strategic | 2 | TRUE
Portfolio Category | CAPEX | 3 | TRUE
Portfolio Category | Unfunded | 4 | TRUE
Governance Channel | Channel A (<$200K) | 1 | TRUE
Governance Channel | Channel B (>$200K) | 2 | TRUE
Program | Digital Transformation | 1 | TRUE
Program | Cyber Security | 2 | TRUE
Program | Cloud Migration | 3 | TRUE
Program | Data & AI | 4 | TRUE
Program | Customer Experience | 5 | TRUE
Theme | Infrastructure | 1 | TRUE
Theme | Digital & Applications | 2 | TRUE
Theme | Data & Analytics | 3 | TRUE
Theme | Cyber Security | 4 | TRUE
Theme | Business Transformation | 5 | TRUE
Business Unit | Retail | 1 | TRUE
Business Unit | Wholesale | 2 | TRUE
Business Unit | Operations | 3 | TRUE
Business Unit | Technology | 4 | TRUE
Business Unit | Finance | 5 | TRUE
Business Unit | HR | 6 | TRUE
Business Unit | Marketing | 7 | TRUE
Sponsor | CIO | 1 | TRUE
Sponsor | CFO | 2 | TRUE
Sponsor | COO | 3 | TRUE
Sponsor | CMO | 4 | TRUE
Sponsor | CTO | 5 | TRUE
Financial Year | FY25 | 1 | TRUE
Financial Year | FY25-26 | 2 | TRUE
Financial Year | FY26 | 3 | TRUE
Financial Year | FY26-27 | 4 | TRUE
Financial Year | FY27 | 5 | TRUE
Financial Year | FY27-28 | 6 | TRUE
Financial Year | FY28 | 7 | TRUE
Financial Year | FY28-29 | 8 | TRUE
Financial Year | FY29 | 9 | TRUE
Financial Year | FY29-30 | 10 | TRUE
Financial Year | FY30 | 11 | TRUE
Stage (Channel A) | Discovery | 1 | TRUE
Stage (Channel A) | Business Case / Full Funding | 2 | TRUE
Stage (Channel A) | Design | 3 | TRUE
Stage (Channel A) | Build | 4 | TRUE
Stage (Channel A) | Testing | 5 | TRUE
Stage (Channel A) | Deployment | 6 | TRUE
Stage (Channel A) | Handover | 7 | TRUE
Stage (Channel B) | Discovery | 1 | TRUE
Stage (Channel B) | Business Case / Seed Funding | 2 | TRUE
Stage (Channel B) | Design | 3 | TRUE
Stage (Channel B) | Business Case / Full Funding | 4 | TRUE
Stage (Channel B) | Build | 5 | TRUE
Stage (Channel B) | Testing | 6 | TRUE
Stage (Channel B) | Deployment | 7 | TRUE
Stage (Channel B) | Handover | 8 | TRUE
Gate Status | Not Started | 1 | TRUE
Gate Status | In Progress | 2 | TRUE
Gate Status | Pending Approval | 3 | TRUE
Gate Status | Approved | 4 | TRUE
Gate Status | Rejected | 5 | TRUE
Gate Status | Complete | 6 | TRUE
Gate Status | On Hold | 7 | TRUE
Gate Outcome |  | 1 | TRUE
Gate Outcome | Proceed | 2 | TRUE
Gate Outcome | Conditional | 3 | TRUE
Gate Outcome | Rework | 4 | TRUE
Gate Outcome | Held | 5 | TRUE
Decision Status | Open | 1 | TRUE
Decision Status | In Review | 2 | TRUE
Decision Status | Approved | 3 | TRUE
Decision Status | Rejected | 4 | TRUE
Decision Status | Closed | 5 | TRUE
Decision Type | Project | 1 | TRUE
Decision Type | Program | 2 | TRUE
Decision Type | Portfolio | 3 | TRUE
Decision Type | Funding | 4 | TRUE
Decision Type | SteerCo | 5 | TRUE
Decision Type | Architecture | 6 | TRUE
Decision Type | Risk | 7 | TRUE
Decision Type | General | 8 | TRUE
Action Status | Open | 1 | TRUE
Action Status | In Progress | 2 | TRUE
Action Status | Complete | 3 | TRUE
Action Status | Overdue | 4 | TRUE
Risk Probability | Low | 1 | TRUE
Risk Probability | Medium | 2 | TRUE
Risk Probability | High | 3 | TRUE
Risk Impact | Low | 1 | TRUE
Risk Impact | Medium | 2 | TRUE
Risk Impact | High | 3 | TRUE
Risk Impact | Critical | 4 | TRUE
Risk Status | Open | 1 | TRUE
Risk Status | Mitigated | 2 | TRUE
Risk Status | Closed | 3 | TRUE
RAID Type | Risk | 1 | TRUE
RAID Type | Issue | 2 | TRUE
RAID Type | Assumption | 3 | TRUE
RAID Type | Dependency | 4 | TRUE
Benefit Status | Planned | 1 | TRUE
Benefit Status | In Progress | 2 | TRUE
Benefit Status | Realised | 3 | TRUE
Benefit Status | At Risk | 4 | TRUE
Benefit Category | Cost Savings | 1 | TRUE
Benefit Category | Revenue Uplift | 2 | TRUE
Benefit Category | Productivity | 3 | TRUE
Benefit Category | Risk Avoidance | 4 | TRUE
Benefit Category | Compliance | 5 | TRUE
Benefit Type | Recurring | 1 | TRUE
Benefit Type | One-Off | 2 | TRUE
Dependency Type | Finish-Start | 1 | TRUE
Dependency Type | Start-Start | 2 | TRUE
Dependency Type | Blocks | 3 | TRUE
Dependency Type | Shared Resource | 4 | TRUE
Dependency Status | Healthy | 1 | TRUE
Dependency Status | At Risk | 2 | TRUE
Dependency Status | Blocked | 3 | TRUE
Skill | PM | 1 | TRUE
Skill | BA | 2 | TRUE
Skill | Dev | 3 | TRUE
Skill | QA | 4 | TRUE
Skill | DevOps | 5 | TRUE
Skill | Data | 6 | TRUE
Skill | Security | 7 | TRUE
Skill | UX | 8 | TRUE
Skill | Architect | 9 | TRUE
Resource Role | Project Manager | 1 | TRUE
Resource Role | Developer | 2 | TRUE
Resource Role | Tester | 3 | TRUE
Resource Role | Analyst | 4 | TRUE
Resource Role | Architect | 5 | TRUE
Milestone | Discovery | 1 | TRUE
Milestone | Business Case / Seed Funding | 2 | TRUE
Milestone | Design | 3 | TRUE
Milestone | Business Case / Full Funding | 4 | TRUE
Milestone | Build | 5 | TRUE
Milestone | Testing | 6 | TRUE
Milestone | Deployment | 7 | TRUE
Milestone | Handover | 8 | TRUE
Pipeline Decision | New | 1 | TRUE
Pipeline Decision | Under Review | 2 | TRUE
Pipeline Decision | Approved | 3 | TRUE
Pipeline Decision | Rejected | 4 | TRUE
Pipeline Decision | Parked | 5 | TRUE

## ConfigRules
Key | Value | Type | Description
GOV_CHANNEL_THRESHOLD | 200000 | currency | Approved $ at/below which a project is Channel A
SCHEDULE_AMBER_VARIANCE | -0.05 | ratio | Schedule variance worse than this → Amber
SCHEDULE_RED_VARIANCE | -0.1 | ratio | Schedule variance worse than this → Red
FINANCIAL_AMBER_VARIANCE | 0.05 | ratio | (Forecast-Approved)/Approved above → Amber
FINANCIAL_RED_VARIANCE | 0.1 | ratio | (Forecast-Approved)/Approved above → Red
BENEFIT_GREEN_THRESHOLD | 0.7 | ratio | Benefit realisation ≥ → Green
BENEFIT_AMBER_THRESHOLD | 0.3 | ratio | Benefit realisation ≥ → Amber (else Red)
DELIVERY_AMBER_DAYS_LATE | 1 | int | Stage gate days late ≥ → Amber
DELIVERY_RED_DAYS_LATE | 15 | int | Stage gate days late ≥ → Red
UPCOMING_GATE_WINDOW_DAYS | 30 | int | Window for 'upcoming stage gates' KPI
PRIORITY_SCORE_WEIGHT_STRAT | 0.3 | ratio | Prioritisation: strategic weight
PRIORITY_SCORE_WEIGHT_BENEFIT | 0.25 | ratio | Prioritisation: benefit weight
PRIORITY_SCORE_WEIGHT_RISK | 0.2 | ratio | Prioritisation: risk-reduction weight
PRIORITY_SCORE_WEIGHT_COMPL | 0.15 | ratio | Prioritisation: compliance weight
PRIORITY_SCORE_WEIGHT_CPLX | 0.1 | ratio | Prioritisation: complexity penalty
CURRENCY_SYMBOL | $ | text | Symbol shown in KPI cards

## Sprints
Sprint ID | Project ID | Project Name | Sprint # | Sprint Name | Start Date | End Date | Points Committed | Points Completed | Stories Committed | Stories Completed | Status | Team
SP0001 | PRJ001 | Customer Portal | 1 | PRJ001 Sprint 1 | 2025-02-14 | 2026-03-13 | 37 | 39 | 7 | 7 | Complete | Alex Brown
SP0002 | PRJ001 | Customer Portal | 2 | PRJ001 Sprint 2 | 2025-02-14 | 2026-03-13 | 37 | 30 | 7 | 6 | Complete | Alex Brown
SP0003 | PRJ001 | Customer Portal | 3 | PRJ001 Sprint 3 | 2025-02-14 | 2026-03-13 | 38 | 41 | 7 | 8 | Complete | Alex Brown
SP0004 | PRJ001 | Customer Portal | 4 | PRJ001 Sprint 4 | 2025-02-14 | 2026-03-13 | 37 | 34 | 7 | 6 | Complete | Alex Brown
SP0005 | PRJ001 | Customer Portal | 5 | PRJ001 Sprint 5 | 2025-02-14 | 2026-03-13 | 32 | 29 | 6 | 5 | Complete | Alex Brown
SP0006 | PRJ001 | Customer Portal | 6 | PRJ001 Sprint 6 | 2025-02-14 | 2026-03-13 | 37 | 30 | 7 | 6 | Complete | Alex Brown
SP0007 | PRJ001 | Customer Portal | 7 | PRJ001 Sprint 7 | 2025-02-14 | 2026-03-13 | 44 | 38 | 8 | 7 | Complete | Alex Brown
SP0008 | PRJ001 | Customer Portal | 8 | PRJ001 Sprint 8 | 2025-02-14 | 2026-03-13 | 34 | 26 | 6 | 5 | Complete | Alex Brown
SP0009 | PRJ002 | Cloud Migration | 1 | PRJ002 Sprint 1 | 2025-03-21 | 2025-10-07 | 32 | 27 | 6 | 5 | Complete | Carlos Diaz
SP0010 | PRJ002 | Cloud Migration | 2 | PRJ002 Sprint 2 | 2025-03-21 | 2025-10-07 | 33 | 33 | 6 | 6 | Complete | Carlos Diaz
SP0011 | PRJ002 | Cloud Migration | 3 | PRJ002 Sprint 3 | 2025-03-21 | 2025-10-07 | 22 | 26 | 4 | 5 | Complete | Carlos Diaz
SP0012 | PRJ002 | Cloud Migration | 4 | PRJ002 Sprint 4 | 2025-03-21 | 2025-10-07 | 23 | 11 | 4 | 2 | Complete | Carlos Diaz
SP0013 | PRJ002 | Cloud Migration | 5 | PRJ002 Sprint 5 | 2025-03-21 | 2025-10-07 | 22 | 22 | 4 | 4 | Complete | Carlos Diaz
SP0014 | PRJ002 | Cloud Migration | 6 | PRJ002 Sprint 6 | 2025-03-21 | 2025-10-07 | 31 | 19 | 6 | 3 | Complete | Carlos Diaz
SP0015 | PRJ002 | Cloud Migration | 7 | PRJ002 Sprint 7 | 2025-03-21 | 2025-10-07 | 22 | 10 | 4 | 2 | Complete | Carlos Diaz
SP0016 | PRJ002 | Cloud Migration | 8 | PRJ002 Sprint 8 | 2025-03-21 | 2025-10-07 | 20 | 12 | 4 | 2 | Complete | Carlos Diaz
SP0017 | PRJ003 | Data Platform | 1 | PRJ003 Sprint 1 | 2025-04-09 | 2026-07-03 | 26 | 22 | 5 | 4 | Complete | Carlos Diaz
SP0018 | PRJ003 | Data Platform | 2 | PRJ003 Sprint 2 | 2025-04-09 | 2026-07-03 | 28 | 16 | 5 | 3 | Complete | Carlos Diaz
SP0019 | PRJ003 | Data Platform | 3 | PRJ003 Sprint 3 | 2025-04-09 | 2026-07-03 | 24 | 15 | 4 | 3 | Complete | Carlos Diaz
SP0020 | PRJ003 | Data Platform | 4 | PRJ003 Sprint 4 | 2025-04-09 | 2026-07-03 | 41 | 39 | 8 | 7 | Complete | Carlos Diaz
SP0021 | PRJ003 | Data Platform | 5 | PRJ003 Sprint 5 | 2025-04-09 | 2026-07-03 | 26 | 20 | 5 | 4 | Complete | Carlos Diaz
SP0022 | PRJ003 | Data Platform | 6 | PRJ003 Sprint 6 | 2025-04-09 | 2026-07-03 | 28 | 31 | 5 | 6 | Complete | Carlos Diaz
SP0023 | PRJ003 | Data Platform | 7 | PRJ003 Sprint 7 | 2025-04-09 | 2026-07-03 | 42 | 44 | 8 | 8 | Complete | Carlos Diaz
SP0024 | PRJ003 | Data Platform | 8 | PRJ003 Sprint 8 | 2025-04-09 | 2026-07-03 | 29 | 26 | 5 | 5 | Complete | Carlos Diaz
SP0025 | PRJ005 | Network Refresh | 1 | PRJ005 Sprint 1 | 2025-07-22 | 2027-01-15 | 42 | 34 | 8 | 6 | Complete | Priya Patel
SP0026 | PRJ005 | Network Refresh | 2 | PRJ005 Sprint 2 | 2025-07-22 | 2027-01-15 | 34 | 23 | 6 | 4 | Complete | Priya Patel
SP0027 | PRJ005 | Network Refresh | 3 | PRJ005 Sprint 3 | 2025-07-22 | 2027-01-15 | 44 | 40 | 8 | 8 | Complete | Priya Patel
SP0028 | PRJ005 | Network Refresh | 4 | PRJ005 Sprint 4 | 2025-07-22 | 2027-01-15 | 44 | 35 | 8 | 7 | Complete | Priya Patel
SP0029 | PRJ005 | Network Refresh | 5 | PRJ005 Sprint 5 | 2025-07-22 | 2027-01-15 | 27 | 16 | 5 | 3 | Complete | Priya Patel
SP0030 | PRJ005 | Network Refresh | 6 | PRJ005 Sprint 6 | 2025-07-22 | 2027-01-15 | 30 | 35 | 6 | 7 | Complete | Priya Patel
SP0031 | PRJ005 | Network Refresh | 7 | PRJ005 Sprint 7 | 2025-07-22 | 2027-01-15 | 36 | 27 | 7 | 5 | Complete | Priya Patel
SP0032 | PRJ005 | Network Refresh | 8 | PRJ005 Sprint 8 | 2025-07-22 | 2027-01-15 | 43 | 44 | 8 | 8 | Complete | Priya Patel
SP0033 | PRJ008 | Mobile App | 1 | PRJ008 Sprint 1 | 2025-05-03 | 2025-08-30 | 21 | 16 | 4 | 3 | Complete | Carlos Diaz
SP0034 | PRJ008 | Mobile App | 2 | PRJ008 Sprint 2 | 2025-05-03 | 2025-08-30 | 21 | 16 | 4 | 3 | Complete | Carlos Diaz
SP0035 | PRJ008 | Mobile App | 3 | PRJ008 Sprint 3 | 2025-05-03 | 2025-08-30 | 34 | 34 | 6 | 6 | Complete | Carlos Diaz
SP0036 | PRJ008 | Mobile App | 4 | PRJ008 Sprint 4 | 2025-05-03 | 2025-08-30 | 25 | 24 | 5 | 4 | Complete | Carlos Diaz
SP0037 | PRJ008 | Mobile App | 5 | PRJ008 Sprint 5 | 2025-05-03 | 2025-08-30 | 30 | 25 | 6 | 5 | Complete | Carlos Diaz
SP0038 | PRJ008 | Mobile App | 6 | PRJ008 Sprint 6 | 2025-05-03 | 2025-08-30 | 33 | 24 | 6 | 4 | Complete | Carlos Diaz
SP0039 | PRJ008 | Mobile App | 7 | PRJ008 Sprint 7 | 2025-05-03 | 2025-08-30 | 36 | 29 | 7 | 5 | Complete | Carlos Diaz
SP0040 | PRJ008 | Mobile App | 8 | PRJ008 Sprint 8 | 2025-05-03 | 2025-08-30 | 24 | 19 | 4 | 3 | Complete | Carlos Diaz
SP0041 | PRJ009 | ERP Modernisation | 1 | PRJ009 Sprint 1 | 2026-01-01 | 2026-09-07 | 29 | 28 | 5 | 5 | Complete | Jane Doe
SP0042 | PRJ009 | ERP Modernisation | 2 | PRJ009 Sprint 2 | 2026-01-01 | 2026-09-07 | 22 | 20 | 4 | 4 | Complete | Jane Doe
SP0043 | PRJ009 | ERP Modernisation | 3 | PRJ009 Sprint 3 | 2026-01-01 | 2026-09-07 | 23 | 22 | 4 | 4 | Complete | Jane Doe
SP0044 | PRJ009 | ERP Modernisation | 4 | PRJ009 Sprint 4 | 2026-01-01 | 2026-09-07 | 22 | 11 | 4 | 2 | Complete | Jane Doe
SP0045 | PRJ009 | ERP Modernisation | 5 | PRJ009 Sprint 5 | 2026-01-01 | 2026-09-07 | 24 | 17 | 4 | 3 | Complete | Jane Doe
SP0046 | PRJ009 | ERP Modernisation | 6 | PRJ009 Sprint 6 | 2026-01-01 | 2026-09-07 | 33 | 37 | 6 | 7 | Complete | Jane Doe
SP0047 | PRJ009 | ERP Modernisation | 7 | PRJ009 Sprint 7 | 2026-01-01 | 2026-09-07 | 30 | 23 | 6 | 4 | Complete | Jane Doe
SP0048 | PRJ009 | ERP Modernisation | 8 | PRJ009 Sprint 8 | 2026-01-01 | 2026-09-07 | 33 | 25 | 6 | 5 | Complete | Jane Doe
SP0049 | PRJ010 | Workforce Enablement | 1 | PRJ010 Sprint 1 | 2025-02-06 | 2026-01-25 | 54 | 51 | 10 | 10 | Complete | Priya Patel
SP0050 | PRJ010 | Workforce Enablement | 2 | PRJ010 Sprint 2 | 2025-02-06 | 2026-01-25 | 56 | 47 | 11 | 9 | Complete | Priya Patel
SP0051 | PRJ010 | Workforce Enablement | 3 | PRJ010 Sprint 3 | 2025-02-06 | 2026-01-25 | 53 | 56 | 10 | 11 | Complete | Priya Patel
SP0052 | PRJ010 | Workforce Enablement | 4 | PRJ010 Sprint 4 | 2025-02-06 | 2026-01-25 | 56 | 52 | 11 | 10 | Complete | Priya Patel
SP0053 | PRJ010 | Workforce Enablement | 5 | PRJ010 Sprint 5 | 2025-02-06 | 2026-01-25 | 47 | 35 | 9 | 7 | Complete | Priya Patel
SP0054 | PRJ010 | Workforce Enablement | 6 | PRJ010 Sprint 6 | 2025-02-06 | 2026-01-25 | 49 | 41 | 9 | 8 | Complete | Priya Patel
SP0055 | PRJ010 | Workforce Enablement | 7 | PRJ010 Sprint 7 | 2025-02-06 | 2026-01-25 | 55 | 47 | 11 | 9 | Complete | Priya Patel
SP0056 | PRJ010 | Workforce Enablement | 8 | PRJ010 Sprint 8 | 2025-02-06 | 2026-01-25 | 57 | 59 | 11 | 11 | Complete | Priya Patel
SP0057 | PRJ011 | IoT Initiative | 1 | PRJ011 Sprint 1 | 2025-11-27 | 2026-04-16 | 55 | 45 | 11 | 9 | Complete | Jane Doe
SP0058 | PRJ011 | IoT Initiative | 2 | PRJ011 Sprint 2 | 2025-11-27 | 2026-04-16 | 43 | 44 | 8 | 8 | Complete | Jane Doe
SP0059 | PRJ011 | IoT Initiative | 3 | PRJ011 Sprint 3 | 2025-11-27 | 2026-04-16 | 48 | 40 | 9 | 8 | Complete | Jane Doe
SP0060 | PRJ011 | IoT Initiative | 4 | PRJ011 Sprint 4 | 2025-11-27 | 2026-04-16 | 42 | 40 | 8 | 8 | Complete | Jane Doe
SP0061 | PRJ011 | IoT Initiative | 5 | PRJ011 Sprint 5 | 2025-11-27 | 2026-04-16 | 44 | 37 | 8 | 7 | Complete | Jane Doe
SP0062 | PRJ011 | IoT Initiative | 6 | PRJ011 Sprint 6 | 2025-11-27 | 2026-04-16 | 52 | 51 | 10 | 10 | Complete | Jane Doe
SP0063 | PRJ011 | IoT Initiative | 7 | PRJ011 Sprint 7 | 2025-11-27 | 2026-04-16 | 50 | 53 | 10 | 10 | Complete | Jane Doe
SP0064 | PRJ011 | IoT Initiative | 8 | PRJ011 Sprint 8 | 2025-11-27 | 2026-04-16 | 53 | 56 | 10 | 11 | Complete | Jane Doe
SP0065 | PRJ013 | API Gateway | 1 | PRJ013 Sprint 1 | 2025-12-05 | 2027-03-07 | 52 | 50 | 10 | 10 | Complete | Priya Patel
SP0066 | PRJ013 | API Gateway | 2 | PRJ013 Sprint 2 | 2025-12-05 | 2027-03-07 | 43 | 38 | 8 | 7 | Complete | Priya Patel
SP0067 | PRJ013 | API Gateway | 3 | PRJ013 Sprint 3 | 2025-12-05 | 2027-03-07 | 51 | 52 | 10 | 10 | Complete | Priya Patel
SP0068 | PRJ013 | API Gateway | 4 | PRJ013 Sprint 4 | 2025-12-05 | 2027-03-07 | 56 | 59 | 11 | 11 | Complete | Priya Patel
SP0069 | PRJ013 | API Gateway | 5 | PRJ013 Sprint 5 | 2025-12-05 | 2027-03-07 | 56 | 61 | 11 | 12 | Complete | Priya Patel
SP0070 | PRJ013 | API Gateway | 6 | PRJ013 Sprint 6 | 2025-12-05 | 2027-03-07 | 54 | 59 | 10 | 11 | Complete | Priya Patel
SP0071 | PRJ013 | API Gateway | 7 | PRJ013 Sprint 7 | 2025-12-05 | 2027-03-07 | 56 | 51 | 11 | 10 | Complete | Priya Patel
SP0072 | PRJ013 | API Gateway | 8 | PRJ013 Sprint 8 | 2025-12-05 | 2027-03-07 | 51 | 41 | 10 | 8 | Complete | Priya Patel
SP0073 | PRJ014 | Identity Mgmt | 1 | PRJ014 Sprint 1 | 2025-02-05 | 2026-03-06 | 48 | 52 | 9 | 10 | Complete | Alex Brown
SP0074 | PRJ014 | Identity Mgmt | 2 | PRJ014 Sprint 2 | 2025-02-05 | 2026-03-06 | 53 | 48 | 10 | 9 | Complete | Alex Brown
SP0075 | PRJ014 | Identity Mgmt | 3 | PRJ014 Sprint 3 | 2025-02-05 | 2026-03-06 | 37 | 32 | 7 | 6 | Complete | Alex Brown
SP0076 | PRJ014 | Identity Mgmt | 4 | PRJ014 Sprint 4 | 2025-02-05 | 2026-03-06 | 46 | 34 | 9 | 6 | Complete | Alex Brown
SP0077 | PRJ014 | Identity Mgmt | 5 | PRJ014 Sprint 5 | 2025-02-05 | 2026-03-06 | 41 | 29 | 8 | 5 | Complete | Alex Brown
SP0078 | PRJ014 | Identity Mgmt | 6 | PRJ014 Sprint 6 | 2025-02-05 | 2026-03-06 | 46 | 51 | 9 | 10 | Complete | Alex Brown
SP0079 | PRJ014 | Identity Mgmt | 7 | PRJ014 Sprint 7 | 2025-02-05 | 2026-03-06 | 50 | 42 | 10 | 8 | Complete | Alex Brown
SP0080 | PRJ014 | Identity Mgmt | 8 | PRJ014 Sprint 8 | 2025-02-05 | 2026-03-06 | 38 | 27 | 7 | 5 | Complete | Alex Brown
SP0081 | PRJ015 | Service Desk | 1 | PRJ015 Sprint 1 | 2025-06-03 | 2026-04-23 | 57 | 56 | 11 | 11 | Complete | John Smith
SP0082 | PRJ015 | Service Desk | 2 | PRJ015 Sprint 2 | 2025-06-03 | 2026-04-23 | 50 | 47 | 10 | 9 | Complete | John Smith
SP0083 | PRJ015 | Service Desk | 3 | PRJ015 Sprint 3 | 2025-06-03 | 2026-04-23 | 60 | 52 | 12 | 10 | Complete | John Smith
SP0084 | PRJ015 | Service Desk | 4 | PRJ015 Sprint 4 | 2025-06-03 | 2026-04-23 | 63 | 64 | 12 | 12 | Complete | John Smith
SP0085 | PRJ015 | Service Desk | 5 | PRJ015 Sprint 5 | 2025-06-03 | 2026-04-23 | 53 | 47 | 10 | 9 | Complete | John Smith
SP0086 | PRJ015 | Service Desk | 6 | PRJ015 Sprint 6 | 2025-06-03 | 2026-04-23 | 53 | 42 | 10 | 8 | Complete | John Smith
SP0087 | PRJ015 | Service Desk | 7 | PRJ015 Sprint 7 | 2025-06-03 | 2026-04-23 | 50 | 41 | 10 | 8 | Complete | John Smith
SP0088 | PRJ015 | Service Desk | 8 | PRJ015 Sprint 8 | 2025-06-03 | 2026-04-23 | 50 | 50 | 10 | 10 | Complete | John Smith
SP0089 | PRJ016 | Infrastructure Upg | 1 | PRJ016 Sprint 1 | 2025-12-01 | 2026-11-26 | 40 | 41 | 8 | 8 | Complete | John Smith
SP0090 | PRJ016 | Infrastructure Upg | 2 | PRJ016 Sprint 2 | 2025-12-01 | 2026-11-26 | 51 | 40 | 10 | 8 | Complete | John Smith
SP0091 | PRJ016 | Infrastructure Upg | 3 | PRJ016 Sprint 3 | 2025-12-01 | 2026-11-26 | 43 | 33 | 8 | 6 | Complete | John Smith
SP0092 | PRJ016 | Infrastructure Upg | 4 | PRJ016 Sprint 4 | 2025-12-01 | 2026-11-26 | 55 | 48 | 11 | 9 | Complete | John Smith
SP0093 | PRJ016 | Infrastructure Upg | 5 | PRJ016 Sprint 5 | 2025-12-01 | 2026-11-26 | 40 | 32 | 8 | 6 | Complete | John Smith
SP0094 | PRJ016 | Infrastructure Upg | 6 | PRJ016 Sprint 6 | 2025-12-01 | 2026-11-26 | 51 | 43 | 10 | 8 | Complete | John Smith
SP0095 | PRJ016 | Infrastructure Upg | 7 | PRJ016 Sprint 7 | 2025-12-01 | 2026-11-26 | 42 | 37 | 8 | 7 | Complete | John Smith
SP0096 | PRJ016 | Infrastructure Upg | 8 | PRJ016 Sprint 8 | 2025-12-01 | 2026-11-26 | 42 | 30 | 8 | 6 | Complete | John Smith
SP0097 | PRJ017 | App Modernisation | 1 | PRJ017 Sprint 1 | 2025-02-17 | 2026-04-07 | 48 | 40 | 9 | 8 | Complete | Priya Patel
SP0098 | PRJ017 | App Modernisation | 2 | PRJ017 Sprint 2 | 2025-02-17 | 2026-04-07 | 40 | 43 | 8 | 8 | Complete | Priya Patel
SP0099 | PRJ017 | App Modernisation | 3 | PRJ017 Sprint 3 | 2025-02-17 | 2026-04-07 | 39 | 43 | 7 | 8 | Complete | Priya Patel
SP0100 | PRJ017 | App Modernisation | 4 | PRJ017 Sprint 4 | 2025-02-17 | 2026-04-07 | 44 | 47 | 8 | 9 | Complete | Priya Patel
SP0101 | PRJ017 | App Modernisation | 5 | PRJ017 Sprint 5 | 2025-02-17 | 2026-04-07 | 48 | 46 | 9 | 9 | Complete | Priya Patel
SP0102 | PRJ017 | App Modernisation | 6 | PRJ017 Sprint 6 | 2025-02-17 | 2026-04-07 | 49 | 37 | 9 | 7 | Complete | Priya Patel
SP0103 | PRJ017 | App Modernisation | 7 | PRJ017 Sprint 7 | 2025-02-17 | 2026-04-07 | 44 | 35 | 8 | 7 | Complete | Priya Patel
SP0104 | PRJ017 | App Modernisation | 8 | PRJ017 Sprint 8 | 2025-02-17 | 2026-04-07 | 39 | 28 | 7 | 5 | Complete | Priya Patel
SP0105 | PRJ020 | Process Automation | 1 | PRJ020 Sprint 1 | 2025-04-25 | 2025-08-05 | 46 | 39 | 9 | 7 | Complete | Carlos Diaz
SP0106 | PRJ020 | Process Automation | 2 | PRJ020 Sprint 2 | 2025-04-25 | 2025-08-05 | 61 | 54 | 12 | 10 | Complete | Carlos Diaz
SP0107 | PRJ020 | Process Automation | 3 | PRJ020 Sprint 3 | 2025-04-25 | 2025-08-05 | 45 | 45 | 9 | 9 | Complete | Carlos Diaz
SP0108 | PRJ020 | Process Automation | 4 | PRJ020 Sprint 4 | 2025-04-25 | 2025-08-05 | 58 | 60 | 11 | 12 | Complete | Carlos Diaz
SP0109 | PRJ020 | Process Automation | 5 | PRJ020 Sprint 5 | 2025-04-25 | 2025-08-05 | 62 | 58 | 12 | 11 | Complete | Carlos Diaz
SP0110 | PRJ020 | Process Automation | 6 | PRJ020 Sprint 6 | 2025-04-25 | 2025-08-05 | 63 | 67 | 12 | 13 | Complete | Carlos Diaz
SP0111 | PRJ020 | Process Automation | 7 | PRJ020 Sprint 7 | 2025-04-25 | 2025-08-05 | 54 | 49 | 10 | 9 | Complete | Carlos Diaz
SP0112 | PRJ020 | Process Automation | 8 | PRJ020 Sprint 8 | 2025-04-25 | 2025-08-05 | 58 | 51 | 11 | 10 | Complete | Carlos Diaz
SP0113 | PRJ022 | DevOps Tools | 1 | PRJ022 Sprint 1 | 2025-04-11 | 2026-01-12 | 27 | 31 | 5 | 6 | Complete | Priya Patel
SP0114 | PRJ022 | DevOps Tools | 2 | PRJ022 Sprint 2 | 2025-04-11 | 2026-01-12 | 37 | 29 | 7 | 5 | Complete | Priya Patel
SP0115 | PRJ022 | DevOps Tools | 3 | PRJ022 Sprint 3 | 2025-04-11 | 2026-01-12 | 31 | 31 | 6 | 6 | Complete | Priya Patel
SP0116 | PRJ022 | DevOps Tools | 4 | PRJ022 Sprint 4 | 2025-04-11 | 2026-01-12 | 26 | 21 | 5 | 4 | Complete | Priya Patel
SP0117 | PRJ022 | DevOps Tools | 5 | PRJ022 Sprint 5 | 2025-04-11 | 2026-01-12 | 37 | 30 | 7 | 6 | Complete | Priya Patel
SP0118 | PRJ022 | DevOps Tools | 6 | PRJ022 Sprint 6 | 2025-04-11 | 2026-01-12 | 42 | 32 | 8 | 6 | Complete | Priya Patel
SP0119 | PRJ022 | DevOps Tools | 7 | PRJ022 Sprint 7 | 2025-04-11 | 2026-01-12 | 39 | 42 | 7 | 8 | Complete | Priya Patel
SP0120 | PRJ022 | DevOps Tools | 8 | PRJ022 Sprint 8 | 2025-04-11 | 2026-01-12 | 35 | 35 | 7 | 7 | Complete | Priya Patel
SP0121 | PRJ023 | Workforce Portal | 1 | PRJ023 Sprint 1 | 2025-11-12 | 2026-11-28 | 55 | 48 | 11 | 9 | Complete | Jane Doe
SP0122 | PRJ023 | Workforce Portal | 2 | PRJ023 Sprint 2 | 2025-11-12 | 2026-11-28 | 44 | 43 | 8 | 8 | Complete | Jane Doe
SP0123 | PRJ023 | Workforce Portal | 3 | PRJ023 Sprint 3 | 2025-11-12 | 2026-11-28 | 56 | 50 | 11 | 10 | Complete | Jane Doe
SP0124 | PRJ023 | Workforce Portal | 4 | PRJ023 Sprint 4 | 2025-11-12 | 2026-11-28 | 51 | 42 | 10 | 8 | Complete | Jane Doe
SP0125 | PRJ023 | Workforce Portal | 5 | PRJ023 Sprint 5 | 2025-11-12 | 2026-11-28 | 46 | 36 | 9 | 7 | Complete | Jane Doe
SP0126 | PRJ023 | Workforce Portal | 6 | PRJ023 Sprint 6 | 2025-11-12 | 2026-11-28 | 54 | 52 | 10 | 10 | Complete | Jane Doe
SP0127 | PRJ023 | Workforce Portal | 7 | PRJ023 Sprint 7 | 2025-11-12 | 2026-11-28 | 43 | 38 | 8 | 7 | Complete | Jane Doe
SP0128 | PRJ023 | Workforce Portal | 8 | PRJ023 Sprint 8 | 2025-11-12 | 2026-11-28 | 52 | 45 | 10 | 9 | Complete | Jane Doe
SP0129 | PRJ024 | Process Mining | 1 | PRJ024 Sprint 1 | 2025-12-06 | 2027-01-24 | 37 | 27 | 7 | 5 | Complete | Jane Doe
SP0130 | PRJ024 | Process Mining | 2 | PRJ024 Sprint 2 | 2025-12-06 | 2027-01-24 | 40 | 28 | 8 | 5 | Complete | Jane Doe
SP0131 | PRJ024 | Process Mining | 3 | PRJ024 Sprint 3 | 2025-12-06 | 2027-01-24 | 43 | 37 | 8 | 7 | Complete | Jane Doe
SP0132 | PRJ024 | Process Mining | 4 | PRJ024 Sprint 4 | 2025-12-06 | 2027-01-24 | 51 | 45 | 10 | 9 | Complete | Jane Doe
SP0133 | PRJ024 | Process Mining | 5 | PRJ024 Sprint 5 | 2025-12-06 | 2027-01-24 | 35 | 30 | 7 | 6 | Complete | Jane Doe
SP0134 | PRJ024 | Process Mining | 6 | PRJ024 Sprint 6 | 2025-12-06 | 2027-01-24 | 42 | 32 | 8 | 6 | Complete | Jane Doe
SP0135 | PRJ024 | Process Mining | 7 | PRJ024 Sprint 7 | 2025-12-06 | 2027-01-24 | 52 | 41 | 10 | 8 | Complete | Jane Doe
SP0136 | PRJ024 | Process Mining | 8 | PRJ024 Sprint 8 | 2025-12-06 | 2027-01-24 | 52 | 55 | 10 | 11 | Complete | Jane Doe
SP0137 | PRJ025 | Customer Insights | 1 | PRJ025 Sprint 1 | 2025-12-02 | 2027-02-17 | 19 | 17 | 3 | 3 | Complete | Sarah Lee
SP0138 | PRJ025 | Customer Insights | 2 | PRJ025 Sprint 2 | 2025-12-02 | 2027-02-17 | 20 | 17 | 4 | 3 | Complete | Sarah Lee
SP0139 | PRJ025 | Customer Insights | 3 | PRJ025 Sprint 3 | 2025-12-02 | 2027-02-17 | 18 | 17 | 3 | 3 | Complete | Sarah Lee
SP0140 | PRJ025 | Customer Insights | 4 | PRJ025 Sprint 4 | 2025-12-02 | 2027-02-17 | 27 | 27 | 5 | 5 | Complete | Sarah Lee
SP0141 | PRJ025 | Customer Insights | 5 | PRJ025 Sprint 5 | 2025-12-02 | 2027-02-17 | 34 | 28 | 6 | 5 | Complete | Sarah Lee
SP0142 | PRJ025 | Customer Insights | 6 | PRJ025 Sprint 6 | 2025-12-02 | 2027-02-17 | 28 | 28 | 5 | 5 | Complete | Sarah Lee
SP0143 | PRJ025 | Customer Insights | 7 | PRJ025 Sprint 7 | 2025-12-02 | 2027-02-17 | 29 | 21 | 5 | 4 | Complete | Sarah Lee
SP0144 | PRJ025 | Customer Insights | 8 | PRJ025 Sprint 8 | 2025-12-02 | 2027-02-17 | 21 | 19 | 4 | 3 | Complete | Sarah Lee
SP0145 | PRJ026 | ERP Modernisation 2 | 1 | PRJ026 Sprint 1 | 2025-09-16 | 2026-07-21 | 46 | 37 | 9 | 7 | Complete | Carlos Diaz
SP0146 | PRJ026 | ERP Modernisation 2 | 2 | PRJ026 Sprint 2 | 2025-09-16 | 2026-07-21 | 46 | 38 | 9 | 7 | Complete | Carlos Diaz
SP0147 | PRJ026 | ERP Modernisation 2 | 3 | PRJ026 Sprint 3 | 2025-09-16 | 2026-07-21 | 30 | 30 | 6 | 6 | Complete | Carlos Diaz
SP0148 | PRJ026 | ERP Modernisation 2 | 4 | PRJ026 Sprint 4 | 2025-09-16 | 2026-07-21 | 45 | 34 | 9 | 6 | Complete | Carlos Diaz
SP0149 | PRJ026 | ERP Modernisation 2 | 5 | PRJ026 Sprint 5 | 2025-09-16 | 2026-07-21 | 39 | 32 | 7 | 6 | Complete | Carlos Diaz
SP0150 | PRJ026 | ERP Modernisation 2 | 6 | PRJ026 Sprint 6 | 2025-09-16 | 2026-07-21 | 34 | 36 | 6 | 7 | Complete | Carlos Diaz
SP0151 | PRJ026 | ERP Modernisation 2 | 7 | PRJ026 Sprint 7 | 2025-09-16 | 2026-07-21 | 32 | 22 | 6 | 4 | Complete | Carlos Diaz
SP0152 | PRJ026 | ERP Modernisation 2 | 8 | PRJ026 Sprint 8 | 2025-09-16 | 2026-07-21 | 37 | 31 | 7 | 6 | Complete | Carlos Diaz
SP0153 | PRJ029 | Analytics Platform 2 | 1 | PRJ029 Sprint 1 | 2025-11-15 | 2026-11-13 | 46 | 39 | 9 | 7 | Complete | John Smith
SP0154 | PRJ029 | Analytics Platform 2 | 2 | PRJ029 Sprint 2 | 2025-11-15 | 2026-11-13 | 58 | 62 | 11 | 12 | Complete | John Smith
SP0155 | PRJ029 | Analytics Platform 2 | 3 | PRJ029 Sprint 3 | 2025-11-15 | 2026-11-13 | 58 | 56 | 11 | 11 | Complete | John Smith
SP0156 | PRJ029 | Analytics Platform 2 | 4 | PRJ029 Sprint 4 | 2025-11-15 | 2026-11-13 | 56 | 48 | 11 | 9 | Complete | John Smith
SP0157 | PRJ029 | Analytics Platform 2 | 5 | PRJ029 Sprint 5 | 2025-11-15 | 2026-11-13 | 52 | 49 | 10 | 9 | Complete | John Smith
SP0158 | PRJ029 | Analytics Platform 2 | 6 | PRJ029 Sprint 6 | 2025-11-15 | 2026-11-13 | 53 | 54 | 10 | 10 | Complete | John Smith
SP0159 | PRJ029 | Analytics Platform 2 | 7 | PRJ029 Sprint 7 | 2025-11-15 | 2026-11-13 | 43 | 43 | 8 | 8 | Complete | John Smith
SP0160 | PRJ029 | Analytics Platform 2 | 8 | PRJ029 Sprint 8 | 2025-11-15 | 2026-11-13 | 49 | 43 | 9 | 8 | Complete | John Smith
SP0161 | PRJ032 | Compliance Hub | 1 | PRJ032 Sprint 1 | 2025-12-20 | 2027-05-19 | 38 | 30 | 7 | 6 | Complete | Carlos Diaz
SP0162 | PRJ032 | Compliance Hub | 2 | PRJ032 Sprint 2 | 2025-12-20 | 2027-05-19 | 54 | 57 | 10 | 11 | Complete | Carlos Diaz
SP0163 | PRJ032 | Compliance Hub | 3 | PRJ032 Sprint 3 | 2025-12-20 | 2027-05-19 | 39 | 27 | 7 | 5 | Complete | Carlos Diaz
SP0164 | PRJ032 | Compliance Hub | 4 | PRJ032 Sprint 4 | 2025-12-20 | 2027-05-19 | 40 | 37 | 8 | 7 | Complete | Carlos Diaz
SP0165 | PRJ032 | Compliance Hub | 5 | PRJ032 Sprint 5 | 2025-12-20 | 2027-05-19 | 53 | 43 | 10 | 8 | Complete | Carlos Diaz
SP0166 | PRJ032 | Compliance Hub | 6 | PRJ032 Sprint 6 | 2025-12-20 | 2027-05-19 | 51 | 42 | 10 | 8 | Complete | Carlos Diaz
SP0167 | PRJ032 | Compliance Hub | 7 | PRJ032 Sprint 7 | 2025-12-20 | 2027-05-19 | 50 | 48 | 10 | 9 | Complete | Carlos Diaz
SP0168 | PRJ032 | Compliance Hub | 8 | PRJ032 Sprint 8 | 2025-12-20 | 2027-05-19 | 41 | 38 | 8 | 7 | Complete | Carlos Diaz
SP0169 | PRJ033 | Risk Platform | 1 | PRJ033 Sprint 1 | 2025-11-22 | 2027-05-22 | 24 | 20 | 4 | 4 | Complete | Priya Patel
SP0170 | PRJ033 | Risk Platform | 2 | PRJ033 Sprint 2 | 2025-11-22 | 2027-05-22 | 40 | 39 | 8 | 7 | Complete | Priya Patel
SP0171 | PRJ033 | Risk Platform | 3 | PRJ033 Sprint 3 | 2025-11-22 | 2027-05-22 | 33 | 23 | 6 | 4 | Complete | Priya Patel
SP0172 | PRJ033 | Risk Platform | 4 | PRJ033 Sprint 4 | 2025-11-22 | 2027-05-22 | 24 | 17 | 4 | 3 | Complete | Priya Patel
SP0173 | PRJ033 | Risk Platform | 5 | PRJ033 Sprint 5 | 2025-11-22 | 2027-05-22 | 36 | 32 | 7 | 6 | Complete | Priya Patel
SP0174 | PRJ033 | Risk Platform | 6 | PRJ033 Sprint 6 | 2025-11-22 | 2027-05-22 | 37 | 33 | 7 | 6 | Complete | Priya Patel
SP0175 | PRJ033 | Risk Platform | 7 | PRJ033 Sprint 7 | 2025-11-22 | 2027-05-22 | 36 | 28 | 7 | 5 | Complete | Priya Patel
SP0176 | PRJ033 | Risk Platform | 8 | PRJ033 Sprint 8 | 2025-11-22 | 2027-05-22 | 25 | 28 | 5 | 5 | Complete | Priya Patel
SP0177 | PRJ034 | Treasury Sys | 1 | PRJ034 Sprint 1 | 2025-11-09 | 2027-01-15 | 29 | 26 | 5 | 5 | Complete | Jane Doe
SP0178 | PRJ034 | Treasury Sys | 2 | PRJ034 Sprint 2 | 2025-11-09 | 2027-01-15 | 30 | 31 | 6 | 6 | Complete | Jane Doe
SP0179 | PRJ034 | Treasury Sys | 3 | PRJ034 Sprint 3 | 2025-11-09 | 2027-01-15 | 22 | 24 | 4 | 4 | Complete | Jane Doe
SP0180 | PRJ034 | Treasury Sys | 4 | PRJ034 Sprint 4 | 2025-11-09 | 2027-01-15 | 29 | 33 | 5 | 6 | Complete | Jane Doe
SP0181 | PRJ034 | Treasury Sys | 5 | PRJ034 Sprint 5 | 2025-11-09 | 2027-01-15 | 28 | 27 | 5 | 5 | Complete | Jane Doe
SP0182 | PRJ034 | Treasury Sys | 6 | PRJ034 Sprint 6 | 2025-11-09 | 2027-01-15 | 20 | 21 | 4 | 4 | Complete | Jane Doe
SP0183 | PRJ034 | Treasury Sys | 7 | PRJ034 Sprint 7 | 2025-11-09 | 2027-01-15 | 34 | 36 | 6 | 7 | Complete | Jane Doe
SP0184 | PRJ034 | Treasury Sys | 8 | PRJ034 Sprint 8 | 2025-11-09 | 2027-01-15 | 26 | 15 | 5 | 3 | Complete | Jane Doe
SP0185 | PRJ035 | Payroll Cloud | 1 | PRJ035 Sprint 1 | 2025-05-04 | 2026-07-21 | 37 | 32 | 7 | 6 | Complete | Jane Doe
SP0186 | PRJ035 | Payroll Cloud | 2 | PRJ035 Sprint 2 | 2025-05-04 | 2026-07-21 | 53 | 41 | 10 | 8 | Complete | Jane Doe
SP0187 | PRJ035 | Payroll Cloud | 3 | PRJ035 Sprint 3 | 2025-05-04 | 2026-07-21 | 40 | 31 | 8 | 6 | Complete | Jane Doe
SP0188 | PRJ035 | Payroll Cloud | 4 | PRJ035 Sprint 4 | 2025-05-04 | 2026-07-21 | 45 | 45 | 9 | 9 | Complete | Jane Doe
SP0189 | PRJ035 | Payroll Cloud | 5 | PRJ035 Sprint 5 | 2025-05-04 | 2026-07-21 | 41 | 41 | 8 | 8 | Complete | Jane Doe
SP0190 | PRJ035 | Payroll Cloud | 6 | PRJ035 Sprint 6 | 2025-05-04 | 2026-07-21 | 38 | 33 | 7 | 6 | Complete | Jane Doe
SP0191 | PRJ035 | Payroll Cloud | 7 | PRJ035 Sprint 7 | 2025-05-04 | 2026-07-21 | 48 | 50 | 9 | 10 | Complete | Jane Doe
SP0192 | PRJ035 | Payroll Cloud | 8 | PRJ035 Sprint 8 | 2025-05-04 | 2026-07-21 | 38 | 37 | 7 | 7 | Complete | Jane Doe
SP0193 | PRJ036 | HR Self-Service | 1 | PRJ036 Sprint 1 | 2025-05-09 | 2025-12-03 | 45 | 50 | 9 | 10 | Complete | Jane Doe
SP0194 | PRJ036 | HR Self-Service | 2 | PRJ036 Sprint 2 | 2025-05-09 | 2025-12-03 | 45 | 36 | 9 | 7 | Complete | Jane Doe
SP0195 | PRJ036 | HR Self-Service | 3 | PRJ036 Sprint 3 | 2025-05-09 | 2025-12-03 | 33 | 26 | 6 | 5 | Complete | Jane Doe
SP0196 | PRJ036 | HR Self-Service | 4 | PRJ036 Sprint 4 | 2025-05-09 | 2025-12-03 | 34 | 34 | 6 | 6 | Complete | Jane Doe
SP0197 | PRJ036 | HR Self-Service | 5 | PRJ036 Sprint 5 | 2025-05-09 | 2025-12-03 | 44 | 38 | 8 | 7 | Complete | Jane Doe
SP0198 | PRJ036 | HR Self-Service | 6 | PRJ036 Sprint 6 | 2025-05-09 | 2025-12-03 | 43 | 41 | 8 | 8 | Complete | Jane Doe
SP0199 | PRJ036 | HR Self-Service | 7 | PRJ036 Sprint 7 | 2025-05-09 | 2025-12-03 | 33 | 31 | 6 | 6 | Complete | Jane Doe
SP0200 | PRJ036 | HR Self-Service | 8 | PRJ036 Sprint 8 | 2025-05-09 | 2025-12-03 | 41 | 44 | 8 | 8 | Complete | Jane Doe
SP0201 | PRJ037 | SAP S/4HANA | 1 | PRJ037 Sprint 1 | 2025-03-06 | 2025-10-22 | 38 | 29 | 7 | 5 | Complete | John Smith
SP0202 | PRJ037 | SAP S/4HANA | 2 | PRJ037 Sprint 2 | 2025-03-06 | 2025-10-22 | 31 | 33 | 6 | 6 | Complete | John Smith
SP0203 | PRJ037 | SAP S/4HANA | 3 | PRJ037 Sprint 3 | 2025-03-06 | 2025-10-22 | 24 | 29 | 4 | 5 | Complete | John Smith
SP0204 | PRJ037 | SAP S/4HANA | 4 | PRJ037 Sprint 4 | 2025-03-06 | 2025-10-22 | 27 | 30 | 5 | 6 | Complete | John Smith
SP0205 | PRJ037 | SAP S/4HANA | 5 | PRJ037 Sprint 5 | 2025-03-06 | 2025-10-22 | 27 | 21 | 5 | 4 | Complete | John Smith
SP0206 | PRJ037 | SAP S/4HANA | 6 | PRJ037 Sprint 6 | 2025-03-06 | 2025-10-22 | 33 | 22 | 6 | 4 | Complete | John Smith
SP0207 | PRJ037 | SAP S/4HANA | 7 | PRJ037 Sprint 7 | 2025-03-06 | 2025-10-22 | 35 | 24 | 7 | 4 | Complete | John Smith
SP0208 | PRJ037 | SAP S/4HANA | 8 | PRJ037 Sprint 8 | 2025-03-06 | 2025-10-22 | 34 | 35 | 6 | 7 | Complete | John Smith
SP0209 | PRJ038 | Salesforce CRM | 1 | PRJ038 Sprint 1 | 2025-09-09 | 2026-01-14 | 38 | 27 | 7 | 5 | Complete | Jane Doe
SP0210 | PRJ038 | Salesforce CRM | 2 | PRJ038 Sprint 2 | 2025-09-09 | 2026-01-14 | 38 | 26 | 7 | 5 | Complete | Jane Doe
SP0211 | PRJ038 | Salesforce CRM | 3 | PRJ038 Sprint 3 | 2025-09-09 | 2026-01-14 | 45 | 41 | 9 | 8 | Complete | Jane Doe
SP0212 | PRJ038 | Salesforce CRM | 4 | PRJ038 Sprint 4 | 2025-09-09 | 2026-01-14 | 40 | 33 | 8 | 6 | Complete | Jane Doe
SP0213 | PRJ038 | Salesforce CRM | 5 | PRJ038 Sprint 5 | 2025-09-09 | 2026-01-14 | 34 | 26 | 6 | 5 | Complete | Jane Doe
SP0214 | PRJ038 | Salesforce CRM | 6 | PRJ038 Sprint 6 | 2025-09-09 | 2026-01-14 | 34 | 30 | 6 | 6 | Complete | Jane Doe
SP0215 | PRJ038 | Salesforce CRM | 7 | PRJ038 Sprint 7 | 2025-09-09 | 2026-01-14 | 44 | 34 | 8 | 6 | Complete | Jane Doe
SP0216 | PRJ038 | Salesforce CRM | 8 | PRJ038 Sprint 8 | 2025-09-09 | 2026-01-14 | 41 | 43 | 8 | 8 | Complete | Jane Doe
Formulas:
Start Date = IFERROR(VLOOKUP([Project ID],Projects!$A:$AK,16,FALSE()),"")
End Date = IFERROR(VLOOKUP([Project ID],Projects!$A:$AK,17,FALSE()),"")

## Releases
Release ID | Project ID | Project Name | Release Name | Version | Type | Planned Date | Actual Date | Status | Owner | Environment | Notes
REL0001 | PRJ001 | Customer Portal | Customer Portal R1 | 1.0.0 | Patch | 2025-05-03 | 2025-05-04 | Delivered | Alex Brown | Production
REL0002 | PRJ001 | Customer Portal | Customer Portal R2 | 2.0.0 | Major | 2025-07-20 | 2025-07-16 | Delivered | Alex Brown | UAT
REL0003 | PRJ001 | Customer Portal | Customer Portal R3 | 3.0.0 | Patch | 2025-10-07 | 2025-10-12 | Delivered | Alex Brown | Production
REL0004 | PRJ001 | Customer Portal | Customer Portal R4 | 4.0.0 | Patch | 2025-12-24 | 2025-12-25 | Delivered | Alex Brown | UAT
REL0005 | PRJ002 | Cloud Migration | Cloud Migration R1 | 1.0.0 | Minor | 2025-04-30 | 2025-05-10 | Delivered | Carlos Diaz | Staging
REL0006 | PRJ002 | Cloud Migration | Cloud Migration R2 | 2.0.0 | Patch | 2025-06-09 | 2025-06-17 | Delivered | Carlos Diaz | Staging
REL0007 | PRJ002 | Cloud Migration | Cloud Migration R3 | 3.0.0 | Major | 2025-07-19 | 2025-07-26 | Delivered | Carlos Diaz | Staging
REL0008 | PRJ002 | Cloud Migration | Cloud Migration R4 | 4.0.0 | Major | 2025-08-28 | 2025-08-29 | Delivered | Carlos Diaz | Staging
REL0009 | PRJ003 | Data Platform | Data Platform R1 | 1.0.0 | Patch | 2025-09-06 | 2025-09-11 | Delivered | Carlos Diaz | Production
REL0010 | PRJ003 | Data Platform | Data Platform R2 | 2.0.0 | Hotfix | 2026-02-03 | 2026-02-02 | Delivered | Carlos Diaz | Production
REL0011 | PRJ004 | AI Assistant | AI Assistant R1 | 1.0.0 | Major | 2026-01-01 | 2026-01-06 | Delivered | Jane Doe | Staging
REL0012 | PRJ004 | AI Assistant | AI Assistant R2 | 2.0.0 | Patch | 2026-04-04 | 2026-04-12 | Delivered | Jane Doe | Staging
REL0013 | PRJ004 | AI Assistant | AI Assistant R3 | 3.0.0 | Hotfix | 2026-07-05 | 2026-06-30 | Delivered | Jane Doe | Production
REL0014 | PRJ004 | AI Assistant | AI Assistant R4 | 4.0.0 | Hotfix | 2026-10-06 |  | Planned | Jane Doe | Staging
REL0015 | PRJ005 | Network Refresh | Network Refresh R1 | 1.0.0 | Minor | 2026-04-19 | 2026-04-15 | Delivered | Priya Patel | Staging
REL0016 | PRJ006 | Cyber Security Program | Cyber Security Program R1 | 1.0.0 | Minor | 2025-08-04 | 2025-08-12 | Delivered | Alex Brown | Staging
REL0017 | PRJ006 | Cyber Security Program | Cyber Security Program R2 | 2.0.0 | Minor | 2025-12-19 | 2025-12-26 | Delivered | Alex Brown | UAT
REL0018 | PRJ007 | CRM Upgrade | CRM Upgrade R1 | 1.0.0 | Major | 2025-11-26 | 2025-11-27 | Delivered | Alex Brown | UAT
REL0019 | PRJ007 | CRM Upgrade | CRM Upgrade R2 | 2.0.0 | Major | 2026-06-10 | 2026-06-16 | Delivered | Alex Brown | UAT
REL0020 | PRJ008 | Mobile App | Mobile App R1 | 1.0.0 | Hotfix | 2025-06-01 | 2025-05-30 | Delivered | Carlos Diaz | Staging
REL0021 | PRJ008 | Mobile App | Mobile App R2 | 2.0.0 | Hotfix | 2025-07-01 | 2025-07-10 | Delivered | Carlos Diaz | UAT
REL0022 | PRJ008 | Mobile App | Mobile App R3 | 3.0.0 | Patch | 2025-07-31 | 2025-08-06 | Delivered | Carlos Diaz | Staging
REL0023 | PRJ009 | ERP Modernisation | ERP Modernisation R1 | 1.0.0 | Major | 2026-02-19 | 2026-02-24 | Delivered | Jane Doe | Production
REL0024 | PRJ009 | ERP Modernisation | ERP Modernisation R2 | 2.0.0 | Hotfix | 2026-04-10 | 2026-04-19 | Delivered | Jane Doe | UAT
REL0025 | PRJ009 | ERP Modernisation | ERP Modernisation R3 | 3.0.0 | Minor | 2026-05-30 | 2026-05-30 | Delivered | Jane Doe | Staging
REL0026 | PRJ009 | ERP Modernisation | ERP Modernisation R4 | 4.0.0 | Hotfix | 2026-07-19 |  | In Progress | Jane Doe | UAT
REL0027 | PRJ010 | Workforce Enablement | Workforce Enablement R1 | 1.0.0 | Patch | 2025-05-05 | 2025-05-13 | Delivered | Priya Patel | Staging
REL0028 | PRJ010 | Workforce Enablement | Workforce Enablement R2 | 2.0.0 | Major | 2025-08-01 | 2025-07-30 | Delivered | Priya Patel | Production
REL0029 | PRJ010 | Workforce Enablement | Workforce Enablement R3 | 3.0.0 | Major | 2025-10-28 | 2025-10-25 | Delivered | Priya Patel | Staging
REL0030 | PRJ011 | IoT Initiative | IoT Initiative R1 | 1.0.0 | Hotfix | 2025-12-25 | 2025-12-23 | Delivered | Jane Doe | Staging
REL0031 | PRJ011 | IoT Initiative | IoT Initiative R2 | 2.0.0 | Hotfix | 2026-01-22 | 2026-01-20 | Delivered | Jane Doe | Staging
REL0032 | PRJ011 | IoT Initiative | IoT Initiative R3 | 3.0.0 | Patch | 2026-02-19 | 2026-02-15 | Delivered | Jane Doe | UAT
REL0033 | PRJ011 | IoT Initiative | IoT Initiative R4 | 4.0.0 | Minor | 2026-03-19 | 2026-03-20 | Delivered | Jane Doe | UAT
REL0034 | PRJ012 | Analytics Platform | Analytics Platform R1 | 1.0.0 | Minor | 2026-01-15 | 2026-01-13 | Delivered | Jane Doe | UAT
REL0035 | PRJ012 | Analytics Platform | Analytics Platform R2 | 2.0.0 | Patch | 2026-04-29 | 2026-04-27 | Delivered | Jane Doe | UAT
REL0036 | PRJ012 | Analytics Platform | Analytics Platform R3 | 3.0.0 | Hotfix | 2026-08-10 |  | In Progress | Jane Doe | Staging
REL0037 | PRJ012 | Analytics Platform | Analytics Platform R4 | 4.0.0 | Hotfix | 2026-11-22 |  | Planned | Jane Doe | Production
REL0038 | PRJ013 | API Gateway | API Gateway R1 | 1.0.0 | Patch | 2026-03-29 | 2026-03-31 | Delivered | Priya Patel | UAT
REL0039 | PRJ013 | API Gateway | API Gateway R2 | 2.0.0 | Patch | 2026-07-21 |  | In Progress | Priya Patel | UAT
REL0040 | PRJ013 | API Gateway | API Gateway R3 | 3.0.0 | Hotfix | 2026-11-12 |  | Planned | Priya Patel | Staging
REL0041 | PRJ014 | Identity Mgmt | Identity Mgmt R1 | 1.0.0 | Hotfix | 2025-06-16 | 2025-06-11 | Delivered | Alex Brown | Production
REL0042 | PRJ014 | Identity Mgmt | Identity Mgmt R2 | 2.0.0 | Major | 2025-10-25 | 2025-10-20 | Delivered | Alex Brown | Production
REL0043 | PRJ015 | Service Desk | Service Desk R1 | 1.0.0 | Patch | 2025-08-23 | 2025-08-28 | Delivered | John Smith | Production
REL0044 | PRJ015 | Service Desk | Service Desk R2 | 2.0.0 | Minor | 2025-11-12 | 2025-11-20 | Delivered | John Smith | Staging
REL0045 | PRJ015 | Service Desk | Service Desk R3 | 3.0.0 | Minor | 2026-02-01 | 2026-02-08 | Delivered | John Smith | Staging
REL0046 | PRJ016 | Infrastructure Upg | Infrastructure Upg R1 | 1.0.0 | Hotfix | 2026-02-11 | 2026-02-07 | Delivered | John Smith | Production
REL0047 | PRJ016 | Infrastructure Upg | Infrastructure Upg R2 | 2.0.0 | Minor | 2026-04-24 | 2026-05-01 | Delivered | John Smith | UAT
REL0048 | PRJ016 | Infrastructure Upg | Infrastructure Upg R3 | 3.0.0 | Minor | 2026-07-05 | 2026-07-10 | Delivered | John Smith | UAT
REL0049 | PRJ016 | Infrastructure Upg | Infrastructure Upg R4 | 4.0.0 | Minor | 2026-09-15 |  | Planned | John Smith | Production
REL0050 | PRJ017 | App Modernisation | App Modernisation R1 | 1.0.0 | Hotfix | 2025-07-05 | 2025-07-03 | Delivered | Priya Patel | Staging
REL0051 | PRJ017 | App Modernisation | App Modernisation R2 | 2.0.0 | Minor | 2025-11-20 | 2025-11-23 | Delivered | Priya Patel | UAT
REL0052 | PRJ018 | RPA Program | RPA Program R1 | 1.0.0 | Major | 2026-02-27 | 2026-02-24 | Delivered | Carlos Diaz | Production
REL0053 | PRJ018 | RPA Program | RPA Program R2 | 2.0.0 | Major | 2026-07-01 | 2026-07-09 | Delivered | Carlos Diaz | Staging
REL0054 | PRJ019 | Vendor Mgmt | Vendor Mgmt R1 | 1.0.0 | Major | 2025-10-07 | 2025-10-02 | Delivered | Carlos Diaz | Staging
REL0055 | PRJ019 | Vendor Mgmt | Vendor Mgmt R2 | 2.0.0 | Major | 2026-04-21 | 2026-04-28 | Delivered | Carlos Diaz | Staging
REL0056 | PRJ020 | Process Automation | Process Automation R1 | 1.0.0 | Patch | 2025-05-29 | 2025-06-07 | Delivered | Carlos Diaz | Production
REL0057 | PRJ020 | Process Automation | Process Automation R2 | 2.0.0 | Minor | 2025-07-02 | 2025-07-04 | Delivered | Carlos Diaz | UAT
REL0058 | PRJ021 | Data Warehouse | Data Warehouse R1 | 1.0.0 | Hotfix | 2025-03-09 | 2025-03-11 | Delivered | Alex Brown | UAT
REL0059 | PRJ021 | Data Warehouse | Data Warehouse R2 | 2.0.0 | Patch | 2025-04-26 | 2025-04-22 | Delivered | Alex Brown | Production
REL0060 | PRJ022 | DevOps Tools | DevOps Tools R1 | 1.0.0 | Major | 2025-07-12 | 2025-07-07 | Delivered | Priya Patel | Production
REL0061 | PRJ022 | DevOps Tools | DevOps Tools R2 | 2.0.0 | Major | 2025-10-12 | 2025-10-21 | Delivered | Priya Patel | Production
REL0062 | PRJ023 | Workforce Portal | Workforce Portal R1 | 1.0.0 | Patch | 2026-03-19 | 2026-03-23 | Delivered | Jane Doe | Production
REL0063 | PRJ023 | Workforce Portal | Workforce Portal R2 | 2.0.0 | Major | 2026-07-24 |  | In Progress | Jane Doe | Production
REL0064 | PRJ024 | Process Mining | Process Mining R1 | 1.0.0 | Minor | 2026-02-26 | 2026-03-04 | Delivered | Jane Doe | UAT
REL0065 | PRJ024 | Process Mining | Process Mining R2 | 2.0.0 | Hotfix | 2026-05-20 | 2026-05-18 | Delivered | Jane Doe | Production
REL0066 | PRJ024 | Process Mining | Process Mining R3 | 3.0.0 | Hotfix | 2026-08-11 |  | In Progress | Jane Doe | Production
REL0067 | PRJ024 | Process Mining | Process Mining R4 | 4.0.0 | Hotfix | 2026-11-02 |  | Planned | Jane Doe | Staging
REL0068 | PRJ025 | Customer Insights | Customer Insights R1 | 1.0.0 | Hotfix | 2026-07-11 | 2026-07-12 | Delivered | Sarah Lee | UAT
REL0069 | PRJ026 | ERP Modernisation 2 | ERP Modernisation 2 R1 | 1.0.0 | Minor | 2025-12-02 | 2025-12-11 | Delivered | Carlos Diaz | Production
REL0070 | PRJ026 | ERP Modernisation 2 | ERP Modernisation 2 R2 | 2.0.0 | Major | 2026-02-17 | 2026-02-21 | Delivered | Carlos Diaz | Production
REL0071 | PRJ026 | ERP Modernisation 2 | ERP Modernisation 2 R3 | 3.0.0 | Major | 2026-05-05 | 2026-05-01 | Delivered | Carlos Diaz | UAT
REL0072 | PRJ027 | Cyber Program | Cyber Program R1 | 1.0.0 | Major | 2025-07-09 | 2025-07-19 | Delivered | Mike Johnson | Production
REL0073 | PRJ027 | Cyber Program | Cyber Program R2 | 2.0.0 | Major | 2025-09-19 | 2025-09-22 | Delivered | Mike Johnson | Production
REL0074 | PRJ027 | Cyber Program | Cyber Program R3 | 3.0.0 | Major | 2025-11-29 | 2025-11-24 | Delivered | Mike Johnson | Staging
REL0075 | PRJ028 | Mobile App 2 | Mobile App 2 R1 | 1.0.0 | Patch | 2025-07-13 | 2025-07-14 | Delivered | Carlos Diaz | Production
REL0076 | PRJ028 | Mobile App 2 | Mobile App 2 R2 | 2.0.0 | Major | 2026-01-20 | 2026-01-21 | Delivered | Carlos Diaz | UAT
REL0077 | PRJ029 | Analytics Platform 2 | Analytics Platform 2 R1 | 1.0.0 | Major | 2026-03-16 | 2026-03-18 | Delivered | John Smith | Staging
REL0078 | PRJ029 | Analytics Platform 2 | Analytics Platform 2 R2 | 2.0.0 | Patch | 2026-07-15 | 2026-07-14 | Delivered | John Smith | UAT
REL0079 | PRJ030 | Service Desk 2 | Service Desk 2 R1 | 1.0.0 | Major | 2025-08-21 | 2025-08-22 | Delivered | Jane Doe | UAT
REL0080 | PRJ030 | Service Desk 2 | Service Desk 2 R2 | 2.0.0 | Hotfix | 2025-12-02 | 2025-12-06 | Delivered | Jane Doe | Staging
REL0081 | PRJ030 | Service Desk 2 | Service Desk 2 R3 | 3.0.0 | Hotfix | 2026-03-16 | 2026-03-26 | Delivered | Jane Doe | Staging
REL0082 | PRJ030 | Service Desk 2 | Service Desk 2 R4 | 4.0.0 | Minor | 2026-06-27 | 2026-07-04 | Delivered | Jane Doe | UAT
REL0083 | PRJ031 | Quality Mgmt | Quality Mgmt R1 | 1.0.0 | Patch | 2026-01-23 | 2026-01-24 | Delivered | Carlos Diaz | UAT
REL0084 | PRJ031 | Quality Mgmt | Quality Mgmt R2 | 2.0.0 | Patch | 2026-06-21 | 2026-06-19 | Delivered | Carlos Diaz | Production
REL0085 | PRJ032 | Compliance Hub | Compliance Hub R1 | 1.0.0 | Hotfix | 2026-06-09 | 2026-06-19 | Delivered | Carlos Diaz | UAT
REL0086 | PRJ032 | Compliance Hub | Compliance Hub R2 | 2.0.0 | Hotfix | 2026-11-28 |  | Planned | Carlos Diaz | Staging
REL0087 | PRJ033 | Risk Platform | Risk Platform R1 | 1.0.0 | Major | 2026-04-07 | 2026-04-12 | Delivered | Priya Patel | Staging
REL0088 | PRJ033 | Risk Platform | Risk Platform R2 | 2.0.0 | Hotfix | 2026-08-22 |  | Planned | Priya Patel | UAT
REL0089 | PRJ033 | Risk Platform | Risk Platform R3 | 3.0.0 | Minor | 2027-01-05 |  | Planned | Priya Patel | Staging
REL0090 | PRJ034 | Treasury Sys | Treasury Sys R1 | 1.0.0 | Major | 2026-02-25 | 2026-03-03 | Delivered | Jane Doe | UAT
REL0091 | PRJ034 | Treasury Sys | Treasury Sys R2 | 2.0.0 | Major | 2026-06-13 | 2026-06-13 | Delivered | Jane Doe | Staging
REL0092 | PRJ034 | Treasury Sys | Treasury Sys R3 | 3.0.0 | Patch | 2026-09-29 |  | Planned | Jane Doe | Staging
REL0093 | PRJ035 | Payroll Cloud | Payroll Cloud R1 | 1.0.0 | Patch | 2025-07-31 | 2025-08-04 | Delivered | Jane Doe | UAT
REL0094 | PRJ035 | Payroll Cloud | Payroll Cloud R2 | 2.0.0 | Major | 2025-10-28 | 2025-10-23 | Delivered | Jane Doe | Production
REL0095 | PRJ035 | Payroll Cloud | Payroll Cloud R3 | 3.0.0 | Hotfix | 2026-01-24 | 2026-01-29 | Delivered | Jane Doe | Production
REL0096 | PRJ035 | Payroll Cloud | Payroll Cloud R4 | 4.0.0 | Minor | 2026-04-23 | 2026-04-29 | Delivered | Jane Doe | Production
REL0097 | PRJ036 | HR Self-Service | HR Self-Service R1 | 1.0.0 | Patch | 2025-07-17 | 2025-07-23 | Delivered | Jane Doe | Production
REL0098 | PRJ036 | HR Self-Service | HR Self-Service R2 | 2.0.0 | Major | 2025-09-24 | 2025-09-29 | Delivered | Jane Doe | Production
REL0099 | PRJ037 | SAP S/4HANA | SAP S/4HANA R1 | 1.0.0 | Patch | 2025-05-02 | 2025-04-27 | Delivered | John Smith | Production
REL0100 | PRJ037 | SAP S/4HANA | SAP S/4HANA R2 | 2.0.0 | Patch | 2025-06-29 | 2025-07-08 | Delivered | John Smith | Production
REL0101 | PRJ037 | SAP S/4HANA | SAP S/4HANA R3 | 3.0.0 | Hotfix | 2025-08-25 | 2025-08-22 | Delivered | John Smith | UAT
REL0102 | PRJ038 | Salesforce CRM | Salesforce CRM R1 | 1.0.0 | Major | 2025-10-21 | 2025-10-22 | Delivered | Jane Doe | Staging
REL0103 | PRJ038 | Salesforce CRM | Salesforce CRM R2 | 2.0.0 | Major | 2025-12-02 | 2025-12-05 | Delivered | Jane Doe | Staging
REL0104 | PRJ039 | M365 Rollout | M365 Rollout R1 | 1.0.0 | Patch | 2025-12-08 | 2025-12-16 | Delivered | Jane Doe | UAT
REL0105 | PRJ039 | M365 Rollout | M365 Rollout R2 | 2.0.0 | Minor | 2026-01-01 | 2026-01-02 | Delivered | Jane Doe | Production
REL0106 | PRJ039 | M365 Rollout | M365 Rollout R3 | 3.0.0 | Hotfix | 2026-01-25 | 2026-02-04 | Delivered | Jane Doe | Production
REL0107 | PRJ039 | M365 Rollout | M365 Rollout R4 | 4.0.0 | Hotfix | 2026-02-18 | 2026-02-21 | Delivered | Jane Doe | Production
REL0108 | PRJ040 | Zero-Trust Net | Zero-Trust Net R1 | 1.0.0 | Minor | 2025-09-14 | 2025-09-23 | Delivered | Alex Brown | Staging

## FYAllocation
Project ID | Project Name | FY | Budget % | Forecast % | Budget Amount | Forecast Amount | Notes
PRJ001 | Customer Portal | FY25 | 50 | 50 | 1296882 | 1203668 | Auto-split from Projects.Financial Year — edit to revise
PRJ001 | Customer Portal | FY26 | 50 | 50 | 1296882 | 1203668 | Auto-split from Projects.Financial Year — edit to revise
PRJ002 | Cloud Migration | FY25 | 100 | 100 | 1851915 | 2065964 | Auto-split from Projects.Financial Year — edit to revise
PRJ003 | Data Platform | FY25 | 50 | 50 | 1947576 | 2220804 | Auto-split from Projects.Financial Year — edit to revise
PRJ003 | Data Platform | FY26 | 50 | 50 | 1947576 | 2220804 | Auto-split from Projects.Financial Year — edit to revise
PRJ004 | AI Assistant | FY25 | 33.3 | 33.3 | 514569 | 606074 | Auto-split from Projects.Financial Year — edit to revise
PRJ004 | AI Assistant | FY26 | 33.3 | 33.3 | 514569 | 606074 | Auto-split from Projects.Financial Year — edit to revise
PRJ004 | AI Assistant | FY27 | 33.3 | 33.3 | 514569 | 606074 | Auto-split from Projects.Financial Year — edit to revise
PRJ005 | Network Refresh | FY25 | 33.3 | 33.3 | 554848 | 581765 | Auto-split from Projects.Financial Year — edit to revise
PRJ005 | Network Refresh | FY26 | 33.3 | 33.3 | 554848 | 581765 | Auto-split from Projects.Financial Year — edit to revise
PRJ005 | Network Refresh | FY27 | 33.3 | 33.3 | 554848 | 581765 | Auto-split from Projects.Financial Year — edit to revise
PRJ006 | Cyber Security Program | FY25 | 50 | 50 | 828831 | 852316 | Auto-split from Projects.Financial Year — edit to revise
PRJ006 | Cyber Security Program | FY26 | 50 | 50 | 828831 | 852316 | Auto-split from Projects.Financial Year — edit to revise
PRJ007 | CRM Upgrade | FY25 | 50 | 50 | 1775338 | 1720411 | Auto-split from Projects.Financial Year — edit to revise
PRJ007 | CRM Upgrade | FY26 | 50 | 50 | 1775338 | 1720411 | Auto-split from Projects.Financial Year — edit to revise
PRJ008 | Mobile App | FY25 | 100 | 100 | 3682125 | 3273975 | Auto-split from Projects.Financial Year — edit to revise
PRJ009 | ERP Modernisation | FY26 | 100 | 100 | 1133721 | 1047705 | Auto-split from Projects.Financial Year — edit to revise
PRJ010 | Workforce Enablement | FY25 | 50 | 50 | 1197458 | 1042514 | Auto-split from Projects.Financial Year — edit to revise
PRJ010 | Workforce Enablement | FY26 | 50 | 50 | 1197458 | 1042514 | Auto-split from Projects.Financial Year — edit to revise
PRJ011 | IoT Initiative | FY25 | 50 | 50 | 233936 | 232505 | Auto-split from Projects.Financial Year — edit to revise
PRJ011 | IoT Initiative | FY26 | 50 | 50 | 233936 | 232505 | Auto-split from Projects.Financial Year — edit to revise
PRJ012 | Analytics Platform | FY25 | 33.3 | 33.3 | 634750 | 719049 | Auto-split from Projects.Financial Year — edit to revise
PRJ012 | Analytics Platform | FY26 | 33.3 | 33.3 | 634750 | 719049 | Auto-split from Projects.Financial Year — edit to revise
PRJ012 | Analytics Platform | FY27 | 33.3 | 33.3 | 634750 | 719049 | Auto-split from Projects.Financial Year — edit to revise
PRJ013 | API Gateway | FY25 | 33.3 | 33.3 | 1314235 | 1326395 | Auto-split from Projects.Financial Year — edit to revise
PRJ013 | API Gateway | FY26 | 33.3 | 33.3 | 1314235 | 1326395 | Auto-split from Projects.Financial Year — edit to revise
PRJ013 | API Gateway | FY27 | 33.3 | 33.3 | 1314235 | 1326395 | Auto-split from Projects.Financial Year — edit to revise
PRJ014 | Identity Mgmt | FY25 | 50 | 50 | 1189146 | 1076298 | Auto-split from Projects.Financial Year — edit to revise
PRJ014 | Identity Mgmt | FY26 | 50 | 50 | 1189146 | 1076298 | Auto-split from Projects.Financial Year — edit to revise
PRJ015 | Service Desk | FY25 | 50 | 50 | 666921 | 640220 | Auto-split from Projects.Financial Year — edit to revise
PRJ015 | Service Desk | FY26 | 50 | 50 | 666921 | 640220 | Auto-split from Projects.Financial Year — edit to revise
PRJ016 | Infrastructure Upg | FY25 | 50 | 50 | 1767685 | 1600128 | Auto-split from Projects.Financial Year — edit to revise
PRJ016 | Infrastructure Upg | FY26 | 50 | 50 | 1767685 | 1600128 | Auto-split from Projects.Financial Year — edit to revise
PRJ017 | App Modernisation | FY25 | 50 | 50 | 1449344 | 1365854 | Auto-split from Projects.Financial Year — edit to revise
PRJ017 | App Modernisation | FY26 | 50 | 50 | 1449344 | 1365854 | Auto-split from Projects.Financial Year — edit to revise
PRJ018 | RPA Program | FY25 | 50 | 50 | 883990 | 1024621 | Auto-split from Projects.Financial Year — edit to revise
PRJ018 | RPA Program | FY26 | 50 | 50 | 883990 | 1024621 | Auto-split from Projects.Financial Year — edit to revise
PRJ019 | Vendor Mgmt | FY25 | 50 | 50 | 250448 | 248502 | Auto-split from Projects.Financial Year — edit to revise
PRJ019 | Vendor Mgmt | FY26 | 50 | 50 | 250448 | 248502 | Auto-split from Projects.Financial Year — edit to revise
PRJ020 | Process Automation | FY25 | 100 | 100 | 3501450 | 3976966 | Auto-split from Projects.Financial Year — edit to revise
PRJ021 | Data Warehouse | FY25 | 100 | 100 | 3926484 | 3496022 | Auto-split from Projects.Financial Year — edit to revise
PRJ022 | DevOps Tools | FY25 | 50 | 50 | 1432132 | 1487208 | Auto-split from Projects.Financial Year — edit to revise
PRJ022 | DevOps Tools | FY26 | 50 | 50 | 1432132 | 1487208 | Auto-split from Projects.Financial Year — edit to revise
PRJ023 | Workforce Portal | FY25 | 50 | 50 | 1409556 | 1526162 | Auto-split from Projects.Financial Year — edit to revise
PRJ023 | Workforce Portal | FY26 | 50 | 50 | 1409556 | 1526162 | Auto-split from Projects.Financial Year — edit to revise
PRJ024 | Process Mining | FY25 | 33.3 | 33.3 | 311145 | 351161 | Auto-split from Projects.Financial Year — edit to revise
PRJ024 | Process Mining | FY26 | 33.3 | 33.3 | 311145 | 351161 | Auto-split from Projects.Financial Year — edit to revise
PRJ024 | Process Mining | FY27 | 33.3 | 33.3 | 311145 | 351161 | Auto-split from Projects.Financial Year — edit to revise
PRJ025 | Customer Insights | FY25 | 33.3 | 33.3 | 625374 | 688800 | Auto-split from Projects.Financial Year — edit to revise
PRJ025 | Customer Insights | FY26 | 33.3 | 33.3 | 625374 | 688800 | Auto-split from Projects.Financial Year — edit to revise
PRJ025 | Customer Insights | FY27 | 33.3 | 33.3 | 625374 | 688800 | Auto-split from Projects.Financial Year — edit to revise
PRJ026 | ERP Modernisation 2 | FY25 | 50 | 50 | 1351776 | 1598494 | Auto-split from Projects.Financial Year — edit to revise
PRJ026 | ERP Modernisation 2 | FY26 | 50 | 50 | 1351776 | 1598494 | Auto-split from Projects.Financial Year — edit to revise
PRJ027 | Cyber Program | FY25 | 50 | 50 | 907752 | 878292 | Auto-split from Projects.Financial Year — edit to revise
PRJ027 | Cyber Program | FY26 | 50 | 50 | 907752 | 878292 | Auto-split from Projects.Financial Year — edit to revise
PRJ028 | Mobile App 2 | FY25 | 50 | 50 | 809480 | 693592 | Auto-split from Projects.Financial Year — edit to revise
PRJ028 | Mobile App 2 | FY26 | 50 | 50 | 809480 | 693592 | Auto-split from Projects.Financial Year — edit to revise
PRJ029 | Analytics Platform 2 | FY25 | 50 | 50 | 997002 | 1125964 | Auto-split from Projects.Financial Year — edit to revise
PRJ029 | Analytics Platform 2 | FY26 | 50 | 50 | 997002 | 1125964 | Auto-split from Projects.Financial Year — edit to revise
PRJ030 | Service Desk 2 | FY25 | 50 | 50 | 557305 | 539541 | Auto-split from Projects.Financial Year — edit to revise
PRJ030 | Service Desk 2 | FY26 | 50 | 50 | 557305 | 539541 | Auto-split from Projects.Financial Year — edit to revise
PRJ031 | Quality Mgmt | FY25 | 50 | 50 | 438754 | 392324 | Auto-split from Projects.Financial Year — edit to revise
PRJ031 | Quality Mgmt | FY26 | 50 | 50 | 438754 | 392324 | Auto-split from Projects.Financial Year — edit to revise
PRJ032 | Compliance Hub | FY25 | 33.3 | 33.3 | 1240887 | 1217753 | Auto-split from Projects.Financial Year — edit to revise
PRJ032 | Compliance Hub | FY26 | 33.3 | 33.3 | 1240887 | 1217753 | Auto-split from Projects.Financial Year — edit to revise
PRJ032 | Compliance Hub | FY27 | 33.3 | 33.3 | 1240887 | 1217753 | Auto-split from Projects.Financial Year — edit to revise
PRJ033 | Risk Platform | FY25 | 33.3 | 33.3 | 515075 | 590972 | Auto-split from Projects.Financial Year — edit to revise
PRJ033 | Risk Platform | FY26 | 33.3 | 33.3 | 515075 | 590972 | Auto-split from Projects.Financial Year — edit to revise
PRJ033 | Risk Platform | FY27 | 33.3 | 33.3 | 515075 | 590972 | Auto-split from Projects.Financial Year — edit to revise
PRJ034 | Treasury Sys | FY25 | 33.3 | 33.3 | 452329 | 428639 | Auto-split from Projects.Financial Year — edit to revise
PRJ034 | Treasury Sys | FY26 | 33.3 | 33.3 | 452329 | 428639 | Auto-split from Projects.Financial Year — edit to revise
PRJ034 | Treasury Sys | FY27 | 33.3 | 33.3 | 452329 | 428639 | Auto-split from Projects.Financial Year — edit to revise
PRJ035 | Payroll Cloud | FY25 | 50 | 50 | 1766210 | 1619384 | Auto-split from Projects.Financial Year — edit to revise
PRJ035 | Payroll Cloud | FY26 | 50 | 50 | 1766210 | 1619384 | Auto-split from Projects.Financial Year — edit to revise
PRJ036 | HR Self-Service | FY25 | 100 | 100 | 2258545 | 2354840 | Auto-split from Projects.Financial Year — edit to revise
PRJ037 | SAP S/4HANA | FY25 | 100 | 100 | 1203695 | 1118978 | Auto-split from Projects.Financial Year — edit to revise
PRJ038 | Salesforce CRM | FY25 | 50 | 50 | 908914 | 1071948 | Auto-split from Projects.Financial Year — edit to revise
PRJ038 | Salesforce CRM | FY26 | 50 | 50 | 908914 | 1071948 | Auto-split from Projects.Financial Year — edit to revise
PRJ039 | M365 Rollout | FY25 | 50 | 50 | 1562602 | 1490838 | Auto-split from Projects.Financial Year — edit to revise
PRJ039 | M365 Rollout | FY26 | 50 | 50 | 1562602 | 1490838 | Auto-split from Projects.Financial Year — edit to revise
PRJ040 | Zero-Trust Net | FY25 | 50 | 50 | 846610 | 729290 | Auto-split from Projects.Financial Year — edit to revise
PRJ040 | Zero-Trust Net | FY26 | 50 | 50 | 846610 | 729290 | Auto-split from Projects.Financial Year — edit to revise

## Programs
Program | Owner | Sponsor | Budget | Forecast | Start FY | End FY | Status | Notes
Digital Transformation | Mike Johnson | CTO | 20682756 | 19929607 | FY25 | FY26 | Active
Cyber Security | Sarah Lee | CFO | 23048795 | 25365239 | FY25 | FY27 | Active
Cloud Migration | Alex Brown | CIO | 19629127 | 19663839 | FY25 | FY27 | Active
Data & AI | Mike Johnson | CIO | 15462956 | 14369534 | FY25 | FY27 | Active
Customer Experience | Priya Patel | CTO | 10175226 | 10299815 | FY25 | FY26 | Active

## PhaseFinancials
Project ID | Stage | Planned Start | Planned End | Actual Start | Actual End | Phase Budget | Phase Forecast | Phase Actual Spend | Status | Notes
PRJ001 | Discovery | 2025-02-14 | 2025-04-04 | 2025-02-14 | 2025-04-04 | 324221 | 371877 | 310352 | Complete
PRJ001 | Business Case / Seed Funding | 2025-04-04 | 2025-05-23 | 2025-04-04 | 2025-05-23 | 324221 | 314848 | 286522 | Complete
PRJ001 | Design | 2025-05-23 | 2025-07-11 | 2025-05-23 | 2025-07-11 | 324221 | 324448 | 304969 | Complete
PRJ001 | Business Case / Full Funding | 2025-07-11 | 2025-08-29 | 2025-07-11 | 2025-08-29 | 324221 | 366210 | 13318 | Complete
PRJ001 | Build | 2025-08-29 | 2025-10-17 | 2025-08-29 | 2025-10-17 | 324221 | 344061 | 23644 | Complete
PRJ001 | Testing | 2025-10-17 | 2025-12-05 | 2025-10-17 | 2025-12-05 | 324221 | 299509 | 273201 | Complete
PRJ001 | Deployment | 2025-12-05 | 2026-01-23 | 2025-12-05 | 2026-01-23 | 324221 | 350422 | 93508 | Complete
PRJ001 | Handover | 2026-01-23 | 2026-03-13 | 2026-01-23 | 2026-03-13 | 324221 | 352889 | 136290 | Complete
PRJ002 | Discovery | 2025-03-21 | 2025-04-15 | 2025-03-21 | 2025-04-15 | 231489 | 240544 | 76121 | Complete
PRJ002 | Business Case / Seed Funding | 2025-04-15 | 2025-05-10 | 2025-04-15 | 2025-05-10 | 231489 | 243777 | 95604 | Complete
PRJ002 | Design | 2025-05-10 | 2025-06-04 | 2025-05-10 | 2025-06-04 | 231489 | 248646 | 110492 | Complete
PRJ002 | Business Case / Full Funding | 2025-06-04 | 2025-06-29 | 2025-06-04 | 2025-06-29 | 231489 | 257455 | 235080 | Complete
PRJ002 | Build | 2025-06-29 | 2025-07-24 | 2025-06-29 | 2025-07-24 | 231489 | 215367 | 90883 | Complete
PRJ002 | Testing | 2025-07-24 | 2025-08-18 | 2025-07-24 | 2025-08-18 | 231489 | 244104 | 7119 | Complete
PRJ002 | Deployment | 2025-08-18 | 2025-09-12 | 2025-08-18 | 2025-09-12 | 231489 | 211109 | 2527 | Complete
PRJ002 | Handover | 2025-09-12 | 2025-10-07 | 2025-09-12 | 2025-10-07 | 231489 | 214425 | 78475 | Complete
PRJ003 | Discovery | 2025-04-09 | 2025-06-04 | 2025-04-09 | 2025-06-04 | 486894 | 521901 | 222738 | Complete
PRJ003 | Business Case / Seed Funding | 2025-06-04 | 2025-07-30 | 2025-06-04 | 2025-07-30 | 486894 | 458921 | 97728 | Complete
PRJ003 | Design | 2025-07-30 | 2025-09-24 | 2025-07-30 | 2025-09-24 | 486894 | 548033 | 188585 | Complete
PRJ003 | Business Case / Full Funding | 2025-09-24 | 2025-11-19 | 2025-09-24 | 2025-11-19 | 486894 | 548106 | 505904 | Complete
PRJ003 | Build | 2025-11-19 | 2026-01-14 | 2025-11-19 | 2026-01-14 | 486894 | 551908 | 443763 | Complete
PRJ003 | Testing | 2026-01-14 | 2026-03-11 | 2026-01-14 | 2026-03-11 | 486894 | 469815 | 401294 | Complete
PRJ003 | Deployment | 2026-03-11 | 2026-05-06 | 2026-03-11 | 2026-05-06 | 486894 | 451692 | 484217 | Complete
PRJ003 | Handover | 2026-05-06 | 2026-07-01 | 2026-05-06 | 2026-07-01 | 486894 | 447339 | 168366 | Complete
PRJ004 | Discovery | 2025-10-01 | 2025-11-27 | 2025-10-01 | 2025-11-27 | 192963 | 203227 | 164619 | Complete
PRJ004 | Business Case / Seed Funding | 2025-11-27 | 2026-01-23 | 2025-11-27 | 2026-01-23 | 192963 | 186688 | 34513 | Complete
PRJ004 | Design | 2026-01-23 | 2026-03-21 | 2026-01-23 | 2026-03-21 | 192963 | 180313 | 93342 | Complete
PRJ004 | Business Case / Full Funding | 2026-03-21 | 2026-05-17 | 2026-03-21 | 2026-05-17 | 192963 | 179759 | 174630 | Complete
PRJ004 | Build | 2026-05-17 | 2026-07-13 | 2026-05-17 | 2026-07-13 | 192963 | 209994 | 179878 | Complete
PRJ004 | Testing | 2026-07-13 | 2026-09-08 | 2026-07-13 |  | 192963 | 220260 | 83738 | In Progress
PRJ004 | Deployment | 2026-09-08 | 2026-11-04 |  |  | 192963 | 195220 | 0 | Planned
PRJ004 | Handover | 2026-11-04 | 2026-12-31 |  |  | 192963 | 179570 | 0 | Planned
PRJ005 | Discovery | 2025-07-22 | 2025-09-27 | 2025-07-22 | 2025-09-27 | 208068 | 214705 | 126251 | Complete
PRJ005 | Business Case / Seed Funding | 2025-09-27 | 2025-12-03 | 2025-09-27 | 2025-12-03 | 208068 | 221658 | 213304 | Complete
PRJ005 | Design | 2025-12-03 | 2026-02-08 | 2025-12-03 | 2026-02-08 | 208068 | 204006 | 159673 | Complete
PRJ005 | Business Case / Full Funding | 2026-02-08 | 2026-04-16 | 2026-02-08 | 2026-04-16 | 208068 | 199008 | 57635 | Complete
PRJ005 | Build | 2026-04-16 | 2026-06-22 | 2026-04-16 | 2026-06-22 | 208068 | 202670 | 18088 | Complete
PRJ005 | Testing | 2026-06-22 | 2026-08-28 | 2026-06-22 |  | 208068 | 216313 | 190698 | In Progress
PRJ005 | Deployment | 2026-08-28 | 2026-11-03 |  |  | 208068 | 221565 | 0 | Planned
PRJ005 | Handover | 2026-11-03 | 2027-01-09 |  |  | 208068 | 225508 | 0 | Planned
PRJ006 | Discovery | 2025-03-20 | 2025-05-10 | 2025-03-20 | 2025-05-10 | 207208 | 197153 | 16974 | Complete
PRJ006 | Business Case / Seed Funding | 2025-05-10 | 2025-06-30 | 2025-05-10 | 2025-06-30 | 207208 | 236826 | 13112 | Complete
PRJ006 | Design | 2025-06-30 | 2025-08-20 | 2025-06-30 | 2025-08-20 | 207208 | 187167 | 47024 | Complete
PRJ006 | Business Case / Full Funding | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-10-10 | 207208 | 228887 | 40885 | Complete
PRJ006 | Build | 2025-10-10 | 2025-11-30 | 2025-10-10 | 2025-11-30 | 207208 | 191902 | 45398 | Complete
PRJ006 | Testing | 2025-11-30 | 2026-01-20 | 2025-11-30 | 2026-01-20 | 207208 | 217077 | 114799 | Complete
PRJ006 | Deployment | 2026-01-20 | 2026-03-12 | 2026-01-20 | 2026-03-12 | 207208 | 230957 | 165458 | Complete
PRJ006 | Handover | 2026-03-12 | 2026-05-02 | 2026-03-12 | 2026-05-02 | 207208 | 202640 | 98781 | Complete
PRJ007 | Discovery | 2025-05-15 | 2025-07-27 | 2025-05-15 | 2025-07-27 | 443834 | 416538 | 235115 | Complete
PRJ007 | Business Case / Seed Funding | 2025-07-27 | 2025-10-08 | 2025-07-27 | 2025-10-08 | 443834 | 500881 | 101959 | Complete
PRJ007 | Design | 2025-10-08 | 2025-12-20 | 2025-10-08 | 2025-12-20 | 443834 | 439800 | 454406 | Complete
PRJ007 | Business Case / Full Funding | 2025-12-20 | 2026-03-03 | 2025-12-20 | 2026-03-03 | 443834 | 495747 | 239288 | Complete
PRJ007 | Build | 2026-03-03 | 2026-05-15 | 2026-03-03 | 2026-05-15 | 443834 | 486001 | 87591 | Complete
PRJ007 | Testing | 2026-05-15 | 2026-07-27 | 2026-05-15 |  | 443834 | 430279 | 76520 | In Progress
PRJ007 | Deployment | 2026-07-27 | 2026-10-08 |  |  | 443834 | 433532 | 0 | Planned
PRJ007 | Handover | 2026-10-08 | 2026-12-20 |  |  | 443834 | 495966 | 0 | Planned
PRJ008 | Discovery | 2025-05-03 | 2025-05-17 | 2025-05-03 | 2025-05-17 | 460266 | 488846 | 71182 | Complete
PRJ008 | Business Case / Seed Funding | 2025-05-17 | 2025-05-31 | 2025-05-17 | 2025-05-31 | 460266 | 515060 | 360055 | Complete
PRJ008 | Design | 2025-05-31 | 2025-06-14 | 2025-05-31 | 2025-06-14 | 460266 | 441920 | 432099 | Complete
PRJ008 | Business Case / Full Funding | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-06-28 | 460266 | 435760 | 13815 | Complete
PRJ008 | Build | 2025-06-28 | 2025-07-12 | 2025-06-28 | 2025-07-12 | 460266 | 490400 | 218752 | Complete
PRJ008 | Testing | 2025-07-12 | 2025-07-26 | 2025-07-12 | 2025-07-26 | 460266 | 444798 | 447965 | Complete
PRJ008 | Deployment | 2025-07-26 | 2025-08-09 | 2025-07-26 | 2025-08-09 | 460266 | 423912 | 208522 | Complete
PRJ008 | Handover | 2025-08-09 | 2025-08-23 | 2025-08-09 | 2025-08-23 | 460266 | 431570 | 242698 | Complete
PRJ009 | Discovery | 2026-01-01 | 2026-02-01 | 2026-01-01 | 2026-02-01 | 141715 | 145539 | 7910 | Complete
PRJ009 | Business Case / Seed Funding | 2026-02-01 | 2026-03-04 | 2026-02-01 | 2026-03-04 | 141715 | 137201 | 14555 | Complete
PRJ009 | Design | 2026-03-04 | 2026-04-04 | 2026-03-04 | 2026-04-04 | 141715 | 150523 | 108922 | Complete
PRJ009 | Business Case / Full Funding | 2026-04-04 | 2026-05-05 | 2026-04-04 | 2026-05-05 | 141715 | 142515 | 43748 | Complete
PRJ009 | Build | 2026-05-05 | 2026-06-05 | 2026-05-05 | 2026-06-05 | 141715 | 141811 | 88395 | Complete
PRJ009 | Testing | 2026-06-05 | 2026-07-06 | 2026-06-05 | 2026-07-06 | 141715 | 146305 | 73451 | Complete
PRJ009 | Deployment | 2026-07-06 | 2026-08-06 | 2026-07-06 |  | 141715 | 142904 | 101357 | In Progress
PRJ009 | Handover | 2026-08-06 | 2026-09-06 |  |  | 141715 | 150443 | 0 | Planned
PRJ010 | Discovery | 2025-02-06 | 2025-03-22 | 2025-02-06 | 2025-03-22 | 299364 | 341199 | 69021 | Complete
PRJ010 | Business Case / Seed Funding | 2025-03-22 | 2025-05-05 | 2025-03-22 | 2025-05-05 | 299364 | 273405 | 11218 | Complete
PRJ010 | Design | 2025-05-05 | 2025-06-18 | 2025-05-05 | 2025-06-18 | 299364 | 289349 | 20698 | Complete
PRJ010 | Business Case / Full Funding | 2025-06-18 | 2025-08-01 | 2025-06-18 | 2025-08-01 | 299364 | 276989 | 71185 | Complete
PRJ010 | Build | 2025-08-01 | 2025-09-14 | 2025-08-01 | 2025-09-14 | 299364 | 315846 | 225007 | Complete
PRJ010 | Testing | 2025-09-14 | 2025-10-28 | 2025-09-14 | 2025-10-28 | 299364 | 298759 | 31843 | Complete
PRJ010 | Deployment | 2025-10-28 | 2025-12-11 | 2025-10-28 | 2025-12-11 | 299364 | 324356 | 276464 | Complete
PRJ010 | Handover | 2025-12-11 | 2026-01-24 | 2025-12-11 | 2026-01-24 | 299364 | 289505 | 64660 | Complete
PRJ011 | Discovery | 2025-11-27 | 2025-12-14 | 2025-11-27 | 2025-12-14 | 58484 | 64124 | 21347 | Complete
PRJ011 | Business Case / Seed Funding | 2025-12-14 | 2025-12-31 | 2025-12-14 | 2025-12-31 | 58484 | 56846 | 36618 | Complete
PRJ011 | Design | 2025-12-31 | 2026-01-17 | 2025-12-31 | 2026-01-17 | 58484 | 63366 | 5787 | Complete
PRJ011 | Business Case / Full Funding | 2026-01-17 | 2026-02-03 | 2026-01-17 | 2026-02-03 | 58484 | 59993 | 43015 | Complete
PRJ011 | Build | 2026-02-03 | 2026-02-20 | 2026-02-03 | 2026-02-20 | 58484 | 59606 | 18749 | Complete
PRJ011 | Testing | 2026-02-20 | 2026-03-09 | 2026-02-20 | 2026-03-09 | 58484 | 65892 | 14653 | Complete
PRJ011 | Deployment | 2026-03-09 | 2026-03-26 | 2026-03-09 | 2026-03-26 | 58484 | 57243 | 4265 | Complete
PRJ011 | Handover | 2026-03-26 | 2026-04-12 | 2026-03-26 | 2026-04-12 | 58484 | 55375 | 55259 | Complete
PRJ012 | Discovery | 2025-10-04 | 2025-12-07 | 2025-10-04 | 2025-12-07 | 238031 | 222668 | 3183 | Complete
PRJ012 | Business Case / Seed Funding | 2025-12-07 | 2026-02-09 | 2025-12-07 | 2026-02-09 | 238031 | 242470 | 83491 | Complete
PRJ012 | Design | 2026-02-09 | 2026-04-14 | 2026-02-09 | 2026-04-14 | 238031 | 224792 | 65940 | Complete
PRJ012 | Business Case / Full Funding | 2026-04-14 | 2026-06-17 | 2026-04-14 | 2026-06-17 | 238031 | 218809 | 169755 | Complete
PRJ012 | Build | 2026-06-17 | 2026-08-20 | 2026-06-17 |  | 238031 | 264993 | 148461 | In Progress
PRJ012 | Testing | 2026-08-20 | 2026-10-23 |  |  | 238031 | 271923 | 0 | Planned
PRJ012 | Deployment | 2026-10-23 | 2026-12-26 |  |  | 238031 | 248931 | 0 | Planned
PRJ012 | Handover | 2026-12-26 | 2027-02-28 |  |  | 238031 | 243286 | 0 | Planned
PRJ013 | Discovery | 2025-12-05 | 2026-01-31 | 2025-12-05 | 2026-01-31 | 492838 | 474050 | 56605 | Complete
PRJ013 | Business Case / Seed Funding | 2026-01-31 | 2026-03-29 | 2026-01-31 | 2026-03-29 | 492838 | 544454 | 293549 | Complete
PRJ013 | Design | 2026-03-29 | 2026-05-25 | 2026-03-29 | 2026-05-25 | 492838 | 565583 | 432282 | Complete
PRJ013 | Business Case / Full Funding | 2026-05-25 | 2026-07-21 | 2026-05-25 |  | 492838 | 508272 | 86577 | In Progress
PRJ013 | Build | 2026-07-21 | 2026-09-16 |  |  | 492838 | 461615 | 0 | Planned
PRJ013 | Testing | 2026-09-16 | 2026-11-12 |  |  | 492838 | 455125 | 0 | Planned
PRJ013 | Deployment | 2026-11-12 | 2027-01-08 |  |  | 492838 | 481084 | 0 | Planned
PRJ013 | Handover | 2027-01-08 | 2027-03-06 |  |  | 492838 | 534259 | 0 | Planned
PRJ014 | Discovery | 2025-02-05 | 2025-03-26 | 2025-02-05 | 2025-03-26 | 297287 | 301197 | 229373 | Complete
PRJ014 | Business Case / Seed Funding | 2025-03-26 | 2025-05-14 | 2025-03-26 | 2025-05-14 | 297287 | 341121 | 80329 | Complete
PRJ014 | Design | 2025-05-14 | 2025-07-02 | 2025-05-14 | 2025-07-02 | 297287 | 303715 | 113713 | Complete
PRJ014 | Business Case / Full Funding | 2025-07-02 | 2025-08-20 | 2025-07-02 | 2025-08-20 | 297287 | 268566 | 110073 | Complete
PRJ014 | Build | 2025-08-20 | 2025-10-08 | 2025-08-20 | 2025-10-08 | 297287 | 320338 | 278243 | Complete
PRJ014 | Testing | 2025-10-08 | 2025-11-26 | 2025-10-08 | 2025-11-26 | 297287 | 325122 | 267500 | Complete
PRJ014 | Deployment | 2025-11-26 | 2026-01-14 | 2025-11-26 | 2026-01-14 | 297287 | 334608 | 185962 | Complete
PRJ014 | Handover | 2026-01-14 | 2026-03-04 | 2026-01-14 | 2026-03-04 | 297287 | 275939 | 214068 | Complete
PRJ015 | Discovery | 2025-06-03 | 2025-07-13 | 2025-06-03 | 2025-07-13 | 166730 | 180411 | 3629 | Complete
PRJ015 | Business Case / Seed Funding | 2025-07-13 | 2025-08-22 | 2025-07-13 | 2025-08-22 | 166730 | 190849 | 149904 | Complete
PRJ015 | Design | 2025-08-22 | 2025-10-01 | 2025-08-22 | 2025-10-01 | 166730 | 177541 | 24795 | Complete
PRJ015 | Business Case / Full Funding | 2025-10-01 | 2025-11-10 | 2025-10-01 | 2025-11-10 | 166730 | 170808 | 42781 | Complete
PRJ015 | Build | 2025-11-10 | 2025-12-20 | 2025-11-10 | 2025-12-20 | 166730 | 180945 | 170391 | Complete
PRJ015 | Testing | 2025-12-20 | 2026-01-29 | 2025-12-20 | 2026-01-29 | 166730 | 165039 | 130314 | Complete
PRJ015 | Deployment | 2026-01-29 | 2026-03-10 | 2026-01-29 | 2026-03-10 | 166730 | 158137 | 167156 | Complete
PRJ015 | Handover | 2026-03-10 | 2026-04-19 | 2026-03-10 | 2026-04-19 | 166730 | 176681 | 169019 | Complete
PRJ016 | Discovery | 2025-12-01 | 2026-01-15 | 2025-12-01 | 2026-01-15 | 441921 | 494636 | 314976 | Complete
PRJ016 | Business Case / Seed Funding | 2026-01-15 | 2026-03-01 | 2026-01-15 | 2026-03-01 | 441921 | 497075 | 208469 | Complete
PRJ016 | Design | 2026-03-01 | 2026-04-15 | 2026-03-01 | 2026-04-15 | 441921 | 503603 | 244494 | Complete
PRJ016 | Business Case / Full Funding | 2026-04-15 | 2026-05-30 | 2026-04-15 | 2026-05-30 | 441921 | 427041 | 315099 | Complete
PRJ016 | Build | 2026-05-30 | 2026-07-14 | 2026-05-30 | 2026-07-14 | 441921 | 495835 | 181443 | Complete
PRJ016 | Testing | 2026-07-14 | 2026-08-28 | 2026-07-14 |  | 441921 | 443832 | 461207 | In Progress
PRJ016 | Deployment | 2026-08-28 | 2026-10-12 |  |  | 441921 | 431903 | 0 | Planned
PRJ016 | Handover | 2026-10-12 | 2026-11-26 |  |  | 441921 | 402270 | 0 | Planned
PRJ017 | Discovery | 2025-02-17 | 2025-04-09 | 2025-02-17 | 2025-04-09 | 362336 | 373213 | 130600 | Complete
PRJ017 | Business Case / Seed Funding | 2025-04-09 | 2025-05-30 | 2025-04-09 | 2025-05-30 | 362336 | 381573 | 164911 | Complete
PRJ017 | Design | 2025-05-30 | 2025-07-20 | 2025-05-30 | 2025-07-20 | 362336 | 367321 | 368337 | Complete
PRJ017 | Business Case / Full Funding | 2025-07-20 | 2025-09-09 | 2025-07-20 | 2025-09-09 | 362336 | 397876 | 109726 | Complete
PRJ017 | Build | 2025-09-09 | 2025-10-30 | 2025-09-09 | 2025-10-30 | 362336 | 413921 | 189818 | Complete
PRJ017 | Testing | 2025-10-30 | 2025-12-20 | 2025-10-30 | 2025-12-20 | 362336 | 388200 | 177412 | Complete
PRJ017 | Deployment | 2025-12-20 | 2026-02-09 | 2025-12-20 | 2026-02-09 | 362336 | 339711 | 367773 | Complete
PRJ017 | Handover | 2026-02-09 | 2026-04-01 | 2026-02-09 | 2026-04-01 | 362336 | 382608 | 252743 | Complete
PRJ018 | Discovery | 2025-10-26 | 2025-12-11 | 2025-10-26 | 2025-12-11 | 220997 | 215674 | 66890 | Complete
PRJ018 | Business Case / Seed Funding | 2025-12-11 | 2026-01-26 | 2025-12-11 | 2026-01-26 | 220997 | 243085 | 3618 | Complete
PRJ018 | Design | 2026-01-26 | 2026-03-13 | 2026-01-26 | 2026-03-13 | 220997 | 201160 | 65673 | Complete
PRJ018 | Business Case / Full Funding | 2026-03-13 | 2026-04-28 | 2026-03-13 | 2026-04-28 | 220997 | 231664 | 12343 | Complete
PRJ018 | Build | 2026-04-28 | 2026-06-13 | 2026-04-28 | 2026-06-13 | 220997 | 215794 | 99855 | Complete
PRJ018 | Testing | 2026-06-13 | 2026-07-29 | 2026-06-13 |  | 220997 | 235376 | 149 | In Progress
PRJ018 | Deployment | 2026-07-29 | 2026-09-13 |  |  | 220997 | 212789 | 0 | Planned
PRJ018 | Handover | 2026-09-13 | 2026-10-29 |  |  | 220997 | 218247 | 0 | Planned
PRJ019 | Discovery | 2025-03-25 | 2025-06-06 | 2025-03-25 | 2025-06-06 | 62612 | 60785 | 56473 | Complete
PRJ019 | Business Case / Seed Funding | 2025-06-06 | 2025-08-18 | 2025-06-06 | 2025-08-18 | 62612 | 66765 | 50548 | Complete
PRJ019 | Design | 2025-08-18 | 2025-10-30 | 2025-08-18 | 2025-10-30 | 62612 | 58777 | 5654 | Complete
PRJ019 | Business Case / Full Funding | 2025-10-30 | 2026-01-11 | 2025-10-30 | 2026-01-11 | 62612 | 60587 | 65474 | Complete
PRJ019 | Build | 2026-01-11 | 2026-03-25 | 2026-01-11 | 2026-03-25 | 62612 | 59430 | 38474 | Complete
PRJ019 | Testing | 2026-03-25 | 2026-06-06 | 2026-03-25 | 2026-06-06 | 62612 | 57614 | 14388 | Complete
PRJ019 | Deployment | 2026-06-06 | 2026-08-18 | 2026-06-06 |  | 62612 | 63757 | 23314 | In Progress
PRJ019 | Handover | 2026-08-18 | 2026-10-30 |  |  | 62612 | 69056 | 0 | Planned
PRJ020 | Discovery | 2025-04-25 | 2025-05-07 | 2025-04-25 | 2025-05-07 | 437681 | 463619 | 194195 | Complete
PRJ020 | Business Case / Seed Funding | 2025-05-07 | 2025-05-19 | 2025-05-07 | 2025-05-19 | 437681 | 499712 | 45101 | Complete
PRJ020 | Design | 2025-05-19 | 2025-05-31 | 2025-05-19 | 2025-05-31 | 437681 | 422500 | 138799 | Complete
PRJ020 | Business Case / Full Funding | 2025-05-31 | 2025-06-12 | 2025-05-31 | 2025-06-12 | 437681 | 427914 | 259152 | Complete
PRJ020 | Build | 2025-06-12 | 2025-06-24 | 2025-06-12 | 2025-06-24 | 437681 | 468201 | 148201 | Complete
PRJ020 | Testing | 2025-06-24 | 2025-07-06 | 2025-06-24 | 2025-07-06 | 437681 | 457176 | 314031 | Complete
PRJ020 | Deployment | 2025-07-06 | 2025-07-18 | 2025-07-06 | 2025-07-18 | 437681 | 415743 | 62359 | Complete
PRJ020 | Handover | 2025-07-18 | 2025-07-30 | 2025-07-18 | 2025-07-30 | 437681 | 454563 | 138358 | Complete
PRJ021 | Discovery | 2025-01-20 | 2025-02-07 | 2025-01-20 | 2025-02-07 | 490810 | 452233 | 292031 | Complete
PRJ021 | Business Case / Seed Funding | 2025-02-07 | 2025-02-25 | 2025-02-07 | 2025-02-25 | 490810 | 518826 | 281294 | Complete
PRJ021 | Design | 2025-02-25 | 2025-03-15 | 2025-02-25 | 2025-03-15 | 490810 | 487861 | 451407 | Complete
PRJ021 | Business Case / Full Funding | 2025-03-15 | 2025-04-02 | 2025-03-15 | 2025-04-02 | 490810 | 495337 | 71433 | Complete
PRJ021 | Build | 2025-04-02 | 2025-04-20 | 2025-04-02 | 2025-04-20 | 490810 | 495952 | 161439 | Complete
PRJ021 | Testing | 2025-04-20 | 2025-05-08 | 2025-04-20 | 2025-05-08 | 490810 | 556442 | 367238 | Complete
PRJ021 | Deployment | 2025-05-08 | 2025-05-26 | 2025-05-08 | 2025-05-26 | 490810 | 499201 | 220400 | Complete
PRJ021 | Handover | 2025-05-26 | 2025-06-13 | 2025-05-26 | 2025-06-13 | 490810 | 493327 | 211427 | Complete
PRJ022 | Discovery | 2025-04-11 | 2025-05-15 | 2025-04-11 | 2025-05-15 | 358033 | 324707 | 210113 | Complete
PRJ022 | Business Case / Seed Funding | 2025-05-15 | 2025-06-18 | 2025-05-15 | 2025-06-18 | 358033 | 407933 | 158238 | Complete
PRJ022 | Design | 2025-06-18 | 2025-07-22 | 2025-06-18 | 2025-07-22 | 358033 | 389885 | 231278 | Complete
PRJ022 | Business Case / Full Funding | 2025-07-22 | 2025-08-25 | 2025-07-22 | 2025-08-25 | 358033 | 349296 | 91219 | Complete
PRJ022 | Build | 2025-08-25 | 2025-09-28 | 2025-08-25 | 2025-09-28 | 358033 | 368076 | 47847 | Complete
PRJ022 | Testing | 2025-09-28 | 2025-11-01 | 2025-09-28 | 2025-11-01 | 358033 | 370857 | 212619 | Complete
PRJ022 | Deployment | 2025-11-01 | 2025-12-05 | 2025-11-01 | 2025-12-05 | 358033 | 348486 | 283957 | Complete
PRJ022 | Handover | 2025-12-05 | 2026-01-08 | 2025-12-05 | 2026-01-08 | 358033 | 357376 | 151480 | Complete
PRJ023 | Discovery | 2025-11-12 | 2025-12-29 | 2025-11-12 | 2025-12-29 | 352389 | 317675 | 298775 | Complete
PRJ023 | Business Case / Seed Funding | 2025-12-29 | 2026-02-14 | 2025-12-29 | 2026-02-14 | 352389 | 394227 | 170286 | Complete
PRJ023 | Design | 2026-02-14 | 2026-04-02 | 2026-02-14 | 2026-04-02 | 352389 | 321938 | 20237 | Complete
PRJ023 | Business Case / Full Funding | 2026-04-02 | 2026-05-19 | 2026-04-02 | 2026-05-19 | 352389 | 390262 | 240461 | Complete
PRJ023 | Build | 2026-05-19 | 2026-07-05 | 2026-05-19 | 2026-07-05 | 352389 | 346529 | 36038 | Complete
PRJ023 | Testing | 2026-07-05 | 2026-08-21 | 2026-07-05 |  | 352389 | 342749 | 178147 | In Progress
PRJ023 | Deployment | 2026-08-21 | 2026-10-07 |  |  | 352389 | 346338 | 0 | Planned
PRJ023 | Handover | 2026-10-07 | 2026-11-23 |  |  | 352389 | 322512 | 0 | Planned
PRJ024 | Discovery | 2025-12-06 | 2026-01-26 | 2025-12-06 | 2026-01-26 | 116679 | 126611 | 82625 | Complete
PRJ024 | Business Case / Seed Funding | 2026-01-26 | 2026-03-18 | 2026-01-26 | 2026-03-18 | 116679 | 126579 | 6496 | Complete
PRJ024 | Design | 2026-03-18 | 2026-05-08 | 2026-03-18 | 2026-05-08 | 116679 | 110993 | 17661 | Complete
PRJ024 | Business Case / Full Funding | 2026-05-08 | 2026-06-28 | 2026-05-08 | 2026-06-28 | 116679 | 126609 | 60681 | Complete
PRJ024 | Build | 2026-06-28 | 2026-08-18 | 2026-06-28 |  | 116679 | 111532 | 82780 | In Progress
PRJ024 | Testing | 2026-08-18 | 2026-10-08 |  |  | 116679 | 129872 | 0 | Planned
PRJ024 | Deployment | 2026-10-08 | 2026-11-28 |  |  | 116679 | 113788 | 0 | Planned
PRJ024 | Handover | 2026-11-28 | 2027-01-18 |  |  | 116679 | 114080 | 0 | Planned
PRJ025 | Discovery | 2025-12-02 | 2026-01-26 | 2025-12-02 | 2026-01-26 | 234515 | 269057 | 1588 | Complete
PRJ025 | Business Case / Seed Funding | 2026-01-26 | 2026-03-22 | 2026-01-26 | 2026-03-22 | 234515 | 239496 | 169358 | Complete
PRJ025 | Design | 2026-03-22 | 2026-05-16 | 2026-03-22 | 2026-05-16 | 234515 | 217789 | 9 | Complete
PRJ025 | Business Case / Full Funding | 2026-05-16 | 2026-07-10 | 2026-05-16 | 2026-07-10 | 234515 | 246463 | 29804 | Complete
PRJ025 | Build | 2026-07-10 | 2026-09-03 | 2026-07-10 |  | 234515 | 216743 | 50306 | In Progress
PRJ025 | Testing | 2026-09-03 | 2026-10-28 |  |  | 234515 | 238839 | 0 | Planned
PRJ025 | Deployment | 2026-10-28 | 2026-12-22 |  |  | 234515 | 259886 | 0 | Planned
PRJ025 | Handover | 2026-12-22 | 2027-02-15 |  |  | 234515 | 237084 | 0 | Planned
PRJ026 | Discovery | 2025-09-16 | 2025-10-24 | 2025-09-16 | 2025-10-24 | 337944 | 308852 | 43224 | Complete
PRJ026 | Business Case / Seed Funding | 2025-10-24 | 2025-12-01 | 2025-10-24 | 2025-12-01 | 337944 | 338329 | 348701 | Complete
PRJ026 | Design | 2025-12-01 | 2026-01-08 | 2025-12-01 | 2026-01-08 | 337944 | 373451 | 298677 | Complete
PRJ026 | Business Case / Full Funding | 2026-01-08 | 2026-02-15 | 2026-01-08 | 2026-02-15 | 337944 | 350340 | 291568 | Complete
PRJ026 | Build | 2026-02-15 | 2026-03-25 | 2026-02-15 | 2026-03-25 | 337944 | 361712 | 304920 | Complete
PRJ026 | Testing | 2026-03-25 | 2026-05-02 | 2026-03-25 | 2026-05-02 | 337944 | 356291 | 153417 | Complete
PRJ026 | Deployment | 2026-05-02 | 2026-06-09 | 2026-05-02 | 2026-06-09 | 337944 | 357899 | 65577 | Complete
PRJ026 | Handover | 2026-06-09 | 2026-07-17 | 2026-06-09 |  | 337944 | 373306 | 233296 | In Progress
PRJ027 | Discovery | 2025-04-29 | 2025-06-03 | 2025-04-29 | 2025-06-03 | 226938 | 213933 | 176727 | Complete
PRJ027 | Business Case / Seed Funding | 2025-06-03 | 2025-07-08 | 2025-06-03 | 2025-07-08 | 226938 | 235260 | 113461 | Complete
PRJ027 | Design | 2025-07-08 | 2025-08-12 | 2025-07-08 | 2025-08-12 | 226938 | 220699 | 159064 | Complete
PRJ027 | Business Case / Full Funding | 2025-08-12 | 2025-09-16 | 2025-08-12 | 2025-09-16 | 226938 | 258658 | 117466 | Complete
PRJ027 | Build | 2025-09-16 | 2025-10-21 | 2025-09-16 | 2025-10-21 | 226938 | 242126 | 93214 | Complete
PRJ027 | Testing | 2025-10-21 | 2025-11-25 | 2025-10-21 | 2025-11-25 | 226938 | 243825 | 25576 | Complete
PRJ027 | Deployment | 2025-11-25 | 2025-12-30 | 2025-11-25 | 2025-12-30 | 226938 | 227896 | 101231 | Complete
PRJ027 | Handover | 2025-12-30 | 2026-02-03 | 2025-12-30 | 2026-02-03 | 226938 | 205831 | 108916 | Complete
PRJ028 | Discovery | 2025-01-04 | 2025-03-16 | 2025-01-04 | 2025-03-16 | 202370 | 210678 | 2342 | Complete
PRJ028 | Business Case / Seed Funding | 2025-03-16 | 2025-05-26 | 2025-03-16 | 2025-05-26 | 202370 | 197450 | 137078 | Complete
PRJ028 | Design | 2025-05-26 | 2025-08-05 | 2025-05-26 | 2025-08-05 | 202370 | 227323 | 131717 | Complete
PRJ028 | Business Case / Full Funding | 2025-08-05 | 2025-10-15 | 2025-08-05 | 2025-10-15 | 202370 | 184290 | 192739 | Complete
PRJ028 | Build | 2025-10-15 | 2025-12-25 | 2025-10-15 | 2025-12-25 | 202370 | 230843 | 99425 | Complete
PRJ028 | Testing | 2025-12-25 | 2026-03-06 | 2025-12-25 | 2026-03-06 | 202370 | 218715 | 58839 | Complete
PRJ028 | Deployment | 2026-03-06 | 2026-05-16 | 2026-03-06 | 2026-05-16 | 202370 | 231802 | 76017 | Complete
PRJ028 | Handover | 2026-05-16 | 2026-07-26 | 2026-05-16 |  | 202370 | 225432 | 106925 | In Progress
PRJ029 | Discovery | 2025-11-15 | 2025-12-30 | 2025-11-15 | 2025-12-30 | 249250 | 246062 | 184828 | Complete
PRJ029 | Business Case / Seed Funding | 2025-12-30 | 2026-02-13 | 2025-12-30 | 2026-02-13 | 249250 | 248666 | 16427 | Complete
PRJ029 | Design | 2026-02-13 | 2026-03-30 | 2026-02-13 | 2026-03-30 | 249250 | 265198 | 92088 | Complete
PRJ029 | Business Case / Full Funding | 2026-03-30 | 2026-05-14 | 2026-03-30 | 2026-05-14 | 249250 | 269141 | 88797 | Complete
PRJ029 | Build | 2026-05-14 | 2026-06-28 | 2026-05-14 | 2026-06-28 | 249250 | 268890 | 205889 | Complete
PRJ029 | Testing | 2026-06-28 | 2026-08-12 | 2026-06-28 |  | 249250 | 241670 | 199584 | In Progress
PRJ029 | Deployment | 2026-08-12 | 2026-09-26 |  |  | 249250 | 243202 | 0 | Planned
PRJ029 | Handover | 2026-09-26 | 2026-11-10 |  |  | 249250 | 248872 | 0 | Planned
PRJ030 | Discovery | 2025-05-10 | 2025-07-13 | 2025-05-10 | 2025-07-13 | 139326 | 157305 | 94378 | Complete
PRJ030 | Business Case / Seed Funding | 2025-07-13 | 2025-09-15 | 2025-07-13 | 2025-09-15 | 139326 | 138509 | 69014 | Complete
PRJ030 | Design | 2025-09-15 | 2025-11-18 | 2025-09-15 | 2025-11-18 | 139326 | 148347 | 84270 | Complete
PRJ030 | Business Case / Full Funding | 2025-11-18 | 2026-01-21 | 2025-11-18 | 2026-01-21 | 139326 | 157697 | 113435 | Complete
PRJ030 | Build | 2026-01-21 | 2026-03-26 | 2026-01-21 | 2026-03-26 | 139326 | 143695 | 18933 | Complete
PRJ030 | Testing | 2026-03-26 | 2026-05-29 | 2026-03-26 | 2026-05-29 | 139326 | 136682 | 139738 | Complete
PRJ030 | Deployment | 2026-05-29 | 2026-08-01 | 2026-05-29 |  | 139326 | 137518 | 90332 | In Progress
PRJ030 | Handover | 2026-08-01 | 2026-10-04 |  |  | 139326 | 139458 | 0 | Planned
PRJ031 | Discovery | 2025-08-27 | 2025-10-22 | 2025-08-27 | 2025-10-22 | 109688 | 99952 | 98131 | Complete
PRJ031 | Business Case / Seed Funding | 2025-10-22 | 2025-12-17 | 2025-10-22 | 2025-12-17 | 109688 | 103085 | 11119 | Complete
PRJ031 | Design | 2025-12-17 | 2026-02-11 | 2025-12-17 | 2026-02-11 | 109688 | 101632 | 107598 | Complete
PRJ031 | Business Case / Full Funding | 2026-02-11 | 2026-04-08 | 2026-02-11 | 2026-04-08 | 109688 | 111784 | 87521 | Complete
PRJ031 | Build | 2026-04-08 | 2026-06-03 | 2026-04-08 | 2026-06-03 | 109688 | 125630 | 93124 | Complete
PRJ031 | Testing | 2026-06-03 | 2026-07-29 | 2026-06-03 |  | 109688 | 118810 | 27252 | In Progress
PRJ031 | Deployment | 2026-07-29 | 2026-09-23 |  |  | 109688 | 123394 | 0 | Planned
PRJ031 | Handover | 2026-09-23 | 2026-11-18 |  |  | 109688 | 103491 | 0 | Planned
PRJ032 | Discovery | 2025-12-20 | 2026-02-22 | 2025-12-20 | 2026-02-22 | 465332 | 522623 | 369290 | Complete
PRJ032 | Business Case / Seed Funding | 2026-02-22 | 2026-04-27 | 2026-02-22 | 2026-04-27 | 465332 | 467666 | 31451 | Complete
PRJ032 | Design | 2026-04-27 | 2026-06-30 | 2026-04-27 | 2026-06-30 | 465332 | 489984 | 55932 | Complete
PRJ032 | Business Case / Full Funding | 2026-06-30 | 2026-09-02 | 2026-06-30 |  | 465332 | 517310 | 35610 | In Progress
PRJ032 | Build | 2026-09-02 | 2026-11-05 |  |  | 465332 | 507602 | 0 | Planned
PRJ032 | Testing | 2026-11-05 | 2027-01-08 |  |  | 465332 | 489359 | 0 | Planned
PRJ032 | Deployment | 2027-01-08 | 2027-03-13 |  |  | 465332 | 516598 | 0 | Planned
PRJ032 | Handover | 2027-03-13 | 2027-05-16 |  |  | 465332 | 526239 | 0 | Planned
PRJ033 | Discovery | 2025-11-22 | 2026-01-29 | 2025-11-22 | 2026-01-29 | 193153 | 189346 | 141709 | Complete
PRJ033 | Business Case / Seed Funding | 2026-01-29 | 2026-04-07 | 2026-01-29 | 2026-04-07 | 193153 | 192073 | 200554 | Complete
PRJ033 | Design | 2026-04-07 | 2026-06-14 | 2026-04-07 | 2026-06-14 | 193153 | 201545 | 40508 | Complete
PRJ033 | Business Case / Full Funding | 2026-06-14 | 2026-08-21 | 2026-06-14 |  | 193153 | 186030 | 88733 | In Progress
PRJ033 | Build | 2026-08-21 | 2026-10-28 |  |  | 193153 | 187653 | 0 | Planned
PRJ033 | Testing | 2026-10-28 | 2027-01-04 |  |  | 193153 | 183553 | 0 | Planned
PRJ033 | Deployment | 2027-01-04 | 2027-03-13 |  |  | 193153 | 181665 | 0 | Planned
PRJ033 | Handover | 2027-03-13 | 2027-05-20 |  |  | 193153 | 213137 | 0 | Planned
PRJ034 | Discovery | 2025-11-09 | 2026-01-02 | 2025-11-09 | 2026-01-02 | 169624 | 186954 | 34249 | Complete
PRJ034 | Business Case / Seed Funding | 2026-01-02 | 2026-02-25 | 2026-01-02 | 2026-02-25 | 169624 | 177346 | 112048 | Complete
PRJ034 | Design | 2026-02-25 | 2026-04-20 | 2026-02-25 | 2026-04-20 | 169624 | 181016 | 36251 | Complete
PRJ034 | Business Case / Full Funding | 2026-04-20 | 2026-06-13 | 2026-04-20 | 2026-06-13 | 169624 | 187010 | 159099 | Complete
PRJ034 | Build | 2026-06-13 | 2026-08-06 | 2026-06-13 |  | 169624 | 167909 | 72672 | In Progress
PRJ034 | Testing | 2026-08-06 | 2026-09-29 |  |  | 169624 | 175839 | 0 | Planned
PRJ034 | Deployment | 2026-09-29 | 2026-11-22 |  |  | 169624 | 155713 | 0 | Planned
PRJ034 | Handover | 2026-11-22 | 2027-01-15 |  |  | 169624 | 160519 | 0 | Planned
PRJ035 | Discovery | 2025-05-04 | 2025-06-28 | 2025-05-04 | 2025-06-28 | 441552 | 477978 | 422362 | Complete
PRJ035 | Business Case / Seed Funding | 2025-06-28 | 2025-08-22 | 2025-06-28 | 2025-08-22 | 441552 | 468292 | 230042 | Complete
PRJ035 | Design | 2025-08-22 | 2025-10-16 | 2025-08-22 | 2025-10-16 | 441552 | 489285 | 264441 | Complete
PRJ035 | Business Case / Full Funding | 2025-10-16 | 2025-12-10 | 2025-10-16 | 2025-12-10 | 441552 | 449692 | 163247 | Complete
PRJ035 | Build | 2025-12-10 | 2026-02-03 | 2025-12-10 | 2026-02-03 | 441552 | 465670 | 259029 | Complete
PRJ035 | Testing | 2026-02-03 | 2026-03-30 | 2026-02-03 | 2026-03-30 | 441552 | 412617 | 31135 | Complete
PRJ035 | Deployment | 2026-03-30 | 2026-05-24 | 2026-03-30 | 2026-05-24 | 441552 | 444589 | 174380 | Complete
PRJ035 | Handover | 2026-05-24 | 2026-07-18 | 2026-05-24 |  | 441552 | 405220 | 36230 | In Progress
PRJ036 | Discovery | 2025-05-09 | 2025-06-04 | 2025-05-09 | 2025-06-04 | 282318 | 309307 | 88405 | Complete
PRJ036 | Business Case / Seed Funding | 2025-06-04 | 2025-06-30 | 2025-06-04 | 2025-06-30 | 282318 | 262410 | 68350 | Complete
PRJ036 | Design | 2025-06-30 | 2025-07-26 | 2025-06-30 | 2025-07-26 | 282318 | 296539 | 98096 | Complete
PRJ036 | Business Case / Full Funding | 2025-07-26 | 2025-08-21 | 2025-07-26 | 2025-08-21 | 282318 | 269898 | 278831 | Complete
PRJ036 | Build | 2025-08-21 | 2025-09-16 | 2025-08-21 | 2025-09-16 | 282318 | 319180 | 74518 | Complete
PRJ036 | Testing | 2025-09-16 | 2025-10-12 | 2025-09-16 | 2025-10-12 | 282318 | 303723 | 20144 | Complete
PRJ036 | Deployment | 2025-10-12 | 2025-11-07 | 2025-10-12 | 2025-11-07 | 282318 | 315594 | 286982 | Complete
PRJ036 | Handover | 2025-11-07 | 2025-12-03 | 2025-11-07 | 2025-12-03 | 282318 | 259364 | 170555 | Complete
PRJ037 | Discovery | 2025-03-06 | 2025-04-03 | 2025-03-06 | 2025-04-03 | 150462 | 167509 | 147212 | Complete
PRJ037 | Business Case / Seed Funding | 2025-04-03 | 2025-05-01 | 2025-04-03 | 2025-05-01 | 150462 | 154225 | 63071 | Complete
PRJ037 | Design | 2025-05-01 | 2025-05-29 | 2025-05-01 | 2025-05-29 | 150462 | 137547 | 110197 | Complete
PRJ037 | Business Case / Full Funding | 2025-05-29 | 2025-06-26 | 2025-05-29 | 2025-06-26 | 150462 | 139586 | 74408 | Complete
PRJ037 | Build | 2025-06-26 | 2025-07-24 | 2025-06-26 | 2025-07-24 | 150462 | 169924 | 41558 | Complete
PRJ037 | Testing | 2025-07-24 | 2025-08-21 | 2025-07-24 | 2025-08-21 | 150462 | 136543 | 53406 | Complete
PRJ037 | Deployment | 2025-08-21 | 2025-09-18 | 2025-08-21 | 2025-09-18 | 150462 | 145229 | 52852 | Complete
PRJ037 | Handover | 2025-09-18 | 2025-10-16 | 2025-09-18 | 2025-10-16 | 150462 | 164182 | 22006 | Complete
PRJ038 | Discovery | 2025-09-09 | 2025-09-24 | 2025-09-09 | 2025-09-24 | 227228 | 235584 | 175095 | Complete
PRJ038 | Business Case / Seed Funding | 2025-09-24 | 2025-10-09 | 2025-09-24 | 2025-10-09 | 227228 | 257005 | 158265 | Complete
PRJ038 | Design | 2025-10-09 | 2025-10-24 | 2025-10-09 | 2025-10-24 | 227228 | 254398 | 56216 | Complete
PRJ038 | Business Case / Full Funding | 2025-10-24 | 2025-11-08 | 2025-10-24 | 2025-11-08 | 227228 | 208648 | 226183 | Complete
PRJ038 | Build | 2025-11-08 | 2025-11-23 | 2025-11-08 | 2025-11-23 | 227228 | 255878 | 167750 | Complete
PRJ038 | Testing | 2025-11-23 | 2025-12-08 | 2025-11-23 | 2025-12-08 | 227228 | 247996 | 8437 | Complete
PRJ038 | Deployment | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-23 | 227228 | 260237 | 226638 | Complete
PRJ038 | Handover | 2025-12-23 | 2026-01-07 | 2025-12-23 | 2026-01-07 | 227228 | 238485 | 146120 | Complete
PRJ039 | Discovery | 2025-11-14 | 2025-11-29 | 2025-11-14 | 2025-11-29 | 390651 | 359457 | 226185 | Complete
PRJ039 | Business Case / Seed Funding | 2025-11-29 | 2025-12-14 | 2025-11-29 | 2025-12-14 | 390651 | 444033 | 110958 | Complete
PRJ039 | Design | 2025-12-14 | 2025-12-29 | 2025-12-14 | 2025-12-29 | 390651 | 355662 | 14603 | Complete
PRJ039 | Business Case / Full Funding | 2025-12-29 | 2026-01-13 | 2025-12-29 | 2026-01-13 | 390651 | 401160 | 266757 | Complete
PRJ039 | Build | 2026-01-13 | 2026-01-28 | 2026-01-13 | 2026-01-28 | 390651 | 393729 | 124457 | Complete
PRJ039 | Testing | 2026-01-28 | 2026-02-12 | 2026-01-28 | 2026-02-12 | 390651 | 434583 | 398479 | Complete
PRJ039 | Deployment | 2026-02-12 | 2026-02-27 | 2026-02-12 | 2026-02-27 | 390651 | 353680 | 22706 | Complete
PRJ039 | Handover | 2026-02-27 | 2026-03-14 | 2026-02-27 | 2026-03-14 | 390651 | 427139 | 332808 | Complete
PRJ040 | Discovery | 2025-02-06 | 2025-04-02 | 2025-02-06 | 2025-04-02 | 211652 | 218753 | 191188 | Complete
PRJ040 | Business Case / Seed Funding | 2025-04-02 | 2025-05-27 | 2025-04-02 | 2025-05-27 | 211652 | 226571 | 163992 | Complete
PRJ040 | Design | 2025-05-27 | 2025-07-21 | 2025-05-27 | 2025-07-21 | 211652 | 219721 | 11587 | Complete
PRJ040 | Business Case / Full Funding | 2025-07-21 | 2025-09-14 | 2025-07-21 | 2025-09-14 | 211652 | 231002 | 154551 | Complete
PRJ040 | Build | 2025-09-14 | 2025-11-08 | 2025-09-14 | 2025-11-08 | 211652 | 213225 | 94857 | Complete
PRJ040 | Testing | 2025-11-08 | 2026-01-02 | 2025-11-08 | 2026-01-02 | 211652 | 197777 | 97328 | Complete
PRJ040 | Deployment | 2026-01-02 | 2026-02-26 | 2026-01-02 | 2026-02-26 | 211652 | 237958 | 218354 | Complete
PRJ040 | Handover | 2026-02-26 | 2026-04-22 | 2026-02-26 | 2026-04-22 | 211652 | 209944 | 43035 | Complete

## ProjectBrief
Project ID | Portfolio / Workstream | Sponsor | Business Owner | Business Solution Manager | Strategic Alignment | Background and Context | Opportunity / Problem Statement | Objective | In Scope | Out of Scope | Assumptions & Constraints | Key Metrics / Success Measures | Approval Type | Funding Ask | Funding Source | Resource Ask | Estimate Commentary | P&L Benefits Commentary | Delivery Milestones | Project Risks | Dependencies
PRJ001 |  | CTO
PRJ002 |  | COO
PRJ003 |  | CFO
PRJ004 |  | CTO
PRJ005 |  | CFO
PRJ006 |  | CMO
PRJ007 |  | CTO
PRJ008 |  | CTO
PRJ009 |  | CFO
PRJ010 |  | CFO
PRJ011 |  | CFO
PRJ012 |  | CMO
PRJ013 |  | CTO
PRJ014 |  | CTO
PRJ015 |  | CIO
PRJ016 |  | CIO
PRJ017 |  | CFO
PRJ018 |  | COO
PRJ019 |  | COO
PRJ020 |  | CIO
PRJ021 |  | CTO
PRJ022 |  | CIO
PRJ023 |  | COO
PRJ024 |  | CFO
PRJ025 |  | CTO
PRJ026 |  | COO
PRJ027 |  | CMO
PRJ028 |  | CTO
PRJ029 |  | CIO
PRJ030 |  | COO
PRJ031 |  | CIO
PRJ032 |  | CIO
PRJ033 |  | CTO
PRJ034 |  | CMO
PRJ035 |  | COO
PRJ036 |  | CFO
PRJ037 |  | CMO
PRJ038 |  | CIO
PRJ039 |  | CIO
PRJ040 |  | CIO

## ProjectLinks
Project ID | Title | Type | URL | Added By | Added On

## _Stages (hidden)
Discovery
Business Case / Seed Funding
Design
Business Case / Full Funding
Build
Testing
Deployment
Handover